## MDL
Alpilla 600 MW Combined Cycle Power Plant - Master document list (MDL)
engine engineering_plan v1.6.0 ¦ generated 2026-09-29T03:49:44Z by EPCE ¦ data 73eaa92ce7c1ff26 ¦ dates computed from the workflow network and the CPM (working days)
Document number | Title | Description | Org | KKS | System | Discipline | Type | DCC | Owner review | BDP | Tender | Sheets | Hours | EWP | CWP | CWA | MR | Equipment | Inputs | Start | IFR | IFA | IFC | EWP need | Float wd | Driving input | Vendor ref | Latest issue
ALP-C01-00000-GE-ITP-0001 | Piling Works - Subcontractor Inspection and Test Plans |  | C01 | 00000 | plant general | general | ITP | Q | approval |  |  | 1 | 8 |  |  |  | MR-CV-001 |  | 1 | 2027-01-14 | 2027-01-28 |  | 2027-02-11 |  |  | PO MR-CV-001
ALP-C01-00000-GE-MOS-0001 | Piling Works - Subcontractor Method Statements, Part 1 of 6 |  | C01 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-001 |  | 1 | 2027-01-14 | 2027-01-28 |  | 2027-02-11 |  |  | PO MR-CV-001
ALP-C01-00000-GE-MOS-0002 | Piling Works - Subcontractor Method Statements, Part 2 of 6 |  | C01 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-001 |  | 1 | 2027-01-14 | 2027-01-28 |  | 2027-02-11 |  |  | PO MR-CV-001
ALP-C01-00000-GE-MOS-0003 | Piling Works - Subcontractor Method Statements, Part 3 of 6 |  | C01 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-001 |  | 1 | 2027-01-14 | 2027-01-28 |  | 2027-02-11 |  |  | PO MR-CV-001
ALP-C01-00000-GE-MOS-0004 | Piling Works - Subcontractor Method Statements, Part 4 of 6 |  | C01 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-001 |  | 1 | 2027-01-14 | 2027-01-28 |  | 2027-02-11 |  |  | PO MR-CV-001
ALP-C01-00000-GE-MOS-0005 | Piling Works - Subcontractor Method Statements, Part 5 of 6 |  | C01 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-001 |  | 1 | 2027-01-14 | 2027-01-28 |  | 2027-02-11 |  |  | PO MR-CV-001
ALP-C01-00000-GE-MOS-0006 | Piling Works - Subcontractor Method Statements, Part 6 of 6 |  | C01 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-001 |  | 1 | 2027-01-14 | 2027-01-28 |  | 2027-02-11 |  |  | PO MR-CV-001
ALP-C02-00000-GE-ITP-0001 | Civil and Building Works - Subcontractor Inspection and Test Plans |  | C02 | 00000 | plant general | general | ITP | Q | approval |  |  | 1 | 8 |  |  |  | MR-CV-002 |  | 1 | 2026-12-24 | 2027-01-07 |  | 2027-01-21 |  |  | PO MR-CV-002
ALP-C02-00000-GE-MOS-0001 | Civil and Building Works - Subcontractor Method Statements, Part 1 of 6 |  | C02 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-002 |  | 1 | 2026-12-24 | 2027-01-07 |  | 2027-01-21 |  |  | PO MR-CV-002
ALP-C02-00000-GE-MOS-0002 | Civil and Building Works - Subcontractor Method Statements, Part 2 of 6 |  | C02 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-002 |  | 1 | 2026-12-24 | 2027-01-07 |  | 2027-01-21 |  |  | PO MR-CV-002
ALP-C02-00000-GE-MOS-0003 | Civil and Building Works - Subcontractor Method Statements, Part 3 of 6 |  | C02 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-002 |  | 1 | 2026-12-24 | 2027-01-07 |  | 2027-01-21 |  |  | PO MR-CV-002
ALP-C02-00000-GE-MOS-0004 | Civil and Building Works - Subcontractor Method Statements, Part 4 of 6 |  | C02 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-002 |  | 1 | 2026-12-24 | 2027-01-07 |  | 2027-01-21 |  |  | PO MR-CV-002
ALP-C02-00000-GE-MOS-0005 | Civil and Building Works - Subcontractor Method Statements, Part 5 of 6 |  | C02 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-002 |  | 1 | 2026-12-24 | 2027-01-07 |  | 2027-01-21 |  |  | PO MR-CV-002
ALP-C02-00000-GE-MOS-0006 | Civil and Building Works - Subcontractor Method Statements, Part 6 of 6 |  | C02 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-002 |  | 1 | 2026-12-24 | 2027-01-07 |  | 2027-01-21 |  |  | PO MR-CV-002
ALP-C03-00UPA-GE-ITP-0001 | Marine Works - Subcontractor Inspection and Test Plans |  | C03 | 00UPA | CW intake and outfall marine structures | general | ITP | Q | approval |  |  | 1 | 8 |  |  |  | MR-CV-003 |  | 1 | 2027-03-02 | 2027-03-16 |  | 2027-03-30 |  |  | PO MR-CV-003
ALP-C03-00UPA-GE-MOS-0001 | Marine Works - Subcontractor Method Statements, Part 1 of 6 |  | C03 | 00UPA | CW intake and outfall marine structures | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-003 |  | 1 | 2027-03-02 | 2027-03-16 |  | 2027-03-30 |  |  | PO MR-CV-003
ALP-C03-00UPA-GE-MOS-0002 | Marine Works - Subcontractor Method Statements, Part 2 of 6 |  | C03 | 00UPA | CW intake and outfall marine structures | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-003 |  | 1 | 2027-03-02 | 2027-03-16 |  | 2027-03-30 |  |  | PO MR-CV-003
ALP-C03-00UPA-GE-MOS-0003 | Marine Works - Subcontractor Method Statements, Part 3 of 6 |  | C03 | 00UPA | CW intake and outfall marine structures | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-003 |  | 1 | 2027-03-02 | 2027-03-16 |  | 2027-03-30 |  |  | PO MR-CV-003
ALP-C03-00UPA-GE-MOS-0004 | Marine Works - Subcontractor Method Statements, Part 4 of 6 |  | C03 | 00UPA | CW intake and outfall marine structures | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-003 |  | 1 | 2027-03-02 | 2027-03-16 |  | 2027-03-30 |  |  | PO MR-CV-003
ALP-C03-00UPA-GE-MOS-0005 | Marine Works - Subcontractor Method Statements, Part 5 of 6 |  | C03 | 00UPA | CW intake and outfall marine structures | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-003 |  | 1 | 2027-03-02 | 2027-03-16 |  | 2027-03-30 |  |  | PO MR-CV-003
ALP-C03-00UPA-GE-MOS-0006 | Marine Works - Subcontractor Method Statements, Part 6 of 6 |  | C03 | 00UPA | CW intake and outfall marine structures | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-CV-003 |  | 1 | 2027-03-02 | 2027-03-16 |  | 2027-03-30 |  |  | PO MR-CV-003
ALP-E01-00ACA-CV-CAL-0001 | 380 kV GIS - Supplier Foundation Loads and Anchor Bolt Drawings |  | E01 | 00ACA | 380 kV GIS switchyard | civil | CAL | E | review |  |  | 3 | 7 |  |  |  | MR-EL-001 |  | 1 | 2027-01-05 | 2027-01-26 |  | 2027-02-23 |  |  | PO MR-EL-001
ALP-E01-00ACA-EL-WIR-0001 | 380 kV GIS - Supplier Electrical Schematics and Wiring Diagrams |  | E01 | 00ACA | 380 kV GIS switchyard | electrical | WIR | F | review |  |  | 12 | 10 | EWP-04-EL-01 | CWP-04-EL-01 | CWA-04 | MR-EL-001 |  | 1 | 2027-02-02 | 2027-02-23 |  | 2027-04-20 | 2028-01-04 | 185 | PO MR-EL-001
ALP-E01-00ACA-IC-DSH-0001 | 380 kV GIS - Supplier Instrument List and Datasheets |  | E01 | 00ACA | 380 kV GIS switchyard | i_and_c | DSH | E | review |  |  | 20 | 8 |  |  |  | MR-EL-001 | 00ACA10 | 1 | 2027-02-09 | 2027-02-23 |  | 2027-04-20 |  |  | PO MR-EL-001
ALP-E01-00ACA-IC-IOL-0001 | 380 kV GIS - Supplier I/O List, Control Philosophy and Interface Signals |  | E01 | 00ACA | 380 kV GIS switchyard | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-EL-001 |  | 1 | 2027-01-19 | 2027-02-09 |  | 2027-03-23 |  |  | PO MR-EL-001
ALP-E01-00ACA-ME-CAL-0001 | 380 kV GIS - Supplier Design Calculations |  | E01 | 00ACA | 380 kV GIS switchyard | mechanical | CAL | E | review |  |  | 4 | 8 |  |  |  | MR-EL-001 |  | 1 | 2027-01-19 | 2027-02-09 |  | 2027-03-23 |  |  | PO MR-EL-001
ALP-E01-00ACA-ME-DSH-0001 | 380 kV GIS - Supplier Certified Datasheets and Performance Curves |  | E01 | 00ACA | 380 kV GIS switchyard | mechanical | DSH | E | review |  |  | 12 | 16 |  |  |  | MR-EL-001 | 00ACA10 | 1 | 2026-12-29 | 2027-01-12 |  | 2027-02-23 |  |  | PO MR-EL-001
ALP-E01-00ACA-ME-GAD-0001 | 380 kV GIS - Supplier GA Drawings |  | E01 | 00ACA | 380 kV GIS switchyard | mechanical | GAD | L | review |  |  | 12 | 22 | EWP-04-EL-01 | CWP-04-EL-01 | CWA-04 | MR-EL-001 | 00ACA10 | 1 | 2026-12-29 | 2027-01-26 |  | 2027-03-09 | 2028-01-04 | 215 | PO MR-EL-001
ALP-E01-00ACA-ME-ITP-0001 | 380 kV GIS - Supplier Inspection and Test Plan |  | E01 | 00ACA | 380 kV GIS switchyard | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-EL-001 |  | 1 | 2026-12-29 | 2027-01-12 |  | 2027-02-09 |  |  | PO MR-EL-001
ALP-E01-00ACA-ME-LST-0001 | 380 kV GIS - Spare Parts and Special Tools Lists |  | E01 | 00ACA | 380 kV GIS switchyard | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-EL-001 |  | 1 | 2027-02-16 | 2027-03-09 |  | 2027-05-04 |  |  | PO MR-EL-001
ALP-E01-00ACA-ME-MDB-0001 | 380 kV GIS - Manufacturing Record Book and Conformity Certificates |  | E01 | 00ACA | 380 kV GIS switchyard | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-EL-001 |  | 1 | 2027-11-16 | 2027-11-30 |  | 2028-01-25 |  |  | PO MR-EL-001
ALP-E01-00ACA-ME-OMM-0001 | 380 kV GIS - Supplier Operation and Maintenance Manual |  | E01 | 00ACA | 380 kV GIS switchyard | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-EL-001 |  | 1 | 2027-09-07 | 2027-10-19 |  | 2028-03-07 |  |  | PO MR-EL-001
ALP-E01-00ACA-ME-PRC-0001 | 380 kV GIS - Supplier Installation and Erection Manual |  | E01 | 00ACA | 380 kV GIS switchyard | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-EL-001 |  | 1 | 2027-08-31 | 2027-09-21 |  | 2027-11-02 |  |  | PO MR-EL-001
ALP-E01-00ACA-ME-TRP-0001 | 380 kV GIS - Factory Acceptance Test Report |  | E01 | 00ACA | 380 kV GIS switchyard | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-EL-001 |  | 1 | 2027-11-09 | 2027-11-16 |  | 2027-11-30 |  |  | PO MR-EL-001
ALP-E01-00ACA-ME-TST-0001 | 380 kV GIS - Factory Acceptance Test Procedure |  | E01 | 00ACA | 380 kV GIS switchyard | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-EL-001 |  | 1 | 2027-08-03 | 2027-08-24 |  | 2027-10-05 |  |  | PO MR-EL-001
ALP-E02-10BBT-CV-CAL-0001 | Unit Auxiliary Transformers - Supplier Foundation Loads and Anchor Bolt Drawings |  | E02 | 10BBT | GT unit auxiliary transformer | civil | CAL | E | review |  |  | 1 | 5 |  |  |  | MR-EL-002 |  | 1 | 2027-03-02 | 2027-03-23 |  | 2027-04-20 |  |  | PO MR-EL-002
ALP-E02-10BBT-EL-WIR-0001 | Unit Auxiliary Transformers - Supplier Electrical Schematics and Wiring Diagrams |  | E02 | 10BBT | GT unit auxiliary transformer | electrical | WIR | F | review |  |  | 16 | 12 | EWP-01-EL-01 | CWP-01-EL-01 | CWA-01 | MR-EL-002 |  | 1 | 2027-03-30 | 2027-04-20 |  | 2027-06-15 | 2028-01-10 | 149 | PO MR-EL-002
ALP-E02-10BBT-IC-DSH-0001 | Unit Auxiliary Transformers - Supplier Instrument List and Datasheets |  | E02 | 10BBT | GT unit auxiliary transformer | i_and_c | DSH | E | review |  |  | 10 | 6 |  |  |  | MR-EL-002 | 10BBT10 20BBT10 | 1 | 2027-04-06 | 2027-04-20 |  | 2027-06-15 |  |  | PO MR-EL-002
ALP-E02-10BBT-IC-IOL-0001 | Unit Auxiliary Transformers - Supplier I/O List, Control Philosophy and Interface Signals |  | E02 | 10BBT | GT unit auxiliary transformer | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-EL-002 |  | 1 | 2027-03-16 | 2027-04-06 |  | 2027-05-18 |  |  | PO MR-EL-002
ALP-E02-10BBT-ME-CAL-0001 | Unit Auxiliary Transformers - Supplier Design Calculations |  | E02 | 10BBT | GT unit auxiliary transformer | mechanical | CAL | E | review |  |  | 1 | 5 |  |  |  | MR-EL-002 |  | 1 | 2027-03-16 | 2027-04-06 |  | 2027-05-18 |  |  | PO MR-EL-002
ALP-E02-10BBT-ME-DSH-0001 | Unit Auxiliary Transformers - Supplier Certified Datasheets and Performance Curves |  | E02 | 10BBT | GT unit auxiliary transformer | mechanical | DSH | E | review |  |  | 2 | 6 |  |  |  | MR-EL-002 | 10BBT10 20BBT10 | 1 | 2027-02-23 | 2027-03-09 |  | 2027-04-20 |  |  | PO MR-EL-002
ALP-E02-10BBT-ME-GAD-0001 | Unit Auxiliary Transformers - Supplier GA Drawings |  | E02 | 10BBT | GT unit auxiliary transformer | mechanical | GAD | L | review |  |  | 2 | 7 | EWP-01-EL-01 | CWP-01-EL-01 | CWA-01 | MR-EL-002 | 10BBT10 20BBT10 | 1 | 2027-02-23 | 2027-03-23 |  | 2027-05-04 | 2028-01-10 | 179 | PO MR-EL-002
ALP-E02-10BBT-ME-ITP-0001 | Unit Auxiliary Transformers - Supplier Inspection and Test Plan |  | E02 | 10BBT | GT unit auxiliary transformer | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-EL-002 |  | 1 | 2027-02-23 | 2027-03-09 |  | 2027-04-06 |  |  | PO MR-EL-002
ALP-E02-10BBT-ME-LST-0001 | Unit Auxiliary Transformers - Spare Parts and Special Tools Lists |  | E02 | 10BBT | GT unit auxiliary transformer | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-EL-002 |  | 1 | 2027-04-13 | 2027-05-04 |  | 2027-06-29 |  |  | PO MR-EL-002
ALP-E02-10BBT-ME-MDB-0001 | Unit Auxiliary Transformers - Manufacturing Record Book and Conformity Certificates |  | E02 | 10BBT | GT unit auxiliary transformer | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-EL-002 |  | 1 | 2027-10-19 | 2027-11-02 |  | 2027-12-28 |  |  | PO MR-EL-002
ALP-E02-10BBT-ME-OMM-0001 | Unit Auxiliary Transformers - Supplier Operation and Maintenance Manual |  | E02 | 10BBT | GT unit auxiliary transformer | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-EL-002 |  | 1 | 2027-08-10 | 2027-09-21 |  | 2028-02-08 |  |  | PO MR-EL-002
ALP-E02-10BBT-ME-PRC-0001 | Unit Auxiliary Transformers - Supplier Installation and Erection Manual |  | E02 | 10BBT | GT unit auxiliary transformer | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-EL-002 |  | 1 | 2027-08-03 | 2027-08-24 |  | 2027-10-05 |  |  | PO MR-EL-002
ALP-E02-10BBT-ME-TRP-0001 | Unit Auxiliary Transformers - Factory Acceptance Test Report |  | E02 | 10BBT | GT unit auxiliary transformer | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-EL-002 |  | 1 | 2027-10-12 | 2027-10-19 |  | 2027-11-02 |  |  | PO MR-EL-002
ALP-E02-10BBT-ME-TST-0001 | Unit Auxiliary Transformers - Factory Acceptance Test Procedure |  | E02 | 10BBT | GT unit auxiliary transformer | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-EL-002 |  | 1 | 2027-07-06 | 2027-07-27 |  | 2027-09-07 |  |  | PO MR-EL-002
ALP-E03-00BBA-IC-IOL-0001 | MV Switchgear 10.5 kV - Supplier I/O List, Control Philosophy and Interface Signals |  | E03 | 00BBA | MV switchgear 10.5 kV | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-EL-003 |  | 1 | 2027-02-12 | 2027-03-05 |  | 2027-04-13 |  |  | PO MR-EL-003
ALP-E03-00BBA-ME-CAL-0001 | MV Switchgear 10.5 kV - Supplier Design Calculations |  | E03 | 00BBA | MV switchgear 10.5 kV | mechanical | CAL | E | review |  |  | 1 | 5 |  |  |  | MR-EL-003 |  | 1 | 2027-02-12 | 2027-03-05 |  | 2027-04-13 |  |  | PO MR-EL-003
ALP-E03-00BBA-ME-DSH-0001 | MV Switchgear 10.5 kV - Supplier Certified Datasheets and Performance Curves |  | E03 | 00BBA | MV switchgear 10.5 kV | mechanical | DSH | E | review |  |  | 2 | 6 |  |  |  | MR-EL-003 | 00BBA10 00BBA20 | 1 | 2027-01-26 | 2027-02-09 |  | 2027-03-18 |  |  | PO MR-EL-003
ALP-E03-00BBA-ME-GAD-0001 | MV Switchgear 10.5 kV - Supplier GA Drawings |  | E03 | 00BBA | MV switchgear 10.5 kV | mechanical | GAD | L | review |  |  | 2 | 7 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 | MR-EL-003 | 00BBA10 00BBA20 | 1 | 2027-01-25 | 2027-02-22 |  | 2027-03-31 | 2027-10-25 | 148 | PO MR-EL-003
ALP-E03-00BBA-ME-ITP-0001 | MV Switchgear 10.5 kV - Supplier Inspection and Test Plan |  | E03 | 00BBA | MV switchgear 10.5 kV | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-EL-003 |  | 1 | 2027-01-26 | 2027-02-09 |  | 2027-03-05 |  |  | PO MR-EL-003
ALP-E03-00BBA-ME-LST-0001 | MV Switchgear 10.5 kV - Spare Parts and Special Tools Lists |  | E03 | 00BBA | MV switchgear 10.5 kV | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-EL-003 |  | 1 | 2027-03-10 | 2027-03-31 |  | 2027-05-20 |  |  | PO MR-EL-003
ALP-E03-00BBA-ME-MDB-0001 | MV Switchgear 10.5 kV - Manufacturing Record Book and Conformity Certificates |  | E03 | 00BBA | MV switchgear 10.5 kV | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-EL-003 |  | 1 | 2027-08-26 | 2027-09-09 |  | 2027-11-04 |  |  | PO MR-EL-003
ALP-E03-00BBA-ME-OMM-0001 | MV Switchgear 10.5 kV - Supplier Operation and Maintenance Manual |  | E03 | 00BBA | MV switchgear 10.5 kV | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-EL-003 |  | 1 | 2027-06-17 | 2027-07-29 |  | 2027-12-16 |  |  | PO MR-EL-003
ALP-E03-00BBA-ME-PRC-0001 | MV Switchgear 10.5 kV - Supplier Installation and Erection Manual |  | E03 | 00BBA | MV switchgear 10.5 kV | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-EL-003 |  | 1 | 2027-06-10 | 2027-07-01 |  | 2027-08-12 |  |  | PO MR-EL-003
ALP-E03-00BBA-ME-TRP-0001 | MV Switchgear 10.5 kV - Factory Acceptance Test Report |  | E03 | 00BBA | MV switchgear 10.5 kV | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-EL-003 |  | 1 | 2027-08-19 | 2027-08-26 |  | 2027-09-09 |  |  | PO MR-EL-003
ALP-E03-00BBA-ME-TST-0001 | MV Switchgear 10.5 kV - Factory Acceptance Test Procedure |  | E03 | 00BBA | MV switchgear 10.5 kV | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-EL-003 |  | 1 | 2027-05-13 | 2027-06-03 |  | 2027-07-15 |  |  | PO MR-EL-003
ALP-E04-00BFT-IC-IOL-0001 | LV Transformers - Supplier I/O List, Control Philosophy and Interface Signals |  | E04 | 00BFT | LV transformers | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-EL-004 |  | 1 | 2027-03-08 | 2027-03-29 |  | 2027-04-26 |  |  | PO MR-EL-004
ALP-E04-00BFT-ME-CAL-0001 | LV Transformers - Supplier Design Calculations |  | E04 | 00BFT | LV transformers | mechanical | CAL | E | review |  |  | 3 | 7 |  |  |  | MR-EL-004 |  | 1 | 2027-03-08 | 2027-03-29 |  | 2027-04-26 |  |  | PO MR-EL-004
ALP-E04-00BFT-ME-DSH-0001 | LV Transformers - Supplier Certified Datasheets and Performance Curves |  | E04 | 00BFT | LV transformers | mechanical | DSH | E | review |  |  | 8 | 12 |  |  |  | MR-EL-004 | 00BFT10 00BFT20 00BFT30 00BFT40 00BFT50 00BFT60 00BFT70 00BFT80 | 1 | 2027-02-24 | 2027-03-10 |  | 2027-04-06 |  |  | PO MR-EL-004
ALP-E04-00BFT-ME-GAD-0001 | LV Transformers - Supplier GA Drawings |  | E04 | 00BFT | LV transformers | mechanical | GAD | L | review |  |  | 8 | 16 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 | MR-EL-004 | 00BFT10 00BFT20 00BFT30 00BFT40 00BFT50 00BFT60 00BFT70 00BFT80 | 1 | 2027-02-19 | 2027-03-19 |  | 2027-04-15 | 2027-10-25 | 137 | PO MR-EL-004
ALP-E04-00BFT-ME-ITP-0001 | LV Transformers - Supplier Inspection and Test Plan |  | E04 | 00BFT | LV transformers | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-EL-004 |  | 1 | 2027-02-24 | 2027-03-10 |  | 2027-03-29 |  |  | PO MR-EL-004
ALP-E04-00BFT-ME-LST-0001 | LV Transformers - Spare Parts and Special Tools Lists |  | E04 | 00BFT | LV transformers | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-EL-004 |  | 1 | 2027-03-25 | 2027-04-15 |  | 2027-05-21 |  |  | PO MR-EL-004
ALP-E04-00BFT-ME-MDB-0001 | LV Transformers - Manufacturing Record Book and Conformity Certificates |  | E04 | 00BFT | LV transformers | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-EL-004 |  | 1 | 2027-07-23 | 2027-08-06 |  | 2027-10-01 |  |  | PO MR-EL-004
ALP-E04-00BFT-ME-OMM-0001 | LV Transformers - Supplier Operation and Maintenance Manual |  | E04 | 00BFT | LV transformers | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-EL-004 |  | 1 | 2027-05-14 | 2027-06-25 |  | 2027-11-12 |  |  | PO MR-EL-004
ALP-E04-00BFT-ME-PRC-0001 | LV Transformers - Supplier Installation and Erection Manual |  | E04 | 00BFT | LV transformers | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-EL-004 |  | 1 | 2027-05-07 | 2027-05-28 |  | 2027-07-09 |  |  | PO MR-EL-004
ALP-E04-00BFT-ME-TRP-0001 | LV Transformers - Factory Acceptance Test Report |  | E04 | 00BFT | LV transformers | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-EL-004 |  | 1 | 2027-07-16 | 2027-07-23 |  | 2027-08-06 |  |  | PO MR-EL-004
ALP-E04-00BFT-ME-TST-0001 | LV Transformers - Factory Acceptance Test Procedure |  | E04 | 00BFT | LV transformers | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-EL-004 |  | 1 | 2027-04-09 | 2027-04-30 |  | 2027-06-11 |  |  | PO MR-EL-004
ALP-E05-00BFA-EL-WIR-0001 | LV Switchboards and MCCs - Supplier Electrical Schematics and Wiring Diagrams |  | E05 | 00BFA | LV switchgear 0.4 kV | electrical | WIR | F | review |  |  | 60 | 34 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 | MR-EL-005 |  | 1 | 2027-03-02 | 2027-03-23 |  | 2027-05-04 | 2027-10-25 | 124 | PO MR-EL-005
ALP-E05-00BFA-IC-IOL-0001 | LV Switchboards and MCCs - Supplier I/O List, Control Philosophy and Interface Signals |  | E05 | 00BFA | LV switchgear 0.4 kV | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-EL-005 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-12 |  |  | PO MR-EL-005
ALP-E05-00BFA-ME-CAL-0001 | LV Switchboards and MCCs - Supplier Design Calculations |  | E05 | 00BFA | LV switchgear 0.4 kV | mechanical | CAL | E | review |  |  | 7 | 11 |  |  |  | MR-EL-005 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-12 |  |  | PO MR-EL-005
ALP-E05-00BFA-ME-DSH-0001 | LV Switchboards and MCCs - Supplier Certified Datasheets and Performance Curves |  | E05 | 00BFA | LV switchgear 0.4 kV | mechanical | DSH | E | review |  |  | 19 | 23 |  |  |  | MR-EL-005 | 00BFA10 00BFA11 00BFA12 00BFA20 00BFA21 00BFA22 00BFA30 00BFA40 00BFA50 00BFA60 00BFA70 00BFA80 00BMA10 00BMA20 00BRA20 | 1 | 2027-02-04 | 2027-02-18 |  | 2027-03-23 |  |  | PO MR-EL-005
ALP-E05-00BFA-ME-GAD-0001 | LV Switchboards and MCCs - Supplier GA Drawings |  | E05 | 00BFA | LV switchgear 0.4 kV | mechanical | GAD | L | review |  |  | 19 | 32.5 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 | MR-EL-005 | 00BFA10 00BFA11 00BFA12 00BFA20 00BFA21 00BFA22 00BFA30 00BFA40 00BFA50 00BFA60 00BFA70 00BFA80 00BMA10 00BMA20 00BRA20 | 1 | 2027-02-01 | 2027-03-01 |  | 2027-04-01 | 2027-10-25 | 147 | PO MR-EL-005
ALP-E05-00BFA-ME-ITP-0001 | LV Switchboards and MCCs - Supplier Inspection and Test Plan |  | E05 | 00BFA | LV switchgear 0.4 kV | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-EL-005 |  | 1 | 2027-02-04 | 2027-02-18 |  | 2027-03-11 |  |  | PO MR-EL-005
ALP-E05-00BFA-ME-LST-0001 | LV Switchboards and MCCs - Spare Parts and Special Tools Lists |  | E05 | 00BFA | LV switchgear 0.4 kV | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-EL-005 |  | 1 | 2027-03-11 | 2027-04-01 |  | 2027-05-13 |  |  | PO MR-EL-005
ALP-E05-00BFA-ME-MDB-0001 | LV Switchboards and MCCs - Manufacturing Record Book and Conformity Certificates |  | E05 | 00BFA | LV switchgear 0.4 kV | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-EL-005 |  | 1 | 2027-07-29 | 2027-08-12 |  | 2027-10-07 |  |  | PO MR-EL-005
ALP-E05-00BFA-ME-OMM-0001 | LV Switchboards and MCCs - Supplier Operation and Maintenance Manual |  | E05 | 00BFA | LV switchgear 0.4 kV | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-EL-005 |  | 1 | 2027-05-20 | 2027-07-01 |  | 2027-11-18 |  |  | PO MR-EL-005
ALP-E05-00BFA-ME-PRC-0001 | LV Switchboards and MCCs - Supplier Installation and Erection Manual |  | E05 | 00BFA | LV switchgear 0.4 kV | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-EL-005 |  | 1 | 2027-05-13 | 2027-06-03 |  | 2027-07-15 |  |  | PO MR-EL-005
ALP-E05-00BFA-ME-TRP-0001 | LV Switchboards and MCCs - Factory Acceptance Test Report |  | E05 | 00BFA | LV switchgear 0.4 kV | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-EL-005 |  | 1 | 2027-07-22 | 2027-07-29 |  | 2027-08-12 |  |  | PO MR-EL-005
ALP-E05-00BFA-ME-TST-0001 | LV Switchboards and MCCs - Factory Acceptance Test Procedure |  | E05 | 00BFA | LV switchgear 0.4 kV | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-EL-005 |  | 1 | 2027-04-15 | 2027-05-06 |  | 2027-06-17 |  |  | PO MR-EL-005
ALP-E06-00XJA-CV-CAL-0001 | Emergency Diesel Generator - Supplier Foundation Loads and Anchor Bolt Drawings |  | E06 | 00XJA | Emergency diesel generator | civil | CAL | E | review |  |  | 1 | 5 |  |  |  | MR-EL-006 |  | 1 | 2027-02-01 | 2027-02-22 |  | 2027-03-18 |  |  | PO MR-EL-006
ALP-E06-00XJA-EL-WIR-0001 | Emergency Diesel Generator - Supplier Electrical Schematics and Wiring Diagrams |  | E06 | 00XJA | Emergency diesel generator | electrical | WIR | F | review |  |  | 8 | 8 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 | MR-EL-006 |  | 1 | 2027-02-25 | 2027-03-18 |  | 2027-05-07 | 2027-10-25 | 121 | PO MR-EL-006
ALP-E06-00XJA-IC-DSH-0001 | Emergency Diesel Generator - Supplier Instrument List and Datasheets |  | E06 | 00XJA | Emergency diesel generator | i_and_c | DSH | E | review |  |  | 10 | 6 |  |  |  | MR-EL-006 | 00XJA10 00XJA10BB001 | 1 | 2027-03-04 | 2027-03-18 |  | 2027-05-07 |  |  | PO MR-EL-006
ALP-E06-00XJA-IC-IOL-0001 | Emergency Diesel Generator - Supplier I/O List, Control Philosophy and Interface Signals |  | E06 | 00XJA | Emergency diesel generator | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-EL-006 |  | 1 | 2027-02-12 | 2027-03-05 |  | 2027-04-13 |  |  | PO MR-EL-006
ALP-E06-00XJA-ME-CAL-0001 | Emergency Diesel Generator - Supplier Design Calculations |  | E06 | 00XJA | Emergency diesel generator | mechanical | CAL | E | review |  |  | 1 | 5 |  |  |  | MR-EL-006 |  | 1 | 2027-02-12 | 2027-03-05 |  | 2027-04-13 |  |  | PO MR-EL-006
ALP-E06-00XJA-ME-DSH-0001 | Emergency Diesel Generator - Supplier Certified Datasheets and Performance Curves |  | E06 | 00XJA | Emergency diesel generator | mechanical | DSH | E | review |  |  | 3 | 7 |  |  |  | MR-EL-006 | 00XJA10 00XJA10BB001 | 1 | 2027-01-26 | 2027-02-09 |  | 2027-03-18 |  |  | PO MR-EL-006
ALP-E06-00XJA-ME-GAD-0001 | Emergency Diesel Generator - Supplier GA Drawings |  | E06 | 00XJA | Emergency diesel generator | mechanical | GAD | L | review |  |  | 3 | 8.5 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 | MR-EL-006 | 00XJA10 00XJA10BB001 | 1 | 2027-01-25 | 2027-02-22 |  | 2027-03-31 | 2027-10-25 | 148 | PO MR-EL-006
ALP-E06-00XJA-ME-ITP-0001 | Emergency Diesel Generator - Supplier Inspection and Test Plan |  | E06 | 00XJA | Emergency diesel generator | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-EL-006 |  | 1 | 2027-01-26 | 2027-02-09 |  | 2027-03-05 |  |  | PO MR-EL-006
ALP-E06-00XJA-ME-LST-0001 | Emergency Diesel Generator - Spare Parts and Special Tools Lists |  | E06 | 00XJA | Emergency diesel generator | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-EL-006 |  | 1 | 2027-03-10 | 2027-03-31 |  | 2027-05-20 |  |  | PO MR-EL-006
ALP-E06-00XJA-ME-MDB-0001 | Emergency Diesel Generator - Manufacturing Record Book and Conformity Certificates |  | E06 | 00XJA | Emergency diesel generator | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-EL-006 |  | 1 | 2027-08-26 | 2027-09-09 |  | 2027-11-04 |  |  | PO MR-EL-006
ALP-E06-00XJA-ME-OMM-0001 | Emergency Diesel Generator - Supplier Operation and Maintenance Manual |  | E06 | 00XJA | Emergency diesel generator | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-EL-006 |  | 1 | 2027-06-17 | 2027-07-29 |  | 2027-12-16 |  |  | PO MR-EL-006
ALP-E06-00XJA-ME-PRC-0001 | Emergency Diesel Generator - Supplier Installation and Erection Manual |  | E06 | 00XJA | Emergency diesel generator | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-EL-006 |  | 1 | 2027-06-10 | 2027-07-01 |  | 2027-08-12 |  |  | PO MR-EL-006
ALP-E06-00XJA-ME-TRP-0001 | Emergency Diesel Generator - Factory Acceptance Test Report |  | E06 | 00XJA | Emergency diesel generator | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-EL-006 |  | 1 | 2027-08-19 | 2027-08-26 |  | 2027-09-09 |  |  | PO MR-EL-006
ALP-E06-00XJA-ME-TST-0001 | Emergency Diesel Generator - Factory Acceptance Test Procedure |  | E06 | 00XJA | Emergency diesel generator | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-EL-006 |  | 1 | 2027-05-13 | 2027-06-03 |  | 2027-07-15 |  |  | PO MR-EL-006
ALP-E07-00BRA-EL-WIR-0001 | UPS, Batteries and DC Systems - Supplier Electrical Schematics and Wiring Diagrams |  | E07 | 00BRA | UPS | electrical | WIR | F | review |  |  | 60 | 34 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 | MR-EL-007 |  | 1 | 2027-03-25 | 2027-04-15 |  | 2027-05-24 | 2027-10-25 | 110 | PO MR-EL-007
ALP-E07-00BRA-IC-IOL-0001 | UPS, Batteries and DC Systems - Supplier I/O List, Control Philosophy and Interface Signals |  | E07 | 00BRA | UPS | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-EL-007 |  | 1 | 2027-03-17 | 2027-04-07 |  | 2027-05-05 |  |  | PO MR-EL-007
ALP-E07-00BRA-ME-CAL-0001 | UPS, Batteries and DC Systems - Supplier Design Calculations |  | E07 | 00BRA | UPS | mechanical | CAL | E | review |  |  | 3 | 7 |  |  |  | MR-EL-007 |  | 1 | 2027-03-17 | 2027-04-07 |  | 2027-05-05 |  |  | PO MR-EL-007
ALP-E07-00BRA-ME-DSH-0001 | UPS, Batteries and DC Systems - Supplier Certified Datasheets and Performance Curves |  | E07 | 00BRA | UPS | mechanical | DSH | E | review |  |  | 8 | 12 |  |  |  | MR-EL-007 | 00BRA10 00BTA10 | 1 | 2027-03-05 | 2027-03-19 |  | 2027-04-15 |  |  | PO MR-EL-007
ALP-E07-00BRA-ME-GAD-0001 | UPS, Batteries and DC Systems - Supplier GA Drawings |  | E07 | 00BRA | UPS | mechanical | GAD | L | review |  |  | 8 | 16 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 | MR-EL-007 | 00BRA10 00BTA10 | 1 | 2027-03-02 | 2027-03-30 |  | 2027-04-26 | 2027-10-25 | 130 | PO MR-EL-007
ALP-E07-00BRA-ME-ITP-0001 | UPS, Batteries and DC Systems - Supplier Inspection and Test Plan |  | E07 | 00BRA | UPS | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-EL-007 |  | 1 | 2027-03-05 | 2027-03-19 |  | 2027-04-07 |  |  | PO MR-EL-007
ALP-E07-00BRA-ME-LST-0001 | UPS, Batteries and DC Systems - Spare Parts and Special Tools Lists |  | E07 | 00BRA | UPS | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-EL-007 |  | 1 | 2027-04-05 | 2027-04-26 |  | 2027-06-01 |  |  | PO MR-EL-007
ALP-E07-00BRA-ME-MDB-0001 | UPS, Batteries and DC Systems - Manufacturing Record Book and Conformity Certificates |  | E07 | 00BRA | UPS | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-EL-007 |  | 1 | 2027-08-03 | 2027-08-17 |  | 2027-10-12 |  |  | PO MR-EL-007
ALP-E07-00BRA-ME-OMM-0001 | UPS, Batteries and DC Systems - Supplier Operation and Maintenance Manual |  | E07 | 00BRA | UPS | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-EL-007 |  | 1 | 2027-05-25 | 2027-07-06 |  | 2027-11-23 |  |  | PO MR-EL-007
ALP-E07-00BRA-ME-PRC-0001 | UPS, Batteries and DC Systems - Supplier Installation and Erection Manual |  | E07 | 00BRA | UPS | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-EL-007 |  | 1 | 2027-05-18 | 2027-06-08 |  | 2027-07-20 |  |  | PO MR-EL-007
ALP-E07-00BRA-ME-TRP-0001 | UPS, Batteries and DC Systems - Factory Acceptance Test Report |  | E07 | 00BRA | UPS | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-EL-007 |  | 1 | 2027-07-27 | 2027-08-03 |  | 2027-08-17 |  |  | PO MR-EL-007
ALP-E07-00BRA-ME-TST-0001 | UPS, Batteries and DC Systems - Factory Acceptance Test Procedure |  | E07 | 00BRA | UPS | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-EL-007 |  | 1 | 2027-04-20 | 2027-05-11 |  | 2027-06-22 |  |  | PO MR-EL-007
ALP-E08-00000-ME-DSH-0001 | Power and Control Cables - Supplier Catalogues and Material Datasheets |  | E08 | 00000 | plant general | mechanical | DSH | E | review |  |  | 1 | 6 |  |  |  | MR-EL-008 |  | 1 | 2027-04-08 | 2027-04-22 |  | 2027-05-06 |  |  | PO MR-EL-008
ALP-E08-00000-ME-ITP-0001 | Power and Control Cables - Supplier Inspection and Test Plan |  | E08 | 00000 | plant general | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-EL-008 |  | 1 | 2027-04-08 | 2027-04-22 |  | 2027-05-06 |  |  | PO MR-EL-008
ALP-E08-00000-ME-MDB-0001 | Power and Control Cables - Manufacturing Record Book and Conformity Certificates |  | E08 | 00000 | plant general | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-EL-008 |  | 1 | 2027-07-29 | 2027-08-12 |  | 2027-10-07 |  |  | PO MR-EL-008
ALP-E09-00BLA-ME-DSH-0001 | Cable Trays, Earthing and Lighting Materials - Supplier Catalogues and Material Datasheets |  | E09 | 00BLA | Lighting and small power | mechanical | DSH | E | review |  |  | 1 | 6 |  |  |  | MR-EL-009 |  | 1 | 2027-03-11 | 2027-03-25 |  | 2027-04-08 |  |  | PO MR-EL-009
ALP-E09-00BLA-ME-ITP-0001 | Cable Trays, Earthing and Lighting Materials - Supplier Inspection and Test Plan |  | E09 | 00BLA | Lighting and small power | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-EL-009 |  | 1 | 2027-03-11 | 2027-03-25 |  | 2027-04-08 |  |  | PO MR-EL-009
ALP-E09-00BLA-ME-MDB-0001 | Cable Trays, Earthing and Lighting Materials - Manufacturing Record Book and Conformity Certificates |  | E09 | 00BLA | Lighting and small power | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-EL-009 |  | 1 | 2027-06-03 | 2027-06-17 |  | 2027-08-12 |  |  | PO MR-EL-009
ALP-E10-00BXA-IC-IOL-0001 | Cathodic Protection - Supplier I/O List, Control Philosophy and Interface Signals | marine structures, buried piping and tanks | E10 | 00BXA | Earthing and lightning protection | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-EL-010 |  | 1 | 2027-05-04 | 2027-05-25 |  | 2027-06-15 |  |  | PO MR-EL-010
ALP-E10-00BXA-ME-ITP-0001 | Cathodic Protection - Supplier Inspection and Test Plan | marine structures, buried piping and tanks | E10 | 00BXA | Earthing and lightning protection | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-EL-010 |  | 1 | 2027-04-27 | 2027-05-11 |  | 2027-05-25 |  |  | PO MR-EL-010
ALP-E10-00BXA-ME-LST-0001 | Cathodic Protection - Spare Parts and Special Tools Lists | marine structures, buried piping and tanks | E10 | 00BXA | Earthing and lightning protection | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-EL-010 |  | 1 | 2027-05-18 | 2027-06-08 |  | 2027-07-06 |  |  | PO MR-EL-010
ALP-E10-00BXA-ME-MDB-0001 | Cathodic Protection - Manufacturing Record Book and Conformity Certificates | marine structures, buried piping and tanks | E10 | 00BXA | Earthing and lightning protection | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-EL-010 |  | 1 | 2027-07-20 | 2027-08-03 |  | 2027-09-28 |  |  | PO MR-EL-010
ALP-E10-00BXA-ME-OMM-0001 | Cathodic Protection - Supplier Operation and Maintenance Manual | marine structures, buried piping and tanks | E10 | 00BXA | Earthing and lightning protection | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-EL-010 |  | 1 | 2027-05-11 | 2027-06-22 |  | 2027-11-09 |  |  | PO MR-EL-010
ALP-E10-00BXA-ME-PRC-0001 | Cathodic Protection - Supplier Installation and Erection Manual | marine structures, buried piping and tanks | E10 | 00BXA | Earthing and lightning protection | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-EL-010 |  | 1 | 2027-05-04 | 2027-05-25 |  | 2027-07-06 |  |  | PO MR-EL-010
ALP-E10-00BXA-ME-TRP-0001 | Cathodic Protection - Factory Acceptance Test Report | marine structures, buried piping and tanks | E10 | 00BXA | Earthing and lightning protection | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-EL-010 |  | 1 | 2027-07-13 | 2027-07-20 |  | 2027-08-03 |  |  | PO MR-EL-010
ALP-E10-00BXA-ME-TST-0001 | Cathodic Protection - Factory Acceptance Test Procedure | marine structures, buried piping and tanks | E10 | 00BXA | Earthing and lightning protection | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-EL-010 |  | 1 | 2027-04-06 | 2027-04-27 |  | 2027-06-08 |  |  | PO MR-EL-010
ALP-E11-00000-IC-IOL-0001 | Construction Power Supply - Supplier I/O List, Control Philosophy and Interface Signals | RMU, temporary distribution | E11 | 00000 | plant general | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-EL-011 |  | 1 | 2026-11-23 | 2026-12-14 |  | 2027-01-04 |  |  | PO MR-EL-011
ALP-E11-00000-ME-ITP-0001 | Construction Power Supply - Supplier Inspection and Test Plan | RMU, temporary distribution | E11 | 00000 | plant general | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-EL-011 |  | 1 | 2026-11-09 | 2026-11-23 |  | 2026-12-07
ALP-E11-00000-ME-LST-0001 | Construction Power Supply - Spare Parts and Special Tools Lists | RMU, temporary distribution | E11 | 00000 | plant general | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-EL-011 |  | 1 | 2026-12-07 | 2026-12-28 |  | 2027-01-25 |  |  | PO MR-EL-011
ALP-E11-00000-ME-MDB-0001 | Construction Power Supply - Manufacturing Record Book and Conformity Certificates | RMU, temporary distribution | E11 | 00000 | plant general | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-EL-011 |  | 1 | 2026-12-14 | 2026-12-28 |  | 2027-02-22 |  |  | PO MR-EL-011
ALP-E11-00000-ME-OMM-0001 | Construction Power Supply - Supplier Operation and Maintenance Manual | RMU, temporary distribution | E11 | 00000 | plant general | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-EL-011 |  | 1 | 2026-11-02 | 2026-11-16 |  | 2027-04-05 |  |  | PO MR-EL-011
ALP-E11-00000-ME-PRC-0001 | Construction Power Supply - Supplier Installation and Erection Manual | RMU, temporary distribution | E11 | 00000 | plant general | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-EL-011 |  | 1 | 2026-11-02 | 2026-11-02 |  | 2026-11-30 |  |  | PO MR-EL-011
ALP-E11-00000-ME-TRP-0001 | Construction Power Supply - Factory Acceptance Test Report | RMU, temporary distribution | E11 | 00000 | plant general | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-EL-011 |  | 1 | 2026-12-07 | 2026-12-14 |  | 2026-12-28 |  |  | PO MR-EL-011
ALP-E11-00000-ME-TST-0001 | Construction Power Supply - Factory Acceptance Test Procedure | RMU, temporary distribution | E11 | 00000 | plant general | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-EL-011 |  | 1 | 2026-11-02 | 2026-11-02 |  | 2026-11-02 |  |  | PO MR-EL-011
ALP-E12-00000-GE-ITP-0001 | Electrical and I&C Installation - Subcontractor Inspection and Test Plans | subcontract | E12 | 00000 | plant general | general | ITP | Q | approval |  |  | 1 | 8 |  |  |  | MR-EL-012 |  | 1 | 2027-07-05 | 2027-07-19 |  | 2027-08-02 |  |  | PO MR-EL-012
ALP-E12-00000-GE-MOS-0001 | Electrical and I&C Installation - Subcontractor Method Statements, Part 1 of 6 | subcontract | E12 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-EL-012 |  | 1 | 2027-07-05 | 2027-07-19 |  | 2027-08-02 |  |  | PO MR-EL-012
ALP-E12-00000-GE-MOS-0002 | Electrical and I&C Installation - Subcontractor Method Statements, Part 2 of 6 | subcontract | E12 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-EL-012 |  | 1 | 2027-07-05 | 2027-07-19 |  | 2027-08-02 |  |  | PO MR-EL-012
ALP-E12-00000-GE-MOS-0003 | Electrical and I&C Installation - Subcontractor Method Statements, Part 3 of 6 | subcontract | E12 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-EL-012 |  | 1 | 2027-07-05 | 2027-07-19 |  | 2027-08-02 |  |  | PO MR-EL-012
ALP-E12-00000-GE-MOS-0004 | Electrical and I&C Installation - Subcontractor Method Statements, Part 4 of 6 | subcontract | E12 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-EL-012 |  | 1 | 2027-07-05 | 2027-07-19 |  | 2027-08-02 |  |  | PO MR-EL-012
ALP-E12-00000-GE-MOS-0005 | Electrical and I&C Installation - Subcontractor Method Statements, Part 5 of 6 | subcontract | E12 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-EL-012 |  | 1 | 2027-07-05 | 2027-07-19 |  | 2027-08-02 |  |  | PO MR-EL-012
ALP-E12-00000-GE-MOS-0006 | Electrical and I&C Installation - Subcontractor Method Statements, Part 6 of 6 | subcontract | E12 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-EL-012 |  | 1 | 2027-07-05 | 2027-07-19 |  | 2027-08-02 |  |  | PO MR-EL-012
ALP-EPC-00000-CM-CMP-0001 | Steam Blowing and Chemical Cleaning Procedure |  | EPC | 00000 | plant general | commissioning | CMP | B | approval |  |  |  | 60 | [5 empty] | 15 | 2027-07-30 | 2027-08-27 | 2027-09-24 | 2027-10-01 |  |  | capacity commissioning
ALP-EPC-00000-CM-CMP-0002 | Performance Test Procedure | ASME PTC 46 | EPC | 00000 | plant general | commissioning | CMP | B | approval |  |  |  | 60 | [5 empty] | 2 | 2027-02-16 | 2027-03-16 | 2027-04-13 | 2027-04-20 |  |  | capacity commissioning
ALP-EPC-00000-CM-CMP-0003 | Grid Code Compliance Test Programme |  | EPC | 00000 | plant general | commissioning | CMP | B | approval |  |  |  | 60 | [5 empty] | 2 | 2027-02-22 | 2027-03-22 | 2027-04-19 | 2027-04-26 |  |  | capacity commissioning
ALP-EPC-00000-CM-CMP-0004 | Operational Demonstration and Reliability Run Procedure |  | EPC | 00000 | plant general | commissioning | CMP | B | approval |  |  |  | 60 | [5 empty] | 2 | 2027-03-08 | 2027-04-05 | 2027-05-03 | 2027-05-10 |  |  | capacity commissioning
ALP-EPC-00000-CM-CMP-0005 | Tests on LDO Procedure |  | EPC | 00000 | plant general | commissioning | CMP | B | approval |  |  |  | 60 | [5 empty] | 3 | 2027-03-08 | 2027-04-21 | 2027-05-19 | 2027-05-26 |  |  | capacity commissioning
ALP-EPC-00000-CM-CMP-0006 | Emission and Noise Test Procedure |  | EPC | 00000 | plant general | commissioning | CMP | B | approval |  |  |  | 60 | [5 empty] | 2 | 2027-03-08 | 2027-05-24 | 2027-06-21 | 2027-06-28 |  |  | capacity commissioning
ALP-EPC-00000-CM-LST-0001 | Commissioning Systems and Turnover Boundaries List |  | EPC | 00000 | plant general | commissioning | LST | P | review |  |  |  | 80 | [5 empty] | 43 | 2027-10-20 | 2027-11-11 |  | 2027-12-09 |  |  | capacity commissioning
ALP-EPC-00000-CM-LST-0002 | Commissioning and Two-Year Operating Spares List |  | EPC | 00000 | plant general | commissioning | LST | P | review |  |  |  | 80 | [5 empty] | 50 | 2026-11-18 | 2027-05-26 |  | 2027-06-23 |  |  | capacity commissioning
ALP-EPC-00000-CM-LST-0003 | Punch List at Taking-Over |  | EPC | 00000 | plant general | commissioning | LST | P | information |  |  | 1 | 40 | [5 empty] | 1 | 2027-10-25 | 2027-11-15 |  | 2027-11-29 |  |  | capacity commissioning
ALP-EPC-00000-CM-LST-0004 | Special Tools List |  | EPC | 00000 | plant general | commissioning | LST | P | review |  |  | 1 | 24 | [5 empty] | 1 | 2027-05-26 | 2027-10-12 |  | 2027-11-09 |  |  | capacity commissioning
ALP-EPC-00000-CM-OMM-0001 | Plant Operation and Maintenance Manual |  | EPC | 00000 | plant general | commissioning | OMM | D | review |  |  |  | 200 | [5 empty] | 42 | 2027-09-24 | 2027-11-08 |  | 2027-12-06 |  |  | capacity commissioning
ALP-EPC-00000-CM-OMM-0002 | Training Manuals and Courseware | classroom, simulator, on-the-job | EPC | 00000 | plant general | commissioning | OMM | D | review |  |  | 1 | 400 | [5 empty] | 1 | 2027-12-02 | 2028-01-27 |  | 2028-02-24 |  |  | capacity commissioning
ALP-EPC-00000-CM-PLN-0001 | Commissioning Plan |  | EPC | 00000 | plant general | commissioning | PLN | B | approval |  |  |  | 120 | [5 empty] | 1 | 2026-11-02 | 2026-11-30 | 2026-12-28 | 2027-01-04
ALP-EPC-00000-CM-PLN-0002 | Training Plan | 60 Owner staff | EPC | 00000 | plant general | commissioning | PLN | B | approval |  |  |  | 120 | [5 empty] | 1 | 2027-05-25 | 2027-12-02 | 2027-12-30 | 2028-01-06 |  |  | capacity commissioning
ALP-EPC-00000-CM-PRC-0001 | Punch List and Completion Procedure |  | EPC | 00000 | plant general | commissioning | PRC | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2027-03-05 | 2027-10-20 | 2027-11-17 | 2027-11-24 |  |  | capacity commissioning
ALP-EPC-00000-CM-PRC-0002 | System Completion, Mechanical Completion and Turnover Procedure |  | EPC | 00000 | plant general | commissioning | PRC | B | approval |  |  | 1 | 60 | [5 empty] | 1 | 2027-11-08 | 2027-11-29 | 2027-12-27 | 2028-01-03 |  |  | capacity commissioning
ALP-EPC-00000-CM-TRP-0001 | Steam Blowing and Chemical Cleaning Report |  | EPC | 00000 | plant general | commissioning | TRP | Q | review |  |  | 1 | 40 | [5 empty] | 1 | 2028-09-18 | 2028-09-25 |  | 2028-10-16 |  |  | after KD-020
ALP-EPC-00000-CM-TRP-0002 | Performance Test Report incl. Uncertainty Analysis | ASME PTC 46 | EPC | 00000 | plant general | commissioning | TRP | Q | review |  |  | 1 | 120 | [5 empty] | 1 | 2029-03-19 | 2029-03-27 |  | 2029-04-17 |  |  | capacity commissioning
ALP-EPC-00000-CM-TRP-0003 | Grid Code Compliance Test Report |  | EPC | 00000 | plant general | commissioning | TRP | Q | review |  |  | 1 | 80 | [5 empty] | 1 | 2029-01-29 | 2029-02-05 |  | 2029-02-26 |  |  | after COM-020
ALP-EPC-00000-CM-TRP-0004 | Operational Demonstration and Reliability Run Report |  | EPC | 00000 | plant general | commissioning | TRP | Q | review |  |  | 1 | 60 | [5 empty] | 1 | 2029-03-28 | 2029-04-04 |  | 2029-04-25 |  |  | after COM-040
ALP-EPC-00000-CM-TRP-0005 | Tests on LDO Report |  | EPC | 00000 | plant general | commissioning | TRP | Q | review |  |  | 1 | 40 | [5 empty] | 1 | 2029-02-26 | 2029-03-05 |  | 2029-03-26 |  |  | after COM-030
ALP-EPC-00000-CM-TRP-0006 | Emission Test and Noise Survey Reports |  | EPC | 00000 | plant general | commissioning | TRP | Q | review |  |  | 1 | 60 | [5 empty] | 1 | 2029-03-26 | 2029-04-03 |  | 2029-04-24 |  |  | capacity commissioning
ALP-EPC-00000-CM-TRP-0007 | Fire Protection System Test Certificates |  | EPC | 00000 | plant general | commissioning | TRP | Q | review |  |  | 1 | 40 | [5 empty] | 1 | 2028-07-04 | 2028-07-11 |  | 2028-08-01 |  |  | after KD-010
ALP-EPC-00000-CV-CAL-0001 | Design Loads: Wind, Seismic, Equipment and Crane Loads |  | EPC | 00000 | plant general | civil | CAL | E | review |  |  |  | 60 | [5 empty] | 4 | 2026-12-28 | 2027-01-18 |  | 2027-02-08 |  |  | ALP-IEC-20MAA-CV-CAL-0001
ALP-EPC-00000-CV-DBR-0001 | Civil and Structural Design Criteria | TBDY 2018, Eurocodes | EPC | 00000 | plant general | civil | DBR | D | approval | yes | yes | 1 | 160 | [5 empty] | 1 | 2026-11-02 | 2026-12-14 | 2027-01-18 | 2027-01-25 |  |  |  |  | A IFR 2026-12-14
ALP-EPC-00000-CV-MRQ-0001 | Piling Works - Material Requisition |  | EPC | 00000 | plant general | civil | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-CV-001 |  | 1 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00000-CV-MRQ-0002 | Civil and Building Works - Material Requisition |  | EPC | 00000 | plant general | civil | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-CV-002 |  | 1 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00000-CV-MRQ-0003 | Marine Works - Material Requisition |  | EPC | 00000 | plant general | civil | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-CV-003 |  | 1 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00000-CV-RPT-0001 | Geotechnical Interpretation Report and Pile Design Basis |  | EPC | 00000 | plant general | civil | RPT | D | review |  |  |  | 60 | [5 empty] | 1 | 2026-12-14 | 2027-01-04 |  | 2027-01-25 |  |  | ALP-EPC-00000-CV-DBR-0001
ALP-EPC-00000-CV-RPT-0002 | Dewatering Design and Discharge Plan |  | EPC | 00000 | plant general | civil | RPT | D | review |  |  | 1 | 80 | [5 empty] | 1 | 2027-05-20 | 2027-06-10 |  | 2027-07-01 |  |  | capacity civil
ALP-EPC-00000-CV-RPT-0003 | Topographic Survey and Site Setting-Out Report |  | EPC | 00000 | plant general | civil | RPT | D | review |  |  | 1 | 60 | [5 empty] | 0 | 2026-11-02 | 2026-11-20 |  | 2026-12-11 |  |  |  |  | A IFR 2026-11-20
ALP-EPC-00000-CV-SPC-0001 | Concrete and Civil Works Specification |  | EPC | 00000 | plant general | civil | SPC | E | approval |  | yes |  | 80 | [5 empty] | 1 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00000-CV-SPC-0002 | Piling Specification |  | EPC | 00000 | plant general | civil | SPC | E | approval |  |  |  | 80 | [5 empty] | 1 | 2027-01-04 | 2027-02-01 | 2027-03-01 | 2027-03-08 |  |  | ALP-EPC-00000-CV-RPT-0001
ALP-EPC-00000-CV-SPC-0003 | Piling Works - Technical Specification |  | EPC | 00000 | plant general | civil | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-CV-001 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00000-CV-SPC-0004 | Civil and Building Works - Technical Specification |  | EPC | 00000 | plant general | civil | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-CV-002 |  | 2 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00000-CV-SPC-0005 | Marine Works - Technical Specification |  | EPC | 00000 | plant general | civil | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-CV-003 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00000-CV-STU-0001 | Site-Specific Seismic Hazard Study | DD-2 / DD-3 | EPC | 00000 | plant general | civil | STU | D | review |  |  | 1 | 160 | [5 empty] | 1 | 2027-05-20 | 2027-06-24 |  | 2027-07-22 |  |  | capacity civil
ALP-EPC-00000-CV-TRP-0001 | Pile Load Test Report and Pile Design Confirmation |  | EPC | 00000 | plant general | civil | TRP | Q | review |  |  | 1 | 40 | [5 empty] | 1 | 2027-06-03 | 2027-06-10 |  | 2027-07-01 |  |  | ALP-EPC-00000-CV-TST-0001
ALP-EPC-00000-CV-TST-0001 | Pile Load Test Procedure |  | EPC | 00000 | plant general | civil | TST | Q | approval |  |  | 1 | 40 | [5 empty] | 1 | 2027-04-16 | 2027-06-03 | 2027-07-01 | 2027-07-08 |  |  | capacity civil
ALP-EPC-00000-EL-BLK-0001 | Cable Block Diagrams, Part 1 of 2 |  | EPC | 00000 | plant general | electrical | BLK | F | approval |  |  | 49 | 412 | [5 empty] | 2 | 2027-09-17 | 2027-11-03 | 2027-12-01 | 2027-12-08 |  |  | capacity electrical
ALP-EPC-00000-EL-BLK-0002 | Cable Block Diagrams, Part 2 of 2 |  | EPC | 00000 | plant general | electrical | BLK | F | approval |  |  | 49 | 412 | [5 empty] | 2 | 2027-10-04 | 2027-11-16 | 2027-12-14 | 2027-12-21 |  |  | capacity electrical
ALP-EPC-00000-EL-CAL-0001 | Cable Sizing Calculation |  | EPC | 00000 | plant general | electrical | CAL | E | review |  |  |  | 60 | [5 empty] | 1 | 2026-12-24 | 2027-01-14 |  | 2027-02-04 |  |  | ALP-EPC-00000-EL-STU-0001
ALP-EPC-00000-EL-CAL-0002 | Battery, UPS and DC System Sizing Calculation |  | EPC | 00000 | plant general | electrical | CAL | E | review |  |  | 1 | 60 | [5 empty] | 1 | 2026-12-09 | 2027-01-05 |  | 2027-01-26 |  |  | capacity electrical
ALP-EPC-00000-EL-CAL-0003 | Emergency Diesel Generator and Transformer Sizing Calculation |  | EPC | 00000 | plant general | electrical | CAL | E | review |  |  | 1 | 60 | [5 empty] | 1 | 2026-12-21 | 2027-01-12 |  | 2027-02-02 |  |  | capacity electrical
ALP-EPC-00000-EL-CAL-0004 | Lighting Calculation | indoor, outdoor, emergency | EPC | 00000 | plant general | electrical | CAL | E | review |  |  | 1 | 80 | [5 empty] | 1 | 2026-12-23 | 2027-01-22 |  | 2027-02-12 |  |  | capacity electrical
ALP-EPC-00000-EL-CAL-0005 | Cathodic Protection Design | marine structures, buried piping and tanks | EPC | 00000 | plant general | electrical | CAL | E | review |  |  | 1 | 120 |  |  |  | MR-EL-010 |  | 1 | 2026-12-14 | 2027-01-04 |  | 2027-01-25 |  |  | ALP-EPC-00000-ME-RPT-0002
ALP-EPC-00000-EL-DBR-0001 | Electrical Design Criteria |  | EPC | 00000 | plant general | electrical | DBR | D | approval | yes | yes | 1 | 160 | [5 empty] | 1 | 2026-11-02 | 2026-12-14 | 2027-01-18 | 2027-01-25 |  |  |  |  | A IFR 2026-12-14
ALP-EPC-00000-EL-LST-0001 | Electrical Load List |  | EPC | 00000 | plant general | electrical | LST | P | review |  | yes |  | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00000-EL-LST-0002 | Construction Power Load List |  | EPC | 00000 | plant general | electrical | LST | P | internal |  | yes | 1 | 24 |  |  |  | MR-EL-011 |  | 1 | 2026-11-02 | 2026-11-02 |  | 2026-11-16
ALP-EPC-00000-EL-LST-0003 | Protection Relay Settings List |  | EPC | 00000 | plant general | electrical | LST | P | review |  |  | 1 | 80 | [5 empty] | 1 | 2027-09-13 | 2027-10-04 |  | 2027-11-01 |  |  | capacity electrical
ALP-EPC-00000-EL-LST-0004 | Hazardous Area Electrical Equipment Register | Ex | EPC | 00000 | plant general | electrical | LST | P | review |  |  | 1 | 40 | [5 empty] | 1 | 2027-09-13 | 2027-10-04 |  | 2027-11-01 |  |  | capacity electrical
ALP-EPC-00000-EL-MRQ-0001 | Power and Control Cables - Material Requisition |  | EPC | 00000 | plant general | electrical | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-EL-008 |  | 1 | 2027-02-08 | 2027-02-15 |  | 2027-02-18 |  |  | ALP-EPC-00000-EL-SPC-0004
ALP-EPC-00000-EL-MRQ-0002 | Cable Trays, Earthing and Lighting Materials - Material Requisition |  | EPC | 00000 | plant general | electrical | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-EL-009 |  | 1 | 2027-01-11 | 2027-01-18 |  | 2027-01-21 |  |  | ALP-EPC-00000-EL-SPC-0005
ALP-EPC-00000-EL-RPT-0001 | Electrical Control and Interlock Philosophy |  | EPC | 00000 | plant general | electrical | RPT | D | review |  |  | 1 | 60 | [5 empty] | 1 | 2027-01-05 | 2027-10-11 |  | 2027-11-01 |  |  | capacity electrical
ALP-EPC-00000-EL-SLD-0001 | Overall Key Single Line Diagram |  | EPC | 00000 | plant general | electrical | SLD | F | approval | yes | yes |  | 60 | [5 empty] | 3 | 2026-11-02 | 2026-11-02 | 2026-12-07 | 2026-12-14
ALP-EPC-00000-EL-SLD-0002 | Construction Power Supply Single Line Diagram and RMU Design |  | EPC | 00000 | plant general | electrical | SLD | F | internal |  | yes | 2 | 60 |  |  |  | MR-EL-011 |  | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-16
ALP-EPC-00000-EL-SPC-0001 | Power and Control Cable Specification |  | EPC | 00000 | plant general | electrical | SPC | E | approval |  |  |  | 80 | [5 empty] | 1 | 2026-12-14 | 2027-01-11 | 2027-02-08 | 2027-02-15 |  |  | ALP-EPC-00000-EL-DBR-0001
ALP-EPC-00000-EL-SPC-0002 | LV and MV Motor Specification |  | EPC | 00000 | plant general | electrical | SPC | E | approval |  |  |  | 80 | [5 empty] | 1 | 2027-01-05 | 2027-10-19 | 2027-11-16 | 2027-11-23 |  |  | capacity electrical
ALP-EPC-00000-EL-SPC-0003 | Revenue Metering and TSO SCADA Interface Specification |  | EPC | 00000 | plant general | electrical | SPC | E | approval |  |  |  | 80 | [5 empty] | 1 | 2026-12-07 | 2027-01-05 | 2027-02-02 | 2027-02-09 |  |  | capacity electrical
ALP-EPC-00000-EL-SPC-0004 | Power and Control Cables - Technical Specification |  | EPC | 00000 | plant general | electrical | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-EL-008 |  | 2 | 2027-01-11 | 2027-02-08 | 2027-03-08 | 2027-03-15 |  |  | ALP-EPC-00000-EL-SPC-0001
ALP-EPC-00000-EL-SPC-0005 | Cable Trays, Earthing and Lighting Materials - Technical Specification |  | EPC | 00000 | plant general | electrical | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-EL-009 |  | 1 | 2026-12-14 | 2027-01-11 | 2027-02-08 | 2027-02-15 |  |  | ALP-EPC-00000-EL-DBR-0001
ALP-EPC-00000-EL-STU-0001 | Load Flow, Short-Circuit and Motor Starting Study | IEC 60909 | EPC | 00000 | plant general | electrical | STU | D | review |  |  |  | 160 | [5 empty] | 1 | 2026-11-18 | 2026-12-24 |  | 2027-01-21 |  |  | capacity electrical
ALP-EPC-00000-EL-STU-0002 | Protection Coordination Study and Relay Settings |  | EPC | 00000 | plant general | electrical | STU | D | review |  |  |  | 160 | [5 empty] | 1 | 2026-12-24 | 2027-01-28 |  | 2027-02-25 |  |  | ALP-EPC-00000-EL-STU-0001
ALP-EPC-00000-EL-STU-0003 | Earthing Study | IEEE 80 | EPC | 00000 | plant general | electrical | STU | D | review |  |  |  | 160 | [5 empty] | 2 | 2027-01-04 | 2027-02-08 |  | 2027-03-08 |  |  | ALP-EPC-00000-CV-RPT-0001
ALP-EPC-00000-EL-STU-0004 | Lightning Protection Risk Assessment | IEC 62305 | EPC | 00000 | plant general | electrical | STU | D | review |  |  |  | 160 | [5 empty] | 1 | 2026-11-09 | 2026-12-15 |  | 2027-01-12 |  |  | capacity electrical
ALP-EPC-00000-EL-STU-0005 | Insulation Coordination Study | 380 kV | EPC | 00000 | plant general | electrical | STU | D | review |  |  |  | 160 | [5 empty] | 1 | 2026-11-02 | 2026-12-07 |  | 2027-01-04
ALP-EPC-00000-EL-STU-0006 | Grid Code Compliance and Reactive Capability Study |  | EPC | 00000 | plant general | electrical | STU | D | review |  |  |  | 160 | [5 empty] | 2 | 2026-12-01 | 2027-01-06 |  | 2027-02-03 |  |  | capacity electrical
ALP-EPC-00000-EL-TRP-0001 | Revenue Metering and TSO SCADA Interface Test Report |  | EPC | 00000 | plant general | electrical | TRP | Q | review |  |  | 1 | 40 | [5 empty] | 1 | 2028-07-04 | 2028-07-11 |  | 2028-08-01 |  |  | after KD-010
ALP-EPC-00000-GE-DBR-0001 | Plant Design Basis Report |  | EPC | 00000 | plant general | general | DBR | D | approval | yes | yes | 1 | 160 | [5 empty] | 0 | 2026-11-02 | 2026-11-16 | 2026-12-21 | 2026-12-28 |  |  |  |  | A IFR 2026-11-16
ALP-EPC-00000-GE-ITP-0001 | Construction Power Supply - Inspection and Test Plan | RMU, temporary distribution | EPC | 00000 | plant general | general | ITP | Q | internal |  | yes | 1 | 16 |  |  |  | MR-EL-011 |  | 1 | 2026-11-02 | 2026-11-02 |  | 2026-11-09
ALP-EPC-00000-GE-LST-0001 | Codes, Standards and Regulations Register | Appendix A.19 | EPC | 00000 | plant general | general | LST | P | review |  |  |  | 80 | [5 empty] | 1 | 2026-11-26 | 2027-03-26 |  | 2027-04-23 |  |  | capacity general
ALP-EPC-00000-GE-LST-0002 | Permits and Authorities Register |  | EPC | 00000 | plant general | general | LST | P | review |  |  |  | 80 | [5 empty] | 1 | 2026-12-08 | 2027-04-12 |  | 2027-05-10 |  |  | capacity general
ALP-EPC-00000-GE-LST-0003 | Tie-in and Terminal Point Register |  | EPC | 00000 | plant general | general | LST | P | review |  |  |  | 80 | [5 empty] | 2 | 2027-03-25 | 2027-04-15 |  | 2027-05-13 |  |  | capacity general
ALP-EPC-00000-GE-LST-0004 | Variation and Change Register | technical proposals | EPC | 00000 | plant general | general | LST | P | review |  |  | 1 | 40 | [5 empty] | 1 | 2026-11-25 | 2027-04-14 |  | 2027-05-12 |  |  | capacity general
ALP-EPC-00000-GE-LST-0005 | As-Built Documentation Index |  | EPC | 00000 | plant general | general | LST | P | review |  |  | 1 | 40 | [5 empty] | 1 | 2027-03-26 | 2027-04-16 |  | 2027-05-14 |  |  | capacity general
ALP-EPC-00000-GE-MDL-0001 | Master Document List | MDL | EPC | 00000 | plant general | general | MDL | A | information |  |  |  | 60 | [5 empty] | 1 | 2027-05-03 | 2027-05-17 |  | 2027-05-24 |  |  | ALP-EPC-00000-GE-PLN-0001
ALP-EPC-00000-GE-MRQ-0001 | Construction Power Supply - Material Requisition | RMU, temporary distribution | EPC | 00000 | plant general | general | MRQ | C | internal |  | yes | 1 | 24 |  |  |  | MR-EL-011 |  | 1 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00000-GE-MRQ-0002 | Electrical and I&C Installation - Material Requisition | subcontract | EPC | 00000 | plant general | general | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-EL-012 |  | 1 | 2027-04-07 | 2027-04-14 |  | 2027-04-19 |  |  | ALP-EPC-00000-GE-SPC-0002
ALP-EPC-00000-GE-MRQ-0003 | Instrument Installation Materials - Material Requisition | tubing, fittings, junction boxes, supports | EPC | 00000 | plant general | general | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-IC-010 |  | 1 | 2027-04-14 | 2027-04-21 |  | 2027-04-26 |  |  | ALP-EPC-00000-GE-SPC-0003
ALP-EPC-00000-GE-MRQ-0004 | Painting and Insulation - Material Requisition | subcontract | EPC | 00000 | plant general | general | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-ME-022 |  | 1 | 2027-04-15 | 2027-04-22 |  | 2027-04-27 |  |  | ALP-EPC-00000-GE-SPC-0004
ALP-EPC-00000-GE-MRQ-0005 | Mechanical and Piping Erection - Material Requisition | subcontract | EPC | 00000 | plant general | general | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-ME-023 |  | 1 | 2027-06-18 | 2027-06-25 |  | 2027-06-30 |  |  | ALP-EPC-00000-GE-SPC-0005
ALP-EPC-00000-GE-MRQ-0006 | Pipe Supports, Spring Hangers and Snubbers - Material Requisition |  | EPC | 00000 | plant general | general | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-PI-005 |  | 1 | 2027-03-18 | 2027-03-25 |  | 2027-03-30 |  |  | ALP-EPC-00000-GE-SPC-0006
ALP-EPC-00000-GE-MRQ-0007 | Piping Specialty Items - Material Requisition | strainers, steam traps, expansion joints, sight glasses | EPC | 00000 | plant general | general | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-PI-006 |  | 1 | 2026-11-30 | 2026-12-07 |  | 2026-12-10 |  |  | ALP-EPC-00000-GE-SPC-0007
ALP-EPC-00000-GE-MRQ-0008 | Safety and Relief Valves - Material Requisition |  | EPC | 00000 | plant general | general | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-PI-007 |  | 1 | 2026-11-30 | 2026-12-07 |  | 2026-12-10 |  |  | ALP-EPC-00000-GE-SPC-0008
ALP-EPC-00000-GE-PLN-0001 | Engineering Execution Plan | workflow, interfaces, timeline | EPC | 00000 | plant general | general | PLN | B | approval |  |  |  | 120 | [5 empty] | 2 | 2027-04-01 | 2027-05-03 | 2027-05-31 | 2027-06-07 |  |  | capacity general
ALP-EPC-00000-GE-PLN-0002 | Advanced Work Packaging Execution Plan | CWA, CWP, EWP, PWP, IWP | EPC | 00000 | plant general | general | PLN | B | approval |  |  |  | 120 | [5 empty] | 1 | 2027-05-03 | 2027-05-31 | 2027-06-28 | 2027-07-05 |  |  | ALP-EPC-00000-GE-PLN-0001
ALP-EPC-00000-GE-PLN-0003 | Project Quality Plan | engineering, procurement, construction | EPC | 00000 | plant general | general | PLN | B | approval |  |  |  | 120 | [5 empty] | 1 | 2027-04-09 | 2027-05-10 | 2027-06-07 | 2027-06-14 |  |  | capacity general
ALP-EPC-00000-GE-PLN-0004 | Interface Management Plan | Owner, IEC, TSO, gas network operator | EPC | 00000 | plant general | general | PLN | B | approval |  |  |  | 120 | [5 empty] | 1 | 2027-04-15 | 2027-05-13 | 2027-06-10 | 2027-06-17 |  |  | ALP-EPC-00000-GE-LST-0003
ALP-EPC-00000-GE-PLN-0005 | Project Execution Plan |  | EPC | 00000 | plant general | general | PLN | B | approval |  |  | 1 | 160 | [5 empty] | 1 | 2027-05-10 | 2027-06-08 | 2027-07-06 | 2027-07-13 |  |  | capacity general
ALP-EPC-00000-GE-PRC-0001 | KKS Identification Manual | project key list and tagging rules | EPC | 00000 | plant general | general | PRC | B | approval | yes |  |  | 80 | [5 empty] | 0 | 2026-11-02 | 2026-11-20 | 2026-12-25 | 2027-01-01 |  |  |  |  | A IFR 2026-11-20
ALP-EPC-00000-GE-PRC-0002 | Document Numbering and Document Control Procedure |  | EPC | 00000 | plant general | general | PRC | B | approval |  |  |  | 80 | [5 empty] | 0 | 2026-11-02 | 2026-11-13 | 2026-12-11 | 2026-12-18 |  |  |  |  | A IFR 2026-11-13
ALP-EPC-00000-GE-PRC-0003 | As-Built Documentation and Engineering Database Handover Procedure |  | EPC | 00000 | plant general | general | PRC | B | approval |  |  |  | 80 | [5 empty] | 1 | 2026-11-13 | 2026-12-09 | 2027-01-06 | 2027-01-13 |  |  | capacity general
ALP-EPC-00000-GE-RPT-0001 | Piling Works - Technical Bid Evaluation |  | EPC | 00000 | plant general | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-CV-001 |  | 1 | 2026-12-03 | 2027-01-14 |  | 2027-01-21 |  |  | capacity general
ALP-EPC-00000-GE-RPT-0002 | Civil and Building Works - Technical Bid Evaluation |  | EPC | 00000 | plant general | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-CV-002 |  | 1 | 2026-12-03 | 2026-12-24 |  | 2026-12-31 |  |  | bids MR-CV-002
ALP-EPC-00000-GE-RPT-0003 | Power and Control Cables - Technical Bid Evaluation |  | EPC | 00000 | plant general | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-EL-008 |  | 1 | 2027-03-18 | 2027-04-08 |  | 2027-04-15 |  |  | bids MR-EL-008
ALP-EPC-00000-GE-RPT-0004 | Construction Power Supply - Technical Bid Evaluation | RMU, temporary distribution | EPC | 00000 | plant general | general | RPT | D | internal |  | yes | 1 | 40 |  |  |  | MR-EL-011 |  | 1 | 2026-11-02 | 2026-11-02 |  | 2026-11-09
ALP-EPC-00000-GE-RPT-0005 | Electrical and I&C Installation - Technical Bid Evaluation | subcontract | EPC | 00000 | plant general | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-EL-012 |  | 1 | 2027-06-14 | 2027-07-05 |  | 2027-07-12 |  |  | bids MR-EL-012
ALP-EPC-00000-GE-RPT-0006 | Field Instruments - Technical Bid Evaluation |  | EPC | 00000 | plant general | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-IC-004 |  | 1 | 2027-03-02 | 2027-03-23 |  | 2027-03-30 |  |  | capacity general
ALP-EPC-00000-GE-RPT-0007 | Control Valves - Technical Bid Evaluation |  | EPC | 00000 | plant general | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-IC-005 |  | 1 | 2027-02-25 | 2027-03-18 |  | 2027-03-25 |  |  | bids MR-IC-005
ALP-EPC-00000-GE-RPT-0008 | Instrument Installation Materials - Technical Bid Evaluation | tubing, fittings, junction boxes, supports | EPC | 00000 | plant general | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-IC-010 |  | 1 | 2027-05-24 | 2027-06-14 |  | 2027-06-21 |  |  | bids MR-IC-010
ALP-EPC-00000-GE-RPT-0009 | Painting and Insulation - Technical Bid Evaluation | subcontract | EPC | 00000 | plant general | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-022 |  | 1 | 2027-06-08 | 2027-06-29 |  | 2027-07-06 |  |  | bids MR-ME-022
ALP-EPC-00000-GE-RPT-0010 | Mechanical and Piping Erection - Technical Bid Evaluation | subcontract | EPC | 00000 | plant general | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-023 |  | 1 | 2027-08-25 | 2027-09-15 |  | 2027-09-22 |  |  | bids MR-ME-023
ALP-EPC-00000-GE-RPT-0011 | Piping Bulk Materials - Technical Bid Evaluation | carbon steel, stainless | EPC | 00000 | plant general | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-PI-001 |  | 1 | 2027-01-07 | 2027-01-28 |  | 2027-02-04 |  |  | bids MR-PI-001
ALP-EPC-00000-GE-RPT-0012 | Valves - Technical Bid Evaluation | manual and check | EPC | 00000 | plant general | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-PI-003 |  | 1 | 2027-02-15 | 2027-03-08 |  | 2027-03-15 |  |  | capacity general
ALP-EPC-00000-GE-RPT-0013 | Pipe Supports, Spring Hangers and Snubbers - Technical Bid Evaluation |  | EPC | 00000 | plant general | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-PI-005 |  | 1 | 2027-05-04 | 2027-05-25 |  | 2027-06-01 |  |  | bids MR-PI-005
ALP-EPC-00000-GE-RPT-0014 | Piping Specialty Items - Technical Bid Evaluation | strainers, steam traps, expansion joints, sight glasses | EPC | 00000 | plant general | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-PI-006 |  | 1 | 2027-03-15 | 2027-04-05 |  | 2027-04-12 |  |  | capacity general
ALP-EPC-00000-GE-RPT-0015 | Safety and Relief Valves - Technical Bid Evaluation |  | EPC | 00000 | plant general | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-PI-007 |  | 1 | 2027-03-04 | 2027-04-01 |  | 2027-04-08 |  |  | capacity general
ALP-EPC-00000-GE-RPT-0016 | Structural Steel Supply and Fabrication - Technical Bid Evaluation |  | EPC | 00000 | plant general | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-SS-001 |  | 1 | 2027-01-07 | 2027-01-28 |  | 2027-02-04 |  |  | capacity general
ALP-EPC-00000-GE-SPC-0001 | Construction Power Supply - Technical Specification | RMU, temporary distribution | EPC | 00000 | plant general | general | SPC | E | internal |  | yes | 1 | 80 |  |  |  | MR-EL-011 |  | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-16
ALP-EPC-00000-GE-SPC-0002 | Electrical and I&C Installation - Technical Specification | subcontract | EPC | 00000 | plant general | general | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-EL-012 |  | 2 | 2026-12-14 | 2027-04-07 | 2027-05-05 | 2027-05-12 |  |  | capacity general
ALP-EPC-00000-GE-SPC-0003 | Instrument Installation Materials - Technical Specification | tubing, fittings, junction boxes, supports | EPC | 00000 | plant general | general | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-IC-010 |  | 2 | 2027-03-15 | 2027-04-14 | 2027-05-12 | 2027-05-19 |  |  | capacity general
ALP-EPC-00000-GE-SPC-0004 | Painting and Insulation - Technical Specification | subcontract | EPC | 00000 | plant general | general | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-ME-022 |  | 3 | 2027-03-18 | 2027-04-15 | 2027-05-13 | 2027-05-20 |  |  | capacity general
ALP-EPC-00000-GE-SPC-0005 | Mechanical and Piping Erection - Technical Specification | subcontract | EPC | 00000 | plant general | general | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-ME-023 |  | 3 | 2027-05-21 | 2027-06-18 | 2027-07-16 | 2027-07-23 |  |  | ALP-EPC-00000-PI-SPC-0003
ALP-EPC-00000-GE-SPC-0006 | Pipe Supports, Spring Hangers and Snubbers - Technical Specification |  | EPC | 00000 | plant general | general | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-PI-005 |  | 2 | 2027-02-18 | 2027-03-18 | 2027-04-15 | 2027-04-22 |  |  | capacity general
ALP-EPC-00000-GE-SPC-0007 | Piping Specialty Items - Technical Specification | strainers, steam traps, expansion joints, sight glasses | EPC | 00000 | plant general | general | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-PI-006 |  | 1 | 2026-11-02 | 2026-11-30 | 2026-12-28 | 2027-01-04
ALP-EPC-00000-GE-SPC-0008 | Safety and Relief Valves - Technical Specification |  | EPC | 00000 | plant general | general | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-PI-007 |  | 1 | 2026-11-02 | 2026-11-30 | 2026-12-28 | 2027-01-04
ALP-EPC-00000-HS-DBR-0001 | HSE Design Criteria | noise, safety distances, escape and access, ergonomics, hazardous substances | EPC | 00000 | plant general | hse | DBR | D | approval | yes |  | 1 | 200 | [5 empty] | 1 | 2026-11-02 | 2026-12-14 | 2027-01-18 | 2027-01-25 |  |  |  |  | A IFR 2026-12-14
ALP-EPC-00000-HS-HAZ-0001 | HAZID Report |  | EPC | 00000 | plant general | hse | HAZ | S | approval |  |  |  | 160 | [5 empty] | 3 | 2027-01-01 | 2027-02-17 | 2027-03-17 | 2027-03-24 |  |  | capacity hse
ALP-EPC-00000-HS-HAZ-0002 | GT Fuel Gas System and Gas Station - HAZOP Report |  | EPC | 00000 | plant general | hse | HAZ | S | approval |  |  |  | 160 | [5 empty] | 3 | 2027-05-06 | 2027-06-03 | 2027-07-01 | 2027-07-08 |  |  | ALP-EPC-00EKC-PR-PID-0001
ALP-EPC-00000-HS-HAZ-0003 | Water-Steam Cycle - HAZOP Report |  | EPC | 00000 | plant general | hse | HAZ | S | approval |  |  |  | 160 | [5 empty] | 16 | 2027-06-15 | 2027-07-13 | 2027-08-10 | 2027-08-17 |  |  | ALP-EPC-20LCB-PR-PID-0001
ALP-EPC-00000-HS-HAZ-0004 | LDO and Ammonia Systems - HAZOP Report |  | EPC | 00000 | plant general | hse | HAZ | S | approval |  |  |  | 160 | [5 empty] | 4 | 2027-06-11 | 2027-07-09 | 2027-08-06 | 2027-08-13 |  |  | ALP-EPC-10HSB-PR-PID-0001
ALP-EPC-00000-HS-HAZ-0005 | Water Treatment and Chemicals - HAZOP Report |  | EPC | 00000 | plant general | hse | HAZ | S | approval |  |  |  | 160 | [5 empty] | 8 | 2027-06-14 | 2027-07-16 | 2027-08-13 | 2027-08-20 |  |  | capacity hse
ALP-EPC-00000-HS-HAZ-0006 | BOP Utilities - HAZOP Report | aux boiler, air, N2, H2, CCW | EPC | 00000 | plant general | hse | HAZ | S | approval |  |  |  | 160 | [5 empty] | 7 | 2027-05-10 | 2027-06-07 | 2027-07-05 | 2027-07-12 |  |  | ALP-EPC-00QJA-PR-PID-0001
ALP-EPC-00000-HS-HAZ-0007 | SIL Determination and Verification | IEC 61511 | EPC | 00000 | plant general | hse | HAZ | S | approval |  |  |  | 160 | [5 empty] | 5 | 2027-07-16 | 2027-08-13 | 2027-09-10 | 2027-09-17 |  |  | ALP-EPC-00000-HS-HAZ-0005
ALP-EPC-00000-HS-HAZ-0008 | Hazardous Area Classification Report and Drawings | IEC 60079-10-1 | EPC | 00000 | plant general | hse | HAZ | S | approval |  |  | 6 | 360 | [5 empty] | 5 | 2027-07-09 | 2027-08-17 | 2027-09-14 | 2027-09-21 |  |  | capacity hse
ALP-EPC-00000-HS-HAZ-0009 | Fire Protection Concept and Fire Risk Assessment | NFPA 850 | EPC | 00000 | plant general | hse | HAZ | S | approval |  |  |  | 160 | [5 empty] | 2 | 2026-12-14 | 2027-01-11 | 2027-02-08 | 2027-02-15 |  |  | ALP-EPC-00000-HS-DBR-0001
ALP-EPC-00000-HS-HAZ-0010 | Major Accident Assessment and QRA | Seveso lower tier | EPC | 00000 | plant general | hse | HAZ | S | approval |  |  |  | 160 | [5 empty] | 2 | 2027-07-15 | 2027-09-10 | 2027-10-08 | 2027-10-15 |  |  | capacity hse
ALP-EPC-00000-HS-PLN-0001 | HSE in Design Plan and Safety-in-Design Register |  | EPC | 00000 | plant general | hse | PLN | B | approval |  |  |  | 120 | [5 empty] | 1 | 2026-11-16 | 2026-12-14 | 2027-01-11 | 2027-01-18 |  |  | ALP-EPC-00000-GE-DBR-0001
ALP-EPC-00000-HS-PLN-0002 | Construction HSE Plan and Site Safety Plan | ISO 45001 | EPC | 00000 | plant general | hse | PLN | B | approval |  |  | 1 | 160 | [5 empty] | 1 | 2027-01-18 | 2027-03-15 | 2027-04-12 | 2027-04-19 |  |  | capacity hse
ALP-EPC-00000-HS-PLN-0003 | Construction Environmental and Social Management Plan | CESMP | EPC | 00000 | plant general | hse | PLN | B | approval |  |  | 1 | 200 | [5 empty] | 1 | 2027-02-23 | 2027-03-24 | 2027-04-21 | 2027-04-28 |  |  | capacity hse
ALP-EPC-00000-HS-PLN-0004 | Waste Management Plan | construction and operation | EPC | 00000 | plant general | hse | PLN | B | approval |  |  | 1 | 80 | [5 empty] | 1 | 2027-03-05 | 2027-04-02 | 2027-04-30 | 2027-05-07 |  |  | capacity hse
ALP-EPC-00000-HS-PLN-0005 | Emergency Response Plan | construction and operation | EPC | 00000 | plant general | hse | PLN | B | approval |  |  | 1 | 80 | [5 empty] | 1 | 2027-09-10 | 2027-10-08 | 2027-11-05 | 2027-11-12 |  |  | ALP-EPC-00000-HS-HAZ-0010
ALP-EPC-00000-HS-PLN-0006 | Radiation Protection Plan | industrial radiography | EPC | 00000 | plant general | hse | PLN | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2027-05-21 | 2027-08-19 | 2027-09-16 | 2027-09-23 |  |  | capacity hse
ALP-EPC-00000-HS-RPT-0001 | EIA Conditions Compliance Matrix |  | EPC | 00000 | plant general | hse | RPT | D | review |  |  |  | 60 | [5 empty] | 1 | 2026-11-02 | 2026-12-14 |  | 2027-01-04 |  |  |  |  | A IFR 2026-12-14
ALP-EPC-00000-HS-RPT-0002 | Constructability and Maintainability Review | AWP input | EPC | 00000 | plant general | hse | RPT | D | review |  |  |  | 60 | [5 empty] | 2 | 2026-12-07 | 2027-03-26 |  | 2027-04-16 |  |  | capacity hse
ALP-EPC-00000-HS-RPT-0003 | Soil and Groundwater Baseline Survey Report |  | EPC | 00000 | plant general | hse | RPT | D | review |  |  | 1 | 80 | [5 empty] | 1 | 2027-03-15 | 2027-04-06 |  | 2027-04-27 |  |  | capacity hse
ALP-EPC-00000-HS-RPT-0004 | HAZOP Close-Out Report |  | EPC | 00000 | plant general | hse | RPT | D | review |  |  | 1 | 80 | [5 empty] | 2 | 2027-08-16 | 2027-09-06 |  | 2027-09-27 |  |  | capacity hse
ALP-EPC-00000-HS-RPT-0005 | Explosion Protection Document | ATEX 2014/34/EU, workplace directive | EPC | 00000 | plant general | hse | RPT | D | review |  |  | 1 | 80 | [5 empty] | 1 | 2027-08-17 | 2027-09-07 |  | 2027-09-28 |  |  | ALP-EPC-00000-HS-HAZ-0008
ALP-EPC-00000-HS-RPT-0006 | Occupational Health and Safety Risk Assessment | design phase | EPC | 00000 | plant general | hse | RPT | D | review |  |  | 1 | 60 | [5 empty] | 1 | 2027-03-24 | 2027-04-14 |  | 2027-05-05 |  |  | capacity hse
ALP-EPC-00000-HS-STU-0001 | Noise Study | near field and environmental | EPC | 00000 | plant general | hse | STU | D | review |  |  |  | 160 | [5 empty] | 3 | 2027-01-11 | 2027-02-15 |  | 2027-03-15 |  |  | ALP-IEC-10MBA-HS-RPT-0001
ALP-EPC-00000-HS-STU-0002 | Stack Dispersion Confirmation | stack height 65 m | EPC | 00000 | plant general | hse | STU | D | review |  |  |  | 160 | [5 empty] | 1 | 2026-12-14 | 2027-01-18 |  | 2027-02-15 |  |  | ALP-EPC-00000-PR-HMB-0001
ALP-EPC-00000-HS-STU-0003 | Fire and Gas Detector Mapping Study |  | EPC | 00000 | plant general | hse | STU | D | review |  |  | 1 | 120 | [5 empty] | 2 | 2027-08-19 | 2027-09-28 |  | 2027-10-26 |  |  | capacity hse
ALP-EPC-00000-HV-DBR-0001 | HVAC Design Criteria |  | EPC | 00000 | plant general | hvac | DBR | D | approval |  | yes | 1 | 160 | [5 empty] | 1 | 2026-11-02 | 2026-12-14 | 2027-01-11 | 2027-01-18 |  |  |  |  | A IFR 2026-12-14
ALP-EPC-00000-IC-CNR-0001 | Unit Coordination, Load Control, Export Limiter and Fuel Transfer |  | EPC | 00000 | plant general | i_and_c | CNR | F | review |  |  |  | 60 | [5 empty] | 2 | 2027-02-08 | 2027-03-01 |  | 2027-03-29 |  |  | ALP-IEC-10MBY-IC-CNR-0001
ALP-EPC-00000-IC-DBR-0001 | I&C Design Criteria and Control Philosophy |  | EPC | 00000 | plant general | i_and_c | DBR | D | approval | yes | yes | 1 | 160 | [5 empty] | 1 | 2026-11-02 | 2026-12-14 | 2027-01-18 | 2027-01-25 |  |  |  |  | A IFR 2026-12-14
ALP-EPC-00000-IC-IOL-0001 | Plant I/O List | DCS | EPC | 00000 | plant general | i_and_c | IOL | P | review |  |  |  | 60 | [5 empty] | 2 | 2027-07-06 | 2027-07-27 |  | 2027-08-24 |  |  | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00000-IC-LST-0001 | Instrument Index |  | EPC | 00000 | plant general | i_and_c | LST | P | review |  |  |  | 80 | [5 empty] | 42 | 2027-06-15 | 2027-07-06 |  | 2027-08-03 |  |  | ALP-EPC-20LCB-PR-PID-0001
ALP-EPC-00000-IC-LST-0002 | Alarm List |  | EPC | 00000 | plant general | i_and_c | LST | P | review |  |  | 1 | 80 | [5 empty] | 1 | 2027-01-04 | 2027-01-25 |  | 2027-02-22 |  |  | ALP-EPC-00000-IC-RPT-0001
ALP-EPC-00000-IC-LST-0003 | Interlock and Trip List |  | EPC | 00000 | plant general | i_and_c | LST | P | review |  |  | 1 | 80 | [5 empty] | 1 | 2027-08-17 | 2027-09-08 |  | 2027-10-06 |  |  | capacity i_and_c
ALP-EPC-00000-IC-MRQ-0001 | Field Instruments - Material Requisition |  | EPC | 00000 | plant general | i_and_c | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-IC-004 |  | 1 | 2027-01-11 | 2027-01-18 |  | 2027-01-21 |  |  | ALP-EPC-00000-IC-SPC-0003
ALP-EPC-00000-IC-MRQ-0002 | Control Valves - Material Requisition |  | EPC | 00000 | plant general | i_and_c | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-IC-005 |  | 1 | 2027-01-11 | 2027-01-18 |  | 2027-01-21 |  |  | ALP-EPC-00000-IC-SPC-0004
ALP-EPC-00000-IC-RPT-0001 | Alarm Management Philosophy | EEMUA 191 / IEC 62682 | EPC | 00000 | plant general | i_and_c | RPT | D | review |  |  |  | 60 | [5 empty] | 1 | 2026-12-14 | 2027-01-04 |  | 2027-01-25 |  |  | ALP-EPC-00000-IC-DBR-0001
ALP-EPC-00000-IC-RPT-0002 | OT Cybersecurity Concept | IEC 62443, SL2 | EPC | 00000 | plant general | i_and_c | RPT | D | review |  |  |  | 60 | [5 empty] | 1 | 2026-12-14 | 2027-01-04 |  | 2027-01-25 |  |  | ALP-EPC-00000-IC-DBR-0001
ALP-EPC-00000-IC-SPC-0001 | Field Instrument Specification |  | EPC | 00000 | plant general | i_and_c | SPC | E | approval |  |  |  | 80 | [5 empty] | 1 | 2026-12-14 | 2027-01-11 | 2027-02-08 | 2027-02-15 |  |  | ALP-EPC-00000-IC-DBR-0001
ALP-EPC-00000-IC-SPC-0002 | Control Valve Specification |  | EPC | 00000 | plant general | i_and_c | SPC | E | approval |  |  |  | 80 | [5 empty] | 1 | 2026-12-14 | 2027-01-11 | 2027-02-08 | 2027-02-15 |  |  | ALP-EPC-00000-IC-DBR-0001
ALP-EPC-00000-IC-SPC-0003 | Field Instruments - Technical Specification |  | EPC | 00000 | plant general | i_and_c | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-IC-004 |  | 1 | 2026-12-14 | 2027-01-11 | 2027-02-08 | 2027-02-15 |  |  | ALP-EPC-00000-IC-DBR-0001
ALP-EPC-00000-IC-SPC-0004 | Control Valves - Technical Specification |  | EPC | 00000 | plant general | i_and_c | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-IC-005 |  | 1 | 2026-12-14 | 2027-01-11 | 2027-02-08 | 2027-02-15 |  |  | ALP-EPC-00000-IC-DBR-0001
ALP-EPC-00000-IC-SPC-0005 | DCS Functional Design Specification |  | EPC | 00000 | plant general | i_and_c | SPC | E | approval |  |  | 1 | 200 | [5 empty] | 1 | 2026-12-14 | 2027-01-11 | 2027-02-08 | 2027-02-15 |  |  | ALP-EPC-00000-IC-DBR-0001
ALP-EPC-00000-IC-SPC-0006 | BOP SIS - Safety Requirements Specification | IEC 61511 | EPC | 00000 | plant general | i_and_c | SPC | E | approval |  |  | 1 | 120 | [5 empty] | 1 | 2027-09-07 | 2027-10-05 | 2027-11-02 | 2027-11-09 |  |  | capacity i_and_c
ALP-EPC-00000-IC-TRP-0001 | OT Cybersecurity Acceptance Test Report |  | EPC | 00000 | plant general | i_and_c | TRP | Q | review |  |  | 1 | 40 | [5 empty] | 1 | 2028-09-18 | 2028-09-25 |  | 2028-10-16 |  |  | after KD-020
ALP-EPC-00000-IC-TST-0001 | DCS Site Acceptance Test Procedure |  | EPC | 00000 | plant general | i_and_c | TST | Q | approval |  |  | 1 | 80 | [5 empty] | 1 | 2026-12-14 | 2027-01-04 | 2027-02-01 | 2027-02-08 |  |  | ALP-EPC-00000-IC-DBR-0001
ALP-EPC-00000-IC-TST-0002 | OT Cybersecurity Acceptance Test Procedure | IEC 62443 | EPC | 00000 | plant general | i_and_c | TST | Q | approval |  |  | 1 | 60 | [5 empty] | 1 | 2027-01-04 | 2027-01-25 | 2027-02-22 | 2027-03-01 |  |  | ALP-EPC-00000-IC-RPT-0002
ALP-EPC-00000-ME-DBR-0001 | Mechanical Design Criteria | rotating and static equipment codes, margins, NPSH, vibration, noise, materials and corrosion allowance | EPC | 00000 | plant general | mechanical | DBR | D | approval | yes |  | 1 | 200 | [5 empty] | 2 | 2027-01-11 | 2027-02-08 | 2027-03-15 | 2027-03-22 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00000-ME-LST-0001 | Heavy and Oversized Piece List | power island and BOP | EPC | 00000 | plant general | mechanical | LST | P | review |  |  | 1 | 24 | [5 empty] | 1 | 2026-12-07 | 2026-12-28 |  | 2027-01-25 |  |  | ALP-EPC-00000-ME-STU-0001
ALP-EPC-00000-ME-PLN-0001 | Marine Operations Plan | heavy-lift barge, harbour master approval | EPC | 00000 | plant general | mechanical | PLN | B | approval |  |  | 1 | 80 | [5 empty] | 1 | 2026-12-07 | 2027-01-04 | 2027-02-01 | 2027-02-08 |  |  | ALP-EPC-00000-ME-STU-0001
ALP-EPC-00000-ME-RPT-0001 | Abnormal Load Route Survey and Transport Drawings |  | EPC | 00000 | plant general | mechanical | RPT | D | review |  |  | 10 | 120 | [5 empty] | 1 | 2026-12-07 | 2027-01-06 |  | 2027-01-27 |  |  | ALP-EPC-00000-ME-STU-0001
ALP-EPC-00000-ME-RPT-0002 | Materials Selection and Corrosion Control Report | marine atmosphere, seawater | EPC | 00000 | plant general | mechanical | RPT | D | review |  |  | 1 | 120 | [5 empty] | 1 | 2026-11-02 | 2026-12-14 |  | 2027-01-04 |  |  |  |  | A IFR 2026-12-14
ALP-EPC-00000-ME-SPC-0001 | General Mechanical Specification | rotating and static equipment | EPC | 00000 | plant general | mechanical | SPC | E | approval |  | yes |  | 80 | [5 empty] | 1 | 2026-11-02 | 2026-12-14 | 2027-01-11 | 2027-01-18 |  |  |  |  | A IFR 2026-12-14
ALP-EPC-00000-ME-SPC-0002 | Painting and Coating Specification | ISO 12944, C5 | EPC | 00000 | plant general | mechanical | SPC | E | approval |  |  |  | 80 | [5 empty] | 1 | 2026-11-02 | 2026-12-14 | 2027-01-11 | 2027-01-18 |  |  |  |  | A IFR 2026-12-14
ALP-EPC-00000-ME-SPC-0003 | Insulation Specification |  | EPC | 00000 | plant general | mechanical | SPC | E | approval |  |  |  | 80 | [5 empty] | 1 | 2026-11-16 | 2026-12-14 | 2027-01-11 | 2027-01-18 |  |  | ALP-EPC-00000-GE-DBR-0001
ALP-EPC-00000-ME-STU-0001 | Heavy Transport, Lifting and Erection Study | barge, SPMT, cranes | EPC | 00000 | plant general | mechanical | STU | D | review |  |  |  | 160 | [5 empty] | 1 | 2026-11-02 | 2026-12-07 |  | 2027-01-04
ALP-EPC-00000-ME-STU-0002 | Mechanical Handling and Maintenance Access Study |  | EPC | 00000 | plant general | mechanical | STU | D | review |  |  | 1 | 80 | [5 empty] | 1 | 2026-11-16 | 2026-12-21 |  | 2027-01-18 |  |  | capacity mechanical
ALP-EPC-00000-PC-PRC-0001 | Progress Measurement and Reporting Procedure |  | EPC | 00000 | plant general | project_control | PRC | B | approval |  |  |  | 80 | [5 empty] | 1 | 2026-11-02 | 2026-12-14 | 2027-01-11 | 2027-01-18 |  |  |  |  | A IFR 2026-12-14
ALP-EPC-00000-PC-SCH-0001 | Level 3 Project Schedule | CPM | EPC | 00000 | plant general | project_control | SCH | B | review |  |  |  | 80 | [5 empty] | 2 | 2027-05-31 | 2027-06-21 |  | 2027-07-12 |  |  | ALP-EPC-00000-GE-PLN-0002
ALP-EPC-00000-PI-LST-0001 | Valve List |  | EPC | 00000 | plant general | piping | LST | P | review |  |  |  | 80 | [5 empty] | 42 | 2027-12-21 | 2028-01-11 |  | 2028-02-08 |  |  | capacity piping
ALP-EPC-00000-PI-M3D-0001 | 30 % 3D Model Review Report |  | EPC | 00000 | plant general | piping | M3D | L | review |  |  |  | 80 | [5 empty] | 1 | 2026-11-20 | 2026-12-14 |  | 2027-01-04 |  |  | capacity piping
ALP-EPC-00000-PI-M3D-0002 | 60 % 3D Model Review Report |  | EPC | 00000 | plant general | piping | M3D | L | review |  |  |  | 80 | [5 empty] | 8 | 2027-05-11 | 2027-06-01 |  | 2027-06-22 |  |  | ALP-EPC-00UPC-PI-PPL-0001
ALP-EPC-00000-PI-M3D-0003 | 90 % 3D Model Review Report |  | EPC | 00000 | plant general | piping | M3D | L | review |  |  |  | 80 | [5 empty] | 41 | 2028-03-01 | 2028-03-22 |  | 2028-04-12 |  |  | ALP-EPC-20LCA-PI-ISO-0001
ALP-EPC-00000-PI-M3D-0004 | Plant 3D Model and IFC4 Export - As-Built | native model format | EPC | 00000 | plant general | piping | M3D | L | review |  |  | 1 | 1500 | [5 empty] | 1 | 2028-03-22 | 2028-06-14 |  | 2028-07-05 |  |  | ALP-EPC-00000-PI-M3D-0003
ALP-EPC-00000-PI-MRQ-0001 | Piping Bulk Materials - Material Requisition | carbon steel, stainless | EPC | 00000 | plant general | piping | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-PI-001 |  | 1 | 2026-11-30 | 2026-12-07 |  | 2026-12-10 |  |  | ALP-EPC-00000-PI-SPC-0004
ALP-EPC-00000-PI-MRQ-0002 | Alloy Piping P91 / P22 - Material Requisition | main steam, reheat | EPC | 00000 | plant general | piping | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-PI-002 |  | 1 | 2027-01-11 | 2027-01-18 |  | 2027-01-21 |  |  | ALP-EPC-00000-PI-SPC-0005
ALP-EPC-00000-PI-MRQ-0003 | Valves - Material Requisition | manual and check | EPC | 00000 | plant general | piping | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-PI-003 |  | 1 | 2026-12-15 | 2026-12-22 |  | 2026-12-25 |  |  | ALP-EPC-00000-PI-SPC-0006
ALP-EPC-00000-PI-MRQ-0004 | GRP CW Pipes and Fittings - Material Requisition |  | EPC | 00000 | plant general | piping | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-PI-004 |  | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00000-PI-PLT-0001 | Plot Plan |  | EPC | 00000 | plant general | piping | PLT | L | approval | yes | yes | 2 | 200 | [5 empty] | 3 | 2026-11-02 | 2026-11-02 | 2026-12-07 | 2026-12-14
ALP-EPC-00000-PI-RPT-0001 | Pipe Stress Analysis Criteria and Critical Line List |  | EPC | 00000 | plant general | piping | RPT | D | review |  |  |  | 60 | [5 empty] | 2 | 2026-12-14 | 2027-01-04 |  | 2027-01-25 |  |  | ALP-EPC-00000-PI-SPC-0002
ALP-EPC-00000-PI-SPC-0001 | Piping Material Classes |  | EPC | 00000 | plant general | piping | SPC | E | approval |  | yes |  | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00000-PI-SPC-0002 | Piping Design and Layout Criteria |  | EPC | 00000 | plant general | piping | SPC | E | approval |  |  |  | 80 | [5 empty] | 1 | 2026-11-02 | 2026-12-14 | 2027-01-11 | 2027-01-18 |  |  |  |  | A IFR 2026-12-14
ALP-EPC-00000-PI-SPC-0003 | Welding, Heat Treatment and NDE Specification |  | EPC | 00000 | plant general | piping | SPC | E | approval |  |  |  | 80 | [5 empty] | 1 | 2026-11-27 | 2027-05-21 | 2027-06-18 | 2027-06-25 |  |  | capacity piping
ALP-EPC-00000-PI-SPC-0004 | Piping Bulk Materials - Technical Specification | carbon steel, stainless | EPC | 00000 | plant general | piping | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-PI-001 |  | 1 | 2026-11-02 | 2026-11-30 | 2026-12-28 | 2027-01-04
ALP-EPC-00000-PI-SPC-0005 | Alloy Piping P91 / P22 - Technical Specification | main steam, reheat | EPC | 00000 | plant general | piping | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-PI-002 |  | 6 | 2026-12-14 | 2027-01-11 | 2027-02-08 | 2027-02-15 |  |  | ALP-EPC-00000-PR-HMB-0001
ALP-EPC-00000-PI-SPC-0006 | Valves - Technical Specification | manual and check | EPC | 00000 | plant general | piping | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-PI-003 |  | 1 | 2026-11-17 | 2026-12-15 | 2027-01-12 | 2027-01-19 |  |  | capacity piping
ALP-EPC-00000-PI-SPC-0007 | GRP CW Pipes and Fittings - Technical Specification |  | EPC | 00000 | plant general | piping | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-PI-004 |  | 2 | 2026-11-02 | 2026-11-30 | 2026-12-28 | 2027-01-04
ALP-EPC-00000-PR-CAL-0001 | Performance Guarantee Calculation and Correction Curves |  | EPC | 00000 | plant general | process | CAL | E | review |  |  |  | 60 | [5 empty] | 1 | 2026-12-14 | 2027-01-04 |  | 2027-01-25 |  |  | ALP-EPC-00000-PR-HMB-0001
ALP-EPC-00000-PR-CAL-0002 | Degradation Curves | recoverable and non-recoverable, output and heat rate | EPC | 00000 | plant general | process | CAL | E | review |  |  | 1 | 80 | [5 empty] | 1 | 2027-01-04 | 2027-06-16 |  | 2027-07-07 |  |  | capacity process
ALP-EPC-00000-PR-DBR-0001 | Process Design Criteria | design margins, design pressure / temperature, line sizing, overpressure protection API 520/521, utility and site conditions | EPC | 00000 | plant general | process | DBR | D | approval | yes |  | 1 | 200 | [5 empty] | 2 | 2026-12-14 | 2027-01-11 | 2027-02-15 | 2027-02-22 |  |  | ALP-EPC-00000-PR-HMB-0001
ALP-EPC-00000-PR-HMB-0001 | Plant Heat and Mass Balances | 9 cases | EPC | 00000 | plant general | process | HMB | F | approval | yes | yes | 9 | 480 | [5 empty] | 1 | 2026-11-02 | 2026-12-14 | 2027-01-18 | 2027-01-25 |  |  |  |  | A IFR 2026-12-14
ALP-EPC-00000-PR-LST-0001 | Equipment List |  | EPC | 00000 | plant general | process | LST | P | review |  | yes |  | 80 | [5 empty] | 3 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00000-PR-LST-0002 | Line List |  | EPC | 00000 | plant general | process | LST | P | review |  |  |  | 80 | [5 empty] | 42 | 2027-06-15 | 2027-07-06 |  | 2027-08-03 |  |  | ALP-EPC-20LCB-PR-PID-0001
ALP-EPC-00000-PR-LST-0003 | Chemical Consumption, Effluent and Emission Inventory |  | EPC | 00000 | plant general | process | LST | P | review |  |  | 1 | 60 | [5 empty] | 1 | 2027-06-04 | 2027-06-25 |  | 2027-07-23 |  |  | ALP-EPC-00000-PR-STU-0001
ALP-EPC-00000-PR-PFD-0001 | Plant Process Flow Diagrams |  | EPC | 00000 | plant general | process | PFD | F | approval | yes | yes | 4 | 105 | [5 empty] | 1 | 2026-11-02 | 2026-11-02 | 2026-12-07 | 2026-12-14
ALP-EPC-00000-PR-PFD-0002 | Utility Flow Diagrams | water, air, nitrogen, steam, chemicals | EPC | 00000 | plant general | process | PFD | F | approval |  |  | 8 | 40 | [5 empty] | 1 | 2026-12-14 | 2027-01-11 | 2027-02-08 | 2027-02-15 |  |  | ALP-EPC-00000-PR-HMB-0001
ALP-EPC-00000-PR-RPT-0001 | Cycle Chemistry Concept | AVT(O), sampling, dosing | EPC | 00000 | plant general | process | RPT | D | review |  |  |  | 60 | [5 empty] | 1 | 2026-11-02 | 2026-11-23 |  | 2026-12-14
ALP-EPC-00000-PR-RPT-0002 | Operating Philosophy | start-up, load, shutdown, fuel changeover | EPC | 00000 | plant general | process | RPT | D | review |  |  | 1 | 80 | [5 empty] | 1 | 2026-11-02 | 2026-11-23 |  | 2026-12-14
ALP-EPC-00000-PR-RPT-0003 | Isolation, Drainage and Venting Philosophy |  | EPC | 00000 | plant general | process | RPT | D | review |  |  | 1 | 60 | [5 empty] | 1 | 2026-11-02 | 2026-11-23 |  | 2026-12-14
ALP-EPC-00000-PR-RPT-0004 | Equipment Sparing and Redundancy Philosophy |  | EPC | 00000 | plant general | process | RPT | D | review |  |  | 1 | 40 | [5 empty] | 1 | 2026-12-07 | 2026-12-28 |  | 2027-01-18 |  |  | ALP-EPC-00000-PR-STU-0002
ALP-EPC-00000-PR-STU-0001 | Plant Water Balance |  | EPC | 00000 | plant general | process | STU | D | review |  |  |  | 160 | [5 empty] | 1 | 2026-12-14 | 2027-06-04 |  | 2027-07-02 |  |  | capacity process
ALP-EPC-00000-PR-STU-0002 | Reliability, Availability and Maintainability Study |  | EPC | 00000 | plant general | process | STU | D | review |  |  |  | 160 | [5 empty] | 1 | 2026-11-02 | 2026-12-07 |  | 2027-01-04
ALP-EPC-00000-PR-STU-0003 | CW Thermal Plume and Outfall Dispersion Study |  | EPC | 00000 | plant general | process | STU | D | review |  |  |  | 160 | [5 empty] | 1 | 2026-12-14 | 2027-06-02 |  | 2027-06-30 |  |  | capacity process
ALP-EPC-00000-PR-STU-0004 | Carbon Capture Readiness Study |  | EPC | 00000 | plant general | process | STU | D | review |  |  |  | 160 | [5 empty] | 1 | 2026-11-02 | 2026-12-07 |  | 2027-01-04
ALP-EPC-00000-SS-MRQ-0001 | Structural Steel Supply and Fabrication - Material Requisition |  | EPC | 00000 | plant general | structural | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-SS-001 |  | 1 | 2026-11-02 | 2026-11-09 |  | 2026-11-12
ALP-EPC-00000-SS-SPC-0001 | Structural Steel Specification |  | EPC | 00000 | plant general | structural | SPC | E | approval |  | yes |  | 80 | [5 empty] | 1 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00000-SS-SPC-0002 | Structural Steel Supply and Fabrication - Technical Specification |  | EPC | 00000 | plant general | structural | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-SS-001 |  | 1 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00ACA-CM-CMP-0001 | 380 kV GIS Switchyard - System Commissioning Procedure |  | EPC | 00ACA | 380 kV GIS switchyard | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2026-11-30 | 2026-12-28 | 2027-01-25 | 2027-02-01 |  |  | ALP-EPC-00000-CM-PLN-0001
ALP-EPC-00ACA-CM-MDB-0001 | 380 kV GIS Switchyard - System Turnover Dossier |  | EPC | 00ACA | 380 kV GIS switchyard | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-01-04 | 2028-01-18 |  | 2028-01-25 |  |  | as late as possible (need)
ALP-EPC-00ACA-CM-OMM-0001 | 380 kV GIS Switchyard - Operating Procedures | English / Turkish | EPC | 00ACA | 380 kV GIS switchyard | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2026-12-28 | 2027-02-08 |  | 2027-03-08 |  |  | ALP-EPC-00ACA-CM-CMP-0001
ALP-EPC-00ACA-EL-DSH-0001 | 380 kV GIS Switchyard: Switchgear - Datasheet |  | EPC | 00ACA | 380 kV GIS switchyard | electrical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-EL-001 | 00ACA10 | 2 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00ACA-EL-ITP-0001 | 380 kV GIS - Inspection and Test Plan |  | EPC | 00ACA | 380 kV GIS switchyard | electrical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-EL-001 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00ACA-EL-MRQ-0001 | 380 kV GIS - Material Requisition |  | EPC | 00ACA | 380 kV GIS switchyard | electrical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-EL-001 |  | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00ACA-EL-SLD-0001 | 380 kV GIS Switchyard - Single Line Diagram |  | EPC | 00ACA | 380 kV GIS switchyard | electrical | SLD | F | approval |  |  | 2 | 75 | [5 empty] | 2 | 2027-01-06 | 2027-10-14 | 2027-11-11 | 2027-11-18 |  |  | capacity electrical
ALP-EPC-00ACA-EL-SPC-0001 | 380 kV GIS - Technical Specification |  | EPC | 00ACA | 380 kV GIS switchyard | electrical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-EL-001 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00ACA-GE-RPT-0001 | 380 kV GIS - Technical Bid Evaluation |  | EPC | 00ACA | 380 kV GIS switchyard | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-EL-001 |  | 1 | 2026-11-05 | 2026-11-26 |  | 2026-12-03 |  |  | bids MR-EL-001
ALP-EPC-00ACA-IC-DSH-0001 | 380 kV GIS Switchyard - Instrument Datasheets |  | EPC | 00ACA | 380 kV GIS switchyard | i_and_c | DSH | E | approval |  |  | 40 | 68 |  |  |  | MR-IC-004 |  | 1 | 2027-01-11 | 2027-02-08 | 2027-03-01 | 2027-03-08 |  |  | ALP-EPC-00000-IC-SPC-0001
ALP-EPC-00ACA-IC-LOG-0001 | 380 kV GIS Switchyard - Logic Diagrams |  | EPC | 00ACA | 380 kV GIS switchyard | i_and_c | LOG | F | approval |  |  | 19 | 168 | [5 empty] | 1 | 2027-01-04 | 2027-02-25 | 2027-03-25 | 2027-04-01 |  |  | ALP-EPC-00000-IC-RPT-0001
ALP-EPC-00BBA-CM-CMP-0001 | MV Switchgear 10.5 kV - System Commissioning Procedure |  | EPC | 00BBA | MV switchgear 10.5 kV | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2026-11-30 | 2026-12-28 | 2027-01-25 | 2027-02-01 |  |  | ALP-EPC-00000-CM-PLN-0001
ALP-EPC-00BBA-CM-MDB-0001 | MV Switchgear 10.5 kV - System Turnover Dossier |  | EPC | 00BBA | MV switchgear 10.5 kV | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-01-04 | 2028-01-18 |  | 2028-01-25 |  |  | as late as possible (need)
ALP-EPC-00BBA-CM-OMM-0001 | MV Switchgear 10.5 kV - Operating Procedures | English / Turkish | EPC | 00BBA | MV switchgear 10.5 kV | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2026-12-28 | 2027-02-08 |  | 2027-03-08 |  |  | ALP-EPC-00BBA-CM-CMP-0001
ALP-EPC-00BBA-EL-DSH-0001 | MV Switchgear 10.5 kV - Datasheet | 2 items | EPC | 00BBA | MV switchgear 10.5 kV | electrical | DSH | E | approval |  | yes | 2 | 26 |  |  |  | MR-EL-003 | 00BBA10 00BBA20 | 2 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00BBA-EL-ITP-0001 | MV Switchgear 10.5 kV - Inspection and Test Plan |  | EPC | 00BBA | MV switchgear 10.5 kV | electrical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-EL-003 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00BBA-EL-MRQ-0001 | MV Switchgear 10.5 kV - Material Requisition |  | EPC | 00BBA | MV switchgear 10.5 kV | electrical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-EL-003 |  | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00BBA-EL-SLD-0001 | MV Switchgear 10.5 kV - Single Line Diagram |  | EPC | 00BBA | MV switchgear 10.5 kV | electrical | SLD | F | approval |  |  | 2 | 75 | [5 empty] | 2 | 2026-11-23 | 2026-12-15 | 2027-01-12 | 2027-01-19 |  |  | capacity electrical
ALP-EPC-00BBA-EL-SPC-0001 | MV Switchgear 10.5 kV - Technical Specification |  | EPC | 00BBA | MV switchgear 10.5 kV | electrical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-EL-003 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00BBA-EL-WIR-0001 | MV Schematic and Wiring Diagrams |  | EPC | 00BBA | MV switchgear 10.5 kV | electrical | WIR | F | information |  |  | 36 | 200 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-04-06 | 2027-05-18 |  | 2027-05-25 | 2027-10-25 | 109 | capacity electrical
ALP-EPC-00BBA-GE-RPT-0001 | MV Switchgear 10.5 kV - Technical Bid Evaluation |  | EPC | 00BBA | MV switchgear 10.5 kV | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-EL-003 |  | 1 | 2026-12-17 | 2027-01-07 |  | 2027-01-14 |  |  | bids MR-EL-003
ALP-EPC-00BFA-CM-CMP-0001 | LV Switchgear 0.4 kV - System Commissioning Procedure |  | EPC | 00BFA | LV switchgear 0.4 kV | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2026-11-30 | 2026-12-28 | 2027-01-25 | 2027-02-01 |  |  | ALP-EPC-00000-CM-PLN-0001
ALP-EPC-00BFA-CM-MDB-0001 | LV Switchgear 0.4 kV - System Turnover Dossier |  | EPC | 00BFA | LV switchgear 0.4 kV | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-01-04 | 2028-01-18 |  | 2028-01-25 |  |  | as late as possible (need)
ALP-EPC-00BFA-CM-OMM-0001 | LV Switchgear 0.4 kV - Operating Procedures | English / Turkish | EPC | 00BFA | LV switchgear 0.4 kV | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2026-12-28 | 2027-02-08 |  | 2027-03-08 |  |  | ALP-EPC-00BFA-CM-CMP-0001
ALP-EPC-00BFA-EL-DSH-0001 | LV Switchgear 0.4 kV - Datasheet | 12 items | EPC | 00BFA | LV switchgear 0.4 kV | electrical | DSH | E | approval |  | yes | 12 | 126 |  |  |  | MR-EL-005 | 00BFA10 00BFA11 00BFA12 00BFA20 00BFA21 00BFA22 00BFA30 00BFA40 00BFA50 00BFA60 00BFA70 00BFA80 | 2 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00BFA-EL-ITP-0001 | LV Switchboards and MCCs - Inspection and Test Plan |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-EL-005 |  | 1 | 2026-11-04 | 2026-11-18 | 2026-12-09 | 2026-12-16 |  |  | capacity electrical
ALP-EPC-00BFA-EL-MRQ-0001 | LV Switchboards and MCCs - Material Requisition |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-EL-005 |  | 5 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00BFA-EL-SLD-0001 | LV Switchgear 0.4 kV - Single Line Diagram |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | SLD | F | approval |  |  | 2 | 75 | [5 empty] | 2 | 2026-11-27 | 2026-12-21 | 2027-01-18 | 2027-01-25 |  |  | capacity electrical
ALP-EPC-00BFA-EL-SPC-0001 | LV Switchboards and MCCs - Technical Specification |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-EL-005 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00BFA-EL-WIR-0001 | LV Schematic and Wiring Diagrams, Part 1 of 13 |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | WIR | F | information |  |  | 97 | 311 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-01-25 | 2027-05-06 |  | 2027-05-13 | 2027-10-25 | 117 | capacity electrical
ALP-EPC-00BFA-EL-WIR-0002 | LV Schematic and Wiring Diagrams, Part 10 of 13 |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | WIR | F | information |  |  | 96 | 308 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-01-25 | 2027-05-11 |  | 2027-05-18 | 2027-10-25 | 114 | capacity electrical
ALP-EPC-00BFA-EL-WIR-0003 | LV Schematic and Wiring Diagrams, Part 11 of 13 |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | WIR | F | information |  |  | 96 | 308 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-01-25 | 2027-05-19 |  | 2027-05-26 | 2027-10-25 | 108 | capacity electrical
ALP-EPC-00BFA-EL-WIR-0004 | LV Schematic and Wiring Diagrams, Part 12 of 13 |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | WIR | F | information |  |  | 96 | 308 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-01-25 | 2027-06-03 |  | 2027-06-10 | 2027-10-25 | 97 | capacity electrical
ALP-EPC-00BFA-EL-WIR-0005 | LV Schematic and Wiring Diagrams, Part 13 of 13 |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | WIR | F | information |  |  | 96 | 308 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-01-28 | 2027-06-11 |  | 2027-06-18 | 2027-10-25 | 91 | capacity electrical
ALP-EPC-00BFA-EL-WIR-0006 | LV Schematic and Wiring Diagrams, Part 2 of 13 |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | WIR | F | information |  |  | 97 | 311 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-05-11 | 2027-06-22 |  | 2027-06-29 | 2027-10-25 | 84 | capacity electrical
ALP-EPC-00BFA-EL-WIR-0007 | LV Schematic and Wiring Diagrams, Part 3 of 13 |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | WIR | F | information |  |  | 96 | 308 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-05-11 | 2027-06-24 |  | 2027-07-01 | 2027-10-25 | 82 | capacity electrical
ALP-EPC-00BFA-EL-WIR-0008 | LV Schematic and Wiring Diagrams, Part 4 of 13 |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | WIR | F | information |  |  | 96 | 308 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-05-18 | 2027-06-30 |  | 2027-07-07 | 2027-10-25 | 78 | capacity electrical
ALP-EPC-00BFA-EL-WIR-0009 | LV Schematic and Wiring Diagrams, Part 5 of 13 |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | WIR | F | information |  |  | 96 | 308 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-05-19 | 2027-07-05 |  | 2027-07-12 | 2027-10-25 | 75 | capacity electrical
ALP-EPC-00BFA-EL-WIR-0010 | LV Schematic and Wiring Diagrams, Part 6 of 13 |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | WIR | F | information |  |  | 96 | 308 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-06-02 | 2027-07-16 |  | 2027-07-23 | 2027-10-25 | 66 | capacity electrical
ALP-EPC-00BFA-EL-WIR-0011 | LV Schematic and Wiring Diagrams, Part 7 of 13 |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | WIR | F | information |  |  | 96 | 308 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-06-11 | 2027-07-27 |  | 2027-08-03 | 2027-10-25 | 59 | capacity electrical
ALP-EPC-00BFA-EL-WIR-0012 | LV Schematic and Wiring Diagrams, Part 8 of 13 |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | WIR | F | information |  |  | 96 | 308 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-06-22 | 2027-08-04 |  | 2027-08-11 | 2027-10-25 | 53 | capacity electrical
ALP-EPC-00BFA-EL-WIR-0013 | LV Schematic and Wiring Diagrams, Part 9 of 13 |  | EPC | 00BFA | LV switchgear 0.4 kV | electrical | WIR | F | information |  |  | 96 | 308 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-06-23 | 2027-08-05 |  | 2027-08-12 | 2027-10-25 | 52 | capacity electrical
ALP-EPC-00BFA-GE-RPT-0001 | LV Switchboards and MCCs - Technical Bid Evaluation |  | EPC | 00BFA | LV switchgear 0.4 kV | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-EL-005 |  | 1 | 2027-01-07 | 2027-01-28 |  | 2027-02-04 |  |  | capacity general
ALP-EPC-00BFT-CM-CMP-0001 | LV Transformers - System Commissioning Procedure |  | EPC | 00BFT | LV transformers | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2026-11-30 | 2026-12-28 | 2027-01-25 | 2027-02-01 |  |  | ALP-EPC-00000-CM-PLN-0001
ALP-EPC-00BFT-CM-MDB-0001 | LV Transformers - System Turnover Dossier |  | EPC | 00BFT | LV transformers | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-01-04 | 2028-01-18 |  | 2028-01-25 |  |  | as late as possible (need)
ALP-EPC-00BFT-CM-OMM-0001 | LV Transformers - Operating Procedures | English / Turkish | EPC | 00BFT | LV transformers | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2026-12-28 | 2027-02-08 |  | 2027-03-08 |  |  | ALP-EPC-00BFT-CM-CMP-0001
ALP-EPC-00BFT-EL-DSH-0001 | LV Transformers - Datasheet | 8 items | EPC | 00BFT | LV transformers | electrical | DSH | E | approval |  | yes | 8 | 86 |  |  |  | MR-EL-004 | 00BFT10 00BFT20 00BFT30 00BFT40 00BFT50 00BFT60 00BFT70 00BFT80 | 2 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00BFT-EL-ITP-0001 | LV Transformers - Inspection and Test Plan |  | EPC | 00BFT | LV transformers | electrical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-EL-004 |  | 1 | 2026-11-13 | 2026-11-27 | 2026-12-18 | 2026-12-25 |  |  | capacity electrical
ALP-EPC-00BFT-EL-MRQ-0001 | LV Transformers - Material Requisition |  | EPC | 00BFT | LV transformers | electrical | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-EL-004 |  | 2 | 2026-11-02 | 2026-11-09 |  | 2026-11-12
ALP-EPC-00BFT-EL-SPC-0001 | LV Transformers - Technical Specification |  | EPC | 00BFT | LV transformers | electrical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-EL-004 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00BFT-GE-RPT-0001 | LV Transformers - Technical Bid Evaluation |  | EPC | 00BFT | LV transformers | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-EL-004 |  | 1 | 2026-12-10 | 2027-02-19 |  | 2027-02-26 |  |  | capacity general
ALP-EPC-00BLA-CM-CMP-0001 | Lighting and Small Power - System Commissioning Procedure |  | EPC | 00BLA | Lighting and small power | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2026-11-30 | 2026-12-28 | 2027-01-25 | 2027-02-01 |  |  | ALP-EPC-00000-CM-PLN-0001
ALP-EPC-00BLA-CM-MDB-0001 | Lighting and Small Power - System Turnover Dossier |  | EPC | 00BLA | Lighting and small power | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-01-04 | 2028-01-18 |  | 2028-01-25 |  |  | as late as possible (need)
ALP-EPC-00BLA-CM-OMM-0001 | Lighting and Small Power - Operating Procedures | English / Turkish | EPC | 00BLA | Lighting and small power | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2026-12-29 | 2027-02-09 |  | 2027-03-09 |  |  | capacity commissioning
ALP-EPC-00BLA-EL-SLD-0001 | Lighting and Small Power - Single Line Diagram |  | EPC | 00BLA | Lighting and small power | electrical | SLD | F | approval |  |  | 2 | 75 | [5 empty] | 2 | 2027-01-06 | 2027-10-19 | 2027-11-16 | 2027-11-23 |  |  | capacity electrical
ALP-EPC-00BLA-GE-RPT-0001 | Cable Trays, Earthing and Lighting Materials - Technical Bid Evaluation |  | EPC | 00BLA | Lighting and small power | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-EL-009 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-03-18 |  |  | bids MR-EL-009
ALP-EPC-00BLA-IC-LOG-0001 | Lighting and Small Power - Logic Diagrams |  | EPC | 00BLA | Lighting and small power | i_and_c | LOG | F | approval |  |  | 60 | 496 | [5 empty] | 1 | 2027-01-04 | 2027-03-01 | 2027-03-29 | 2027-04-05 |  |  | ALP-EPC-00000-IC-RPT-0001
ALP-EPC-00BMA-CM-CMP-0001 | Emergency LV Switchgear - System Commissioning Procedure |  | EPC | 00BMA | Emergency LV switchgear | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2026-11-30 | 2026-12-28 | 2027-01-25 | 2027-02-01 |  |  | ALP-EPC-00000-CM-PLN-0001
ALP-EPC-00BMA-CM-MDB-0001 | Emergency LV Switchgear - System Turnover Dossier |  | EPC | 00BMA | Emergency LV switchgear | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-01-04 | 2028-01-18 |  | 2028-01-25 |  |  | as late as possible (need)
ALP-EPC-00BMA-CM-OMM-0001 | Emergency LV Switchgear - Operating Procedures | English / Turkish | EPC | 00BMA | Emergency LV switchgear | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-01-04 | 2027-02-15 |  | 2027-03-15 |  |  | capacity commissioning
ALP-EPC-00BMA-EL-DSH-0001 | Emergency LV Switchgear - Datasheet | 2 items | EPC | 00BMA | Emergency LV switchgear | electrical | DSH | E | approval |  | yes | 2 | 26 |  |  |  | MR-EL-005 | 00BMA10 00BMA20 | 2 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00BMA-EL-SLD-0001 | Emergency LV Switchgear - Single Line Diagram |  | EPC | 00BMA | Emergency LV switchgear | electrical | SLD | F | approval |  |  | 2 | 75 | [5 empty] | 2 | 2027-01-11 | 2027-10-25 | 2027-11-22 | 2027-11-29 |  |  | capacity electrical
ALP-EPC-00BMA-IC-LOG-0001 | Emergency LV Switchgear - Logic Diagrams |  | EPC | 00BMA | Emergency LV switchgear | i_and_c | LOG | F | approval |  |  | 15 | 136 | [5 empty] | 1 | 2027-01-04 | 2027-02-19 | 2027-03-19 | 2027-03-26 |  |  | ALP-EPC-00000-IC-RPT-0001
ALP-EPC-00BRA-CM-CMP-0001 | UPS - System Commissioning Procedure |  | EPC | 00BRA | UPS | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2026-12-10 | 2027-01-07 | 2027-02-04 | 2027-02-11 |  |  | capacity commissioning
ALP-EPC-00BRA-CM-MDB-0001 | UPS - System Turnover Dossier |  | EPC | 00BRA | UPS | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-01-04 | 2028-01-18 |  | 2028-01-25 |  |  | as late as possible (need)
ALP-EPC-00BRA-CM-OMM-0001 | UPS - Operating Procedures | English / Turkish | EPC | 00BRA | UPS | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-01-07 | 2027-02-18 |  | 2027-03-18 |  |  | ALP-EPC-00BRA-CM-CMP-0001
ALP-EPC-00BRA-EL-DSH-0001 | UPS - Datasheet |  | EPC | 00BRA | UPS | electrical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-EL-007 | 00BRA10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00BRA-EL-DSH-0002 | UPS: Switchgear - Datasheet |  | EPC | 00BRA | UPS | electrical | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-EL-005 | 00BRA20 | 3 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00BRA-EL-ITP-0001 | UPS, Batteries and DC Systems - Inspection and Test Plan |  | EPC | 00BRA | UPS | electrical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-EL-007 |  | 1 | 2026-11-16 | 2026-11-30 | 2026-12-21 | 2026-12-28 |  |  | capacity electrical
ALP-EPC-00BRA-EL-MRQ-0001 | UPS, Batteries and DC Systems - Material Requisition |  | EPC | 00BRA | UPS | electrical | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-EL-007 |  | 4 | 2026-11-16 | 2026-11-23 |  | 2026-11-26 |  |  | ALP-EPC-00BRA-EL-DSH-0002
ALP-EPC-00BRA-EL-SLD-0001 | UPS - Single Line Diagram |  | EPC | 00BRA | UPS | electrical | SLD | F | approval |  |  | 2 | 75 | [5 empty] | 2 | 2027-01-14 | 2027-10-29 | 2027-11-26 | 2027-12-03 |  |  | capacity electrical
ALP-EPC-00BRA-EL-SPC-0001 | UPS, Batteries and DC Systems - Technical Specification |  | EPC | 00BRA | UPS | electrical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-EL-007 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00BRA-GE-RPT-0001 | UPS, Batteries and DC Systems - Technical Bid Evaluation |  | EPC | 00BRA | UPS | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-EL-007 |  | 1 | 2027-02-09 | 2027-03-02 |  | 2027-03-09 |  |  | capacity general
ALP-EPC-00BRA-IC-LOG-0001 | UPS - Logic Diagrams |  | EPC | 00BRA | UPS | i_and_c | LOG | F | approval |  |  | 30 | 256 | [5 empty] | 1 | 2027-01-04 | 2027-03-01 | 2027-03-29 | 2027-04-05 |  |  | ALP-EPC-00000-IC-RPT-0001
ALP-EPC-00BTA-CM-CMP-0001 | Batteries and DC 220 V - System Commissioning Procedure |  | EPC | 00BTA | Batteries and DC 220 V | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2026-12-22 | 2027-01-19 | 2027-02-16 | 2027-02-23 |  |  | capacity commissioning
ALP-EPC-00BTA-CM-MDB-0001 | Batteries and DC 220 V - System Turnover Dossier |  | EPC | 00BTA | Batteries and DC 220 V | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-01-04 | 2028-01-18 |  | 2028-01-25 |  |  | as late as possible (need)
ALP-EPC-00BTA-CM-OMM-0001 | Batteries and DC 220 V - Operating Procedures | English / Turkish | EPC | 00BTA | Batteries and DC 220 V | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-01-19 | 2027-03-02 |  | 2027-03-30 |  |  | ALP-EPC-00BTA-CM-CMP-0001
ALP-EPC-00BTA-EL-DSH-0001 | Batteries and DC 220 V: Battery - Datasheet |  | EPC | 00BTA | Batteries and DC 220 V | electrical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-EL-007 | 00BTA10 | 2 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00BTA-IC-LOG-0001 | Batteries and DC 220 V - Logic Diagrams |  | EPC | 00BTA | Batteries and DC 220 V | i_and_c | LOG | F | approval |  |  | 15 | 136 | [5 empty] | 1 | 2027-01-04 | 2027-02-19 | 2027-03-19 | 2027-03-26 |  |  | ALP-EPC-00000-IC-RPT-0001
ALP-EPC-00BXA-CM-CMP-0001 | Earthing and Lightning Protection - System Commissioning Procedure |  | EPC | 00BXA | Earthing and lightning protection | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2026-12-28 | 2027-01-25 | 2027-02-22 | 2027-03-01 |  |  | capacity commissioning
ALP-EPC-00BXA-CM-MDB-0001 | Earthing and Lightning Protection - System Turnover Dossier |  | EPC | 00BXA | Earthing and lightning protection | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-01-04 | 2028-01-18 |  | 2028-01-25 |  |  | as late as possible (need)
ALP-EPC-00BXA-GE-ITP-0001 | Cathodic Protection - Inspection and Test Plan | marine structures, buried piping and tanks | EPC | 00BXA | Earthing and lightning protection | general | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-EL-010 |  | 1 | 2027-02-18 | 2027-03-04 | 2027-03-25 | 2027-04-01 |  |  | capacity general
ALP-EPC-00BXA-GE-MRQ-0001 | Cathodic Protection - Material Requisition | marine structures, buried piping and tanks | EPC | 00BXA | Earthing and lightning protection | general | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-EL-010 |  | 1 | 2027-02-11 | 2027-02-18 |  | 2027-02-23 |  |  | ALP-EPC-00BXA-GE-SPC-0001
ALP-EPC-00BXA-GE-RPT-0001 | Cathodic Protection - Technical Bid Evaluation | marine structures, buried piping and tanks | EPC | 00BXA | Earthing and lightning protection | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-EL-010 |  | 1 | 2027-04-06 | 2027-04-27 |  | 2027-05-04 |  |  | bids MR-EL-010
ALP-EPC-00BXA-GE-SPC-0001 | Cathodic Protection - Technical Specification | marine structures, buried piping and tanks | EPC | 00BXA | Earthing and lightning protection | general | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-EL-010 |  | 2 | 2027-01-14 | 2027-02-11 | 2027-03-11 | 2027-03-18 |  |  | capacity general
ALP-EPC-00CJA-CM-CMP-0001 | Plant DCS - System Commissioning Procedure |  | EPC | 00CJA | Plant DCS | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2027-01-08 | 2027-02-05 | 2027-03-05 | 2027-03-12 |  |  | capacity commissioning
ALP-EPC-00CJA-CM-MDB-0001 | Plant DCS - System Turnover Dossier |  | EPC | 00CJA | Plant DCS | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-03-20 | 2028-04-03 |  | 2028-04-10 |  |  | as late as possible (need)
ALP-EPC-00CJA-CM-OMM-0001 | Plant DCS - Operating Procedures | English / Turkish | EPC | 00CJA | Plant DCS | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-02-09 | 2027-03-23 |  | 2027-04-20 |  |  | capacity commissioning
ALP-EPC-00CJA-GE-RPT-0001 | Plant DCS - Technical Bid Evaluation |  | EPC | 00CJA | Plant DCS | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-IC-001 |  | 1 | 2026-12-22 | 2027-01-12 |  | 2027-01-19 |  |  | capacity general
ALP-EPC-00CJA-IC-BLK-0001 | Plant DCS - System Architecture |  | EPC | 00CJA | Plant DCS | i_and_c | BLK | F | approval | yes |  | 1 | 40 | [5 empty] | 2 | 2027-01-11 | 2027-02-01 | 2027-03-08 | 2027-03-15 |  |  | ALP-IEC-10MBY-IC-BLK-0001
ALP-EPC-00CJA-IC-DSH-0001 | Plant DCS: Control Systems - Datasheet | 6 items | EPC | 00CJA | Plant DCS | i_and_c | DSH | E | approval |  | yes | 6 | 66 |  |  |  | MR-IC-001 | 00CJA10 00CJA20 00CJA30 00CJA40 00CJA50 00CJA60 | 2 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00CJA-IC-ITP-0001 | Plant DCS - Inspection and Test Plan |  | EPC | 00CJA | Plant DCS | i_and_c | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-IC-001 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00CJA-IC-LOG-0001 | Plant DCS - Logic Diagrams |  | EPC | 00CJA | Plant DCS | i_and_c | LOG | F | approval |  |  | 30 | 256 | [5 empty] | 1 | 2027-01-04 | 2027-03-01 | 2027-03-29 | 2027-04-05 |  |  | ALP-EPC-00000-IC-RPT-0001
ALP-EPC-00CJA-IC-MRQ-0001 | Plant DCS - Material Requisition |  | EPC | 00CJA | Plant DCS | i_and_c | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-IC-001 |  | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00CJA-IC-SPC-0001 | Plant DCS - Technical Specification |  | EPC | 00CJA | Plant DCS | i_and_c | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-IC-001 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00CJG-CM-CMP-0001 | Safety Instrumented Systems - System Commissioning Procedure | BOP | EPC | 00CJG | Safety instrumented systems (BOP) | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2027-01-19 | 2027-02-16 | 2027-03-16 | 2027-03-23 |  |  | capacity commissioning
ALP-EPC-00CJG-CM-MDB-0001 | Safety Instrumented Systems - System Turnover Dossier | BOP | EPC | 00CJG | Safety instrumented systems (BOP) | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-03-20 | 2028-04-03 |  | 2028-04-10 |  |  | as late as possible (need)
ALP-EPC-00CJG-CM-OMM-0001 | Safety Instrumented Systems - Operating Procedures | English / Turkish; BOP | EPC | 00CJG | Safety instrumented systems (BOP) | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-02-16 | 2027-03-30 |  | 2027-04-27 |  |  | ALP-EPC-00CJG-CM-CMP-0001
ALP-EPC-00CJG-GE-ITP-0001 | BOP Safety Instrumented System - Inspection and Test Plan | IEC 61511 | EPC | 00CJG | Safety instrumented systems (BOP) | general | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-IC-008 |  | 1 | 2027-02-22 | 2027-03-08 | 2027-03-29 | 2027-04-05 |  |  | ALP-EPC-00CJG-GE-SPC-0001
ALP-EPC-00CJG-GE-MRQ-0001 | BOP Safety Instrumented System - Material Requisition | IEC 61511 | EPC | 00CJG | Safety instrumented systems (BOP) | general | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-IC-008 |  | 2 | 2027-03-08 | 2027-03-15 |  | 2027-03-18 |  |  | ALP-EPC-00CJG-IC-DSH-0001
ALP-EPC-00CJG-GE-RPT-0001 | BOP Safety Instrumented System - Technical Bid Evaluation | IEC 61511 | EPC | 00CJG | Safety instrumented systems (BOP) | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-IC-008 |  | 1 | 2027-04-29 | 2027-05-20 |  | 2027-05-27 |  |  | bids MR-IC-008
ALP-EPC-00CJG-GE-SPC-0001 | BOP Safety Instrumented System - Technical Specification | IEC 61511 | EPC | 00CJG | Safety instrumented systems (BOP) | general | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-IC-008 |  | 2 | 2027-01-25 | 2027-02-22 | 2027-03-22 | 2027-03-29 |  |  | ALP-EPC-00CJG-IC-BLK-0001
ALP-EPC-00CJG-IC-BLK-0001 | Safety Instrumented Systems - System Architecture | BOP | EPC | 00CJG | Safety instrumented systems (BOP) | i_and_c | BLK | F | approval |  |  | 1 | 40 | [5 empty] | 2 | 2027-01-04 | 2027-01-25 | 2027-02-22 | 2027-03-01 |  |  | ALP-EPC-00000-IC-RPT-0002
ALP-EPC-00CJG-IC-DSH-0001 | Safety Instrumented Systems: Control System - Datasheet | BOP | EPC | 00CJG | Safety instrumented systems (BOP) | i_and_c | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-IC-008 | 00CJG10 | 2 | 2027-02-22 | 2027-03-08 | 2027-03-29 | 2027-04-05 |  |  | ALP-EPC-00CJG-GE-SPC-0001
ALP-EPC-00CKA-CM-CMP-0001 | Historian, Performance Monitoring and Operator Training Simulator - System Commissioning Procedure |  | EPC | 00CKA | Historian, performance monitoring and operator training simulator | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2027-01-25 | 2027-02-22 | 2027-03-22 | 2027-03-29 |  |  | capacity commissioning
ALP-EPC-00CKA-CM-MDB-0001 | Historian, Performance Monitoring and Operator Training Simulator - System Turnover Dossier |  | EPC | 00CKA | Historian, performance monitoring and operator training simulator | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-03-20 | 2028-04-03 |  | 2028-04-10 |  |  | as late as possible (need)
ALP-EPC-00CKA-CM-OMM-0001 | Historian, Performance Monitoring and Operator Training Simulator - Operating Procedures | English / Turkish | EPC | 00CKA | Historian, performance monitoring and operator training simulator | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-02-22 | 2027-04-05 |  | 2027-05-03 |  |  | ALP-EPC-00CKA-CM-CMP-0001
ALP-EPC-00CKA-GE-ITP-0001 | Operator Training Simulator, Historian and Performance Monitoring - Inspection and Test Plan |  | EPC | 00CKA | Historian, performance monitoring and operator training simulator | general | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-IC-009 |  | 1 | 2027-02-22 | 2027-03-08 | 2027-03-29 | 2027-04-05 |  |  | ALP-EPC-00CKA-GE-SPC-0001
ALP-EPC-00CKA-GE-MRQ-0001 | Operator Training Simulator, Historian and Performance Monitoring - Material Requisition |  | EPC | 00CKA | Historian, performance monitoring and operator training simulator | general | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-IC-009 |  | 2 | 2027-03-08 | 2027-03-15 |  | 2027-03-18 |  |  | ALP-EPC-00CKA-IC-DSH-0001
ALP-EPC-00CKA-GE-RPT-0001 | Operator Training Simulator, Historian and Performance Monitoring - Technical Bid Evaluation |  | EPC | 00CKA | Historian, performance monitoring and operator training simulator | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-IC-009 |  | 1 | 2027-05-13 | 2027-06-03 |  | 2027-06-10 |  |  | bids MR-IC-009
ALP-EPC-00CKA-GE-SPC-0001 | Operator Training Simulator, Historian and Performance Monitoring - Technical Specification |  | EPC | 00CKA | Historian, performance monitoring and operator training simulator | general | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-IC-009 |  | 2 | 2027-01-25 | 2027-02-22 | 2027-03-22 | 2027-03-29 |  |  | ALP-EPC-00CKA-IC-BLK-0001
ALP-EPC-00CKA-IC-BLK-0001 | Historian, Performance Monitoring and Operator Training Simulator - System Architecture |  | EPC | 00CKA | Historian, performance monitoring and operator training simulator | i_and_c | BLK | F | approval |  |  | 1 | 40 | [5 empty] | 2 | 2027-01-04 | 2027-01-25 | 2027-02-22 | 2027-03-01 |  |  | ALP-EPC-00000-IC-RPT-0002
ALP-EPC-00CKA-IC-DSH-0001 | Historian, Performance Monitoring and Operator Training Simulator: Control System - Datasheet |  | EPC | 00CKA | Historian, performance monitoring and operator training simulator | i_and_c | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-IC-009 | 00CKA10 | 2 | 2027-02-22 | 2027-03-08 | 2027-03-29 | 2027-04-05 |  |  | ALP-EPC-00CKA-GE-SPC-0001
ALP-EPC-00CKA-IC-LOG-0001 | Historian, Performance Monitoring and Operator Training Simulator - Logic Diagrams |  | EPC | 00CKA | Historian, performance monitoring and operator training simulator | i_and_c | LOG | F | approval |  |  | 3 | 40 | [5 empty] | 1 | 2027-01-06 | 2027-02-05 | 2027-03-05 | 2027-03-12 |  |  | capacity i_and_c
ALP-EPC-00CQA-CM-CMP-0001 | Continuous Emission Monitoring - System Commissioning Procedure |  | EPC | 00CQA | Continuous emission monitoring | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2027-01-25 | 2027-02-22 | 2027-03-22 | 2027-03-29 |  |  | capacity commissioning
ALP-EPC-00CQA-CM-MDB-0001 | Continuous Emission Monitoring - System Turnover Dossier |  | EPC | 00CQA | Continuous emission monitoring | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-03-20 | 2028-04-03 |  | 2028-04-10 |  |  | as late as possible (need)
ALP-EPC-00CQA-CM-OMM-0001 | Continuous Emission Monitoring - Operating Procedures | English / Turkish | EPC | 00CQA | Continuous emission monitoring | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-02-22 | 2027-04-05 |  | 2027-05-03 |  |  | ALP-EPC-00CQA-CM-CMP-0001
ALP-EPC-00CQA-GE-RPT-0001 | Continuous Emission Monitoring System - Technical Bid Evaluation |  | EPC | 00CQA | Continuous emission monitoring | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-IC-002 |  | 1 | 2027-02-22 | 2027-03-15 |  | 2027-03-22 |  |  | capacity general
ALP-EPC-00CQA-IC-BLK-0001 | Continuous Emission Monitoring - System Architecture |  | EPC | 00CQA | Continuous emission monitoring | i_and_c | BLK | F | approval |  |  | 1 | 40 | [5 empty] | 2 | 2027-01-04 | 2027-01-25 | 2027-02-22 | 2027-03-01 |  |  | ALP-EPC-00000-IC-RPT-0002
ALP-EPC-00CQA-IC-DSH-0001 | Continuous Emission Monitoring: Analyser - Datasheet |  | EPC | 00CQA | Continuous emission monitoring | i_and_c | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-IC-002 | 00CQA10 | 2 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00CQA-IC-DSH-0002 | Continuous Emission Monitoring - Instrument Datasheets |  | EPC | 00CQA | Continuous emission monitoring | i_and_c | DSH | E | approval |  |  | 30 | 53 |  |  |  | MR-IC-004 |  | 1 | 2027-01-11 | 2027-02-08 | 2027-03-01 | 2027-03-08 |  |  | ALP-EPC-00000-IC-SPC-0001
ALP-EPC-00CQA-IC-ITP-0001 | Continuous Emission Monitoring System - Inspection and Test Plan |  | EPC | 00CQA | Continuous emission monitoring | i_and_c | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-IC-002 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00CQA-IC-LOG-0001 | Continuous Emission Monitoring - Logic Diagrams |  | EPC | 00CQA | Continuous emission monitoring | i_and_c | LOG | F | approval |  |  | 14 | 128 | [5 empty] | 1 | 2027-01-11 | 2027-02-25 | 2027-03-25 | 2027-04-01 |  |  | capacity i_and_c
ALP-EPC-00CQA-IC-MRQ-0001 | Continuous Emission Monitoring System - Material Requisition |  | EPC | 00CQA | Continuous emission monitoring | i_and_c | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-IC-002 |  | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00CQA-IC-SPC-0001 | Continuous Emission Monitoring System - Technical Specification |  | EPC | 00CQA | Continuous emission monitoring | i_and_c | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-IC-002 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00CQA-IC-TRP-0001 | CEMS Certification, QAL1 / QAL2 and AST Reports | EN 14181 | EPC | 00CQA | Continuous emission monitoring | i_and_c | TRP | Q | review |  |  | 1 | 40 | [5 empty] | 1 | 2029-02-12 | 2029-02-19 |  | 2029-03-12 |  |  | after COM-010
ALP-EPC-00CYA-CM-CMP-0001 | Telecom, CCTV, Access Control, Security - System Commissioning Procedure |  | EPC | 00CYA | Telecom, CCTV, access control, security | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2027-01-25 | 2027-02-22 | 2027-03-22 | 2027-03-29 |  |  | capacity commissioning
ALP-EPC-00CYA-CM-MDB-0001 | Telecom, CCTV, Access Control, Security - System Turnover Dossier |  | EPC | 00CYA | Telecom, CCTV, access control, security | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-03-20 | 2028-04-03 |  | 2028-04-10 |  |  | as late as possible (need)
ALP-EPC-00CYA-CM-OMM-0001 | Telecom, CCTV, Access Control, Security - Operating Procedures | English / Turkish | EPC | 00CYA | Telecom, CCTV, access control, security | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-02-22 | 2027-04-05 |  | 2027-05-03 |  |  | ALP-EPC-00CYA-CM-CMP-0001
ALP-EPC-00CYA-GE-ITP-0001 | Telecom, CCTV, Access Control and Perimeter Security - Inspection and Test Plan |  | EPC | 00CYA | Telecom, CCTV, access control, security | general | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-IC-007 |  | 1 | 2027-03-02 | 2027-03-16 | 2027-04-06 | 2027-04-13 |  |  | capacity general
ALP-EPC-00CYA-GE-MRQ-0001 | Telecom, CCTV, Access Control and Perimeter Security - Material Requisition |  | EPC | 00CYA | Telecom, CCTV, access control, security | general | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-IC-007 |  | 2 | 2027-03-11 | 2027-03-18 |  | 2027-03-23 |  |  | ALP-EPC-00CYA-IC-DSH-0001
ALP-EPC-00CYA-GE-RPT-0001 | Telecom, CCTV, Access Control and Perimeter Security - Technical Bid Evaluation |  | EPC | 00CYA | Telecom, CCTV, access control, security | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-IC-007 |  | 1 | 2027-05-04 | 2027-05-25 |  | 2027-06-01 |  |  | bids MR-IC-007
ALP-EPC-00CYA-GE-SPC-0001 | Telecom, CCTV, Access Control and Perimeter Security - Technical Specification |  | EPC | 00CYA | Telecom, CCTV, access control, security | general | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-IC-007 |  | 3 | 2027-01-28 | 2027-02-25 | 2027-03-25 | 2027-04-01 |  |  | capacity general
ALP-EPC-00CYA-IC-BLK-0001 | Telecom, CCTV, Access Control, Security - System Architecture |  | EPC | 00CYA | Telecom, CCTV, access control, security | i_and_c | BLK | F | approval |  |  | 1 | 40 | [5 empty] | 2 | 2027-01-04 | 2027-01-25 | 2027-02-22 | 2027-03-01 |  |  | ALP-EPC-00000-IC-RPT-0002
ALP-EPC-00CYA-IC-DSH-0001 | Telecom, CCTV, Access Control, Security - Datasheet |  | EPC | 00CYA | Telecom, CCTV, access control, security | i_and_c | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-IC-007 | 00CYA10 | 2 | 2027-02-25 | 2027-03-11 | 2027-04-01 | 2027-04-08 |  |  | ALP-EPC-00CYA-GE-SPC-0001
ALP-EPC-00CYA-IC-LOG-0001 | Telecom, CCTV, Access Control, Security - Logic Diagrams |  | EPC | 00CYA | Telecom, CCTV, access control, security | i_and_c | LOG | F | approval |  |  | 9 | 88 | [5 empty] | 1 | 2027-01-08 | 2027-02-17 | 2027-03-17 | 2027-03-24 |  |  | capacity i_and_c
ALP-EPC-00EGA-CM-CMP-0001 | LDO Unloading - System Commissioning Procedure |  | EPC | 00EGA | LDO unloading | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-04-22 | 2027-05-20 | 2027-06-17 | 2027-06-24 |  |  | ALP-EPC-00EGA-IC-CNR-0001
ALP-EPC-00EGA-CM-MDB-0001 | LDO Unloading - System Turnover Dossier |  | EPC | 00EGA | LDO unloading | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-03-20 | 2028-04-03 |  | 2028-04-10 |  |  | as late as possible (need)
ALP-EPC-00EGA-CM-OMM-0001 | LDO Unloading - Operating Procedures | English / Turkish | EPC | 00EGA | LDO unloading | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-05-20 | 2027-07-01 |  | 2027-07-29 |  |  | ALP-EPC-00EGA-CM-CMP-0001
ALP-EPC-00EGA-GE-RPT-0001 | LDO Unloading and Forwarding / Treatment Skids - Technical Bid Evaluation |  | EPC | 00EGA | LDO unloading | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-016 |  | 1 | 2026-12-17 | 2027-01-07 |  | 2027-01-14 |  |  | bids MR-ME-016
ALP-EPC-00EGA-IC-CEM-0001 | LDO Unloading - Cause and Effect Matrix |  | EPC | 00EGA | LDO unloading | i_and_c | CEM | F | approval |  |  | 2 | 40 | [5 empty] | 2 | 2027-08-26 | 2027-09-17 | 2027-10-15 | 2027-10-22 |  |  | capacity i_and_c
ALP-EPC-00EGA-IC-CNR-0001 | LDO Unloading - Control Narrative |  | EPC | 00EGA | LDO unloading | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-04-01 | 2027-04-22 |  | 2027-05-20 |  |  | ALP-EPC-00EGA-PR-PID-0001
ALP-EPC-00EGA-IC-DSH-0001 | LDO Unloading - Instrument Datasheets |  | EPC | 00EGA | LDO unloading | i_and_c | DSH | E | approval |  |  | 30 | 53 |  |  |  | MR-IC-004 |  | 2 | 2027-04-01 | 2027-04-29 | 2027-05-20 | 2027-05-27 |  |  | ALP-EPC-00EGA-PR-PID-0001
ALP-EPC-00EGA-IC-DSH-0002 | LDO Unloading - Control Valve Sizing and Datasheets |  | EPC | 00EGA | LDO unloading | i_and_c | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-IC-005 |  | 3 | 2027-04-01 | 2027-04-15 | 2027-05-06 | 2027-05-13 |  |  | ALP-EPC-00EGA-PR-PID-0001
ALP-EPC-00EGA-IC-HMI-0001 | LDO Unloading - Operator Displays | HMI graphics | EPC | 00EGA | LDO unloading | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-04-22 | 2027-05-14 |  | 2027-06-04 |  |  | ALP-EPC-00EGA-IC-CNR-0001
ALP-EPC-00EGA-IC-LOG-0001 | LDO Unloading - Logic Diagrams |  | EPC | 00EGA | LDO unloading | i_and_c | LOG | F | approval |  |  | 24 | 208 | [5 empty] | 3 | 2027-04-22 | 2027-06-17 | 2027-07-15 | 2027-07-22 |  |  | ALP-EPC-00EGA-IC-CNR-0001
ALP-EPC-00EGA-ME-CAL-0001 | LDO Unloading - Sizing and Hydraulic Calculation |  | EPC | 00EGA | LDO unloading | mechanical | CAL | E | review |  |  | 5 | 70 | [5 empty] | 2 | 2027-01-11 | 2027-02-04 |  | 2027-02-25 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00EGA-ME-DSH-0001 | LDO Unloading: Package - Datasheet |  | EPC | 00EGA | LDO unloading | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-ME-016 | 00EGA10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00EGA-ME-DSH-0002 | LDO Unloading: Filters - Datasheet | 2 items | EPC | 00EGA | LDO unloading | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-016 | 00EGA10AT001 00EGA10AT002 | 3 | 2027-02-08 | 2027-02-22 | 2027-03-15 | 2027-03-22 |  |  | ALP-EPC-00000-ME-DBR-0001
ALP-EPC-00EGA-ME-DSH-0003 | LDO Unloading: Pumps - Datasheet | 4 items | EPC | 00EGA | LDO unloading | mechanical | DSH | E | approval |  |  | 4 | 46 |  |  |  | MR-ME-016 | 00EGA10AP001 00EGA10AP002 00EGA10AP003 00EGA10AP004 | 3 | 2027-02-08 | 2027-02-24 | 2027-03-17 | 2027-03-24 |  |  | ALP-EPC-00000-ME-DBR-0001
ALP-EPC-00EGA-ME-DSH-0004 | LDO Unloading: Tank - Datasheet |  | EPC | 00EGA | LDO unloading | mechanical | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-ME-016 | 00EGA10BB001 | 3 | 2027-02-08 | 2027-02-22 | 2027-03-15 | 2027-03-22 |  |  | ALP-EPC-00000-ME-DBR-0001
ALP-EPC-00EGA-ME-ITP-0001 | LDO Unloading and Forwarding / Treatment Skids - Inspection and Test Plan |  | EPC | 00EGA | LDO unloading | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-016 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00EGA-ME-MRQ-0001 | LDO Unloading and Forwarding / Treatment Skids - Material Requisition |  | EPC | 00EGA | LDO unloading | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-016 |  | 8 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00EGA-ME-SPC-0001 | LDO Unloading and Forwarding / Treatment Skids - Technical Specification |  | EPC | 00EGA | LDO unloading | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-016 |  | 4 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00EGA-PI-ISO-0001 | LDO Unloading - Isometric Drawings |  | EPC | 00EGA | LDO unloading | piping | ISO | L | information |  |  | 60 | 600 | EWP-10-PI-01 | CWP-10-PI-01 | CWA-10 |  |  | 3 | 2027-09-22 | 2027-11-17 |  | 2027-11-24 | 2027-12-27 | 23 | capacity piping
ALP-EPC-00EGA-PI-SUP-0001 | LDO Unloading - Pipe Support Drawings |  | EPC | 00EGA | LDO unloading | piping | SUP | L | information |  |  | 15 | 90 | EWP-10-PI-01 | CWP-10-PI-01 | CWA-10 | MR-PI-005 |  | 1 | 2027-12-09 | 2028-01-14 |  | 2028-01-21 | 2027-12-27 | -19 | capacity piping
ALP-EPC-00EGA-PR-DSH-0001 | LDO Unloading - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00EGA | LDO unloading | process | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-PI-007 |  | 2 | 2027-05-07 | 2027-05-24 | 2027-06-14 | 2027-06-21 |  |  | capacity process
ALP-EPC-00EGA-PR-PID-0001 | LDO Unloading - P&ID |  | EPC | 00EGA | LDO unloading | process | PID | F | approval |  |  | 2 | 220 | [5 empty] | 3 | 2027-02-23 | 2027-04-01 | 2027-05-06 | 2027-05-13 |  |  | capacity process
ALP-EPC-00EGA-PR-SDS-0001 | LDO Unloading - System Design Description |  | EPC | 00EGA | LDO unloading | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00EGB-CM-CMP-0001 | LDO Storage - System Commissioning Procedure |  | EPC | 00EGB | LDO storage | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-04-27 | 2027-05-25 | 2027-06-22 | 2027-06-29 |  |  | ALP-EPC-00EGB-IC-CNR-0001
ALP-EPC-00EGB-CM-MDB-0001 | LDO Storage - System Turnover Dossier |  | EPC | 00EGB | LDO storage | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-03-20 | 2028-04-03 |  | 2028-04-10 |  |  | as late as possible (need)
ALP-EPC-00EGB-CM-OMM-0001 | LDO Storage - Operating Procedures | English / Turkish | EPC | 00EGB | LDO storage | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-05-25 | 2027-07-06 |  | 2027-08-03 |  |  | ALP-EPC-00EGB-CM-CMP-0001
ALP-EPC-00EGB-GE-RPT-0001 | Field-Erected Storage Tanks: LDO Storage and Fire Water - Technical Bid Evaluation | API 650 | EPC | 00EGB | LDO storage | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-017 |  | 1 | 2027-03-02 | 2027-03-24 |  | 2027-03-31 |  |  | capacity general
ALP-EPC-00EGB-IC-CEM-0001 | LDO Storage - Cause and Effect Matrix |  | EPC | 00EGB | LDO storage | i_and_c | CEM | F | approval |  |  | 2 | 40 | [5 empty] | 2 | 2027-09-07 | 2027-09-29 | 2027-10-27 | 2027-11-03 |  |  | capacity i_and_c
ALP-EPC-00EGB-IC-CNR-0001 | LDO Storage - Control Narrative |  | EPC | 00EGB | LDO storage | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-04-06 | 2027-04-27 |  | 2027-05-25 |  |  | ALP-EPC-00EGB-PR-PID-0001
ALP-EPC-00EGB-IC-DSH-0001 | LDO Storage - Instrument Datasheets |  | EPC | 00EGB | LDO storage | i_and_c | DSH | E | approval |  |  | 30 | 53 |  |  |  | MR-IC-004 |  | 2 | 2027-04-06 | 2027-05-04 | 2027-05-25 | 2027-06-01 |  |  | ALP-EPC-00EGB-PR-PID-0001
ALP-EPC-00EGB-IC-HMI-0001 | LDO Storage - Operator Displays | HMI graphics | EPC | 00EGB | LDO storage | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-04-27 | 2027-05-19 |  | 2027-06-09 |  |  | ALP-EPC-00EGB-IC-CNR-0001
ALP-EPC-00EGB-IC-LOG-0001 | LDO Storage - Logic Diagrams |  | EPC | 00EGB | LDO storage | i_and_c | LOG | F | approval |  |  | 18 | 160 | [5 empty] | 3 | 2027-04-27 | 2027-06-17 | 2027-07-15 | 2027-07-22 |  |  | ALP-EPC-00EGB-IC-CNR-0001
ALP-EPC-00EGB-ME-CAL-0001 | LDO Storage - Sizing and Hydraulic Calculation |  | EPC | 00EGB | LDO storage | mechanical | CAL | E | review |  |  | 4 | 62 | [5 empty] | 2 | 2027-02-05 | 2027-03-25 |  | 2027-04-15 |  |  | capacity mechanical
ALP-EPC-00EGB-ME-DSH-0001 | LDO Storage: Tanks - Datasheet | 3 items | EPC | 00EGB | LDO storage | mechanical | DSH | E | approval |  | yes | 3 | 36 |  |  |  | MR-ME-017 | 00EGB10BB001 00EGB10BB002 00EGB10BB003 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00EGB-ME-MRQ-0001 | Field-Erected Storage Tanks: LDO Storage and Fire Water - Material Requisition | API 650 | EPC | 00EGB | LDO storage | mechanical | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-ME-017 |  | 4 | 2026-11-16 | 2026-11-23 |  | 2026-11-26 |  |  | capacity mechanical
ALP-EPC-00EGB-ME-SPC-0001 | Field-Erected Storage Tanks: LDO Storage and Fire Water - Technical Specification | API 650 | EPC | 00EGB | LDO storage | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-017 |  | 4 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00EGB-PI-ISO-0001 | LDO Storage - Isometric Drawings |  | EPC | 00EGB | LDO storage | piping | ISO | L | information |  |  | 50 | 500 | EWP-10-PI-01 | CWP-10-PI-01 | CWA-10 |  |  | 3 | 2027-10-11 | 2027-12-06 |  | 2027-12-13 | 2027-12-27 | 10 | capacity piping
ALP-EPC-00EGB-PI-SUP-0001 | LDO Storage - Pipe Support Drawings |  | EPC | 00EGB | LDO storage | piping | SUP | L | information |  |  | 13 | 78 | EWP-10-PI-01 | CWP-10-PI-01 | CWA-10 | MR-PI-005 |  | 1 | 2027-12-13 | 2028-01-14 |  | 2028-01-21 | 2027-12-27 | -19 | ALP-EPC-00EGB-PI-ISO-0001
ALP-EPC-00EGB-PR-DSH-0001 | LDO Storage - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00EGB | LDO storage | process | DSH | E | approval |  |  | 4 | 32 |  |  |  | MR-PI-007 |  | 2 | 2027-05-24 | 2027-06-24 | 2027-07-15 | 2027-07-22 |  |  | capacity process
ALP-EPC-00EGB-PR-PID-0001 | LDO Storage - P&ID |  | EPC | 00EGB | LDO storage | process | PID | F | approval |  |  | 2 | 220 | [5 empty] | 3 | 2027-03-01 | 2027-04-06 | 2027-05-11 | 2027-05-18 |  |  | capacity process
ALP-EPC-00EGB-PR-SDS-0001 | LDO Storage - System Design Description |  | EPC | 00EGB | LDO storage | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00EGC-CM-CMP-0001 | LDO Forwarding and Treatment - System Commissioning Procedure |  | EPC | 00EGC | LDO forwarding and treatment | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-03-15 | 2027-04-12 | 2027-05-10 | 2027-05-17 |  |  | ALP-EPC-00EGC-IC-CNR-0001
ALP-EPC-00EGC-CM-MDB-0001 | LDO Forwarding and Treatment - System Turnover Dossier |  | EPC | 00EGC | LDO forwarding and treatment | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-03-20 | 2028-04-03 |  | 2028-04-10 |  |  | as late as possible (need)
ALP-EPC-00EGC-CM-OMM-0001 | LDO Forwarding and Treatment - Operating Procedures | English / Turkish | EPC | 00EGC | LDO forwarding and treatment | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-04-12 | 2027-05-24 |  | 2027-06-21 |  |  | ALP-EPC-00EGC-CM-CMP-0001
ALP-EPC-00EGC-IC-CEM-0001 | LDO Forwarding and Treatment - Cause and Effect Matrix |  | EPC | 00EGC | LDO forwarding and treatment | i_and_c | CEM | F | approval |  |  | 3 | 52 | [5 empty] | 2 | 2027-09-07 | 2027-09-29 | 2027-10-27 | 2027-11-03 |  |  | capacity i_and_c
ALP-EPC-00EGC-IC-CNR-0001 | LDO Forwarding and Treatment - Control Narrative |  | EPC | 00EGC | LDO forwarding and treatment | i_and_c | CNR | F | review |  |  | 2 | 90 | [5 empty] | 2 | 2027-02-19 | 2027-03-15 |  | 2027-04-12 |  |  | ALP-EPC-00EGC-PR-PID-0001
ALP-EPC-00EGC-IC-DSH-0001 | LDO Forwarding and Treatment - Instrument Datasheets |  | EPC | 00EGC | LDO forwarding and treatment | i_and_c | DSH | E | approval |  |  | 70 | 113 |  |  |  | MR-IC-004 |  | 2 | 2027-02-19 | 2027-03-19 | 2027-04-09 | 2027-04-16 |  |  | ALP-EPC-00EGC-PR-PID-0001
ALP-EPC-00EGC-IC-DSH-0002 | LDO Forwarding and Treatment - Control Valve Sizing and Datasheets |  | EPC | 00EGC | LDO forwarding and treatment | i_and_c | DSH | E | approval |  |  | 6 | 44 |  |  |  | MR-IC-005 |  | 3 | 2027-02-19 | 2027-03-09 | 2027-03-30 | 2027-04-06 |  |  | ALP-EPC-00EGC-PR-PID-0001
ALP-EPC-00EGC-IC-HMI-0001 | LDO Forwarding and Treatment - Operator Displays | HMI graphics | EPC | 00EGC | LDO forwarding and treatment | i_and_c | HMI | F | review |  |  | 4 | 56 | [5 empty] | 2 | 2027-03-15 | 2027-04-07 |  | 2027-04-28 |  |  | ALP-EPC-00EGC-IC-CNR-0001
ALP-EPC-00EGC-IC-LOG-0001 | LDO Forwarding and Treatment - Logic Diagrams |  | EPC | 00EGC | LDO forwarding and treatment | i_and_c | LOG | F | approval |  |  | 44 | 368 | [5 empty] | 3 | 2027-03-15 | 2027-05-10 | 2027-06-07 | 2027-06-14 |  |  | ALP-EPC-00EGC-IC-CNR-0001
ALP-EPC-00EGC-ME-CAL-0001 | LDO Forwarding and Treatment - Sizing and Hydraulic Calculation |  | EPC | 00EGC | LDO forwarding and treatment | mechanical | CAL | E | review |  |  | 9 | 102 | [5 empty] | 2 | 2027-01-11 | 2027-02-09 |  | 2027-03-02 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00EGC-ME-DSH-0001 | LDO Forwarding and Treatment: Package - Datasheet |  | EPC | 00EGC | LDO forwarding and treatment | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-ME-016 | 00EGC10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00EGC-ME-DSH-0002 | LDO Forwarding and Treatment: Filters - Datasheet | 3 items | EPC | 00EGC | LDO forwarding and treatment | mechanical | DSH | E | approval |  |  | 3 | 36 |  |  |  | MR-ME-016 | 00EGC10AT001 00EGC10AT002 00EGC10AT003 | 3 | 2027-02-09 | 2027-02-24 | 2027-03-17 | 2027-03-24 |  |  | ALP-EPC-00EGC-ME-CAL-0001
ALP-EPC-00EGC-ME-DSH-0003 | LDO Forwarding and Treatment: Pumps - Datasheet | 3 items | EPC | 00EGC | LDO forwarding and treatment | mechanical | DSH | E | approval |  |  | 3 | 36 |  |  |  | MR-ME-016 | 00EGC10AP001 00EGC10AP002 00EGC10AP003 | 3 | 2027-02-09 | 2027-02-24 | 2027-03-17 | 2027-03-24 |  |  | ALP-EPC-00EGC-ME-CAL-0001
ALP-EPC-00EGC-PI-ISO-0001 | LDO Forwarding and Treatment - Isometric Drawings |  | EPC | 00EGC | LDO forwarding and treatment | piping | ISO | L | information |  |  | 120 | 1200 | EWP-10-PI-01 | CWP-10-PI-01 | CWA-10 |  |  | 4 | 2027-07-23 | 2027-09-22 |  | 2027-09-29 | 2027-12-27 | 63 | capacity piping
ALP-EPC-00EGC-PI-STR-0001 | LDO Forwarding and Treatment - Pipe Stress Analysis |  | EPC | 00EGC | LDO forwarding and treatment | piping | STR | E | review |  |  | 1 | 80 | [5 empty] | 2 | 2027-06-25 | 2027-07-23 |  | 2027-08-13 |  |  | capacity piping
ALP-EPC-00EGC-PI-SUP-0001 | LDO Forwarding and Treatment - Pipe Support Drawings |  | EPC | 00EGC | LDO forwarding and treatment | piping | SUP | L | information |  |  | 30 | 180 | EWP-10-PI-01 | CWP-10-PI-01 | CWA-10 | MR-PI-005 |  | 2 | 2027-12-06 | 2028-01-17 |  | 2028-01-24 | 2027-12-27 | -20 | capacity piping
ALP-EPC-00EGC-PR-DSH-0001 | LDO Forwarding and Treatment - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00EGC | LDO forwarding and treatment | process | DSH | E | approval |  |  | 4 | 32 |  |  |  | MR-PI-007 |  | 2 | 2027-06-11 | 2027-06-29 | 2027-07-20 | 2027-07-27 |  |  | capacity process
ALP-EPC-00EGC-PR-PID-0001 | LDO Forwarding and Treatment - P&ID |  | EPC | 00EGC | LDO forwarding and treatment | process | PID | F | approval |  |  | 4 | 420 | [5 empty] | 3 | 2027-01-11 | 2027-02-19 | 2027-03-26 | 2027-04-02 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00EGC-PR-SDS-0001 | LDO Forwarding and Treatment - System Design Description |  | EPC | 00EGC | LDO forwarding and treatment | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00EKA-CM-CMP-0001 | Gas Receiving, Filtration and Fiscal Metering Station - System Commissioning Procedure |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-03-16 | 2027-04-13 | 2027-05-11 | 2027-05-18 |  |  | ALP-EPC-00EKA-IC-CNR-0001
ALP-EPC-00EKA-CM-MDB-0001 | Gas Receiving, Filtration and Fiscal Metering Station - System Turnover Dossier |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-03-20 | 2028-04-03 |  | 2028-04-10 |  |  | as late as possible (need)
ALP-EPC-00EKA-CM-OMM-0001 | Gas Receiving, Filtration and Fiscal Metering Station - Operating Procedures | English / Turkish | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-04-13 | 2027-05-25 |  | 2027-06-22 |  |  | ALP-EPC-00EKA-CM-CMP-0001
ALP-EPC-00EKA-GE-RPT-0001 | Gas Receiving and Metering Station - Technical Bid Evaluation |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-015 |  | 1 | 2026-12-17 | 2027-01-07 |  | 2027-01-14 |  |  | bids MR-ME-015
ALP-EPC-00EKA-IC-CEM-0001 | Gas Receiving, Filtration and Fiscal Metering Station - Cause and Effect Matrix |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | i_and_c | CEM | F | approval |  |  | 4 | 64 | [5 empty] | 2 | 2027-09-07 | 2027-09-30 | 2027-10-28 | 2027-11-04 |  |  | capacity i_and_c
ALP-EPC-00EKA-IC-CNR-0001 | Gas Receiving, Filtration and Fiscal Metering Station - Control Narrative |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | i_and_c | CNR | F | review |  |  | 3 | 120 | [5 empty] | 2 | 2027-02-22 | 2027-03-16 |  | 2027-04-13 |  |  | ALP-EPC-00EKA-PR-PID-0001
ALP-EPC-00EKA-IC-DSH-0001 | Gas Receiving, Filtration and Fiscal Metering Station - Instrument Datasheets |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | i_and_c | DSH | E | approval |  |  | 110 | 173 |  |  |  | MR-IC-004 |  | 2 | 2027-02-22 | 2027-03-22 | 2027-04-12 | 2027-04-19 |  |  | ALP-EPC-00EKA-PR-PID-0001
ALP-EPC-00EKA-IC-DSH-0002 | Gas Receiving, Filtration and Fiscal Metering Station - Control Valve Sizing and Datasheets |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | i_and_c | DSH | E | approval |  |  | 8 | 56 |  |  |  | MR-IC-005 |  | 3 | 2027-02-22 | 2027-03-16 | 2027-04-06 | 2027-04-13 |  |  | capacity i_and_c
ALP-EPC-00EKA-IC-HMI-0001 | Gas Receiving, Filtration and Fiscal Metering Station - Operator Displays | HMI graphics | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | i_and_c | HMI | F | review |  |  | 5 | 68 | [5 empty] | 2 | 2027-03-16 | 2027-04-09 |  | 2027-04-30 |  |  | ALP-EPC-00EKA-IC-CNR-0001
ALP-EPC-00EKA-IC-LOG-0001 | Gas Receiving, Filtration and Fiscal Metering Station - Logic Diagrams |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | i_and_c | LOG | F | approval |  |  | 52 | 432 | [5 empty] | 3 | 2027-03-16 | 2027-05-11 | 2027-06-08 | 2027-06-15 |  |  | ALP-EPC-00EKA-IC-CNR-0001
ALP-EPC-00EKA-ME-CAL-0001 | Gas Receiving, Filtration and Fiscal Metering Station - Sizing and Hydraulic Calculation |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | CAL | E | review |  |  | 10 | 110 | [5 empty] | 2 | 2027-01-11 | 2027-02-10 |  | 2027-03-03 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00EKA-ME-DSH-0001 | Gas Receiving, Filtration and Fiscal Metering Station: Package - Datasheet |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-ME-015 | 00EKA10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00EKA-ME-DSH-0002 | Gas Receiving, Filtration and Fiscal Metering Station: Filters - Datasheet | 2 items | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-015 | 00EKA10AT001 00EKA10AT002 | 3 | 2027-02-10 | 2027-02-24 | 2027-03-17 | 2027-03-24 |  |  | ALP-EPC-00EKA-ME-CAL-0001
ALP-EPC-00EKA-ME-DSH-0003 | Gas Receiving, Filtration and Fiscal Metering Station: Heat Exchangers - Datasheet | 2 items | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-015 | 00EKA10AC001 00EKA10AC002 | 3 | 2027-02-10 | 2027-02-24 | 2027-03-17 | 2027-03-24 |  |  | ALP-EPC-00EKA-ME-CAL-0001
ALP-EPC-00EKA-ME-DSH-0004 | Gas Receiving, Filtration and Fiscal Metering Station: Tank - Datasheet |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-ME-015 | 00EKA10BB001 | 3 | 2027-02-10 | 2027-02-24 | 2027-03-17 | 2027-03-24 |  |  | ALP-EPC-00EKA-ME-CAL-0001
ALP-EPC-00EKA-ME-ITP-0001 | Gas Receiving and Metering Station - Inspection and Test Plan |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-015 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00EKA-ME-MRQ-0001 | Gas Receiving and Metering Station - Material Requisition |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-015 |  | 5 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00EKA-ME-SPC-0001 | Gas Receiving and Metering Station - Technical Specification |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-015 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00EKA-PI-ISO-0001 | Gas Receiving, Filtration and Fiscal Metering Station - Isometric Drawings |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | piping | ISO | L | information |  |  | 150 | 1500 | EWP-09-PI-01 | CWP-09-PI-01 | CWA-09 |  |  | 4 | 2027-07-06 | 2027-08-31 |  | 2027-09-07 | 2027-11-29 | 59 | ALP-EPC-00EKA-PI-STR-0001
ALP-EPC-00EKA-PI-STR-0001 | Gas Receiving, Filtration and Fiscal Metering Station - Pipe Stress Analysis |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | piping | STR | E | review |  |  | 2 | 140 | [5 empty] | 2 | 2027-05-11 | 2027-07-06 |  | 2027-07-27 |  |  | capacity piping
ALP-EPC-00EKA-PI-SUP-0001 | Gas Receiving, Filtration and Fiscal Metering Station - Pipe Support Drawings |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | piping | SUP | L | information |  |  | 38 | 228 | EWP-09-PI-01 | CWP-09-PI-01 | CWA-09 | MR-PI-005 |  | 2 | 2027-10-11 | 2027-11-22 |  | 2027-11-29 | 2027-11-29 | 0 | capacity piping
ALP-EPC-00EKA-PR-DSH-0001 | Gas Receiving, Filtration and Fiscal Metering Station - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | process | DSH | E | approval |  |  | 8 | 56 |  |  |  | MR-PI-007 |  | 2 | 2027-06-11 | 2027-07-01 | 2027-07-22 | 2027-07-29 |  |  | capacity process
ALP-EPC-00EKA-PR-PID-0001 | Gas Receiving, Filtration and Fiscal Metering Station - P&ID |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | process | PID | F | approval | yes |  | 5 | 520 | [5 empty] | 3 | 2027-01-11 | 2027-02-22 | 2027-04-05 | 2027-04-12 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00EKA-PR-SDS-0001 | Gas Receiving, Filtration and Fiscal Metering Station - System Design Description |  | EPC | 00EKA | Gas receiving, filtration and fiscal metering station | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00EKC-CM-CMP-0001 | Fuel Gas Distribution to GT and Auxiliary Boiler - System Commissioning Procedure |  | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-05-27 | 2027-06-24 | 2027-07-22 | 2027-07-29 |  |  | ALP-EPC-00EKC-IC-CNR-0001
ALP-EPC-00EKC-CM-MDB-0001 | Fuel Gas Distribution to GT and Auxiliary Boiler - System Turnover Dossier |  | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-03-20 | 2028-04-03 |  | 2028-04-10 |  |  | as late as possible (need)
ALP-EPC-00EKC-CM-OMM-0001 | Fuel Gas Distribution to GT and Auxiliary Boiler - Operating Procedures | English / Turkish | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-06-24 | 2027-08-05 |  | 2027-09-02 |  |  | ALP-EPC-00EKC-CM-CMP-0001
ALP-EPC-00EKC-IC-CEM-0001 | Fuel Gas Distribution to GT and Auxiliary Boiler - Cause and Effect Matrix |  | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | i_and_c | CEM | F | approval |  |  | 1 | 28 | [5 empty] | 2 | 2027-08-16 | 2027-09-21 | 2027-10-19 | 2027-10-26 |  |  | capacity i_and_c
ALP-EPC-00EKC-IC-CNR-0001 | Fuel Gas Distribution to GT and Auxiliary Boiler - Control Narrative |  | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-05-06 | 2027-05-27 |  | 2027-06-24 |  |  | ALP-EPC-00EKC-PR-PID-0001
ALP-EPC-00EKC-IC-DSH-0001 | Fuel Gas Distribution to GT and Auxiliary Boiler - Instrument Datasheets |  | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | i_and_c | DSH | E | approval |  |  | 30 | 53 |  |  |  | MR-IC-004 |  | 2 | 2027-05-06 | 2027-06-03 | 2027-06-24 | 2027-07-01 |  |  | ALP-EPC-00EKC-PR-PID-0001
ALP-EPC-00EKC-IC-DSH-0002 | Fuel Gas Distribution to GT and Auxiliary Boiler - Control Valve Sizing and Datasheets |  | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | i_and_c | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-IC-005 |  | 3 | 2027-05-06 | 2027-05-20 | 2027-06-10 | 2027-06-17 |  |  | ALP-EPC-00EKC-PR-PID-0001
ALP-EPC-00EKC-IC-HMI-0001 | Fuel Gas Distribution to GT and Auxiliary Boiler - Operator Displays | HMI graphics | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-05-27 | 2027-06-18 |  | 2027-07-09 |  |  | ALP-EPC-00EKC-IC-CNR-0001
ALP-EPC-00EKC-IC-LOG-0001 | Fuel Gas Distribution to GT and Auxiliary Boiler - Logic Diagrams |  | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | i_and_c | LOG | F | approval |  |  | 12 | 112 | [5 empty] | 3 | 2027-05-27 | 2027-07-09 | 2027-08-06 | 2027-08-13 |  |  | ALP-EPC-00EKC-IC-CNR-0001
ALP-EPC-00EKC-ME-CAL-0001 | Fuel Gas Distribution to GT and Auxiliary Boiler - Sizing and Hydraulic Calculation |  | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | mechanical | CAL | E | review |  |  | 3 | 54 | [5 empty] | 2 | 2027-03-03 | 2027-03-25 |  | 2027-04-15 |  |  | capacity mechanical
ALP-EPC-00EKC-PI-ISO-0001 | Fuel Gas Distribution to GT and Auxiliary Boiler - Isometric Drawings |  | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | piping | ISO | L | information |  |  | 60 | 600 | EWP-09-PI-01 | CWP-09-PI-01 | CWA-09 |  |  | 4 | 2027-07-23 | 2027-09-17 |  | 2027-09-24 | 2027-11-29 | 46 | ALP-EPC-00EKC-PI-STR-0001
ALP-EPC-00EKC-PI-STR-0001 | Fuel Gas Distribution to GT and Auxiliary Boiler - Pipe Stress Analysis |  | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | piping | STR | E | review |  |  | 2 | 140 | [5 empty] | 3 | 2027-06-24 | 2027-07-23 |  | 2027-08-13 |  |  | capacity piping
ALP-EPC-00EKC-PI-SUP-0001 | Fuel Gas Distribution to GT and Auxiliary Boiler - Pipe Support Drawings |  | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | piping | SUP | L | information |  |  | 15 | 90 | EWP-09-PI-01 | CWP-09-PI-01 | CWA-09 | MR-PI-005 |  | 2 | 2027-10-26 | 2027-12-01 |  | 2027-12-08 | 2027-11-29 | -7 | capacity piping
ALP-EPC-00EKC-PR-DSH-0001 | Fuel Gas Distribution to GT and Auxiliary Boiler - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | process | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-PI-007 |  | 2 | 2027-06-04 | 2027-06-18 | 2027-07-09 | 2027-07-16 |  |  | capacity process
ALP-EPC-00EKC-PR-PID-0001 | Fuel Gas Distribution to GT and Auxiliary Boiler - P&ID |  | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | process | PID | F | approval |  |  | 2 | 220 | [5 empty] | 3 | 2027-03-31 | 2027-05-06 | 2027-06-10 | 2027-06-17 |  |  | capacity process
ALP-EPC-00EKC-PR-SDS-0001 | Fuel Gas Distribution to GT and Auxiliary Boiler - System Design Description |  | EPC | 00EKC | Fuel gas distribution to GT and auxiliary boiler | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00GBA-CM-CMP-0001 | Seawater Reverse Osmosis - System Commissioning Procedure |  | EPC | 00GBA | Seawater reverse osmosis | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-03-23 | 2027-04-20 | 2027-05-18 | 2027-05-25 |  |  | ALP-EPC-00GBA-IC-CNR-0001
ALP-EPC-00GBA-CM-MDB-0001 | Seawater Reverse Osmosis - System Turnover Dossier |  | EPC | 00GBA | Seawater reverse osmosis | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-03-20 | 2028-04-03 |  | 2028-04-10 |  |  | as late as possible (need)
ALP-EPC-00GBA-CM-OMM-0001 | Seawater Reverse Osmosis - Operating Procedures | English / Turkish | EPC | 00GBA | Seawater reverse osmosis | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-04-20 | 2027-06-01 |  | 2027-06-29 |  |  | ALP-EPC-00GBA-CM-CMP-0001
ALP-EPC-00GBA-GE-RPT-0001 | Water Treatment Package - Technical Bid Evaluation | SWRO, demin, condensate polishing | EPC | 00GBA | Seawater reverse osmosis | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-012 |  | 1 | 2026-12-24 | 2027-01-14 |  | 2027-01-21 |  |  | bids MR-ME-012
ALP-EPC-00GBA-IC-CNR-0001 | Seawater Reverse Osmosis - Control Narrative |  | EPC | 00GBA | Seawater reverse osmosis | i_and_c | CNR | F | review |  |  | 2 | 90 | [5 empty] | 2 | 2027-03-01 | 2027-03-23 |  | 2027-04-20 |  |  | ALP-EPC-00GBA-PR-PID-0001
ALP-EPC-00GBA-IC-DSH-0001 | Seawater Reverse Osmosis - Instrument Datasheets |  | EPC | 00GBA | Seawater reverse osmosis | i_and_c | DSH | E | approval |  |  | 60 | 98 |  |  |  | MR-IC-004 |  | 2 | 2027-03-01 | 2027-03-29 | 2027-04-19 | 2027-04-26 |  |  | ALP-EPC-00GBA-PR-PID-0001
ALP-EPC-00GBA-IC-DSH-0002 | Seawater Reverse Osmosis - Control Valve Sizing and Datasheets |  | EPC | 00GBA | Seawater reverse osmosis | i_and_c | DSH | E | approval |  |  | 4 | 32 |  |  |  | MR-IC-005 |  | 3 | 2027-03-01 | 2027-03-17 | 2027-04-07 | 2027-04-14 |  |  | ALP-EPC-00GBA-PR-PID-0001
ALP-EPC-00GBA-IC-HMI-0001 | Seawater Reverse Osmosis - Operator Displays | HMI graphics | EPC | 00GBA | Seawater reverse osmosis | i_and_c | HMI | F | review |  |  | 3 | 44 | [5 empty] | 2 | 2027-03-23 | 2027-04-14 |  | 2027-05-05 |  |  | ALP-EPC-00GBA-IC-CNR-0001
ALP-EPC-00GBA-ME-CAL-0001 | Seawater Reverse Osmosis - Sizing and Hydraulic Calculation |  | EPC | 00GBA | Seawater reverse osmosis | mechanical | CAL | E | review |  |  | 7 | 86 | [5 empty] | 2 | 2027-01-11 | 2027-02-08 |  | 2027-03-01 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00GBA-ME-DSH-0001 | Seawater Reverse Osmosis: Package - Datasheet |  | EPC | 00GBA | Seawater reverse osmosis | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-ME-012 | 00GBA10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00GBA-ME-DSH-0002 | Seawater Reverse Osmosis: Filters - Datasheet | 5 items | EPC | 00GBA | Seawater reverse osmosis | mechanical | DSH | E | approval |  |  | 5 | 56 |  |  |  | MR-ME-012 | 00GBA10AT001 00GBA10AT002 00GBA10AT003 00GBA10AT004 00GBA10AT005 | 3 | 2027-02-08 | 2027-02-24 | 2027-03-17 | 2027-03-24 |  |  | ALP-EPC-00GBA-ME-CAL-0001
ALP-EPC-00GBA-ME-DSH-0003 | Seawater Reverse Osmosis: Pumps - Datasheet | 6 items | EPC | 00GBA | Seawater reverse osmosis | mechanical | DSH | E | approval |  |  | 6 | 66 |  |  |  | MR-ME-012 | 00GBA10AP001 00GBA10AP002 00GBA10AP003 00GBA10AP004 00GBA10AP005 00GBA10AP006 | 3 | 2027-02-08 | 2027-02-24 | 2027-03-17 | 2027-03-24 |  |  | ALP-EPC-00GBA-ME-CAL-0001
ALP-EPC-00GBA-ME-DSH-0004 | Seawater Reverse Osmosis: Tank - Datasheet |  | EPC | 00GBA | Seawater reverse osmosis | mechanical | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-ME-012 | 00GBA10BB001 | 3 | 2027-02-08 | 2027-02-22 | 2027-03-15 | 2027-03-22 |  |  | ALP-EPC-00GBA-ME-CAL-0001
ALP-EPC-00GBA-PI-ISO-0001 | Seawater Reverse Osmosis - Isometric Drawings |  | EPC | 00GBA | Seawater reverse osmosis | piping | ISO | L | information |  |  | 80 | 800 | EWP-07-PI-01 | CWP-07-PI-01 | CWA-07 |  |  | 3 | 2027-10-26 | 2027-12-21 |  | 2027-12-28 | 2028-01-24 | 19 | capacity piping
ALP-EPC-00GBA-PI-SUP-0001 | Seawater Reverse Osmosis - Pipe Support Drawings |  | EPC | 00GBA | Seawater reverse osmosis | piping | SUP | L | information |  |  | 20 | 120 | EWP-07-PI-01 | CWP-07-PI-01 | CWA-07 | MR-PI-005 |  | 1 | 2027-12-28 | 2028-02-07 |  | 2028-02-14 | 2028-01-24 | -15 | ALP-EPC-00GBA-PI-ISO-0001
ALP-EPC-00GBA-PR-DSH-0001 | Seawater Reverse Osmosis - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00GBA | Seawater reverse osmosis | process | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-PI-007 |  | 2 | 2027-06-11 | 2027-06-25 | 2027-07-16 | 2027-07-23 |  |  | capacity process
ALP-EPC-00GBA-PR-PID-0001 | Seawater Reverse Osmosis - P&ID |  | EPC | 00GBA | Seawater reverse osmosis | process | PID | F | approval |  |  | 3 | 320 | [5 empty] | 3 | 2027-01-15 | 2027-03-01 | 2027-04-05 | 2027-04-12 |  |  | capacity process
ALP-EPC-00GBA-PR-SDS-0001 | Seawater Reverse Osmosis - System Design Description |  | EPC | 00GBA | Seawater reverse osmosis | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00GCA-CM-CMP-0001 | Demineralisation - System Commissioning Procedure |  | EPC | 00GCA | Demineralisation | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-05-27 | 2027-06-24 | 2027-07-22 | 2027-07-29 |  |  | ALP-EPC-00GCA-IC-CNR-0001
ALP-EPC-00GCA-CM-MDB-0001 | Demineralisation - System Turnover Dossier |  | EPC | 00GCA | Demineralisation | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-03-20 | 2028-04-03 |  | 2028-04-10 |  |  | as late as possible (need)
ALP-EPC-00GCA-CM-OMM-0001 | Demineralisation - Operating Procedures | English / Turkish | EPC | 00GCA | Demineralisation | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-06-24 | 2027-08-05 |  | 2027-09-02 |  |  | ALP-EPC-00GCA-CM-CMP-0001
ALP-EPC-00GCA-IC-CNR-0001 | Demineralisation - Control Narrative |  | EPC | 00GCA | Demineralisation | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-05-06 | 2027-05-27 |  | 2027-06-24 |  |  | ALP-EPC-00GCA-PR-PID-0001
ALP-EPC-00GCA-IC-DSH-0001 | Demineralisation - Instrument Datasheets |  | EPC | 00GCA | Demineralisation | i_and_c | DSH | E | approval |  |  | 40 | 68 |  |  |  | MR-IC-004 |  | 2 | 2027-05-06 | 2027-06-03 | 2027-06-24 | 2027-07-01 |  |  | ALP-EPC-00GCA-PR-PID-0001
ALP-EPC-00GCA-IC-DSH-0002 | Demineralisation - Control Valve Sizing and Datasheets |  | EPC | 00GCA | Demineralisation | i_and_c | DSH | E | approval |  |  | 4 | 32 |  |  |  | MR-IC-005 |  | 3 | 2027-05-06 | 2027-05-24 | 2027-06-14 | 2027-06-21 |  |  | ALP-EPC-00GCA-PR-PID-0001
ALP-EPC-00GCA-IC-HMI-0001 | Demineralisation - Operator Displays | HMI graphics | EPC | 00GCA | Demineralisation | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-05-27 | 2027-06-18 |  | 2027-07-09 |  |  | ALP-EPC-00GCA-IC-CNR-0001
ALP-EPC-00GCA-ME-CAL-0001 | Demineralisation - Sizing and Hydraulic Calculation |  | EPC | 00GCA | Demineralisation | mechanical | CAL | E | review |  |  | 5 | 70 | [5 empty] | 2 | 2027-01-11 | 2027-02-04 |  | 2027-02-25 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00GCA-ME-DSH-0001 | Demineralisation: Package - Datasheet |  | EPC | 00GCA | Demineralisation | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-ME-012 | 00GCA10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00GCA-ME-DSH-0002 | Demineralisation: Filters - Datasheet | 4 items | EPC | 00GCA | Demineralisation | mechanical | DSH | E | approval |  |  | 4 | 46 |  |  |  | MR-ME-012 | 00GCA10AT001 00GCA10AT002 00GCA10AT003 00GCA10AT004 | 3 | 2027-02-08 | 2027-02-24 | 2027-03-17 | 2027-03-24 |  |  | ALP-EPC-00000-ME-DBR-0001
ALP-EPC-00GCA-ME-DSH-0003 | Demineralisation: Pumps - Datasheet | 2 items | EPC | 00GCA | Demineralisation | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-012 | 00GCA10AP001 00GCA10AP002 | 3 | 2027-02-08 | 2027-02-22 | 2027-03-15 | 2027-03-22 |  |  | ALP-EPC-00000-ME-DBR-0001
ALP-EPC-00GCA-PI-ISO-0001 | Demineralisation - Isometric Drawings |  | EPC | 00GCA | Demineralisation | piping | ISO | L | information |  |  | 60 | 600 | EWP-07-PI-01 | CWP-07-PI-01 | CWA-07 |  |  | 3 | 2027-11-05 | 2028-01-03 |  | 2028-01-10 | 2028-01-24 | 10 | capacity piping
ALP-EPC-00GCA-PI-SUP-0001 | Demineralisation - Pipe Support Drawings |  | EPC | 00GCA | Demineralisation | piping | SUP | L | information |  |  | 15 | 90 | EWP-07-PI-01 | CWP-07-PI-01 | CWA-07 | MR-PI-005 |  | 1 | 2028-01-10 | 2028-02-15 |  | 2028-02-22 | 2028-01-24 | -21 | ALP-EPC-00GCA-PI-ISO-0001
ALP-EPC-00GCA-PR-DSH-0001 | Demineralisation - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00GCA | Demineralisation | process | DSH | E | approval |  |  | 1 | 14 |  |  |  | MR-PI-007 |  | 2 | 2027-05-07 | 2027-05-24 | 2027-06-14 | 2027-06-21 |  |  | capacity process
ALP-EPC-00GCA-PR-PID-0001 | Demineralisation - P&ID |  | EPC | 00GCA | Demineralisation | process | PID | F | approval |  |  | 2 | 220 | [5 empty] | 3 | 2027-03-31 | 2027-05-06 | 2027-06-10 | 2027-06-17 |  |  | capacity process
ALP-EPC-00GCA-PR-SDS-0001 | Demineralisation - System Design Description |  | EPC | 00GCA | Demineralisation | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00GHA-CM-CMP-0001 | Demineralised Water Storage and Distribution - System Commissioning Procedure |  | EPC | 00GHA | Demineralised water storage and distribution | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-05-27 | 2027-06-24 | 2027-07-22 | 2027-07-29 |  |  | ALP-EPC-00GHA-IC-CNR-0001
ALP-EPC-00GHA-CM-MDB-0001 | Demineralised Water Storage and Distribution - System Turnover Dossier |  | EPC | 00GHA | Demineralised water storage and distribution | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-03-20 | 2028-04-03 |  | 2028-04-10 |  |  | as late as possible (need)
ALP-EPC-00GHA-CM-OMM-0001 | Demineralised Water Storage and Distribution - Operating Procedures | English / Turkish | EPC | 00GHA | Demineralised water storage and distribution | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-06-24 | 2027-08-05 |  | 2027-09-02 |  |  | ALP-EPC-00GHA-CM-CMP-0001
ALP-EPC-00GHA-GE-RPT-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Technical Bid Evaluation |  | EPC | 00GHA | Demineralised water storage and distribution | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-013 |  | 1 | 2026-12-03 | 2027-01-14 |  | 2027-01-21 |  |  | capacity general
ALP-EPC-00GHA-IC-CNR-0001 | Demineralised Water Storage and Distribution - Control Narrative |  | EPC | 00GHA | Demineralised water storage and distribution | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-05-06 | 2027-05-27 |  | 2027-06-24 |  |  | ALP-EPC-00GHA-PR-PID-0001
ALP-EPC-00GHA-IC-DSH-0001 | Demineralised Water Storage and Distribution - Instrument Datasheets |  | EPC | 00GHA | Demineralised water storage and distribution | i_and_c | DSH | E | approval |  |  | 25 | 45.5 |  |  |  | MR-IC-004 |  | 2 | 2027-05-06 | 2027-06-03 | 2027-06-24 | 2027-07-01 |  |  | ALP-EPC-00GHA-PR-PID-0001
ALP-EPC-00GHA-IC-DSH-0002 | Demineralised Water Storage and Distribution - Control Valve Sizing and Datasheets |  | EPC | 00GHA | Demineralised water storage and distribution | i_and_c | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-IC-005 |  | 3 | 2027-05-06 | 2027-05-20 | 2027-06-10 | 2027-06-17 |  |  | ALP-EPC-00GHA-PR-PID-0001
ALP-EPC-00GHA-IC-HMI-0001 | Demineralised Water Storage and Distribution - Operator Displays | HMI graphics | EPC | 00GHA | Demineralised water storage and distribution | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-05-27 | 2027-06-18 |  | 2027-07-09 |  |  | ALP-EPC-00GHA-IC-CNR-0001
ALP-EPC-00GHA-IC-LOG-0001 | Demineralised Water Storage and Distribution - Logic Diagrams |  | EPC | 00GHA | Demineralised water storage and distribution | i_and_c | LOG | F | approval |  |  | 19 | 168 | [5 empty] | 3 | 2027-05-27 | 2027-07-20 | 2027-08-17 | 2027-08-24 |  |  | ALP-EPC-00GHA-IC-CNR-0001
ALP-EPC-00GHA-ME-CAL-0001 | Demineralised Water Storage and Distribution - Sizing and Hydraulic Calculation |  | EPC | 00GHA | Demineralised water storage and distribution | mechanical | CAL | E | review |  |  | 4 | 62 | [5 empty] | 2 | 2027-02-03 | 2027-03-12 |  | 2027-04-02 |  |  | capacity mechanical
ALP-EPC-00GHA-ME-DSH-0001 | Demineralised Water Storage and Distribution: Tanks - Datasheet | 2 items | EPC | 00GHA | Demineralised water storage and distribution | mechanical | DSH | E | approval |  | yes | 2 | 26 |  |  |  | MR-ME-013 | 00GHA10BB001 00GHA10BB002 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00GHA-ME-DSH-0002 | Demineralised Water Storage and Distribution: Pumps - Datasheet | 2 items | EPC | 00GHA | Demineralised water storage and distribution | mechanical | DSH | E | approval |  | yes | 2 | 26 |  |  |  | MR-ME-013 | 00GHA10AP001 00GHA10AP002 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00GHA-ME-ITP-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Inspection and Test Plan |  | EPC | 00GHA | Demineralised water storage and distribution | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-013 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00GHA-ME-MRQ-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Material Requisition |  | EPC | 00GHA | Demineralised water storage and distribution | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-013 |  | 6 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00GHA-ME-SPC-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Technical Specification |  | EPC | 00GHA | Demineralised water storage and distribution | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-013 |  | 4 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00GHA-PI-ISO-0001 | Demineralised Water Storage and Distribution - Isometric Drawings |  | EPC | 00GHA | Demineralised water storage and distribution | piping | ISO | L | information |  |  | 50 | 500 | EWP-07-PI-01 | CWP-07-PI-01 | CWA-07 |  |  | 3 | 2027-11-23 | 2028-01-21 |  | 2028-01-28 | 2028-01-24 | -4 | capacity piping
ALP-EPC-00GHA-PI-SUP-0001 | Demineralised Water Storage and Distribution - Pipe Support Drawings |  | EPC | 00GHA | Demineralised water storage and distribution | piping | SUP | L | information |  |  | 13 | 78 | EWP-07-PI-01 | CWP-07-PI-01 | CWA-07 | MR-PI-005 |  | 1 | 2028-01-28 | 2028-03-02 |  | 2028-03-09 | 2028-01-24 | -33 | ALP-EPC-00GHA-PI-ISO-0001
ALP-EPC-00GHA-PR-DSH-0001 | Demineralised Water Storage and Distribution - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00GHA | Demineralised water storage and distribution | process | DSH | E | approval |  |  | 1 | 14 |  |  |  | MR-PI-007 |  | 2 | 2027-06-11 | 2027-06-25 | 2027-07-16 | 2027-07-23 |  |  | capacity process
ALP-EPC-00GHA-PR-PID-0001 | Demineralised Water Storage and Distribution - P&ID |  | EPC | 00GHA | Demineralised water storage and distribution | process | PID | F | approval |  |  | 2 | 220 | [5 empty] | 3 | 2027-03-31 | 2027-05-06 | 2027-06-10 | 2027-06-17 |  |  | capacity process
ALP-EPC-00GHA-PR-SDS-0001 | Demineralised Water Storage and Distribution - System Design Description |  | EPC | 00GHA | Demineralised water storage and distribution | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00GKA-CM-CMP-0001 | Potable Water - System Commissioning Procedure |  | EPC | 00GKA | Potable water | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-07-02 | 2027-07-30 | 2027-08-27 | 2027-09-03 |  |  | ALP-EPC-00GKA-IC-CNR-0001
ALP-EPC-00GKA-CM-MDB-0001 | Potable Water - System Turnover Dossier |  | EPC | 00GKA | Potable water | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-03-20 | 2028-04-03 |  | 2028-04-10 |  |  | as late as possible (need)
ALP-EPC-00GKA-CM-OMM-0001 | Potable Water - Operating Procedures | English / Turkish | EPC | 00GKA | Potable water | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-07-30 | 2027-09-10 |  | 2027-10-08 |  |  | ALP-EPC-00GKA-CM-CMP-0001
ALP-EPC-00GKA-IC-CNR-0001 | Potable Water - Control Narrative |  | EPC | 00GKA | Potable water | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-06-11 | 2027-07-02 |  | 2027-07-30 |  |  | ALP-EPC-00GKA-PR-PID-0001
ALP-EPC-00GKA-IC-DSH-0001 | Potable Water - Instrument Datasheets |  | EPC | 00GKA | Potable water | i_and_c | DSH | E | approval |  |  | 10 | 23 |  |  |  | MR-IC-004 |  | 2 | 2027-06-11 | 2027-07-01 | 2027-07-22 | 2027-07-29 |  |  | ALP-EPC-00GKA-PR-PID-0001
ALP-EPC-00GKA-IC-HMI-0001 | Potable Water - Operator Displays | HMI graphics | EPC | 00GKA | Potable water | i_and_c | HMI | F | review |  |  | 1 | 20 | [5 empty] | 2 | 2027-07-02 | 2027-07-23 |  | 2027-08-13 |  |  | ALP-EPC-00GKA-IC-CNR-0001
ALP-EPC-00GKA-IC-LOG-0001 | Potable Water - Logic Diagrams |  | EPC | 00GKA | Potable water | i_and_c | LOG | F | approval |  |  | 10 | 96 | [5 empty] | 3 | 2027-07-02 | 2027-09-16 | 2027-10-14 | 2027-10-21 |  |  | capacity i_and_c
ALP-EPC-00GKA-ME-CAL-0001 | Potable Water - Sizing and Hydraulic Calculation |  | EPC | 00GKA | Potable water | mechanical | CAL | E | review |  |  | 2 | 46 | [5 empty] | 2 | 2027-02-02 | 2027-03-11 |  | 2027-04-01 |  |  | capacity mechanical
ALP-EPC-00GKA-ME-DSH-0001 | Potable Water: Tank - Datasheet |  | EPC | 00GKA | Potable water | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-ME-013 | 00GKA10BB001 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00GKA-ME-DSH-0002 | Potable Water: Filters - Datasheet | 2 items | EPC | 00GKA | Potable water | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-013 | 00GKA10AT001 00GKA10AT002 | 3 | 2027-03-11 | 2027-03-25 | 2027-04-15 | 2027-04-22 |  |  | ALP-EPC-00GKA-ME-CAL-0001
ALP-EPC-00GKA-ME-DSH-0003 | Potable Water: Pumps - Datasheet | 3 items | EPC | 00GKA | Potable water | mechanical | DSH | E | approval |  |  | 3 | 36 |  |  |  | MR-ME-013 | 00GKA10AP001 00GKA10AP002 00GKA10AP003 | 3 | 2027-03-11 | 2027-03-26 | 2027-04-16 | 2027-04-23 |  |  | ALP-EPC-00GKA-ME-CAL-0001
ALP-EPC-00GKA-PI-ISO-0001 | Potable Water - Isometric Drawings |  | EPC | 00GKA | Potable water | piping | ISO | L | information |  |  | 25 | 250 | EWP-12-PI-01 | CWP-12-PI-01 | CWA-12 |  |  | 3 | 2027-06-24 | 2027-08-19 |  | 2027-08-26 | 2027-07-12 | -33 | capacity piping
ALP-EPC-00GKA-PI-PPL-0001 | Potable Water - Underground Piping Drawings |  | EPC | 00GKA | Potable water | piping | PPL | L | review |  |  | 3 | 90 | EWP-12-PI-01 | CWP-12-PI-01 | CWA-12 |  |  | 2 | 2027-06-11 | 2027-07-21 |  | 2027-08-18 | 2027-07-12 | -27 | ALP-EPC-00GKA-PR-PID-0001
ALP-EPC-00GKA-PI-SUP-0001 | Potable Water - Pipe Support Drawings |  | EPC | 00GKA | Potable water | piping | SUP | L | information |  |  | 7 | 42 | EWP-12-PI-01 | CWP-12-PI-01 | CWA-12 | MR-PI-005 |  | 1 | 2027-08-26 | 2027-09-23 |  | 2027-09-30 | 2027-07-12 | -58 | ALP-EPC-00GKA-PI-ISO-0001
ALP-EPC-00GKA-PR-PID-0001 | Potable Water - P&ID |  | EPC | 00GKA | Potable water | process | PID | F | approval |  |  | 1 | 120 | [5 empty] | 3 | 2027-05-07 | 2027-06-11 | 2027-07-16 | 2027-07-23 |  |  | capacity process
ALP-EPC-00GKA-PR-SDS-0001 | Potable Water - System Design Description |  | EPC | 00GKA | Potable water | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00GMA-CM-CMP-0001 | Process Drains and Waste Water Collection - System Commissioning Procedure |  | EPC | 00GMA | Process drains and waste water collection | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-04-21 | 2027-05-19 | 2027-06-16 | 2027-06-23 |  |  | ALP-EPC-00GMA-IC-CNR-0001
ALP-EPC-00GMA-CM-MDB-0001 | Process Drains and Waste Water Collection - System Turnover Dossier |  | EPC | 00GMA | Process drains and waste water collection | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-03 | 2028-04-17 |  | 2028-04-24 |  |  | capacity commissioning
ALP-EPC-00GMA-CM-OMM-0001 | Process Drains and Waste Water Collection - Operating Procedures | English / Turkish | EPC | 00GMA | Process drains and waste water collection | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-05-19 | 2027-07-22 |  | 2027-08-19 |  |  | capacity commissioning
ALP-EPC-00GMA-IC-CNR-0001 | Process Drains and Waste Water Collection - Control Narrative |  | EPC | 00GMA | Process drains and waste water collection | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-03-31 | 2027-04-21 |  | 2027-05-19 |  |  | ALP-EPC-00GMA-PR-PID-0001
ALP-EPC-00GMA-IC-DSH-0001 | Process Drains and Waste Water Collection - Instrument Datasheets |  | EPC | 00GMA | Process drains and waste water collection | i_and_c | DSH | E | approval |  |  | 30 | 53 |  |  |  | MR-IC-004 |  | 2 | 2027-03-31 | 2027-04-28 | 2027-05-19 | 2027-05-26 |  |  | ALP-EPC-00GMA-PR-PID-0001
ALP-EPC-00GMA-IC-HMI-0001 | Process Drains and Waste Water Collection - Operator Displays | HMI graphics | EPC | 00GMA | Process drains and waste water collection | i_and_c | HMI | F | review |  |  | 3 | 44 | [5 empty] | 2 | 2027-04-21 | 2027-05-13 |  | 2027-06-03 |  |  | ALP-EPC-00GMA-IC-CNR-0001
ALP-EPC-00GMA-IC-LOG-0001 | Process Drains and Waste Water Collection - Logic Diagrams |  | EPC | 00GMA | Process drains and waste water collection | i_and_c | LOG | F | approval |  |  | 34 | 288 | [5 empty] | 3 | 2027-04-21 | 2027-06-16 | 2027-07-14 | 2027-07-21 |  |  | ALP-EPC-00GMA-IC-CNR-0001
ALP-EPC-00GMA-ME-CAL-0001 | Process Drains and Waste Water Collection - Sizing and Hydraulic Calculation |  | EPC | 00GMA | Process drains and waste water collection | mechanical | CAL | E | review |  |  | 6 | 78 | [5 empty] | 2 | 2027-01-11 | 2027-02-05 |  | 2027-02-26 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00GMA-ME-DSH-0004 | Process Drains and Waste Water Collection: Filter - Datasheet |  | EPC | 00GMA | Process drains and waste water collection | mechanical | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-ME-014 | 00GMA10AT001 | 3 | 2027-02-08 | 2027-03-05 | 2027-03-26 | 2027-04-02 |  |  | capacity mechanical
ALP-EPC-00GMA-ME-DSH-0005 | Process Drains and Waste Water Collection: Pumps - Datasheet | 6 items | EPC | 00GMA | Process drains and waste water collection | mechanical | DSH | E | approval |  |  | 6 | 66 |  |  |  | MR-ME-014 | 00GMA10AP001 00GMA10AP002 00GMA10AP003 00GMA10AP004 00GMA10AP005 00GMA10AP006 | 3 | 2027-02-12 | 2027-03-03 | 2027-03-24 | 2027-03-31 |  |  | capacity mechanical
ALP-EPC-00GMA-ME-DSH-0006 | Process Drains and Waste Water Collection: Tank - Datasheet |  | EPC | 00GMA | Process drains and waste water collection | mechanical | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-ME-014 | 00GMA10BB001 | 3 | 2027-02-22 | 2027-03-08 | 2027-03-29 | 2027-04-05 |  |  | capacity mechanical
ALP-EPC-00GMA-PI-ISO-0001 | Process Drains and Waste Water Collection - Isometric Drawings |  | EPC | 00GMA | Process drains and waste water collection | piping | ISO | L | information |  |  | 60 | 600 | EWP-12-PI-01 | CWP-12-PI-01 | CWA-12 |  |  | 3 | 2027-06-01 | 2027-07-27 |  | 2027-08-03 | 2027-07-12 | -16 | ALP-EPC-00000-PI-M3D-0002
ALP-EPC-00GMA-PI-PPL-0001 | Process Drains and Waste Water Collection - Underground Piping Drawings |  | EPC | 00GMA | Process drains and waste water collection | piping | PPL | L | review |  |  | 8 | 240 | EWP-12-PI-01 | CWP-12-PI-01 | CWA-12 |  |  | 2 | 2027-05-10 | 2027-06-25 |  | 2027-07-23 | 2027-07-12 | -9 | capacity piping
ALP-EPC-00GMA-PI-SUP-0001 | Process Drains and Waste Water Collection - Pipe Support Drawings |  | EPC | 00GMA | Process drains and waste water collection | piping | SUP | L | information |  |  | 15 | 90 | EWP-12-PI-01 | CWP-12-PI-01 | CWA-12 | MR-PI-005 |  | 1 | 2027-08-03 | 2027-09-08 |  | 2027-09-15 | 2027-07-12 | -47 | ALP-EPC-00GMA-PI-ISO-0001
ALP-EPC-00GMA-PR-PID-0001 | Process Drains and Waste Water Collection - P&ID |  | EPC | 00GMA | Process drains and waste water collection | process | PID | F | approval |  |  | 3 | 320 | [5 empty] | 3 | 2027-02-19 | 2027-03-31 | 2027-05-05 | 2027-05-12 |  |  | capacity process
ALP-EPC-00GMA-PR-SDS-0001 | Process Drains and Waste Water Collection - System Design Description |  | EPC | 00GMA | Process drains and waste water collection | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00GNA-CM-CMP-0001 | Waste Water Treatment - System Commissioning Procedure |  | EPC | 00GNA | Waste water treatment | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-04-21 | 2027-05-19 | 2027-06-16 | 2027-06-23 |  |  | ALP-EPC-00GNA-IC-CNR-0001
ALP-EPC-00GNA-CM-MDB-0001 | Waste Water Treatment - System Turnover Dossier |  | EPC | 00GNA | Waste water treatment | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-03 | 2028-04-17 |  | 2028-04-24 |  |  | capacity commissioning
ALP-EPC-00GNA-CM-OMM-0001 | Waste Water Treatment - Operating Procedures | English / Turkish | EPC | 00GNA | Waste water treatment | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-05-19 | 2027-07-23 |  | 2027-08-20 |  |  | capacity commissioning
ALP-EPC-00GNA-GE-RPT-0001 | Waste Water and Sanitary Treatment Packages - Technical Bid Evaluation |  | EPC | 00GNA | Waste water treatment | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-014 |  | 1 | 2027-01-07 | 2027-01-28 |  | 2027-02-04 |  |  | capacity general
ALP-EPC-00GNA-IC-CNR-0001 | Waste Water Treatment - Control Narrative |  | EPC | 00GNA | Waste water treatment | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-03-31 | 2027-04-21 |  | 2027-05-19 |  |  | ALP-EPC-00GNA-PR-PID-0001
ALP-EPC-00GNA-IC-DSH-0001 | Waste Water Treatment - Instrument Datasheets |  | EPC | 00GNA | Waste water treatment | i_and_c | DSH | E | approval |  |  | 40 | 68 |  |  |  | MR-IC-004 |  | 2 | 2027-03-31 | 2027-04-28 | 2027-05-19 | 2027-05-26 |  |  | ALP-EPC-00GNA-PR-PID-0001
ALP-EPC-00GNA-IC-DSH-0002 | Waste Water Treatment - Control Valve Sizing and Datasheets |  | EPC | 00GNA | Waste water treatment | i_and_c | DSH | E | approval |  |  | 3 | 26 |  |  |  | MR-IC-005 |  | 3 | 2027-03-31 | 2027-04-15 | 2027-05-06 | 2027-05-13 |  |  | ALP-EPC-00GNA-PR-PID-0001
ALP-EPC-00GNA-IC-HMI-0001 | Waste Water Treatment - Operator Displays | HMI graphics | EPC | 00GNA | Waste water treatment | i_and_c | HMI | F | review |  |  | 3 | 44 | [5 empty] | 2 | 2027-04-21 | 2027-05-13 |  | 2027-06-03 |  |  | ALP-EPC-00GNA-IC-CNR-0001
ALP-EPC-00GNA-ME-CAL-0001 | Waste Water Treatment - Sizing and Hydraulic Calculation |  | EPC | 00GNA | Waste water treatment | mechanical | CAL | E | review |  |  | 6 | 78 | [5 empty] | 2 | 2027-01-11 | 2027-02-05 |  | 2027-02-26 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00GNA-ME-DSH-0001 | Waste Water Treatment: Package - Datasheet |  | EPC | 00GNA | Waste water treatment | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-ME-014 | 00GNA10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00GNA-ME-DSH-0002 | Waste Water Treatment: Pumps - Datasheet | 6 items | EPC | 00GNA | Waste water treatment | mechanical | DSH | E | approval |  |  | 6 | 66 |  |  |  | MR-ME-014 | 00GNA10AP001 00GNA10AP002 00GNA10AP003 00GNA10AP004 00GNA10AP005 00GNA10AP006 | 3 | 2027-02-22 | 2027-03-10 | 2027-03-31 | 2027-04-07 |  |  | capacity mechanical
ALP-EPC-00GNA-ME-DSH-0003 | Waste Water Treatment: Tanks - Datasheet | 4 items | EPC | 00GNA | Waste water treatment | mechanical | DSH | E | approval |  |  | 4 | 46 |  |  |  | MR-ME-014 | 00GNA10BB001 00GNA10BB002 00GNA10BB003 00GNA10BB004 | 3 | 2027-02-22 | 2027-03-10 | 2027-03-31 | 2027-04-07 |  |  | capacity mechanical
ALP-EPC-00GNA-ME-ITP-0001 | Waste Water and Sanitary Treatment Packages - Inspection and Test Plan |  | EPC | 00GNA | Waste water treatment | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-014 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00GNA-ME-MRQ-0001 | Waste Water and Sanitary Treatment Packages - Material Requisition |  | EPC | 00GNA | Waste water treatment | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-014 |  | 9 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00GNA-ME-SPC-0001 | Waste Water and Sanitary Treatment Packages - Technical Specification |  | EPC | 00GNA | Waste water treatment | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-014 |  | 5 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00GNA-PI-ISO-0001 | Waste Water Treatment - Isometric Drawings |  | EPC | 00GNA | Waste water treatment | piping | ISO | L | information |  |  | 60 | 600 | EWP-07-PI-01 | CWP-07-PI-01 | CWA-07 |  |  | 3 | 2027-11-16 | 2028-01-11 |  | 2028-01-18 | 2028-01-24 | 4 | capacity piping
ALP-EPC-00GNA-PI-SUP-0001 | Waste Water Treatment - Pipe Support Drawings |  | EPC | 00GNA | Waste water treatment | piping | SUP | L | information |  |  | 15 | 90 | EWP-07-PI-01 | CWP-07-PI-01 | CWA-07 | MR-PI-005 |  | 1 | 2028-01-18 | 2028-02-23 |  | 2028-03-01 | 2028-01-24 | -27 | ALP-EPC-00GNA-PI-ISO-0001
ALP-EPC-00GNA-PR-PID-0001 | Waste Water Treatment - P&ID |  | EPC | 00GNA | Waste water treatment | process | PID | F | approval |  |  | 3 | 320 | [5 empty] | 3 | 2027-02-19 | 2027-03-31 | 2027-05-05 | 2027-05-12 |  |  | capacity process
ALP-EPC-00GNA-PR-SDS-0001 | Waste Water Treatment - System Design Description |  | EPC | 00GNA | Waste water treatment | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00GQA-CM-MDB-0001 | Storm Water Drainage - System Turnover Dossier |  | EPC | 00GQA | Storm water drainage | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2026-11-06 | 2026-12-21 |  | 2026-12-28 |  |  | capacity commissioning
ALP-EPC-00GUA-CM-CMP-0001 | Sanitary Waste Water Treatment - System Commissioning Procedure |  | EPC | 00GUA | Sanitary waste water treatment | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-07-05 | 2027-08-02 | 2027-08-30 | 2027-09-06 |  |  | ALP-EPC-00GUA-IC-CNR-0001
ALP-EPC-00GUA-CM-MDB-0001 | Sanitary Waste Water Treatment - System Turnover Dossier |  | EPC | 00GUA | Sanitary waste water treatment | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-03 | 2028-04-17 |  | 2028-04-24 |  |  | capacity commissioning
ALP-EPC-00GUA-CM-OMM-0001 | Sanitary Waste Water Treatment - Operating Procedures | English / Turkish | EPC | 00GUA | Sanitary waste water treatment | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-08-02 | 2027-09-13 |  | 2027-10-11 |  |  | ALP-EPC-00GUA-CM-CMP-0001
ALP-EPC-00GUA-IC-CNR-0001 | Sanitary Waste Water Treatment - Control Narrative |  | EPC | 00GUA | Sanitary waste water treatment | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-06-14 | 2027-07-05 |  | 2027-08-02 |  |  | ALP-EPC-00GUA-PR-PID-0001
ALP-EPC-00GUA-IC-DSH-0001 | Sanitary Waste Water Treatment - Instrument Datasheets |  | EPC | 00GUA | Sanitary waste water treatment | i_and_c | DSH | E | approval |  |  | 10 | 23 |  |  |  | MR-IC-004 |  | 2 | 2027-06-14 | 2027-07-02 | 2027-07-23 | 2027-07-30 |  |  | ALP-EPC-00GUA-PR-PID-0001
ALP-EPC-00GUA-IC-HMI-0001 | Sanitary Waste Water Treatment - Operator Displays | HMI graphics | EPC | 00GUA | Sanitary waste water treatment | i_and_c | HMI | F | review |  |  | 1 | 20 | [5 empty] | 2 | 2027-07-05 | 2027-07-26 |  | 2027-08-16 |  |  | ALP-EPC-00GUA-IC-CNR-0001
ALP-EPC-00GUA-ME-CAL-0001 | Sanitary Waste Water Treatment - Sizing and Hydraulic Calculation |  | EPC | 00GUA | Sanitary waste water treatment | mechanical | CAL | E | review |  |  | 2 | 46 | [5 empty] | 2 | 2027-01-11 | 2027-02-02 |  | 2027-02-23 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00GUA-ME-DSH-0001 | Sanitary Waste Water Treatment: Package - Datasheet |  | EPC | 00GUA | Sanitary waste water treatment | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-ME-014 | 00GUA10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00GUA-ME-DSH-0002 | Sanitary Waste Water Treatment: Pumps - Datasheet | 2 items | EPC | 00GUA | Sanitary waste water treatment | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-014 | 00GUA10AP001 00GUA10AP002 | 3 | 2027-02-22 | 2027-03-08 | 2027-03-29 | 2027-04-05 |  |  | capacity mechanical
ALP-EPC-00GUA-PI-ISO-0001 | Sanitary Waste Water Treatment - Isometric Drawings |  | EPC | 00GUA | Sanitary waste water treatment | piping | ISO | L | information |  |  | 20 | 200 | EWP-07-PI-01 | CWP-07-PI-01 | CWA-07 |  |  | 3 | 2027-12-06 | 2028-01-28 |  | 2028-02-04 | 2028-01-24 | -9 | capacity piping
ALP-EPC-00GUA-PI-SUP-0001 | Sanitary Waste Water Treatment - Pipe Support Drawings |  | EPC | 00GUA | Sanitary waste water treatment | piping | SUP | L | information |  |  | 5 | 30 | EWP-07-PI-01 | CWP-07-PI-01 | CWA-07 | MR-PI-005 |  | 1 | 2028-02-04 | 2028-03-01 |  | 2028-03-08 | 2028-01-24 | -32 | ALP-EPC-00GUA-PI-ISO-0001
ALP-EPC-00GUA-PR-PID-0001 | Sanitary Waste Water Treatment - P&ID |  | EPC | 00GUA | Sanitary waste water treatment | process | PID | F | approval |  |  | 1 | 120 | [5 empty] | 3 | 2027-05-10 | 2027-06-14 | 2027-07-19 | 2027-07-26 |  |  | capacity process
ALP-EPC-00GUA-PR-SDS-0001 | Sanitary Waste Water Treatment - System Design Description |  | EPC | 00GUA | Sanitary waste water treatment | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00LBG-CM-CMP-0001 | Auxiliary Steam - System Commissioning Procedure |  | EPC | 00LBG | Auxiliary steam | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-08-02 | 2027-08-30 | 2027-09-27 | 2027-10-04 |  |  | capacity commissioning
ALP-EPC-00LBG-CM-MDB-0001 | Auxiliary Steam - System Turnover Dossier |  | EPC | 00LBG | Auxiliary steam | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-05-22 | 2028-06-05 |  | 2028-06-12 |  |  | as late as possible (need)
ALP-EPC-00LBG-CM-OMM-0001 | Auxiliary Steam - Operating Procedures | English / Turkish | EPC | 00LBG | Auxiliary steam | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-09-01 | 2027-10-13 |  | 2027-11-10 |  |  | capacity commissioning
ALP-EPC-00LBG-IC-CEM-0001 | Auxiliary Steam - Cause and Effect Matrix |  | EPC | 00LBG | Auxiliary steam | i_and_c | CEM | F | approval |  |  | 1 | 28 | [5 empty] | 2 | 2027-09-07 | 2027-09-28 | 2027-10-26 | 2027-11-02 |  |  | capacity i_and_c
ALP-EPC-00LBG-IC-CNR-0001 | Auxiliary Steam - Control Narrative |  | EPC | 00LBG | Auxiliary steam | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-05-07 | 2027-05-28 |  | 2027-06-25 |  |  | ALP-EPC-00LBG-PR-PID-0001
ALP-EPC-00LBG-IC-DSH-0001 | Auxiliary Steam - Instrument Datasheets |  | EPC | 00LBG | Auxiliary steam | i_and_c | DSH | E | approval |  |  | 30 | 53 |  |  |  | MR-IC-004 |  | 2 | 2027-05-07 | 2027-06-04 | 2027-06-25 | 2027-07-02 |  |  | ALP-EPC-00LBG-PR-PID-0001
ALP-EPC-00LBG-IC-DSH-0002 | Auxiliary Steam - Control Valve Sizing and Datasheets |  | EPC | 00LBG | Auxiliary steam | i_and_c | DSH | E | approval |  |  | 4 | 32 |  |  |  | MR-IC-005 |  | 3 | 2027-05-07 | 2027-05-25 | 2027-06-15 | 2027-06-22 |  |  | ALP-EPC-00LBG-PR-PID-0001
ALP-EPC-00LBG-IC-HMI-0001 | Auxiliary Steam - Operator Displays | HMI graphics | EPC | 00LBG | Auxiliary steam | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-05-28 | 2027-06-21 |  | 2027-07-12 |  |  | ALP-EPC-00LBG-IC-CNR-0001
ALP-EPC-00LBG-IC-LOG-0001 | Auxiliary Steam - Logic Diagrams |  | EPC | 00LBG | Auxiliary steam | i_and_c | LOG | F | approval |  |  | 12 | 112 | [5 empty] | 3 | 2027-05-28 | 2027-07-13 | 2027-08-10 | 2027-08-17 |  |  | capacity i_and_c
ALP-EPC-00LBG-ME-CAL-0001 | Auxiliary Steam - Sizing and Hydraulic Calculation |  | EPC | 00LBG | Auxiliary steam | mechanical | CAL | E | review |  |  | 4 | 62 | [5 empty] | 2 | 2027-03-03 | 2027-03-26 |  | 2027-04-16 |  |  | capacity mechanical
ALP-EPC-00LBG-PI-ISO-0001 | Auxiliary Steam - Isometric Drawings |  | EPC | 00LBG | Auxiliary steam | piping | ISO | L | information |  |  | 80 | 800 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 |  |  | 6 | 2027-08-31 | 2027-10-26 |  | 2027-11-02 | 2027-12-13 | 29 | capacity piping
ALP-EPC-00LBG-PI-STR-0001 | Auxiliary Steam - Pipe Stress Analysis |  | EPC | 00LBG | Auxiliary steam | piping | STR | E | review |  |  | 3 | 200 | [5 empty] | 5 | 2027-07-19 | 2027-08-18 |  | 2027-09-08 |  |  | ALP-EPC-00UQA-PI-PPL-0003
ALP-EPC-00LBG-PI-SUP-0001 | Auxiliary Steam - Pipe Support Drawings |  | EPC | 00LBG | Auxiliary steam | piping | SUP | L | information |  |  | 20 | 120 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 | MR-PI-005 |  | 2 | 2027-12-08 | 2028-01-18 |  | 2028-01-25 | 2027-12-13 | -31 | capacity piping
ALP-EPC-00LBG-PR-DSH-0001 | Auxiliary Steam - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00LBG | Auxiliary steam | process | DSH | E | approval |  |  | 3 | 26 |  |  |  | MR-PI-007 |  | 2 | 2027-06-11 | 2027-06-28 | 2027-07-19 | 2027-07-26 |  |  | capacity process
ALP-EPC-00LBG-PR-PID-0001 | Auxiliary Steam - P&ID |  | EPC | 00LBG | Auxiliary steam | process | PID | F | approval |  |  | 2 | 220 | [5 empty] | 3 | 2027-03-31 | 2027-05-07 | 2027-06-11 | 2027-06-18 |  |  | capacity process
ALP-EPC-00LBG-PR-SDS-0001 | Auxiliary Steam - System Design Description |  | EPC | 00LBG | Auxiliary steam | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00LDA-CM-CMP-0001 | Condensate Polishing - System Commissioning Procedure |  | EPC | 00LDA | Condensate polishing | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-05-28 | 2027-06-25 | 2027-07-23 | 2027-07-30 |  |  | ALP-EPC-00LDA-IC-CNR-0001
ALP-EPC-00LDA-CM-MDB-0001 | Condensate Polishing - System Turnover Dossier |  | EPC | 00LDA | Condensate polishing | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-03 | 2028-04-17 |  | 2028-04-24 |  |  | capacity commissioning
ALP-EPC-00LDA-CM-OMM-0001 | Condensate Polishing - Operating Procedures | English / Turkish | EPC | 00LDA | Condensate polishing | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-06-25 | 2027-08-06 |  | 2027-09-03 |  |  | ALP-EPC-00LDA-CM-CMP-0001
ALP-EPC-00LDA-IC-CNR-0001 | Condensate Polishing - Control Narrative |  | EPC | 00LDA | Condensate polishing | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-05-07 | 2027-05-28 |  | 2027-06-25 |  |  | ALP-EPC-00LDA-PR-PID-0001
ALP-EPC-00LDA-IC-DSH-0001 | Condensate Polishing - Instrument Datasheets |  | EPC | 00LDA | Condensate polishing | i_and_c | DSH | E | approval |  |  | 40 | 68 |  |  |  | MR-IC-004 |  | 2 | 2027-05-07 | 2027-06-04 | 2027-06-25 | 2027-07-02 |  |  | ALP-EPC-00LDA-PR-PID-0001
ALP-EPC-00LDA-IC-DSH-0002 | Condensate Polishing - Control Valve Sizing and Datasheets |  | EPC | 00LDA | Condensate polishing | i_and_c | DSH | E | approval |  |  | 4 | 32 |  |  |  | MR-IC-005 |  | 3 | 2027-05-07 | 2027-05-25 | 2027-06-15 | 2027-06-22 |  |  | ALP-EPC-00LDA-PR-PID-0001
ALP-EPC-00LDA-IC-HMI-0001 | Condensate Polishing - Operator Displays | HMI graphics | EPC | 00LDA | Condensate polishing | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-05-28 | 2027-06-22 |  | 2027-07-13 |  |  | capacity i_and_c
ALP-EPC-00LDA-ME-CAL-0001 | Condensate Polishing - Sizing and Hydraulic Calculation |  | EPC | 00LDA | Condensate polishing | mechanical | CAL | E | review |  |  | 5 | 70 | [5 empty] | 2 | 2027-01-11 | 2027-02-04 |  | 2027-02-25 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00LDA-ME-DSH-0001 | Condensate Polishing: Package - Datasheet |  | EPC | 00LDA | Condensate polishing | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-ME-012 | 00LDA10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00LDA-ME-DSH-0002 | Condensate Polishing: Filters - Datasheet | 2 items | EPC | 00LDA | Condensate polishing | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-012 | 00LDA10AT001 00LDA10AT002 | 3 | 2027-02-08 | 2027-02-22 | 2027-03-15 | 2027-03-22 |  |  | ALP-EPC-00000-ME-DBR-0001
ALP-EPC-00LDA-ME-ITP-0001 | Water Treatment Package - Inspection and Test Plan | SWRO, demin, condensate polishing | EPC | 00LDA | Condensate polishing | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-012 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00LDA-ME-MRQ-0001 | Water Treatment Package - Material Requisition | SWRO, demin, condensate polishing | EPC | 00LDA | Condensate polishing | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-012 |  | 10 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00LDA-ME-SPC-0001 | Water Treatment Package - Technical Specification | SWRO, demin, condensate polishing | EPC | 00LDA | Condensate polishing | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-012 |  | 5 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00LDA-PI-ISO-0001 | Condensate Polishing - Isometric Drawings |  | EPC | 00LDA | Condensate polishing | piping | ISO | L | information |  |  | 60 | 600 | EWP-07-PI-01 | CWP-07-PI-01 | CWA-07 |  |  | 3 | 2027-11-17 | 2028-01-12 |  | 2028-01-19 | 2028-01-24 | 3 | capacity piping
ALP-EPC-00LDA-PI-SUP-0001 | Condensate Polishing - Pipe Support Drawings |  | EPC | 00LDA | Condensate polishing | piping | SUP | L | information |  |  | 15 | 90 | EWP-07-PI-01 | CWP-07-PI-01 | CWA-07 | MR-PI-005 |  | 1 | 2028-01-19 | 2028-02-24 |  | 2028-03-02 | 2028-01-24 | -28 | ALP-EPC-00LDA-PI-ISO-0001
ALP-EPC-00LDA-PR-DSH-0001 | Condensate Polishing - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00LDA | Condensate polishing | process | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-PI-007 |  | 2 | 2027-06-11 | 2027-06-25 | 2027-07-16 | 2027-07-23 |  |  | capacity process
ALP-EPC-00LDA-PR-PID-0001 | Condensate Polishing - P&ID |  | EPC | 00LDA | Condensate polishing | process | PID | F | approval |  |  | 2 | 220 | [5 empty] | 3 | 2027-04-01 | 2027-05-07 | 2027-06-11 | 2027-06-18 |  |  | capacity process
ALP-EPC-00LDA-PR-SDS-0001 | Condensate Polishing - System Design Description |  | EPC | 00LDA | Condensate polishing | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00PAA-CM-CMP-0001 | CW Intake, Screens and Outfall - System Commissioning Procedure |  | EPC | 00PAA | CW intake, screens and outfall | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-04-22 | 2027-05-20 | 2027-06-17 | 2027-06-24 |  |  | ALP-EPC-00PAA-IC-CNR-0001
ALP-EPC-00PAA-CM-MDB-0001 | CW Intake, Screens and Outfall - System Turnover Dossier |  | EPC | 00PAA | CW intake, screens and outfall | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-03 | 2028-04-17 |  | 2028-04-24 |  |  | capacity commissioning
ALP-EPC-00PAA-CM-OMM-0001 | CW Intake, Screens and Outfall - Operating Procedures | English / Turkish | EPC | 00PAA | CW intake, screens and outfall | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-05-20 | 2027-07-28 |  | 2027-08-25 |  |  | capacity commissioning
ALP-EPC-00PAA-GE-RPT-0001 | Travelling Band Screens and Trash Rakes - Technical Bid Evaluation |  | EPC | 00PAA | CW intake, screens and outfall | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-004 |  | 1 | 2027-01-12 | 2027-02-02 |  | 2027-02-09 |  |  | capacity general
ALP-EPC-00PAA-IC-CNR-0001 | CW Intake, Screens and Outfall - Control Narrative |  | EPC | 00PAA | CW intake, screens and outfall | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-04-01 | 2027-04-22 |  | 2027-05-20 |  |  | ALP-EPC-00PAA-PR-PID-0001
ALP-EPC-00PAA-IC-DSH-0001 | CW Intake, Screens and Outfall - Instrument Datasheets |  | EPC | 00PAA | CW intake, screens and outfall | i_and_c | DSH | E | approval |  |  | 40 | 68 |  |  |  | MR-IC-004 |  | 2 | 2027-04-01 | 2027-04-29 | 2027-05-20 | 2027-05-27 |  |  | ALP-EPC-00PAA-PR-PID-0001
ALP-EPC-00PAA-IC-HMI-0001 | CW Intake, Screens and Outfall - Operator Displays | HMI graphics | EPC | 00PAA | CW intake, screens and outfall | i_and_c | HMI | F | review |  |  | 3 | 44 | [5 empty] | 2 | 2027-04-22 | 2027-05-17 |  | 2027-06-07 |  |  | capacity i_and_c
ALP-EPC-00PAA-IC-LOG-0001 | CW Intake, Screens and Outfall - Logic Diagrams |  | EPC | 00PAA | CW intake, screens and outfall | i_and_c | LOG | F | approval |  |  | 46 | 384 | [5 empty] | 3 | 2027-04-22 | 2027-06-25 | 2027-07-23 | 2027-07-30 |  |  | capacity i_and_c
ALP-EPC-00PAA-ME-CAL-0001 | CW Intake, Screens and Outfall - Sizing and Hydraulic Calculation |  | EPC | 00PAA | CW intake, screens and outfall | mechanical | CAL | E | review |  |  | 2 | 46 | [5 empty] | 2 | 2027-01-15 | 2027-02-08 |  | 2027-03-01 |  |  | capacity mechanical
ALP-EPC-00PAA-ME-DSH-0001 | CW Intake, Screens and Outfall: Filters - Datasheet | 4 items | EPC | 00PAA | CW intake, screens and outfall | mechanical | DSH | E | approval |  | yes | 4 | 46 |  |  |  | MR-ME-004 | 00PAA10AT001 00PAA10AT002 00PAA10AT003 00PAA10AT004 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00PAA-ME-DSH-0002 | CW Intake, Screens and Outfall: Pumps - Datasheet | 2 items | EPC | 00PAA | CW intake, screens and outfall | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-004 | 00PAA10AP001 00PAA10AP002 | 3 | 2027-02-24 | 2027-03-10 | 2027-03-31 | 2027-04-07 |  |  | capacity mechanical
ALP-EPC-00PAA-ME-DSH-0003 | CW Intake, Screens and Outfall: Valves - Datasheet | 2 items | EPC | 00PAA | CW intake, screens and outfall | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-004 | 00PAA10AA001 00PAA10AA002 | 3 | 2027-02-24 | 2027-03-10 | 2027-03-31 | 2027-04-07 |  |  | capacity mechanical
ALP-EPC-00PAA-ME-ITP-0001 | Travelling Band Screens and Trash Rakes - Inspection and Test Plan |  | EPC | 00PAA | CW intake, screens and outfall | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-004 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00PAA-ME-MRQ-0001 | Travelling Band Screens and Trash Rakes - Material Requisition |  | EPC | 00PAA | CW intake, screens and outfall | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-004 |  | 4 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00PAA-ME-SPC-0001 | Travelling Band Screens and Trash Rakes - Technical Specification |  | EPC | 00PAA | CW intake, screens and outfall | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-004 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00PAA-PI-ISO-0001 | CW Intake, Screens and Outfall - Isometric Drawings |  | EPC | 00PAA | CW intake, screens and outfall | piping | ISO | L | information |  |  | 20 | 200 | EWP-05-PI-01 | CWP-05-PI-01 | CWA-05 |  |  | 3 | 2027-06-25 | 2027-08-19 |  | 2027-08-26 | 2027-09-20 | 17 | capacity piping
ALP-EPC-00PAA-PI-SUP-0001 | CW Intake, Screens and Outfall - Pipe Support Drawings |  | EPC | 00PAA | CW intake, screens and outfall | piping | SUP | L | information |  |  | 5 | 30 | EWP-05-PI-01 | CWP-05-PI-01 | CWA-05 | MR-PI-005 |  | 1 | 2027-08-26 | 2027-09-21 |  | 2027-09-28 | 2027-09-20 | -6 | ALP-EPC-00PAA-PI-ISO-0001
ALP-EPC-00PAA-PR-PID-0001 | CW Intake, Screens and Outfall - P&ID |  | EPC | 00PAA | CW intake, screens and outfall | process | PID | F | approval |  |  | 3 | 320 | [5 empty] | 3 | 2027-02-19 | 2027-04-01 | 2027-05-06 | 2027-05-13 |  |  | capacity process
ALP-EPC-00PAA-PR-SDS-0001 | CW Intake, Screens and Outfall - System Design Description |  | EPC | 00PAA | CW intake, screens and outfall | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00PAA-PR-STU-0001 | CW Intake Hydraulic Model Study and Pump Sump Model Test | ANSI/HI 9.8 | EPC | 00PAA | CW intake, screens and outfall | process | STU | D | review |  |  | 1 | 200 | [5 empty] | 1 | 2026-11-03 | 2026-12-10 |  | 2027-01-07 |  |  | capacity process
ALP-EPC-00PAB-CM-CMP-0001 | CW Piping - System Commissioning Procedure |  | EPC | 00PAB | CW piping | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-05-28 | 2027-06-25 | 2027-07-23 | 2027-07-30 |  |  | ALP-EPC-00PAB-IC-CNR-0001
ALP-EPC-00PAB-CM-MDB-0001 | CW Piping - System Turnover Dossier |  | EPC | 00PAB | CW piping | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-03 | 2028-04-17 |  | 2028-04-24 |  |  | capacity commissioning
ALP-EPC-00PAB-CM-OMM-0001 | CW Piping - Operating Procedures | English / Turkish | EPC | 00PAB | CW piping | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-06-25 | 2027-08-06 |  | 2027-09-03 |  |  | ALP-EPC-00PAB-CM-CMP-0001
ALP-EPC-00PAB-GE-RPT-0001 | GRP CW Pipes and Fittings - Technical Bid Evaluation |  | EPC | 00PAB | CW piping | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-PI-004 |  | 1 | 2026-12-10 | 2027-01-13 |  | 2027-01-20 |  |  | capacity general
ALP-EPC-00PAB-IC-CNR-0001 | CW Piping - Control Narrative |  | EPC | 00PAB | CW piping | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-05-07 | 2027-05-28 |  | 2027-06-25 |  |  | ALP-EPC-00PAB-PR-PID-0001
ALP-EPC-00PAB-IC-DSH-0001 | CW Piping - Instrument Datasheets |  | EPC | 00PAB | CW piping | i_and_c | DSH | E | approval |  |  | 20 | 38 |  |  |  | MR-IC-004 |  | 2 | 2027-05-11 | 2027-06-10 | 2027-07-01 | 2027-07-08 |  |  | capacity i_and_c
ALP-EPC-00PAB-IC-HMI-0001 | CW Piping - Operator Displays | HMI graphics | EPC | 00PAB | CW piping | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-05-28 | 2027-06-23 |  | 2027-07-14 |  |  | capacity i_and_c
ALP-EPC-00PAB-IC-LOG-0001 | CW Piping - Logic Diagrams |  | EPC | 00PAB | CW piping | i_and_c | LOG | F | approval |  |  | 18 | 160 | [5 empty] | 3 | 2027-05-28 | 2027-07-23 | 2027-08-20 | 2027-08-27 |  |  | capacity i_and_c
ALP-EPC-00PAB-ME-CAL-0001 | CW Piping - Sizing and Hydraulic Calculation |  | EPC | 00PAB | CW piping | mechanical | CAL | E | review |  |  | 2 | 46 | [5 empty] | 2 | 2027-01-11 | 2027-02-02 |  | 2027-02-23 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00PAB-ME-DSH-0001 | CW Piping: Valves - Datasheet | 2 items | EPC | 00PAB | CW piping | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-PI-004 | 00PAB10AA001 00PAB10AA002 | 3 | 2027-02-08 | 2027-02-22 | 2027-03-15 | 2027-03-22 |  |  | ALP-EPC-00000-ME-DBR-0001
ALP-EPC-00PAB-PI-ISO-0001 | CW Piping - Isometric Drawings |  | EPC | 00PAB | CW piping | piping | ISO | L | information |  |  | 40 | 400 | EWP-05-PI-01 | CWP-05-PI-01 | CWA-05 |  |  | 4 | 2027-06-24 | 2027-08-19 |  | 2027-08-26 | 2027-09-20 | 17 | capacity piping
ALP-EPC-00PAB-PI-PPL-0001 | CW Piping - Underground Piping Drawings |  | EPC | 00PAB | CW piping | piping | PPL | L | review |  |  | 2 | 60 | EWP-05-PI-01 | CWP-05-PI-01 | CWA-05 |  |  | 2 | 2027-05-11 | 2027-06-24 |  | 2027-07-22 | 2027-09-20 | 42 | capacity piping
ALP-EPC-00PAB-PI-STR-0001 | CW Piping - Pipe Stress Analysis |  | EPC | 00PAB | CW piping | piping | STR | E | review |  |  | 2 | 140 | [5 empty] | 2 | 2027-05-11 | 2027-06-09 |  | 2027-06-30 |  |  | ALP-EPC-00UPC-PI-PPL-0001
ALP-EPC-00PAB-PI-SUP-0001 | CW Piping - Pipe Support Drawings |  | EPC | 00PAB | CW piping | piping | SUP | L | information |  |  | 10 | 60 | EWP-05-PI-01 | CWP-05-PI-01 | CWA-05 | MR-PI-005 |  | 2 | 2027-08-26 | 2027-09-27 |  | 2027-10-04 | 2027-09-20 | -10 | ALP-EPC-00PAB-PI-ISO-0001
ALP-EPC-00PAB-PR-PID-0001 | CW Piping - P&ID |  | EPC | 00PAB | CW piping | process | PID | F | approval |  |  | 2 | 220 | [5 empty] | 3 | 2027-04-01 | 2027-05-07 | 2027-06-11 | 2027-06-18 |  |  | capacity process
ALP-EPC-00PAB-PR-SDS-0001 | CW Piping - System Design Description |  | EPC | 00PAB | CW piping | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00PAB-PR-STU-0001 | CW System Hydraulic Transient Analysis | surge / water hammer | EPC | 00PAB | CW piping | process | STU | D | review |  |  | 1 | 160 | [5 empty] | 2 | 2027-06-11 | 2027-07-16 |  | 2027-08-13 |  |  | capacity process
ALP-EPC-00PAC-CM-CMP-0001 | CW Pumps - System Commissioning Procedure |  | EPC | 00PAC | CW pumps | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-05-31 | 2027-06-28 | 2027-07-26 | 2027-08-02 |  |  | ALP-EPC-00PAC-IC-CNR-0001
ALP-EPC-00PAC-CM-MDB-0001 | CW Pumps - System Turnover Dossier |  | EPC | 00PAC | CW pumps | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-03 | 2028-04-17 |  | 2028-04-24 |  |  | capacity commissioning
ALP-EPC-00PAC-CM-OMM-0001 | CW Pumps - Operating Procedures | English / Turkish | EPC | 00PAC | CW pumps | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-06-28 | 2027-08-09 |  | 2027-09-06 |  |  | ALP-EPC-00PAC-CM-CMP-0001
ALP-EPC-00PAC-GE-RPT-0001 | CW Pumps - Technical Bid Evaluation |  | EPC | 00PAC | CW pumps | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-003 |  | 1 | 2026-12-17 | 2027-01-07 |  | 2027-01-14 |  |  | bids MR-ME-003
ALP-EPC-00PAC-IC-CNR-0001 | CW Pumps - Control Narrative |  | EPC | 00PAC | CW pumps | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-05-10 | 2027-05-31 |  | 2027-06-28 |  |  | ALP-EPC-00PAC-PR-PID-0001
ALP-EPC-00PAC-IC-DSH-0001 | CW Pumps - Instrument Datasheets |  | EPC | 00PAC | CW pumps | i_and_c | DSH | E | approval |  |  | 30 | 53 |  |  |  | MR-IC-004 |  | 2 | 2027-05-19 | 2027-06-22 | 2027-07-13 | 2027-07-20 |  |  | capacity i_and_c
ALP-EPC-00PAC-IC-HMI-0001 | CW Pumps - Operator Displays | HMI graphics | EPC | 00PAC | CW pumps | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-05-31 | 2027-06-28 |  | 2027-07-19 |  |  | capacity i_and_c
ALP-EPC-00PAC-IC-LOG-0001 | CW Pumps - Logic Diagrams |  | EPC | 00PAC | CW pumps | i_and_c | LOG | F | approval |  |  | 24 | 208 | [5 empty] | 3 | 2027-05-31 | 2027-09-17 | 2027-10-15 | 2027-10-22 |  |  | capacity i_and_c
ALP-EPC-00PAC-ME-CAL-0001 | CW Pumps - Sizing and Hydraulic Calculation |  | EPC | 00PAC | CW pumps | mechanical | CAL | E | review |  |  | 2 | 46 | [5 empty] | 2 | 2027-01-11 | 2027-02-02 |  | 2027-02-23 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00PAC-ME-DSH-0001 | CW Pumps - Datasheet | 2 items | EPC | 00PAC | CW pumps | mechanical | DSH | E | approval |  | yes | 2 | 26 |  |  |  | MR-ME-003 | 00PAC10AP001 00PAC10AP002 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00PAC-ME-ITP-0001 | CW Pumps - Inspection and Test Plan |  | EPC | 00PAC | CW pumps | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-003 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00PAC-ME-MRQ-0001 | CW Pumps - Material Requisition |  | EPC | 00PAC | CW pumps | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-003 |  | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00PAC-ME-SPC-0001 | CW Pumps - Technical Specification |  | EPC | 00PAC | CW pumps | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-003 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00PAC-PI-ISO-0001 | CW Pumps - Isometric Drawings |  | EPC | 00PAC | CW pumps | piping | ISO | L | information |  |  | 20 | 200 | EWP-05-PI-01 | CWP-05-PI-01 | CWA-05 |  |  | 3 | 2027-06-25 | 2027-08-19 |  | 2027-08-26 | 2027-09-20 | 17 | capacity piping
ALP-EPC-00PAC-PI-SUP-0001 | CW Pumps - Pipe Support Drawings |  | EPC | 00PAC | CW pumps | piping | SUP | L | information |  |  | 5 | 30 | EWP-05-PI-01 | CWP-05-PI-01 | CWA-05 | MR-PI-005 |  | 1 | 2027-08-26 | 2027-09-21 |  | 2027-09-28 | 2027-09-20 | -6 | ALP-EPC-00PAC-PI-ISO-0001
ALP-EPC-00PAC-PR-PID-0001 | CW Pumps - P&ID |  | EPC | 00PAC | CW pumps | process | PID | F | approval | yes |  | 2 | 220 | [5 empty] | 3 | 2027-04-01 | 2027-05-10 | 2027-06-21 | 2027-06-28 |  |  | capacity process
ALP-EPC-00PAC-PR-SDS-0001 | CW Pumps - System Design Description |  | EPC | 00PAC | CW pumps | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00PAH-CM-CMP-0001 | Condenser Tube Cleaning - System Commissioning Procedure |  | EPC | 00PAH | Condenser tube cleaning | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-05-31 | 2027-06-28 | 2027-07-26 | 2027-08-02 |  |  | ALP-EPC-00PAH-IC-CNR-0001
ALP-EPC-00PAH-CM-MDB-0001 | Condenser Tube Cleaning - System Turnover Dossier |  | EPC | 00PAH | Condenser tube cleaning | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-03 | 2028-04-17 |  | 2028-04-24 |  |  | capacity commissioning
ALP-EPC-00PAH-CM-OMM-0001 | Condenser Tube Cleaning - Operating Procedures | English / Turkish | EPC | 00PAH | Condenser tube cleaning | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-06-28 | 2027-08-09 |  | 2027-09-06 |  |  | ALP-EPC-00PAH-CM-CMP-0001
ALP-EPC-00PAH-GE-RPT-0001 | Condenser Tube Cleaning System - Technical Bid Evaluation |  | EPC | 00PAH | Condenser tube cleaning | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-006 |  | 1 | 2027-02-19 | 2027-03-12 |  | 2027-03-19 |  |  | capacity general
ALP-EPC-00PAH-IC-CNR-0001 | Condenser Tube Cleaning - Control Narrative |  | EPC | 00PAH | Condenser tube cleaning | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-05-10 | 2027-05-31 |  | 2027-06-28 |  |  | ALP-EPC-00PAH-PR-PID-0001
ALP-EPC-00PAH-IC-DSH-0001 | Condenser Tube Cleaning - Instrument Datasheets |  | EPC | 00PAH | Condenser tube cleaning | i_and_c | DSH | E | approval |  |  | 20 | 38 |  |  |  | MR-IC-004 |  | 2 | 2027-05-17 | 2027-06-16 | 2027-07-07 | 2027-07-14 |  |  | capacity i_and_c
ALP-EPC-00PAH-IC-HMI-0001 | Condenser Tube Cleaning - Operator Displays | HMI graphics | EPC | 00PAH | Condenser tube cleaning | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-05-31 | 2027-06-29 |  | 2027-07-20 |  |  | capacity i_and_c
ALP-EPC-00PAH-IC-LOG-0001 | Condenser Tube Cleaning - Logic Diagrams |  | EPC | 00PAH | Condenser tube cleaning | i_and_c | LOG | F | approval |  |  | 18 | 160 | [5 empty] | 3 | 2027-05-31 | 2027-09-27 | 2027-10-25 | 2027-11-01 |  |  | capacity i_and_c
ALP-EPC-00PAH-ME-CAL-0001 | Condenser Tube Cleaning - Sizing and Hydraulic Calculation |  | EPC | 00PAH | Condenser tube cleaning | mechanical | CAL | E | review |  |  | 3 | 54 | [5 empty] | 2 | 2027-02-04 | 2027-03-16 |  | 2027-04-06 |  |  | capacity mechanical
ALP-EPC-00PAH-ME-DSH-0001 | Condenser Tube Cleaning: Package - Datasheet |  | EPC | 00PAH | Condenser tube cleaning | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-ME-006 | 00PAH10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00PAH-ME-DSH-0002 | Condenser Tube Cleaning: Filters - Datasheet | 2 items | EPC | 00PAH | Condenser tube cleaning | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-006 | 00PAH10AT001 00PAH10AT002 | 3 | 2027-03-16 | 2027-03-30 | 2027-04-20 | 2027-04-27 |  |  | ALP-EPC-00PAH-ME-CAL-0001
ALP-EPC-00PAH-ME-DSH-0003 | Condenser Tube Cleaning: Pumps - Datasheet | 2 items | EPC | 00PAH | Condenser tube cleaning | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-006 | 00PAH10AP001 00PAH10AP002 | 3 | 2027-03-16 | 2027-03-30 | 2027-04-20 | 2027-04-27 |  |  | ALP-EPC-00PAH-ME-CAL-0001
ALP-EPC-00PAH-ME-ITP-0001 | Condenser Tube Cleaning System - Inspection and Test Plan |  | EPC | 00PAH | Condenser tube cleaning | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-006 |  | 1 | 2026-11-16 | 2026-11-30 | 2026-12-21 | 2026-12-28 |  |  | capacity mechanical
ALP-EPC-00PAH-ME-MRQ-0001 | Condenser Tube Cleaning System - Material Requisition |  | EPC | 00PAH | Condenser tube cleaning | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-006 |  | 4 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00PAH-ME-SPC-0001 | Condenser Tube Cleaning System - Technical Specification |  | EPC | 00PAH | Condenser tube cleaning | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-006 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00PAH-PI-ISO-0001 | Condenser Tube Cleaning - Isometric Drawings |  | EPC | 00PAH | Condenser tube cleaning | piping | ISO | L | information |  |  | 30 | 300 | EWP-02-PI-01 | CWP-02-PI-01 | CWA-02 |  |  | 3 | 2027-12-09 | 2028-02-07 |  | 2028-02-14 | 2028-01-31 | -10 | capacity piping
ALP-EPC-00PAH-PI-SUP-0001 | Condenser Tube Cleaning - Pipe Support Drawings |  | EPC | 00PAH | Condenser tube cleaning | piping | SUP | L | information |  |  | 8 | 48 | EWP-02-PI-01 | CWP-02-PI-01 | CWA-02 | MR-PI-005 |  | 1 | 2028-02-14 | 2028-03-13 |  | 2028-03-20 | 2028-01-31 | -35 | ALP-EPC-00PAH-PI-ISO-0001
ALP-EPC-00PAH-PR-PID-0001 | Condenser Tube Cleaning - P&ID |  | EPC | 00PAH | Condenser tube cleaning | process | PID | F | approval |  |  | 2 | 220 | [5 empty] | 3 | 2027-04-02 | 2027-05-10 | 2027-06-14 | 2027-06-21 |  |  | capacity process
ALP-EPC-00PAH-PR-SDS-0001 | Condenser Tube Cleaning - System Design Description |  | EPC | 00PAH | Condenser tube cleaning | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00PBA-CM-CMP-0001 | Electro-Chlorination - System Commissioning Procedure |  | EPC | 00PBA | Electro-chlorination | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-04-22 | 2027-05-20 | 2027-06-17 | 2027-06-24 |  |  | ALP-EPC-00PBA-IC-CNR-0001
ALP-EPC-00PBA-CM-MDB-0001 | Electro-Chlorination - System Turnover Dossier |  | EPC | 00PBA | Electro-chlorination | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-03 | 2028-04-17 |  | 2028-04-24 |  |  | capacity commissioning
ALP-EPC-00PBA-CM-OMM-0001 | Electro-Chlorination - Operating Procedures | English / Turkish | EPC | 00PBA | Electro-chlorination | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-05-20 | 2027-07-28 |  | 2027-08-25 |  |  | capacity commissioning
ALP-EPC-00PBA-GE-RPT-0001 | Electro-Chlorination Package - Technical Bid Evaluation |  | EPC | 00PBA | Electro-chlorination | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-005 |  | 1 | 2027-01-13 | 2027-02-03 |  | 2027-02-10 |  |  | capacity general
ALP-EPC-00PBA-IC-CNR-0001 | Electro-Chlorination - Control Narrative |  | EPC | 00PBA | Electro-chlorination | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-04-01 | 2027-04-22 |  | 2027-05-20 |  |  | ALP-EPC-00PBA-PR-PID-0001
ALP-EPC-00PBA-IC-DSH-0001 | Electro-Chlorination - Instrument Datasheets |  | EPC | 00PBA | Electro-chlorination | i_and_c | DSH | E | approval |  |  | 40 | 68 |  |  |  | MR-IC-004 |  | 2 | 2027-04-01 | 2027-04-29 | 2027-05-20 | 2027-05-27 |  |  | ALP-EPC-00PBA-PR-PID-0001
ALP-EPC-00PBA-IC-DSH-0002 | Electro-Chlorination - Control Valve Sizing and Datasheets |  | EPC | 00PBA | Electro-chlorination | i_and_c | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-IC-005 |  | 3 | 2027-04-01 | 2027-04-15 | 2027-05-06 | 2027-05-13 |  |  | ALP-EPC-00PBA-PR-PID-0001
ALP-EPC-00PBA-IC-HMI-0001 | Electro-Chlorination - Operator Displays | HMI graphics | EPC | 00PBA | Electro-chlorination | i_and_c | HMI | F | review |  |  | 3 | 44 | [5 empty] | 2 | 2027-04-22 | 2027-05-27 |  | 2027-06-17 |  |  | capacity i_and_c
ALP-EPC-00PBA-ME-CAL-0001 | Electro-Chlorination - Sizing and Hydraulic Calculation |  | EPC | 00PBA | Electro-chlorination | mechanical | CAL | E | review |  |  | 5 | 70 | [5 empty] | 2 | 2027-01-11 | 2027-02-04 |  | 2027-02-25 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00PBA-ME-DSH-0001 | Electro-Chlorination: Package - Datasheet |  | EPC | 00PBA | Electro-chlorination | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-ME-005 | 00PBA10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00PBA-ME-DSH-0002 | Electro-Chlorination: Fans - Datasheet | 2 items | EPC | 00PBA | Electro-chlorination | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-005 | 00PBA10AN001 00PBA10AN002 | 3 | 2027-02-24 | 2027-03-10 | 2027-03-31 | 2027-04-07 |  |  | capacity mechanical
ALP-EPC-00PBA-ME-DSH-0003 | Electro-Chlorination: Filters - Datasheet | 2 items | EPC | 00PBA | Electro-chlorination | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-005 | 00PBA10AT001 00PBA10AT002 | 3 | 2027-02-24 | 2027-03-10 | 2027-03-31 | 2027-04-07 |  |  | capacity mechanical
ALP-EPC-00PBA-ME-DSH-0004 | Electro-Chlorination: Pumps - Datasheet | 4 items | EPC | 00PBA | Electro-chlorination | mechanical | DSH | E | approval |  |  | 4 | 46 |  |  |  | MR-ME-005 | 00PBA10AP001 00PBA10AP002 00PBA10AP003 00PBA10AP004 | 3 | 2027-02-24 | 2027-03-12 | 2027-04-02 | 2027-04-09 |  |  | capacity mechanical
ALP-EPC-00PBA-ME-DSH-0005 | Electro-Chlorination: Tanks - Datasheet | 2 items | EPC | 00PBA | Electro-chlorination | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-005 | 00PBA10BB001 00PBA10BB002 | 3 | 2027-02-24 | 2027-03-10 | 2027-03-31 | 2027-04-07 |  |  | capacity mechanical
ALP-EPC-00PBA-ME-ITP-0001 | Electro-Chlorination Package - Inspection and Test Plan |  | EPC | 00PBA | Electro-chlorination | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-005 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00PBA-ME-MRQ-0001 | Electro-Chlorination Package - Material Requisition |  | EPC | 00PBA | Electro-chlorination | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-005 |  | 6 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00PBA-ME-SPC-0001 | Electro-Chlorination Package - Technical Specification |  | EPC | 00PBA | Electro-chlorination | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-005 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00PBA-PI-ISO-0001 | Electro-Chlorination - Isometric Drawings |  | EPC | 00PBA | Electro-chlorination | piping | ISO | L | information |  |  | 50 | 500 | EWP-05-PI-01 | CWP-05-PI-01 | CWA-05 |  |  | 3 | 2027-06-09 | 2027-08-18 |  | 2027-08-25 | 2027-09-20 | 18 | capacity piping
ALP-EPC-00PBA-PI-SUP-0001 | Electro-Chlorination - Pipe Support Drawings |  | EPC | 00PBA | Electro-chlorination | piping | SUP | L | information |  |  | 13 | 78 | EWP-05-PI-01 | CWP-05-PI-01 | CWA-05 | MR-PI-005 |  | 1 | 2027-08-25 | 2027-09-28 |  | 2027-10-05 | 2027-09-20 | -11 | ALP-EPC-00PBA-PI-ISO-0001
ALP-EPC-00PBA-PR-PID-0001 | Electro-Chlorination - P&ID |  | EPC | 00PBA | Electro-chlorination | process | PID | F | approval |  |  | 3 | 320 | [5 empty] | 3 | 2027-02-22 | 2027-04-01 | 2027-05-06 | 2027-05-13 |  |  | capacity process
ALP-EPC-00PBA-PR-SDS-0001 | Electro-Chlorination - System Design Description |  | EPC | 00PBA | Electro-chlorination | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00PGA-CM-CMP-0001 | Closed Cooling Water - System Commissioning Procedure |  | EPC | 00PGA | Closed cooling water | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-03-16 | 2027-04-13 | 2027-05-11 | 2027-05-18 |  |  | ALP-EPC-00PGA-IC-CNR-0001
ALP-EPC-00PGA-CM-MDB-0001 | Closed Cooling Water - System Turnover Dossier |  | EPC | 00PGA | Closed cooling water | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-03 | 2028-04-17 |  | 2028-04-24 |  |  | capacity commissioning
ALP-EPC-00PGA-CM-OMM-0001 | Closed Cooling Water - Operating Procedures | English / Turkish | EPC | 00PGA | Closed cooling water | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-04-13 | 2027-05-25 |  | 2027-06-22 |  |  | ALP-EPC-00PGA-CM-CMP-0001
ALP-EPC-00PGA-GE-RPT-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Technical Bid Evaluation |  | EPC | 00PGA | Closed cooling water | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-007 |  | 1 | 2027-01-14 | 2027-02-09 |  | 2027-02-16 |  |  | capacity general
ALP-EPC-00PGA-IC-CNR-0001 | Closed Cooling Water - Control Narrative |  | EPC | 00PGA | Closed cooling water | i_and_c | CNR | F | review |  |  | 2 | 90 | [5 empty] | 2 | 2027-02-22 | 2027-03-16 |  | 2027-04-13 |  |  | ALP-EPC-00PGA-PR-PID-0001
ALP-EPC-00PGA-IC-DSH-0001 | Closed Cooling Water - Instrument Datasheets |  | EPC | 00PGA | Closed cooling water | i_and_c | DSH | E | approval |  |  | 70 | 113 |  |  |  | MR-IC-004 |  | 2 | 2027-02-22 | 2027-03-24 | 2027-04-14 | 2027-04-21 |  |  | capacity i_and_c
ALP-EPC-00PGA-IC-DSH-0002 | Closed Cooling Water - Control Valve Sizing and Datasheets |  | EPC | 00PGA | Closed cooling water | i_and_c | DSH | E | approval |  |  | 6 | 44 |  |  |  | MR-IC-005 |  | 3 | 2027-02-26 | 2027-03-16 | 2027-04-06 | 2027-04-13 |  |  | capacity i_and_c
ALP-EPC-00PGA-IC-HMI-0001 | Closed Cooling Water - Operator Displays | HMI graphics | EPC | 00PGA | Closed cooling water | i_and_c | HMI | F | review |  |  | 4 | 56 | [5 empty] | 2 | 2027-03-16 | 2027-04-08 |  | 2027-04-29 |  |  | ALP-EPC-00PGA-IC-CNR-0001
ALP-EPC-00PGA-IC-LOG-0001 | Closed Cooling Water - Logic Diagrams |  | EPC | 00PGA | Closed cooling water | i_and_c | LOG | F | approval |  |  | 38 | 320 | [5 empty] | 3 | 2027-03-16 | 2027-05-27 | 2027-06-24 | 2027-07-01 |  |  | capacity i_and_c
ALP-EPC-00PGA-ME-CAL-0001 | Closed Cooling Water - Sizing and Hydraulic Calculation |  | EPC | 00PGA | Closed cooling water | mechanical | CAL | E | review |  |  | 12 | 126 | [5 empty] | 2 | 2027-01-11 | 2027-02-12 |  | 2027-03-05 |  |  | capacity mechanical
ALP-EPC-00PGA-ME-DSH-0001 | Closed Cooling Water: Heat Exchangers - Datasheet | 2 items | EPC | 00PGA | Closed cooling water | mechanical | DSH | E | approval |  | yes | 2 | 26 |  |  |  | MR-ME-007 | 00PGA10AC001 00PGA10AC002 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00PGA-ME-DSH-0002 | Closed Cooling Water: Pumps - Datasheet | 2 items | EPC | 00PGA | Closed cooling water | mechanical | DSH | E | approval |  | yes | 2 | 26 |  |  |  | MR-ME-007 | 00PGA10AP001 00PGA10AP002 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00PGA-ME-DSH-0003 | Closed Cooling Water: Tanks - Datasheet | 2 items | EPC | 00PGA | Closed cooling water | mechanical | DSH | E | approval |  | yes | 2 | 26 |  |  |  | MR-ME-007 | 00PGA10BB001 00PGA10BB002 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00PGA-ME-DSH-0004 | Closed Cooling Water: Filter - Datasheet |  | EPC | 00PGA | Closed cooling water | mechanical | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-ME-007 | 00PGA10AT001 | 3 | 2027-02-22 | 2027-03-08 | 2027-03-29 | 2027-04-05 |  |  | capacity mechanical
ALP-EPC-00PGA-ME-ITP-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Inspection and Test Plan |  | EPC | 00PGA | Closed cooling water | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-007 |  | 1 | 2026-11-03 | 2026-11-17 | 2026-12-08 | 2026-12-15 |  |  | capacity mechanical
ALP-EPC-00PGA-ME-MRQ-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Material Requisition |  | EPC | 00PGA | Closed cooling water | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-007 |  | 5 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00PGA-ME-SPC-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Technical Specification |  | EPC | 00PGA | Closed cooling water | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-007 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00PGA-PI-ISO-0001 | Closed Cooling Water - Isometric Drawings |  | EPC | 00PGA | Closed cooling water | piping | ISO | L | information |  |  | 150 | 1500 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 |  |  | 6 | 2027-08-17 | 2027-10-13 |  | 2027-10-20 | 2027-12-13 | 38 | capacity piping
ALP-EPC-00PGA-PI-STR-0001 | Closed Cooling Water - Pipe Stress Analysis |  | EPC | 00PGA | Closed cooling water | piping | STR | E | review |  |  | 2 | 140 | [5 empty] | 4 | 2027-07-19 | 2027-08-17 |  | 2027-09-07 |  |  | ALP-EPC-00UQA-PI-PPL-0003
ALP-EPC-00PGA-PI-SUP-0001 | Closed Cooling Water - Pipe Support Drawings |  | EPC | 00PGA | Closed cooling water | piping | SUP | L | information |  |  | 38 | 228 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 | MR-PI-005 |  | 2 | 2027-12-06 | 2028-01-18 |  | 2028-01-25 | 2027-12-13 | -31 | capacity piping
ALP-EPC-00PGA-PR-DSH-0001 | Closed Cooling Water - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00PGA | Closed cooling water | process | DSH | E | approval |  |  | 3 | 26 |  |  |  | MR-PI-007 |  | 2 | 2027-06-11 | 2027-06-28 | 2027-07-19 | 2027-07-26 |  |  | capacity process
ALP-EPC-00PGA-PR-PID-0001 | Closed Cooling Water - P&ID |  | EPC | 00PGA | Closed cooling water | process | PID | F | approval |  |  | 4 | 420 | [5 empty] | 3 | 2027-01-11 | 2027-02-22 | 2027-03-29 | 2027-04-05 |  |  | capacity process
ALP-EPC-00PGA-PR-SDS-0001 | Closed Cooling Water - System Design Description |  | EPC | 00PGA | Closed cooling water | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00QCA-CM-CMP-0001 | Chemical Dosing - System Commissioning Procedure |  | EPC | 00QCA | Chemical dosing | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-04-23 | 2027-05-21 | 2027-06-18 | 2027-06-25 |  |  | ALP-EPC-00QCA-IC-CNR-0001
ALP-EPC-00QCA-CM-MDB-0001 | Chemical Dosing - System Turnover Dossier |  | EPC | 00QCA | Chemical dosing | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-03 | 2028-04-17 |  | 2028-04-24 |  |  | capacity commissioning
ALP-EPC-00QCA-CM-OMM-0001 | Chemical Dosing - Operating Procedures | English / Turkish | EPC | 00QCA | Chemical dosing | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-05-21 | 2027-07-30 |  | 2027-08-27 |  |  | capacity commissioning
ALP-EPC-00QCA-GE-RPT-0001 | Chemical Dosing Skid - Technical Bid Evaluation |  | EPC | 00QCA | Chemical dosing | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-011 |  | 1 | 2027-05-07 | 2027-05-28 |  | 2027-06-04 |  |  | bids MR-ME-011
ALP-EPC-00QCA-IC-CEM-0001 | Chemical Dosing - Cause and Effect Matrix |  | EPC | 00QCA | Chemical dosing | i_and_c | CEM | F | approval |  |  | 3 | 52 | [5 empty] | 2 | 2027-09-07 | 2027-09-29 | 2027-10-27 | 2027-11-03 |  |  | capacity i_and_c
ALP-EPC-00QCA-IC-CNR-0001 | Chemical Dosing - Control Narrative |  | EPC | 00QCA | Chemical dosing | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-04-02 | 2027-04-23 |  | 2027-05-21 |  |  | ALP-EPC-00QCA-PR-PID-0001
ALP-EPC-00QCA-IC-DSH-0001 | Chemical Dosing - Instrument Datasheets |  | EPC | 00QCA | Chemical dosing | i_and_c | DSH | E | approval |  |  | 40 | 68 |  |  |  | MR-IC-004 |  | 2 | 2027-04-02 | 2027-05-03 | 2027-05-24 | 2027-05-31 |  |  | capacity i_and_c
ALP-EPC-00QCA-IC-HMI-0001 | Chemical Dosing - Operator Displays | HMI graphics | EPC | 00QCA | Chemical dosing | i_and_c | HMI | F | review |  |  | 3 | 44 | [5 empty] | 2 | 2027-04-23 | 2027-06-03 |  | 2027-06-24 |  |  | capacity i_and_c
ALP-EPC-00QCA-IC-LOG-0001 | Chemical Dosing - Logic Diagrams |  | EPC | 00QCA | Chemical dosing | i_and_c | LOG | F | approval |  |  | 37 | 312 | [5 empty] | 3 | 2027-04-23 | 2027-09-21 | 2027-10-19 | 2027-10-26 |  |  | capacity i_and_c
ALP-EPC-00QCA-ME-CAL-0001 | Chemical Dosing - Sizing and Hydraulic Calculation |  | EPC | 00QCA | Chemical dosing | mechanical | CAL | E | review |  |  | 6 | 78 | [5 empty] | 2 | 2027-02-04 | 2027-03-19 |  | 2027-04-09 |  |  | capacity mechanical
ALP-EPC-00QCA-ME-DSH-0001 | Chemical Dosing: Package - Datasheet |  | EPC | 00QCA | Chemical dosing | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-ME-011 | 00QCA10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00QCA-ME-DSH-0002 | Chemical Dosing: Pumps - Datasheet | 6 items | EPC | 00QCA | Chemical dosing | mechanical | DSH | E | approval |  |  | 6 | 66 |  |  |  | MR-ME-011 | 00QCA10AP001 00QCA10AP002 00QCA10AP003 00QCA10AP004 00QCA10AP005 00QCA10AP006 | 3 | 2027-03-19 | 2027-04-06 | 2027-04-27 | 2027-05-04 |  |  | ALP-EPC-00QCA-ME-CAL-0001
ALP-EPC-00QCA-ME-DSH-0003 | Chemical Dosing: Tanks - Datasheet | 3 items | EPC | 00QCA | Chemical dosing | mechanical | DSH | E | approval |  |  | 3 | 36 |  |  |  | MR-ME-011 | 00QCA10BB001 00QCA10BB002 00QCA10BB003 | 3 | 2027-03-19 | 2027-04-05 | 2027-04-26 | 2027-05-03 |  |  | ALP-EPC-00QCA-ME-CAL-0001
ALP-EPC-00QCA-ME-ITP-0001 | Chemical Dosing Skid - Inspection and Test Plan |  | EPC | 00QCA | Chemical dosing | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-011 |  | 1 | 2026-11-12 | 2026-11-26 | 2026-12-17 | 2026-12-24 |  |  | capacity mechanical
ALP-EPC-00QCA-ME-MRQ-0001 | Chemical Dosing Skid - Material Requisition |  | EPC | 00QCA | Chemical dosing | mechanical | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-ME-011 |  | 4 | 2027-04-06 | 2027-04-13 |  | 2027-04-16 |  |  | ALP-EPC-00QCA-ME-DSH-0002
ALP-EPC-00QCA-ME-SPC-0001 | Chemical Dosing Skid - Technical Specification |  | EPC | 00QCA | Chemical dosing | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-011 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00QCA-PI-ISO-0001 | Chemical Dosing - Isometric Drawings |  | EPC | 00QCA | Chemical dosing | piping | ISO | L | information |  |  | 60 | 600 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 |  |  | 5 | 2027-09-23 | 2027-11-23 |  | 2027-11-30 | 2027-12-13 | 9 | capacity piping
ALP-EPC-00QCA-PI-SUP-0001 | Chemical Dosing - Pipe Support Drawings |  | EPC | 00QCA | Chemical dosing | piping | SUP | L | information |  |  | 15 | 90 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 | MR-PI-005 |  | 1 | 2027-12-09 | 2028-01-14 |  | 2028-01-21 | 2027-12-13 | -29 | capacity piping
ALP-EPC-00QCA-PR-DSH-0001 | Chemical Dosing - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00QCA | Chemical dosing | process | DSH | E | approval |  |  | 6 | 44 |  |  |  | MR-PI-007 |  | 2 | 2027-06-11 | 2027-06-29 | 2027-07-20 | 2027-07-27 |  |  | capacity process
ALP-EPC-00QCA-PR-PID-0001 | Chemical Dosing - P&ID |  | EPC | 00QCA | Chemical dosing | process | PID | F | approval |  |  | 3 | 320 | [5 empty] | 3 | 2027-02-23 | 2027-04-02 | 2027-05-07 | 2027-05-14 |  |  | capacity process
ALP-EPC-00QCA-PR-SDS-0001 | Chemical Dosing - System Design Description |  | EPC | 00QCA | Chemical dosing | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00QEA-CM-CMP-0001 | Compressed Air - System Commissioning Procedure |  | EPC | 00QEA | Compressed air | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-04-23 | 2027-05-21 | 2027-06-18 | 2027-06-25 |  |  | ALP-EPC-00QEA-IC-CNR-0001
ALP-EPC-00QEA-CM-MDB-0001 | Compressed Air - System Turnover Dossier |  | EPC | 00QEA | Compressed air | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-03 | 2028-04-17 |  | 2028-04-24 |  |  | capacity commissioning
ALP-EPC-00QEA-CM-OMM-0001 | Compressed Air - Operating Procedures | English / Turkish | EPC | 00QEA | Compressed air | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-05-21 | 2027-07-30 |  | 2027-08-27 |  |  | capacity commissioning
ALP-EPC-00QEA-GE-RPT-0001 | Air Compressors and Dryers - Technical Bid Evaluation |  | EPC | 00QEA | Compressed air | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-008 |  | 1 | 2027-01-20 | 2027-02-15 |  | 2027-02-22 |  |  | capacity general
ALP-EPC-00QEA-IC-CEM-0001 | Compressed Air - Cause and Effect Matrix |  | EPC | 00QEA | Compressed air | i_and_c | CEM | F | approval |  |  | 2 | 40 | [5 empty] | 2 | 2027-09-07 | 2027-09-29 | 2027-10-27 | 2027-11-03 |  |  | capacity i_and_c
ALP-EPC-00QEA-IC-CNR-0001 | Compressed Air - Control Narrative |  | EPC | 00QEA | Compressed air | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-04-02 | 2027-04-23 |  | 2027-05-21 |  |  | ALP-EPC-00QEA-PR-PID-0001
ALP-EPC-00QEA-IC-DSH-0001 | Compressed Air - Instrument Datasheets |  | EPC | 00QEA | Compressed air | i_and_c | DSH | E | approval |  |  | 45 | 75.5 |  |  |  | MR-IC-004 |  | 2 | 2027-04-02 | 2027-06-04 | 2027-06-25 | 2027-07-02 |  |  | capacity i_and_c
ALP-EPC-00QEA-IC-DSH-0002 | Compressed Air - Control Valve Sizing and Datasheets |  | EPC | 00QEA | Compressed air | i_and_c | DSH | E | approval |  |  | 3 | 26 |  |  |  | MR-IC-005 |  | 3 | 2027-04-09 | 2027-04-28 | 2027-05-19 | 2027-05-26 |  |  | capacity i_and_c
ALP-EPC-00QEA-IC-HMI-0001 | Compressed Air - Operator Displays | HMI graphics | EPC | 00QEA | Compressed air | i_and_c | HMI | F | review |  |  | 3 | 44 | [5 empty] | 2 | 2027-04-28 | 2027-07-02 |  | 2027-07-23 |  |  | capacity i_and_c
ALP-EPC-00QEA-ME-CAL-0001 | Compressed Air - Sizing and Hydraulic Calculation |  | EPC | 00QEA | Compressed air | mechanical | CAL | E | review |  |  | 8 | 94 | [5 empty] | 2 | 2027-01-21 | 2027-02-18 |  | 2027-03-11 |  |  | capacity mechanical
ALP-EPC-00QEA-ME-DSH-0001 | Compressed Air: Compressors - Datasheet | 3 items | EPC | 00QEA | Compressed air | mechanical | DSH | E | approval |  | yes | 3 | 36 |  |  |  | MR-ME-008 | 00QEA10AN001 00QEA10AN002 00QEA10AN003 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00QEA-ME-DSH-0002 | Compressed Air: Filters - Datasheet | 3 items | EPC | 00QEA | Compressed air | mechanical | DSH | E | approval |  | yes | 3 | 36 |  |  |  | MR-ME-008 | 00QEA10AT001 00QEA10AT002 00QEA10AT003 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00QEA-ME-DSH-0003 | Compressed Air: Tanks - Datasheet | 2 items | EPC | 00QEA | Compressed air | mechanical | DSH | E | approval |  | yes | 2 | 26 |  |  |  | MR-ME-008 | 00QEA10BB001 00QEA10BB002 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00QEA-ME-ITP-0001 | Air Compressors and Dryers - Inspection and Test Plan |  | EPC | 00QEA | Compressed air | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-008 |  | 1 | 2026-11-04 | 2026-11-18 | 2026-12-09 | 2026-12-16 |  |  | capacity mechanical
ALP-EPC-00QEA-ME-MRQ-0001 | Air Compressors and Dryers - Material Requisition |  | EPC | 00QEA | Compressed air | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-008 |  | 4 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00QEA-ME-SPC-0001 | Air Compressors and Dryers - Technical Specification |  | EPC | 00QEA | Compressed air | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-008 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00QEA-PI-ISO-0001 | Compressed Air - Isometric Drawings |  | EPC | 00QEA | Compressed air | piping | ISO | L | information |  |  | 100 | 1000 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 |  |  | 5 | 2027-07-19 | 2027-10-06 |  | 2027-10-13 | 2027-12-13 | 43 | capacity piping
ALP-EPC-00QEA-PI-SUP-0001 | Compressed Air - Pipe Support Drawings |  | EPC | 00QEA | Compressed air | piping | SUP | L | information |  |  | 25 | 150 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 | MR-PI-005 |  | 1 | 2027-12-07 | 2028-01-18 |  | 2028-01-25 | 2027-12-13 | -31 | capacity piping
ALP-EPC-00QEA-PR-DSH-0001 | Compressed Air - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00QEA | Compressed air | process | DSH | E | approval |  |  | 6 | 44 |  |  |  | MR-PI-007 |  | 2 | 2027-06-14 | 2027-06-30 | 2027-07-21 | 2027-07-28 |  |  | capacity process
ALP-EPC-00QEA-PR-PID-0001 | Compressed Air - P&ID |  | EPC | 00QEA | Compressed air | process | PID | F | approval |  |  | 3 | 320 | [5 empty] | 3 | 2027-02-23 | 2027-04-02 | 2027-05-07 | 2027-05-14 |  |  | capacity process
ALP-EPC-00QEA-PR-SDS-0001 | Compressed Air - System Design Description |  | EPC | 00QEA | Compressed air | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00QHA-CM-CMP-0001 | Auxiliary Boiler - System Commissioning Procedure |  | EPC | 00QHA | Auxiliary boiler | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-04-26 | 2027-05-24 | 2027-06-21 | 2027-06-28 |  |  | ALP-EPC-00QHA-IC-CNR-0001
ALP-EPC-00QHA-CM-MDB-0001 | Auxiliary Boiler - System Turnover Dossier |  | EPC | 00QHA | Auxiliary boiler | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-03 | 2028-04-17 |  | 2028-04-24 |  |  | capacity commissioning
ALP-EPC-00QHA-CM-OMM-0001 | Auxiliary Boiler - Operating Procedures | English / Turkish | EPC | 00QHA | Auxiliary boiler | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-05-24 | 2027-08-02 |  | 2027-08-30 |  |  | capacity commissioning
ALP-EPC-00QHA-GE-RPT-0001 | Auxiliary Boiler - Technical Bid Evaluation |  | EPC | 00QHA | Auxiliary boiler | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-009 |  | 1 | 2026-12-17 | 2027-01-07 |  | 2027-01-14 |  |  | bids MR-ME-009
ALP-EPC-00QHA-IC-CEM-0001 | Auxiliary Boiler - Cause and Effect Matrix |  | EPC | 00QHA | Auxiliary boiler | i_and_c | CEM | F | approval |  |  | 3 | 52 | [5 empty] | 2 | 2027-09-07 | 2027-09-29 | 2027-10-27 | 2027-11-03 |  |  | capacity i_and_c
ALP-EPC-00QHA-IC-CNR-0001 | Auxiliary Boiler - Control Narrative |  | EPC | 00QHA | Auxiliary boiler | i_and_c | CNR | F | review |  |  | 2 | 90 | [5 empty] | 2 | 2027-04-02 | 2027-04-26 |  | 2027-05-24 |  |  | ALP-EPC-00QHA-PR-PID-0001
ALP-EPC-00QHA-IC-DSH-0001 | Auxiliary Boiler - Instrument Datasheets |  | EPC | 00QHA | Auxiliary boiler | i_and_c | DSH | E | approval |  |  | 60 | 98 |  |  |  | MR-IC-004 |  | 2 | 2027-04-14 | 2027-07-14 | 2027-08-04 | 2027-08-11 |  |  | capacity i_and_c
ALP-EPC-00QHA-IC-DSH-0002 | Auxiliary Boiler - Control Valve Sizing and Datasheets |  | EPC | 00QHA | Auxiliary boiler | i_and_c | DSH | E | approval |  |  | 6 | 44 |  |  |  | MR-IC-005 |  | 3 | 2027-04-15 | 2027-06-09 | 2027-06-30 | 2027-07-07 |  |  | capacity i_and_c
ALP-EPC-00QHA-IC-HMI-0001 | Auxiliary Boiler - Operator Displays | HMI graphics | EPC | 00QHA | Auxiliary boiler | i_and_c | HMI | F | review |  |  | 3 | 44 | [5 empty] | 2 | 2027-04-28 | 2027-07-27 |  | 2027-08-17 |  |  | capacity i_and_c
ALP-EPC-00QHA-ME-CAL-0001 | Auxiliary Boiler - Sizing and Hydraulic Calculation |  | EPC | 00QHA | Auxiliary boiler | mechanical | CAL | E | review |  |  | 6 | 78 | [5 empty] | 2 | 2027-01-11 | 2027-02-05 |  | 2027-02-26 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00QHA-ME-DSH-0001 | Auxiliary Boiler - Datasheet |  | EPC | 00QHA | Auxiliary boiler | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-ME-009 | 00QHA10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00QHA-ME-DSH-0002 | Auxiliary Boiler: Fan - Datasheet |  | EPC | 00QHA | Auxiliary boiler | mechanical | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-ME-009 | 00QHA10AN001 | 3 | 2027-02-08 | 2027-02-22 | 2027-03-15 | 2027-03-22 |  |  | ALP-EPC-00000-ME-DBR-0001
ALP-EPC-00QHA-ME-DSH-0003 | Auxiliary Boiler: Pumps - Datasheet | 2 items | EPC | 00QHA | Auxiliary boiler | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-009 | 00QHA10AP001 00QHA10AP002 | 3 | 2027-02-08 | 2027-02-22 | 2027-03-15 | 2027-03-22 |  |  | ALP-EPC-00000-ME-DBR-0001
ALP-EPC-00QHA-ME-DSH-0004 | Auxiliary Boiler: Tanks - Datasheet | 2 items | EPC | 00QHA | Auxiliary boiler | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-009 | 00QHA10BB001 00QHA10BB002 | 3 | 2027-02-08 | 2027-02-22 | 2027-03-15 | 2027-03-22 |  |  | ALP-EPC-00000-ME-DBR-0001
ALP-EPC-00QHA-ME-ITP-0001 | Auxiliary Boiler - Inspection and Test Plan |  | EPC | 00QHA | Auxiliary boiler | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-009 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00QHA-ME-MRQ-0001 | Auxiliary Boiler - Material Requisition |  | EPC | 00QHA | Auxiliary boiler | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-009 |  | 5 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00QHA-ME-SPC-0001 | Auxiliary Boiler - Technical Specification |  | EPC | 00QHA | Auxiliary boiler | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-009 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00QHA-PI-ISO-0001 | Auxiliary Boiler - Isometric Drawings |  | EPC | 00QHA | Auxiliary boiler | piping | ISO | L | information |  |  | 80 | 800 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 |  |  | 6 | 2027-08-31 | 2027-11-08 |  | 2027-11-15 | 2027-12-13 | 20 | capacity piping
ALP-EPC-00QHA-PI-STR-0001 | Auxiliary Boiler - Pipe Stress Analysis |  | EPC | 00QHA | Auxiliary boiler | piping | STR | E | review |  |  | 2 | 140 | [5 empty] | 4 | 2027-07-19 | 2027-08-17 |  | 2027-09-07 |  |  | ALP-EPC-00UQA-PI-PPL-0003
ALP-EPC-00QHA-PI-SUP-0001 | Auxiliary Boiler - Pipe Support Drawings |  | EPC | 00QHA | Auxiliary boiler | piping | SUP | L | information |  |  | 20 | 120 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 | MR-PI-005 |  | 2 | 2027-12-08 | 2028-01-18 |  | 2028-01-25 | 2027-12-13 | -31 | capacity piping
ALP-EPC-00QHA-PR-DSH-0001 | Auxiliary Boiler - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00QHA | Auxiliary boiler | process | DSH | E | approval |  |  | 4 | 32 |  |  |  | MR-PI-007 |  | 2 | 2027-06-14 | 2027-06-30 | 2027-07-21 | 2027-07-28 |  |  | capacity process
ALP-EPC-00QHA-PR-PID-0001 | Auxiliary Boiler - P&ID |  | EPC | 00QHA | Auxiliary boiler | process | PID | F | approval |  |  | 3 | 320 | [5 empty] | 3 | 2027-02-23 | 2027-04-02 | 2027-05-07 | 2027-05-14 |  |  | capacity process
ALP-EPC-00QHA-PR-SDS-0001 | Auxiliary Boiler - System Design Description |  | EPC | 00QHA | Auxiliary boiler | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00QJA-CM-CMP-0001 | Nitrogen Supply - System Commissioning Procedure |  | EPC | 00QJA | Nitrogen supply | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-05-31 | 2027-06-28 | 2027-07-26 | 2027-08-02 |  |  | ALP-EPC-00QJA-IC-CNR-0001
ALP-EPC-00QJA-CM-MDB-0001 | Nitrogen Supply - System Turnover Dossier |  | EPC | 00QJA | Nitrogen supply | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-03 | 2028-04-17 |  | 2028-04-24 |  |  | capacity commissioning
ALP-EPC-00QJA-CM-OMM-0001 | Nitrogen Supply - Operating Procedures | English / Turkish | EPC | 00QJA | Nitrogen supply | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-06-28 | 2027-08-10 |  | 2027-09-07 |  |  | capacity commissioning
ALP-EPC-00QJA-GE-RPT-0001 | Nitrogen, Hydrogen and CO2 Supply - Technical Bid Evaluation |  | EPC | 00QJA | Nitrogen supply | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-010 |  | 1 | 2027-05-13 | 2027-06-03 |  | 2027-06-10 |  |  | bids MR-ME-010
ALP-EPC-00QJA-IC-CEM-0001 | Nitrogen Supply - Cause and Effect Matrix |  | EPC | 00QJA | Nitrogen supply | i_and_c | CEM | F | approval |  |  | 1 | 28 | [5 empty] | 2 | 2027-09-07 | 2027-09-28 | 2027-10-26 | 2027-11-02 |  |  | capacity i_and_c
ALP-EPC-00QJA-IC-CNR-0001 | Nitrogen Supply - Control Narrative |  | EPC | 00QJA | Nitrogen supply | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-05-10 | 2027-05-31 |  | 2027-06-28 |  |  | ALP-EPC-00QJA-PR-PID-0001
ALP-EPC-00QJA-IC-DSH-0001 | Nitrogen Supply - Instrument Datasheets |  | EPC | 00QJA | Nitrogen supply | i_and_c | DSH | E | approval |  |  | 20 | 38 |  |  |  | MR-IC-004 |  | 2 | 2027-05-27 | 2027-09-09 | 2027-09-30 | 2027-10-07 |  |  | capacity i_and_c
ALP-EPC-00QJA-IC-DSH-0002 | Nitrogen Supply - Control Valve Sizing and Datasheets |  | EPC | 00QJA | Nitrogen supply | i_and_c | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-IC-005 |  | 3 | 2027-06-04 | 2027-07-27 | 2027-08-17 | 2027-08-24 |  |  | capacity i_and_c
ALP-EPC-00QJA-IC-HMI-0001 | Nitrogen Supply - Operator Displays | HMI graphics | EPC | 00QJA | Nitrogen supply | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-06-09 | 2027-09-20 |  | 2027-10-11 |  |  | capacity i_and_c
ALP-EPC-00QJA-IC-LOG-0001 | Nitrogen Supply - Logic Diagrams |  | EPC | 00QJA | Nitrogen supply | i_and_c | LOG | F | approval |  |  | 12 | 112 | [5 empty] | 3 | 2027-06-10 | 2027-10-13 | 2027-11-10 | 2027-11-17 |  |  | capacity i_and_c
ALP-EPC-00QJA-ME-CAL-0001 | Nitrogen Supply - Sizing and Hydraulic Calculation |  | EPC | 00QJA | Nitrogen supply | mechanical | CAL | E | review |  |  | 4 | 62 | [5 empty] | 2 | 2027-02-05 | 2027-03-22 |  | 2027-04-12 |  |  | capacity mechanical
ALP-EPC-00QJA-ME-DSH-0001 | Nitrogen Supply: Package - Datasheet |  | EPC | 00QJA | Nitrogen supply | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-ME-010 | 00QJA10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00QJA-ME-DSH-0002 | Nitrogen Supply: Tank - Datasheet |  | EPC | 00QJA | Nitrogen supply | mechanical | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-ME-010 | 00QJA10BB001 | 3 | 2027-03-22 | 2027-04-05 | 2027-04-26 | 2027-05-03 |  |  | ALP-EPC-00QJA-ME-CAL-0001
ALP-EPC-00QJA-ME-ITP-0001 | Nitrogen, Hydrogen and CO2 Supply - Inspection and Test Plan |  | EPC | 00QJA | Nitrogen supply | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-010 |  | 1 | 2026-11-16 | 2026-11-30 | 2026-12-21 | 2026-12-28 |  |  | capacity mechanical
ALP-EPC-00QJA-ME-MRQ-0001 | Nitrogen, Hydrogen and CO2 Supply - Material Requisition |  | EPC | 00QJA | Nitrogen supply | mechanical | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-ME-010 |  | 4 | 2027-04-05 | 2027-04-12 |  | 2027-04-15 |  |  | ALP-EPC-00QJA-ME-DSH-0002
ALP-EPC-00QJA-ME-SPC-0001 | Nitrogen, Hydrogen and CO2 Supply - Technical Specification |  | EPC | 00QJA | Nitrogen supply | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-010 |  | 4 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00QJA-PI-ISO-0001 | Nitrogen Supply - Isometric Drawings |  | EPC | 00QJA | Nitrogen supply | piping | ISO | L | information |  |  | 40 | 400 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 |  |  | 5 | 2027-10-11 | 2027-12-06 |  | 2027-12-13 | 2027-12-13 | 0 | capacity piping
ALP-EPC-00QJA-PI-SUP-0001 | Nitrogen Supply - Pipe Support Drawings |  | EPC | 00QJA | Nitrogen supply | piping | SUP | L | information |  |  | 10 | 60 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 | MR-PI-005 |  | 1 | 2027-12-13 | 2028-01-12 |  | 2028-01-19 | 2027-12-13 | -27 | ALP-EPC-00QJA-PI-ISO-0001
ALP-EPC-00QJA-PR-DSH-0001 | Nitrogen Supply - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00QJA | Nitrogen supply | process | DSH | E | approval |  |  | 3 | 26 |  |  |  | MR-PI-007 |  | 2 | 2027-06-14 | 2027-06-29 | 2027-07-20 | 2027-07-27 |  |  | capacity process
ALP-EPC-00QJA-PR-PID-0001 | Nitrogen Supply - P&ID |  | EPC | 00QJA | Nitrogen supply | process | PID | F | approval |  |  | 2 | 220 | [5 empty] | 3 | 2027-04-02 | 2027-05-10 | 2027-06-14 | 2027-06-21 |  |  | capacity process
ALP-EPC-00QJA-PR-SDS-0001 | Nitrogen Supply - System Design Description |  | EPC | 00QJA | Nitrogen supply | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00QJB-CM-CMP-0001 | Hydrogen and CO2 Supply - System Commissioning Procedure |  | EPC | 00QJB | Hydrogen and CO2 supply | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-05-31 | 2027-06-28 | 2027-07-26 | 2027-08-02 |  |  | ALP-EPC-00QJB-IC-CNR-0001
ALP-EPC-00QJB-CM-MDB-0001 | Hydrogen and CO2 Supply - System Turnover Dossier |  | EPC | 00QJB | Hydrogen and CO2 supply | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-17 | 2028-05-01 |  | 2028-05-08 |  |  | capacity commissioning
ALP-EPC-00QJB-CM-OMM-0001 | Hydrogen and CO2 Supply - Operating Procedures | English / Turkish | EPC | 00QJB | Hydrogen and CO2 supply | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-06-28 | 2027-08-26 |  | 2027-09-23 |  |  | capacity commissioning
ALP-EPC-00QJB-IC-CEM-0001 | Hydrogen and CO2 Supply - Cause and Effect Matrix |  | EPC | 00QJB | Hydrogen and CO2 supply | i_and_c | CEM | F | approval |  |  | 1 | 28 | [5 empty] | 2 | 2027-09-07 | 2027-09-28 | 2027-10-26 | 2027-11-02 |  |  | capacity i_and_c
ALP-EPC-00QJB-IC-CNR-0001 | Hydrogen and CO2 Supply - Control Narrative |  | EPC | 00QJB | Hydrogen and CO2 supply | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-05-10 | 2027-05-31 |  | 2027-06-28 |  |  | ALP-EPC-00QJB-PR-PID-0001
ALP-EPC-00QJB-IC-DSH-0001 | Hydrogen and CO2 Supply - Instrument Datasheets |  | EPC | 00QJB | Hydrogen and CO2 supply | i_and_c | DSH | E | approval |  |  | 20 | 38 |  |  |  | MR-IC-004 |  | 2 | 2027-06-09 | 2027-09-27 | 2027-10-18 | 2027-10-25 |  |  | capacity i_and_c
ALP-EPC-00QJB-IC-DSH-0002 | Hydrogen and CO2 Supply - Control Valve Sizing and Datasheets |  | EPC | 00QJB | Hydrogen and CO2 supply | i_and_c | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-IC-005 |  | 3 | 2027-07-05 | 2027-09-15 | 2027-10-06 | 2027-10-13 |  |  | capacity i_and_c
ALP-EPC-00QJB-IC-HMI-0001 | Hydrogen and CO2 Supply - Operator Displays | HMI graphics | EPC | 00QJB | Hydrogen and CO2 supply | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-07-05 | 2027-09-23 |  | 2027-10-14 |  |  | capacity i_and_c
ALP-EPC-00QJB-IC-LOG-0001 | Hydrogen and CO2 Supply - Logic Diagrams |  | EPC | 00QJB | Hydrogen and CO2 supply | i_and_c | LOG | F | approval |  |  | 9 | 88 | [5 empty] | 3 | 2027-07-05 | 2027-10-12 | 2027-11-09 | 2027-11-16 |  |  | capacity i_and_c
ALP-EPC-00QJB-ME-CAL-0001 | Hydrogen and CO2 Supply - Sizing and Hydraulic Calculation |  | EPC | 00QJB | Hydrogen and CO2 supply | mechanical | CAL | E | review |  |  | 3 | 54 | [5 empty] | 2 | 2027-02-05 | 2027-03-24 |  | 2027-04-14 |  |  | capacity mechanical
ALP-EPC-00QJB-ME-DSH-0001 | Hydrogen and CO2 Supply: Package - Datasheet |  | EPC | 00QJB | Hydrogen and CO2 supply | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-ME-010 | 00QJB10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00QJB-PI-ISO-0001 | Hydrogen and CO2 Supply - Isometric Drawings |  | EPC | 00QJB | Hydrogen and CO2 supply | piping | ISO | L | information |  |  | 30 | 300 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 |  |  | 3 | 2027-11-17 | 2028-01-14 |  | 2028-01-21 | 2027-12-13 | -29 | capacity piping
ALP-EPC-00QJB-PI-SUP-0001 | Hydrogen and CO2 Supply - Pipe Support Drawings |  | EPC | 00QJB | Hydrogen and CO2 supply | piping | SUP | L | information |  |  | 8 | 48 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 | MR-PI-005 |  | 1 | 2028-01-21 | 2028-02-18 |  | 2028-02-25 | 2027-12-13 | -54 | ALP-EPC-00QJB-PI-ISO-0001
ALP-EPC-00QJB-PR-DSH-0001 | Hydrogen and CO2 Supply - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00QJB | Hydrogen and CO2 supply | process | DSH | E | approval |  |  | 3 | 26 |  |  |  | MR-PI-007 |  | 2 | 2027-06-14 | 2027-06-29 | 2027-07-20 | 2027-07-27 |  |  | capacity process
ALP-EPC-00QJB-PR-PID-0001 | Hydrogen and CO2 Supply - P&ID |  | EPC | 00QJB | Hydrogen and CO2 supply | process | PID | F | approval |  |  | 2 | 220 | [5 empty] | 3 | 2027-04-02 | 2027-05-10 | 2027-06-14 | 2027-06-21 |  |  | capacity process
ALP-EPC-00QJB-PR-SDS-0001 | Hydrogen and CO2 Supply - System Design Description |  | EPC | 00QJB | Hydrogen and CO2 supply | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00QUA-CM-CMP-0001 | Sampling and SWAS - System Commissioning Procedure |  | EPC | 00QUA | Sampling and SWAS | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-06-02 | 2027-06-30 | 2027-07-28 | 2027-08-04 |  |  | ALP-EPC-00QUA-IC-CNR-0001
ALP-EPC-00QUA-CM-MDB-0001 | Sampling and SWAS - System Turnover Dossier |  | EPC | 00QUA | Sampling and SWAS | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-17 | 2028-05-01 |  | 2028-05-08 |  |  | capacity commissioning
ALP-EPC-00QUA-CM-OMM-0001 | Sampling and SWAS - Operating Procedures | English / Turkish | EPC | 00QUA | Sampling and SWAS | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-06-30 | 2027-09-01 |  | 2027-09-29 |  |  | capacity commissioning
ALP-EPC-00QUA-GE-RPT-0001 | Steam/Water Analysis System - Technical Bid Evaluation |  | EPC | 00QUA | Sampling and SWAS | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-IC-003 |  | 1 | 2027-02-22 | 2027-03-15 |  | 2027-03-22 |  |  | capacity general
ALP-EPC-00QUA-IC-CEM-0001 | Sampling and SWAS - Cause and Effect Matrix |  | EPC | 00QUA | Sampling and SWAS | i_and_c | CEM | F | approval |  |  | 2 | 40 | [5 empty] | 2 | 2027-09-07 | 2027-09-29 | 2027-10-27 | 2027-11-03 |  |  | capacity i_and_c
ALP-EPC-00QUA-IC-CNR-0001 | Sampling and SWAS - Control Narrative |  | EPC | 00QUA | Sampling and SWAS | i_and_c | CNR | F | review |  |  | 2 | 90 | [5 empty] | 2 | 2027-05-11 | 2027-06-02 |  | 2027-06-30 |  |  | ALP-EPC-00QUA-PR-PID-0001
ALP-EPC-00QUA-IC-DSH-0001 | Sampling and SWAS - Instrument Datasheets |  | EPC | 00QUA | Sampling and SWAS | i_and_c | DSH | E | approval |  |  | 60 | 98 |  |  |  | MR-IC-004 |  | 2 | 2027-07-05 | 2027-10-05 | 2027-10-26 | 2027-11-02 |  |  | capacity i_and_c
ALP-EPC-00QUA-IC-HMI-0001 | Sampling and SWAS - Operator Displays | HMI graphics | EPC | 00QUA | Sampling and SWAS | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-07-05 | 2027-09-28 |  | 2027-10-19 |  |  | capacity i_and_c
ALP-EPC-00QUA-IC-ITP-0001 | Steam/Water Analysis System - Inspection and Test Plan |  | EPC | 00QUA | Sampling and SWAS | i_and_c | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-IC-003 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00QUA-IC-LOG-0001 | Sampling and SWAS - Logic Diagrams |  | EPC | 00QUA | Sampling and SWAS | i_and_c | LOG | F | approval |  |  | 25 | 216 | [5 empty] | 3 | 2027-07-05 | 2027-11-09 | 2027-12-07 | 2027-12-14 |  |  | capacity i_and_c
ALP-EPC-00QUA-IC-MRQ-0001 | Steam/Water Analysis System - Material Requisition |  | EPC | 00QUA | Sampling and SWAS | i_and_c | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-IC-003 |  | 3 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00QUA-IC-SPC-0001 | Steam/Water Analysis System - Technical Specification |  | EPC | 00QUA | Sampling and SWAS | i_and_c | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-IC-003 |  | 2 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00QUA-ME-CAL-0001 | Sampling and SWAS - Sizing and Hydraulic Calculation |  | EPC | 00QUA | Sampling and SWAS | mechanical | CAL | E | review |  |  | 8 | 94 | [5 empty] | 2 | 2027-02-04 | 2027-03-23 |  | 2027-04-13 |  |  | capacity mechanical
ALP-EPC-00QUA-ME-DSH-0001 | Sampling and SWAS: Package - Datasheet |  | EPC | 00QUA | Sampling and SWAS | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-IC-003 | 00QUA10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00QUA-ME-DSH-0002 | Sampling and SWAS: Heat Exchanger - Datasheet |  | EPC | 00QUA | Sampling and SWAS | mechanical | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-IC-003 | 00QUA10AC001 | 3 | 2027-03-23 | 2027-04-06 | 2027-04-27 | 2027-05-04 |  |  | ALP-EPC-00QUA-ME-CAL-0001
ALP-EPC-00QUA-PI-ISO-0001 | Sampling and SWAS - Isometric Drawings |  | EPC | 00QUA | Sampling and SWAS | piping | ISO | L | information |  |  | 60 | 600 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 |  |  | 3 | 2027-10-26 | 2027-12-21 |  | 2027-12-28 | 2027-12-13 | -11 | capacity piping
ALP-EPC-00QUA-PI-SUP-0001 | Sampling and SWAS - Pipe Support Drawings |  | EPC | 00QUA | Sampling and SWAS | piping | SUP | L | information |  |  | 15 | 90 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 | MR-PI-005 |  | 1 | 2027-12-28 | 2028-02-02 |  | 2028-02-09 | 2027-12-13 | -42 | ALP-EPC-00QUA-PI-ISO-0001
ALP-EPC-00QUA-PR-PID-0001 | Sampling and SWAS - P&ID |  | EPC | 00QUA | Sampling and SWAS | process | PID | F | approval |  |  | 2 | 220 | [5 empty] | 3 | 2027-04-02 | 2027-05-11 | 2027-06-15 | 2027-06-22 |  |  | capacity process
ALP-EPC-00QUA-PR-SDS-0001 | Sampling and SWAS - System Design Description |  | EPC | 00QUA | Sampling and SWAS | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00SAA-CM-CMP-0001 | HVAC - System Commissioning Procedure |  | EPC | 00SAA | HVAC | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-03-24 | 2027-04-21 | 2027-05-19 | 2027-05-26 |  |  | ALP-EPC-00SAA-IC-CNR-0001
ALP-EPC-00SAA-CM-MDB-0001 | HVAC - System Turnover Dossier |  | EPC | 00SAA | HVAC | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-17 | 2028-05-01 |  | 2028-05-08 |  |  | capacity commissioning
ALP-EPC-00SAA-CM-OMM-0001 | HVAC - Operating Procedures | English / Turkish | EPC | 00SAA | HVAC | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-04-21 | 2027-08-17 |  | 2027-09-14 |  |  | capacity commissioning
ALP-EPC-00SAA-GE-RPT-0001 | HVAC Plant and Equipment - Technical Bid Evaluation |  | EPC | 00SAA | HVAC | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-HV-001 |  | 1 | 2027-01-07 | 2027-01-28 |  | 2027-02-04 |  |  | capacity general
ALP-EPC-00SAA-HV-CAL-0001 | HVAC - Sizing and Hydraulic Calculation |  | EPC | 00SAA | HVAC | hvac | CAL | E | review |  |  | 8 | 94 | [5 empty] | 2 | 2027-01-11 | 2027-02-08 |  | 2027-03-01 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00SAA-HV-DSH-0001 | HVAC: Package - Datasheet |  | EPC | 00SAA | HVAC | hvac | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-HV-001 | 00SAA10 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00SAA-HV-ITP-0001 | HVAC Plant and Equipment - Inspection and Test Plan |  | EPC | 00SAA | HVAC | hvac | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-HV-001 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00SAA-HV-MRQ-0001 | HVAC Plant and Equipment - Material Requisition |  | EPC | 00SAA | HVAC | hvac | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-HV-001 |  | 5 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00SAA-HV-PID-0001 | HVAC - P&ID |  | EPC | 00SAA | HVAC | hvac | PID | F | approval |  |  | 10 | 1020 | [5 empty] | 3 | 2027-01-11 | 2027-03-02 | 2027-04-06 | 2027-04-13 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00SAA-HV-SDS-0001 | HVAC - System Design Description |  | EPC | 00SAA | HVAC | hvac | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00SAA-HV-SPC-0001 | HVAC Plant and Equipment - Technical Specification |  | EPC | 00SAA | HVAC | hvac | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-HV-001 |  | 2 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00SAA-IC-CNR-0001 | HVAC - Control Narrative |  | EPC | 00SAA | HVAC | i_and_c | CNR | F | review |  |  | 3 | 120 | [5 empty] | 2 | 2027-03-02 | 2027-03-24 |  | 2027-04-21 |  |  | ALP-EPC-00SAA-HV-PID-0001
ALP-EPC-00SAA-IC-DSH-0001 | HVAC - Instrument Datasheets |  | EPC | 00SAA | HVAC | i_and_c | DSH | E | approval |  |  | 150 | 233 |  |  |  | MR-IC-004 |  | 2 | 2027-03-02 | 2027-03-31 | 2027-04-21 | 2027-04-28 |  |  | capacity i_and_c
ALP-EPC-00SAA-IC-DSH-0002 | HVAC - Control Valve Sizing and Datasheets |  | EPC | 00SAA | HVAC | i_and_c | DSH | E | approval |  |  | 10 | 68 |  |  |  | MR-IC-005 |  | 3 | 2027-03-09 | 2027-03-30 | 2027-04-20 | 2027-04-27 |  |  | capacity i_and_c
ALP-EPC-00SAA-IC-HMI-0001 | HVAC - Operator Displays | HMI graphics | EPC | 00SAA | HVAC | i_and_c | HMI | F | review |  |  | 10 | 128 | [5 empty] | 2 | 2027-03-24 | 2027-10-04 |  | 2027-10-25 |  |  | capacity i_and_c
ALP-EPC-00SAA-IC-LOG-0001 | HVAC - Logic Diagrams, Part 1 of 2 |  | EPC | 00SAA | HVAC | i_and_c | LOG | F | approval |  |  | 74 | 608 | [5 empty] | 3 | 2027-03-24 | 2027-11-02 | 2027-11-30 | 2027-12-07 |  |  | capacity i_and_c
ALP-EPC-00SAA-IC-LOG-0002 | HVAC - Logic Diagrams, Part 2 of 2 |  | EPC | 00SAA | HVAC | i_and_c | LOG | F | approval |  |  | 74 | 608 | [5 empty] | 3 | 2027-03-24 | 2027-11-09 | 2027-12-07 | 2027-12-14 |  |  | capacity i_and_c
ALP-EPC-00SAA-ME-DSH-0001 | HVAC: Compressors - Datasheet | 3 items | EPC | 00SAA | HVAC | mechanical | DSH | E | approval |  |  | 3 | 36 |  |  |  | MR-HV-001 | 00SAA10AN001 00SAA10AN002 00SAA10AN003 | 3 | 2027-02-08 | 2027-02-23 | 2027-03-16 | 2027-03-23 |  |  | ALP-EPC-00SAA-HV-CAL-0001
ALP-EPC-00SAA-ME-DSH-0002 | HVAC: Fans - Datasheet | 18 items | EPC | 00SAA | HVAC | mechanical | DSH | E | approval |  |  | 18 | 186 |  |  |  | MR-HV-001 | 00SAA11AN001 00SAA11AN002 00SAA11AN003 00SAA11AN004 00SAA11AN005 00SAA11AN006 00SAA11AN007 00SAA11AN008 00SAA12AN001 00SAA12AN002 00SAA12AN003 00SAA12AN004 00SAA13AN001 00SAA13AN002 00SAA13AN003 00SAA13AN004 00SAA14AN001 00SAA14AN002 | 3 | 2027-02-08 | 2027-03-04 | 2027-03-25 | 2027-04-01 |  |  | ALP-EPC-00SAA-HV-CAL-0001
ALP-EPC-00SAA-ME-DSH-0003 | HVAC: Pumps - Datasheet | 2 items | EPC | 00SAA | HVAC | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-HV-001 | 00SAA10AP001 00SAA10AP002 | 3 | 2027-02-10 | 2027-02-24 | 2027-03-17 | 2027-03-24 |  |  | capacity mechanical
ALP-EPC-00SAA-PI-ISO-0001 | HVAC - Isometric Drawings |  | EPC | 00SAA | HVAC | piping | ISO | L | information |  |  | 60 | 600 | EWP-03-HV-01 | CWP-03-HV-01 | CWA-03 |  |  | 2 | 2027-07-06 | 2027-08-31 |  | 2027-09-07 | 2027-10-11 | 24 | ALP-EPC-00UBA-PI-PPL-0001
ALP-EPC-00SAA-PI-SUP-0001 | HVAC - Pipe Support Drawings |  | EPC | 00SAA | HVAC | piping | SUP | L | information |  |  | 15 | 90 | EWP-03-HV-01 | CWP-03-HV-01 | CWA-03 | MR-PI-005 |  | 1 | 2027-09-07 | 2027-10-13 |  | 2027-10-20 | 2027-10-11 | -7 | ALP-EPC-00SAA-PI-ISO-0001
ALP-EPC-00SAA-PR-DSH-0001 | HVAC - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00SAA | HVAC | process | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-PI-007 |  | 2 | 2027-06-14 | 2027-06-28 | 2027-07-19 | 2027-07-26 |  |  | capacity process
ALP-EPC-00SGA-CM-CMP-0001 | Fire Water System - System Commissioning Procedure |  | EPC | 00SGA | Fire water system | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-03-17 | 2027-04-14 | 2027-05-12 | 2027-05-19 |  |  | ALP-EPC-00SGA-IC-CNR-0001
ALP-EPC-00SGA-CM-MDB-0001 | Fire Water System - System Turnover Dossier |  | EPC | 00SGA | Fire water system | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-17 | 2028-05-01 |  | 2028-05-08 |  |  | capacity commissioning
ALP-EPC-00SGA-CM-OMM-0001 | Fire Water System - Operating Procedures | English / Turkish | EPC | 00SGA | Fire water system | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-04-14 | 2027-08-16 |  | 2027-09-13 |  |  | capacity commissioning
ALP-EPC-00SGA-GE-RPT-0001 | Fire Pumps and Fire Protection Systems - Technical Bid Evaluation |  | EPC | 00SGA | Fire water system | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-020 |  | 1 | 2027-01-07 | 2027-01-28 |  | 2027-02-04 |  |  | capacity general
ALP-EPC-00SGA-IC-CEM-0001 | Fire Water System - Cause and Effect Matrix |  | EPC | 00SGA | Fire water system | i_and_c | CEM | F | approval |  |  | 3 | 52 | [5 empty] | 2 | 2027-09-24 | 2027-10-18 | 2027-11-15 | 2027-11-22 |  |  | capacity i_and_c
ALP-EPC-00SGA-IC-CNR-0001 | Fire Water System - Control Narrative |  | EPC | 00SGA | Fire water system | i_and_c | CNR | F | review |  |  | 2 | 90 | [5 empty] | 2 | 2027-02-23 | 2027-03-17 |  | 2027-04-14 |  |  | ALP-EPC-00SGA-PR-PID-0001
ALP-EPC-00SGA-IC-DSH-0001 | Fire Water System - Instrument Datasheets |  | EPC | 00SGA | Fire water system | i_and_c | DSH | E | approval |  |  | 60 | 98 |  |  |  | MR-IC-004 |  | 2 | 2027-03-01 | 2027-10-01 | 2027-10-22 | 2027-10-29 |  |  | capacity i_and_c
ALP-EPC-00SGA-IC-HMI-0001 | Fire Water System - Operator Displays | HMI graphics | EPC | 00SGA | Fire water system | i_and_c | HMI | F | review |  |  | 6 | 80 | [5 empty] | 2 | 2027-03-17 | 2027-10-13 |  | 2027-11-03 |  |  | capacity i_and_c
ALP-EPC-00SGA-IC-LOG-0001 | Fire Water System - Logic Diagrams |  | EPC | 00SGA | Fire water system | i_and_c | LOG | F | approval |  |  | 40 | 336 | [5 empty] | 3 | 2027-03-19 | 2027-11-17 | 2027-12-15 | 2027-12-22 |  |  | capacity i_and_c
ALP-EPC-00SGA-ME-CAL-0001 | Fire Water System - Sizing and Hydraulic Calculation |  | EPC | 00SGA | Fire water system | mechanical | CAL | E | review |  |  | 12 | 126 | [5 empty] | 2 | 2027-01-11 | 2027-02-11 |  | 2027-03-04 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00SGA-ME-DSH-0001 | Fire Water System: Pumps - Datasheet | 3 items | EPC | 00SGA | Fire water system | mechanical | DSH | E | approval |  | yes | 3 | 36 |  |  |  | MR-ME-020 | 00SGA10AP001 00SGA10AP002 00SGA10AP003 | 4 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00SGA-ME-DSH-0002 | Fire Water System: Tanks - Datasheet | 2 items | EPC | 00SGA | Fire water system | mechanical | DSH | E | approval |  | yes | 2 | 26 |  |  |  | MR-ME-017 | 00SGA10BB001 00SGA10BB002 | 4 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00SGA-ME-ITP-0001 | Fire Pumps and Fire Protection Systems - Inspection and Test Plan |  | EPC | 00SGA | Fire water system | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-020 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00SGA-ME-MRQ-0001 | Fire Pumps and Fire Protection Systems - Material Requisition |  | EPC | 00SGA | Fire water system | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-020 |  | 5 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00SGA-ME-SPC-0001 | Fire Pumps and Fire Protection Systems - Technical Specification |  | EPC | 00SGA | Fire water system | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-020 |  | 4 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00SGA-PI-ISO-0001 | Fire Water System - Isometric Drawings |  | EPC | 00SGA | Fire water system | piping | ISO | L | information |  |  | 150 | 1500 | EWP-12-PI-01 | CWP-12-PI-01 | CWA-08 |  |  | 6 | 2027-08-16 | 2027-10-11 |  | 2027-10-18 | 2027-07-12 | -70 | ALP-EPC-00SGA-PI-STR-0001
ALP-EPC-00SGA-PI-PPL-0001 | Fire Water System - Underground Piping Drawings |  | EPC | 00SGA | Fire water system | piping | PPL | L | review |  |  | 15 | 450 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 |  |  | 2 | 2027-06-25 | 2027-08-25 |  | 2027-09-22 | 2027-12-13 | 58 | capacity piping
ALP-EPC-00SGA-PI-STR-0001 | Fire Water System - Pipe Stress Analysis |  | EPC | 00SGA | Fire water system | piping | STR | E | review |  |  | 1 | 80 | [5 empty] | 4 | 2027-07-19 | 2027-08-16 |  | 2027-09-06 |  |  | ALP-EPC-00UQA-PI-PPL-0003
ALP-EPC-00SGA-PI-SUP-0001 | Fire Water System - Pipe Support Drawings |  | EPC | 00SGA | Fire water system | piping | SUP | L | information |  |  | 38 | 228 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 | MR-PI-005 |  | 2 | 2027-12-07 | 2028-01-18 |  | 2028-01-25 | 2027-12-13 | -31 | capacity piping
ALP-EPC-00SGA-PR-CAL-0001 | Fire Water Network Hydraulic Calculation |  | EPC | 00SGA | Fire water system | process | CAL | E | review |  |  | 1 | 80 | [5 empty] | 1 | 2027-06-14 | 2027-07-05 |  | 2027-07-26 |  |  | capacity process
ALP-EPC-00SGA-PR-DSH-0001 | Fire Water System - Safety / Relief Valve Sizing and Datasheets |  | EPC | 00SGA | Fire water system | process | DSH | E | approval |  |  | 4 | 32 |  |  |  | MR-PI-007 |  | 2 | 2027-06-14 | 2027-06-30 | 2027-07-21 | 2027-07-28 |  |  | capacity process
ALP-EPC-00SGA-PR-PID-0001 | Fire Water System - P&ID |  | EPC | 00SGA | Fire water system | process | PID | F | approval |  |  | 6 | 620 | [5 empty] | 3 | 2027-01-11 | 2027-02-23 | 2027-03-30 | 2027-04-06 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00SGA-PR-SDS-0001 | Fire Water System - System Design Description |  | EPC | 00SGA | Fire water system | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00SGC-CM-CMP-0001 | Deluge, Spray and Foam Systems - System Commissioning Procedure |  | EPC | 00SGC | Deluge, spray and foam systems | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-03-17 | 2027-04-14 | 2027-05-12 | 2027-05-19 |  |  | ALP-EPC-00SGC-IC-CNR-0001
ALP-EPC-00SGC-CM-MDB-0001 | Deluge, Spray and Foam Systems - System Turnover Dossier |  | EPC | 00SGC | Deluge, spray and foam systems | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-17 | 2028-05-01 |  | 2028-05-08 |  |  | capacity commissioning
ALP-EPC-00SGC-CM-OMM-0001 | Deluge, Spray and Foam Systems - Operating Procedures | English / Turkish | EPC | 00SGC | Deluge, spray and foam systems | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-04-14 | 2027-08-20 |  | 2027-09-17 |  |  | capacity commissioning
ALP-EPC-00SGC-IC-CEM-0001 | Deluge, Spray and Foam Systems - Cause and Effect Matrix |  | EPC | 00SGC | Deluge, spray and foam systems | i_and_c | CEM | F | approval |  |  | 3 | 52 | [5 empty] | 2 | 2027-09-29 | 2027-10-21 | 2027-11-18 | 2027-11-25 |  |  | capacity i_and_c
ALP-EPC-00SGC-IC-CNR-0001 | Deluge, Spray and Foam Systems - Control Narrative |  | EPC | 00SGC | Deluge, spray and foam systems | i_and_c | CNR | F | review |  |  | 2 | 90 | [5 empty] | 2 | 2027-02-23 | 2027-03-17 |  | 2027-04-14 |  |  | ALP-EPC-00SGC-PR-PID-0001
ALP-EPC-00SGC-IC-DSH-0001 | Deluge, Spray and Foam Systems - Instrument Datasheets |  | EPC | 00SGC | Deluge, spray and foam systems | i_and_c | DSH | E | approval |  |  | 80 | 128 |  |  |  | MR-IC-004 |  | 2 | 2027-03-01 | 2027-10-22 | 2027-11-12 | 2027-11-19 |  |  | capacity i_and_c
ALP-EPC-00SGC-IC-HMI-0001 | Deluge, Spray and Foam Systems - Operator Displays | HMI graphics | EPC | 00SGC | Deluge, spray and foam systems | i_and_c | HMI | F | review |  |  | 6 | 80 | [5 empty] | 2 | 2027-03-23 | 2027-10-25 |  | 2027-11-15 |  |  | capacity i_and_c
ALP-EPC-00SGC-IC-LOG-0001 | Deluge, Spray and Foam Systems - Logic Diagrams |  | EPC | 00SGC | Deluge, spray and foam systems | i_and_c | LOG | F | approval |  |  | 38 | 320 | [5 empty] | 3 | 2027-09-30 | 2027-11-25 | 2027-12-23 | 2027-12-30 |  |  | capacity i_and_c
ALP-EPC-00SGC-ME-CAL-0001 | Deluge, Spray and Foam Systems - Sizing and Hydraulic Calculation |  | EPC | 00SGC | Deluge, spray and foam systems | mechanical | CAL | E | review |  |  | 10 | 110 | [5 empty] | 2 | 2027-01-11 | 2027-02-10 |  | 2027-03-03 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00SGC-ME-DSH-0001 | Deluge, Spray and Foam Systems: Tank - Datasheet |  | EPC | 00SGC | Deluge, spray and foam systems | mechanical | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-ME-020 | 00SGC10BB001 | 3 | 2027-02-22 | 2027-03-08 | 2027-03-29 | 2027-04-05 |  |  | capacity mechanical
ALP-EPC-00SGC-ME-DSH-0002 | Deluge, Spray and Foam Systems: Valves - Datasheet | 10 items | EPC | 00SGC | Deluge, spray and foam systems | mechanical | DSH | E | approval |  |  | 10 | 106 |  |  |  | MR-ME-020 | 00SGC10AA001 00SGC10AA002 00SGC10AA003 00SGC10AA004 00SGC10AA005 00SGC10AA006 00SGC10AA007 00SGC10AA008 00SGC10AA009 00SGC10AA010 | 3 | 2027-02-11 | 2027-03-03 | 2027-03-24 | 2027-03-31 |  |  | capacity mechanical
ALP-EPC-00SGC-PI-ISO-0001 | Deluge, Spray and Foam Systems - Isometric Drawings |  | EPC | 00SGC | Deluge, spray and foam systems | piping | ISO | L | information |  |  | 100 | 1000 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 |  |  | 5 | 2027-08-19 | 2027-10-14 |  | 2027-10-21 | 2027-12-13 | 37 | capacity piping
ALP-EPC-00SGC-PI-SUP-0001 | Deluge, Spray and Foam Systems - Pipe Support Drawings |  | EPC | 00SGC | Deluge, spray and foam systems | piping | SUP | L | information |  |  | 25 | 150 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 | MR-PI-005 |  | 1 | 2027-12-07 | 2028-01-18 |  | 2028-01-25 | 2027-12-13 | -31 | capacity piping
ALP-EPC-00SGC-PR-PID-0001 | Deluge, Spray and Foam Systems - P&ID |  | EPC | 00SGC | Deluge, spray and foam systems | process | PID | F | approval |  |  | 6 | 620 | [5 empty] | 3 | 2027-01-11 | 2027-02-23 | 2027-03-30 | 2027-04-06 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-00SGC-PR-SDS-0001 | Deluge, Spray and Foam Systems - System Design Description |  | EPC | 00SGC | Deluge, spray and foam systems | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-00SGY-CM-CMP-0001 | Fire Detection and Alarm - System Commissioning Procedure |  | EPC | 00SGY | Fire detection and alarm | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2027-02-05 | 2027-03-05 | 2027-04-02 | 2027-04-09 |  |  | capacity commissioning
ALP-EPC-00SGY-CM-MDB-0001 | Fire Detection and Alarm - System Turnover Dossier |  | EPC | 00SGY | Fire detection and alarm | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-17 | 2028-05-01 |  | 2028-05-08 |  |  | capacity commissioning
ALP-EPC-00SGY-CM-OMM-0001 | Fire Detection and Alarm - Operating Procedures | English / Turkish | EPC | 00SGY | Fire detection and alarm | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-03-05 | 2027-04-16 |  | 2027-05-14 |  |  | ALP-EPC-00SGY-CM-CMP-0001
ALP-EPC-00SGY-GE-ITP-0001 | Fire Detection and Alarm System - Inspection and Test Plan |  | EPC | 00SGY | Fire detection and alarm | general | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-IC-006 |  | 1 | 2027-03-02 | 2027-03-23 | 2027-04-13 | 2027-04-20 |  |  | capacity general
ALP-EPC-00SGY-GE-MRQ-0001 | Fire Detection and Alarm System - Material Requisition |  | EPC | 00SGY | Fire detection and alarm | general | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-IC-006 |  | 2 | 2027-03-16 | 2027-03-23 |  | 2027-03-26 |  |  | ALP-EPC-00SGY-IC-DSH-0001
ALP-EPC-00SGY-GE-RPT-0001 | Fire Detection and Alarm System - Technical Bid Evaluation |  | EPC | 00SGY | Fire detection and alarm | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-IC-006 |  | 1 | 2027-05-07 | 2027-05-28 |  | 2027-06-04 |  |  | bids MR-IC-006
ALP-EPC-00SGY-GE-SPC-0001 | Fire Detection and Alarm System - Technical Specification |  | EPC | 00SGY | Fire detection and alarm | general | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-IC-006 |  | 3 | 2027-02-02 | 2027-03-02 | 2027-03-30 | 2027-04-06 |  |  | capacity general
ALP-EPC-00SGY-IC-BLK-0001 | Fire Detection and Alarm - System Architecture |  | EPC | 00SGY | Fire detection and alarm | i_and_c | BLK | F | approval |  |  | 1 | 40 | [5 empty] | 2 | 2027-01-04 | 2027-01-25 | 2027-02-22 | 2027-03-01 |  |  | ALP-EPC-00000-IC-RPT-0002
ALP-EPC-00SGY-IC-DSH-0001 | Fire Detection and Alarm: Control System - Datasheet |  | EPC | 00SGY | Fire detection and alarm | i_and_c | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-IC-006 | 00SGY10 | 2 | 2027-03-02 | 2027-03-16 | 2027-04-06 | 2027-04-13 |  |  | ALP-EPC-00SGY-GE-SPC-0001
ALP-EPC-00SGY-IC-LOG-0001 | Fire Detection and Alarm - Logic Diagrams |  | EPC | 00SGY | Fire detection and alarm | i_and_c | LOG | F | approval |  |  | 40 | 336 | [5 empty] | 1 | 2027-01-11 | 2027-10-15 | 2027-11-12 | 2027-11-19 |  |  | capacity i_and_c
ALP-EPC-00SMA-CM-CMP-0001 | Cranes and Hoists - System Commissioning Procedure |  | EPC | 00SMA | Cranes and hoists | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2027-02-08 | 2027-03-08 | 2027-04-05 | 2027-04-12 |  |  | capacity commissioning
ALP-EPC-00SMA-CM-MDB-0001 | Cranes and Hoists - System Turnover Dossier |  | EPC | 00SMA | Cranes and hoists | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-17 | 2028-05-01 |  | 2028-05-08 |  |  | capacity commissioning
ALP-EPC-00SMA-GE-RPT-0001 | EOT Cranes - Technical Bid Evaluation |  | EPC | 00SMA | Cranes and hoists | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-021 |  | 1 | 2026-12-17 | 2027-01-07 |  | 2027-01-14 |  |  | bids MR-ME-021
ALP-EPC-00SMA-IC-LOG-0001 | Cranes and Hoists - Logic Diagrams |  | EPC | 00SMA | Cranes and hoists | i_and_c | LOG | F | approval |  |  | 12 | 112 | [5 empty] | 1 | 2027-01-18 | 2027-10-08 | 2027-11-05 | 2027-11-12 |  |  | capacity i_and_c
ALP-EPC-00SMA-ME-DSH-0001 | Cranes and Hoists - Datasheet | 6 items | EPC | 00SMA | Cranes and hoists | mechanical | DSH | E | approval |  | yes | 6 | 66 |  |  |  | MR-ME-021 | 00SMA10 00SMA20 00SMA30 00SMA40 00SMA50 00SMA60 | 2 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00SMA-ME-ITP-0001 | EOT Cranes - Inspection and Test Plan |  | EPC | 00SMA | Cranes and hoists | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-021 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00SMA-ME-MRQ-0001 | EOT Cranes - Material Requisition |  | EPC | 00SMA | Cranes and hoists | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-021 |  | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00SMA-ME-SPC-0001 | EOT Cranes - Technical Specification |  | EPC | 00SMA | Cranes and hoists | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-021 |  | 2 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00UAC-CV-ARC-0001 | GIS Building - Architectural Drawings |  | EPC | 00UAC | GIS building | civil | ARC | L | approval |  |  | 8 | 280 | EWP-04-SS-01 | CWP-04-SS-01 | CWA-04 |  |  | 2 | 2026-12-14 | 2027-01-20 | 2027-02-17 | 2027-02-24 | 2027-05-31 | 68 | ALP-EPC-00000-HV-DBR-0001
ALP-EPC-00UAC-CV-CAL-0001 | GIS Building - Structural and Foundation Calculation |  | EPC | 00UAC | GIS building | civil | CAL | E | review |  |  | 1 | 80 | [5 empty] | 2 | 2027-01-18 | 2027-02-08 |  | 2027-03-01 |  |  | ALP-EPC-00000-CV-CAL-0001
ALP-EPC-00UAC-CV-EFD-0001 | GIS Building - Equipment Foundation Drawings |  | EPC | 00UAC | GIS building | civil | EFD | L | approval |  |  | 2 | 100 | EWP-04-CV-01 | CWP-04-CV-01 | CWA-04 |  |  | 2 | 2027-02-18 | 2027-03-12 | 2027-04-09 | 2027-04-16 | 2027-04-05 | -9 | ALP-EPC-00UAC-CV-FND-0001
ALP-EPC-00UAC-CV-FND-0001 | GIS Building - Foundation and Underground Drawings |  | EPC | 00UAC | GIS building | civil | FND | L | approval |  |  | 4 | 200 | EWP-04-CV-01 | CWP-04-CV-01 | CWA-04 |  |  | 3 | 2027-01-18 | 2027-02-18 | 2027-03-18 | 2027-03-25 | 2027-04-05 | 7 | ALP-EPC-00000-CV-CAL-0001
ALP-EPC-00UAC-CV-RBR-0001 | GIS Building - Reinforcement Drawings |  | EPC | 00UAC | GIS building | civil | RBR | L | review |  |  | 8 | 280 | EWP-04-CV-01 | CWP-04-CV-01 | CWA-04 |  |  | 1 | 2027-02-18 | 2027-03-18 |  | 2027-04-08 | 2027-04-05 | -3 | ALP-EPC-00UAC-CV-FND-0001
ALP-EPC-00UAC-EL-CBL-0001 | 380 kV GIS Switchyard - Cable Schedule and Routing |  | EPC | 00UAC | GIS building | electrical | CBL | M | information |  |  | 2 | 24 | EWP-04-EL-01 | CWP-04-EL-01 | CWA-04 |  |  | 3 | 2027-09-08 | 2027-09-30 |  | 2027-10-07 | 2028-01-04 | 63 | capacity electrical
ALP-EPC-00UAC-EL-ELY-0001 | 380 kV GIS Switchyard - Electrical Layouts | equipment, trays, earthing, lighting | EPC | 00UAC | GIS building | electrical | ELY | L | review |  |  | 4 | 120 | EWP-04-EL-01 | CWP-04-EL-01 | CWA-04 |  |  | 3 | 2027-04-06 | 2027-05-07 |  | 2027-06-04 | 2028-01-04 | 152 | capacity electrical
ALP-EPC-00UAC-EL-ELY-0002 | 380 kV GIS Switchyard - Cable Routing, Tray and Trench Layouts |  | EPC | 00UAC | GIS building | electrical | ELY | L | review |  |  | 1 | 25 | EWP-04-EL-01 | CWP-04-EL-01 | CWA-04 |  |  | 1 | 2027-06-10 | 2027-08-26 |  | 2027-09-23 | 2028-01-04 | 73 | capacity electrical
ALP-EPC-00UAC-EL-ELY-0003 | GIS Building - Earthing and Lightning Protection Layouts |  | EPC | 00UAC | GIS building | electrical | ELY | L | review |  |  | 2 | 40 | EWP-04-EL-01 | CWP-04-EL-01 | CWA-04 |  |  | 3 | 2027-02-18 | 2027-08-13 |  | 2027-09-10 | 2028-01-04 | 82 | capacity electrical
ALP-EPC-00UAC-HS-GAD-0001 | GIS Building - Fire Fighting, Escape Route and Safety Signage Layouts |  | EPC | 00UAC | GIS building | hse | GAD | L | approval |  |  | 2 | 24 | EWP-04-CV-01 | CWP-04-CV-01 | CWA-04 |  |  | 3 | 2027-01-20 | 2027-02-18 | 2027-03-18 | 2027-03-25 | 2027-04-05 | 7 | ALP-EPC-00UAC-CV-ARC-0001
ALP-EPC-00UAC-HV-GAD-0001 | GIS Building - Building Services | plumbing, HVAC ducting, fire fighting | EPC | 00UAC | GIS building | hvac | GAD | L | review |  |  | 8 | 200 | EWP-04-CV-01 | CWP-04-CV-01 | CWA-04 |  |  | 2 | 2027-01-20 | 2027-04-06 |  | 2027-05-04 | 2027-04-05 | -21 | capacity hvac
ALP-EPC-00UAC-IC-ELY-0001 | GIS Building - Fire Detection and Alarm Layouts |  | EPC | 00UAC | GIS building | i_and_c | ELY | L | review |  |  | 3 | 42 | EWP-04-EL-01 | CWP-04-EL-01 | CWA-04 | MR-IC-006 |  | 2 | 2027-01-20 | 2027-02-19 |  | 2027-03-19 | 2028-01-04 | 207 | ALP-EPC-00UAC-CV-ARC-0001
ALP-EPC-00UAC-IC-ELY-0002 | 380 kV GIS Switchyard - Instrument Location and I&C Cable Routing |  | EPC | 00UAC | GIS building | i_and_c | ELY | L | review |  |  | 1 | 16 | EWP-04-EL-01 | CWP-04-EL-01 | CWA-04 |  |  | 2 | 2027-07-06 | 2027-08-03 |  | 2027-08-31 | 2028-01-04 | 90 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UAC-IC-HUP-0001 | 380 kV GIS Switchyard - Instrument Hook-Up Drawings |  | EPC | 00UAC | GIS building | i_and_c | HUP | M | information |  |  | 2 | 16 | EWP-04-EL-01 | CWP-04-EL-01 | CWA-04 | MR-IC-010 |  | 2 | 2027-07-06 | 2027-07-20 |  | 2027-07-27 | 2028-01-04 | 115 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UAC-IC-LOP-0001 | 380 kV GIS Switchyard - Junction Box and Cabinet Interconnection Diagrams |  | EPC | 00UAC | GIS building | i_and_c | LOP | M | information |  |  | 4 | 10 | EWP-04-EL-01 | CWP-04-EL-01 | CWA-04 |  |  | 2 | 2027-08-03 | 2027-08-26 |  | 2027-09-02 | 2028-01-04 | 88 | ALP-EPC-00UAC-IC-ELY-0002
ALP-EPC-00UAC-IC-LOP-0002 | 380 kV GIS Switchyard - Loop and Connection Diagrams |  | EPC | 00UAC | GIS building | i_and_c | LOP | M | information |  |  | 30 | 45 | EWP-04-EL-01 | CWP-04-EL-01 | CWA-04 |  |  | 2 | 2027-07-27 | 2027-09-07 |  | 2027-09-14 | 2028-01-04 | 80 | ALP-EPC-00000-IC-IOL-0001
ALP-EPC-00UAC-PI-LAY-0001 | 380 kV GIS Switchyard - Equipment Layout |  | EPC | 00UAC | GIS building | piping | LAY | L | approval |  |  | 2 | 80 | EWP-04-CV-01 | CWP-04-CV-01 | CWA-04 |  |  | 1 | 2026-11-02 | 2026-12-01 | 2026-12-29 | 2027-01-05 | 2027-04-05 | 64
ALP-EPC-00UAC-SS-STL-0001 | GIS Building - Structural Drawings | concrete / steel | EPC | 00UAC | GIS building | structural | STL | L | approval |  |  | 4 | 140 | EWP-04-SS-01 | CWP-04-SS-01 | CWA-04 |  |  | 3 | 2027-02-08 | 2027-03-11 | 2027-04-08 | 2027-04-15 | 2027-05-31 | 32 | ALP-EPC-00UAC-CV-CAL-0001
ALP-EPC-00UAC-SS-STL-0002 | GIS Building - Steel Structure Drawings |  | EPC | 00UAC | GIS building | structural | STL | L | approval |  |  | 10 | 350 | EWP-04-SS-01 | CWP-04-SS-01 | CWA-04 |  |  | 3 | 2027-02-08 | 2027-03-19 | 2027-04-16 | 2027-04-23 | 2027-05-31 | 26 | ALP-EPC-00UAC-CV-CAL-0001
ALP-EPC-00UBA-CV-ARC-0001 | Electrical Building - Architectural Drawings |  | EPC | 00UBA | Electrical building | civil | ARC | L | approval |  |  | 12 | 420 | EWP-03-SS-01 | CWP-03-SS-01 | CWA-03 |  |  | 2 | 2026-12-14 | 2027-01-26 | 2027-02-23 | 2027-03-02 | 2027-05-24 | 59 | ALP-EPC-00000-HV-DBR-0001
ALP-EPC-00UBA-CV-CAL-0001 | Electrical Building - Structural and Foundation Calculation |  | EPC | 00UBA | Electrical building | civil | CAL | E | review |  |  | 1 | 80 | [5 empty] | 2 | 2027-02-02 | 2027-02-24 |  | 2027-03-17 |  |  | capacity civil
ALP-EPC-00UBA-CV-EFD-0001 | Electrical Building - Equipment Foundation Drawings |  | EPC | 00UBA | Electrical building | civil | EFD | L | approval |  |  | 2 | 100 | EWP-03-CV-01 | CWP-03-CV-01 | CWA-03 |  |  | 2 | 2027-02-22 | 2027-03-16 | 2027-04-13 | 2027-04-20 | 2027-03-29 | -16 | ALP-E06-00XJA-CV-CAL-0001
ALP-EPC-00UBA-CV-FND-0001 | Electrical Building - Foundation and Underground Drawings |  | EPC | 00UBA | Electrical building | civil | FND | L | approval |  |  | 4 | 200 | EWP-03-CV-01 | CWP-03-CV-01 | CWA-03 |  |  | 3 | 2027-01-18 | 2027-02-18 | 2027-03-18 | 2027-03-25 | 2027-03-29 | 2 | ALP-EPC-00000-CV-CAL-0001
ALP-EPC-00UBA-CV-RBR-0001 | Electrical Building - Reinforcement Drawings |  | EPC | 00UBA | Electrical building | civil | RBR | L | review |  |  | 10 | 350 | EWP-03-CV-01 | CWP-03-CV-01 | CWA-03 |  |  | 1 | 2027-02-18 | 2027-03-22 |  | 2027-04-12 | 2027-03-29 | -10 | ALP-EPC-00UBA-CV-FND-0001
ALP-EPC-00UBA-EL-CBL-0001 | Electrical Building and Emergency Power - Cable Schedule and Routing |  | EPC | 00UBA | Electrical building | electrical | CBL | M | information |  |  | 13 | 46 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 3 | 2027-03-16 | 2027-04-20 |  | 2027-04-27 | 2027-10-25 | 129 | capacity electrical
ALP-EPC-00UBA-EL-ELY-0001 | Electrical Building and Emergency Power - Electrical Layouts | equipment, trays, earthing, lighting | EPC | 00UBA | Electrical building | electrical | ELY | L | review |  |  | 7 | 210 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 3 | 2027-02-08 | 2027-03-16 |  | 2027-04-13 | 2027-10-25 | 139 | ALP-EPC-00000-EL-STU-0003
ALP-EPC-00UBA-EL-ELY-0002 | Electrical Building and Emergency Power - Cable Routing, Tray and Trench Layouts |  | EPC | 00UBA | Electrical building | electrical | ELY | L | review |  |  | 4 | 100 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-07-06 | 2027-08-06 |  | 2027-09-03 | 2027-10-25 | 36 | ALP-EPC-00UBA-PI-PPL-0001
ALP-EPC-00UBA-EL-ELY-0003 | Electrical Building - Earthing and Lightning Protection Layouts |  | EPC | 00UBA | Electrical building | electrical | ELY | L | review |  |  | 2 | 40 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 3 | 2027-02-18 | 2027-03-19 |  | 2027-04-16 | 2027-10-25 | 136 | ALP-EPC-00UBA-CV-FND-0001
ALP-EPC-00UBA-HS-GAD-0001 | Electrical Building - Fire Fighting, Escape Route and Safety Signage Layouts |  | EPC | 00UBA | Electrical building | hse | GAD | L | approval |  |  | 3 | 36 | EWP-03-CV-01 | CWP-03-CV-01 | CWA-03 |  |  | 3 | 2027-01-26 | 2027-02-25 | 2027-03-25 | 2027-04-01 | 2027-03-29 | -3 | ALP-EPC-00UBA-CV-ARC-0001
ALP-EPC-00UBA-HV-GAD-0001 | Electrical Building and Emergency Power - HVAC Layouts |  | EPC | 00UBA | Electrical building | hvac | GAD | L | review |  |  | 4 | 120 | EWP-03-HV-01 | CWP-03-HV-01 | CWA-03 |  |  | 2 | 2027-04-13 | 2027-05-14 |  | 2027-06-11 | 2027-10-11 | 86 | capacity hvac
ALP-EPC-00UBA-HV-GAD-0002 | Electrical Building - Building Services | plumbing, HVAC ducting, fire fighting | EPC | 00UBA | Electrical building | hvac | GAD | L | review |  |  | 16 | 400 | EWP-03-CV-01 | CWP-03-CV-01 | CWA-03 |  |  | 2 | 2027-01-26 | 2027-04-13 |  | 2027-05-11 | 2027-03-29 | -31 | capacity hvac
ALP-EPC-00UBA-IC-ELY-0001 | Electrical Building - Fire Detection and Alarm Layouts |  | EPC | 00UBA | Electrical building | i_and_c | ELY | L | review |  |  | 4 | 56 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 | MR-IC-006 |  | 2 | 2027-01-26 | 2027-02-26 |  | 2027-03-26 | 2027-10-25 | 151 | ALP-EPC-00UBA-CV-ARC-0001
ALP-EPC-00UBA-IC-ELY-0002 | Electrical Building and Emergency Power - Instrument Location and I&C Cable Routing |  | EPC | 00UBA | Electrical building | i_and_c | ELY | L | review |  |  | 5 | 80 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-07-06 | 2027-08-09 |  | 2027-09-06 | 2027-10-25 | 35 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UBA-IC-HUP-0001 | Electrical Building and Emergency Power - Instrument Hook-Up Drawings |  | EPC | 00UBA | Electrical building | i_and_c | HUP | M | information |  |  | 6 | 48 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 | MR-IC-010 |  | 2 | 2027-07-06 | 2027-07-22 |  | 2027-07-29 | 2027-10-25 | 62 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UBA-IC-LOP-0001 | Electrical Building and Emergency Power - Junction Box and Cabinet Interconnection Diagrams |  | EPC | 00UBA | Electrical building | i_and_c | LOP | M | information |  |  | 15 | 37.5 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-08-09 | 2027-09-14 |  | 2027-09-21 | 2027-10-25 | 24 | ALP-EPC-00UBA-IC-ELY-0002
ALP-EPC-00UBA-IC-LOP-0002 | Electrical Building and Emergency Power - Loop and Connection Diagrams |  | EPC | 00UBA | Electrical building | i_and_c | LOP | M | information |  |  | 127 | 190.5 | EWP-03-EL-01 | CWP-03-EL-01 | CWA-03 |  |  | 2 | 2027-07-27 | 2027-09-07 |  | 2027-09-14 | 2027-10-25 | 29 | ALP-EPC-00000-IC-IOL-0001
ALP-EPC-00UBA-PI-LAY-0001 | Electrical Building and Emergency Power - Equipment Layout |  | EPC | 00UBA | Electrical building | piping | LAY | L | approval |  |  | 8 | 320 | EWP-03-CV-01 | CWP-03-CV-01 | CWA-03 |  |  | 1 | 2026-11-02 | 2026-12-09 | 2027-01-06 | 2027-01-13 | 2027-03-29 | 53
ALP-EPC-00UBA-PI-PPL-0001 | Electrical Building and Emergency Power - Piping General Arrangement |  | EPC | 00UBA | Electrical building | piping | PPL | L | review |  |  | 14 | 1260 | EWP-03-HV-01 | CWP-03-HV-01 | CWA-03 |  |  | 3 | 2027-05-10 | 2027-07-06 |  | 2027-08-03 | 2027-10-11 | 49 | capacity piping
ALP-EPC-00UBA-SS-STL-0001 | Electrical Building - Structural Drawings | concrete / steel | EPC | 00UBA | Electrical building | structural | STL | L | approval |  |  | 6 | 210 | EWP-03-SS-01 | CWP-03-SS-01 | CWA-03 |  |  | 3 | 2027-02-24 | 2027-03-31 | 2027-04-28 | 2027-05-05 | 2027-05-24 | 13 | ALP-EPC-00UBA-CV-CAL-0001
ALP-EPC-00UBA-SS-STL-0002 | Electrical Building - Steel Structure Drawings |  | EPC | 00UBA | Electrical building | structural | STL | L | approval |  |  | 8 | 280 | EWP-03-SS-01 | CWP-03-SS-01 | CWA-03 |  |  | 3 | 2027-02-24 | 2027-04-02 | 2027-04-30 | 2027-05-07 | 2027-05-24 | 11 | ALP-EPC-00UBA-CV-CAL-0001
ALP-EPC-00UBF-CV-CAL-0001 | Transformer Bays - Structural and Foundation Calculation |  | EPC | 00UBF | Transformer bays | civil | CAL | E | review |  |  | 2 | 120 | [5 empty] | 4 | 2027-03-22 | 2027-04-13 |  | 2027-05-04 |  |  | capacity civil
ALP-EPC-00UBF-CV-EFD-0001 | Transformer Bays - Equipment Foundation Drawings |  | EPC | 00UBF | Transformer bays | civil | EFD | L | approval |  |  | 3 | 150 | EWP-01-CV-02 | CWP-01-CV-02 | CWA-01 |  |  | 5 | 2027-04-06 | 2027-04-28 | 2027-05-26 | 2027-06-02 | 2027-04-19 | -32 | ALP-EPC-00UBF-CV-FND-0001
ALP-EPC-00UBF-CV-FND-0001 | Transformer Bays - Foundation and Underground Drawings |  | EPC | 00UBF | Transformer bays | civil | FND | L | approval |  |  | 6 | 300 | EWP-01-CV-02 | CWP-01-CV-02 | CWA-01 |  |  | 7 | 2027-03-02 | 2027-04-06 | 2027-05-04 | 2027-05-11 | 2027-04-19 | -16 | ALP-EPC-00UBF-CV-FND-0002
ALP-EPC-00UBF-CV-FND-0002 | Transformer Bays - Piling Layout and Pile Schedule |  | EPC | 00UBF | Transformer bays | civil | FND | L | approval |  |  | 2 | 80 | EWP-01-CV-01 | CWP-01-CV-01 | CWA-01 |  |  | 3 | 2027-02-01 | 2027-03-02 | 2027-03-30 | 2027-04-06 | 2027-03-22 | -11 | ALP-EPC-00000-CV-SPC-0002
ALP-EPC-00UBF-CV-RBR-0001 | Transformer Bays - Reinforcement Drawings |  | EPC | 00UBF | Transformer bays | civil | RBR | L | review |  |  | 10 | 350 | EWP-01-CV-02 | CWP-01-CV-02 | CWA-01 |  |  | 1 | 2027-04-06 | 2027-05-06 |  | 2027-05-27 | 2027-04-19 | -28 | ALP-EPC-00UBF-CV-FND-0001
ALP-EPC-00UBF-EL-ELY-0001 | Transformer Bays - Earthing and Lightning Protection Layouts |  | EPC | 00UBF | Transformer bays | electrical | ELY | L | review |  |  | 2 | 40 | EWP-01-EL-01 | CWP-01-EL-01 | CWA-01 |  |  | 3 | 2027-08-12 | 2027-09-27 |  | 2027-10-25 | 2028-01-10 | 55 | capacity electrical
ALP-EPC-00UBF-SS-STL-0001 | Transformer Bays - Steel Structure Drawings |  | EPC | 00UBF | Transformer bays | structural | STL | L | approval |  |  | 2 | 70 | EWP-01-SS-01 | CWP-01-SS-01 | CWA-01 |  |  | 3 | 2027-04-13 | 2027-05-12 | 2027-06-09 | 2027-06-16 | 2027-07-12 | 18 | ALP-EPC-00UBF-CV-CAL-0001
ALP-EPC-00UCA-CV-ARC-0001 | Control Building - Architectural Drawings |  | EPC | 00UCA | Control building | civil | ARC | L | approval |  |  | 16 | 560 | EWP-11-SS-01 | CWP-11-SS-01 | CWA-11 |  |  | 2 | 2026-12-15 | 2027-02-02 | 2027-03-02 | 2027-03-09 | 2027-05-24 | 54 | ALP-EPC-00UCA-PI-LAY-0001
ALP-EPC-00UCA-CV-CAL-0001 | Control Building - Structural and Foundation Calculation |  | EPC | 00UCA | Control building | civil | CAL | E | review |  |  | 1 | 80 | [5 empty] | 2 | 2027-03-16 | 2027-04-06 |  | 2027-04-27 |  |  | capacity civil
ALP-EPC-00UCA-CV-FND-0001 | Control Building - Foundation and Underground Drawings |  | EPC | 00UCA | Control building | civil | FND | L | approval |  |  | 3 | 150 | EWP-11-CV-01 | CWP-11-CV-01 | CWA-11 |  |  | 3 | 2027-01-18 | 2027-02-17 | 2027-03-17 | 2027-03-24 | 2027-03-29 | 3 | ALP-EPC-00000-CV-CAL-0001
ALP-EPC-00UCA-CV-RBR-0001 | Control Building - Reinforcement Drawings |  | EPC | 00UCA | Control building | civil | RBR | L | review |  |  | 8 | 280 | EWP-11-CV-01 | CWP-11-CV-01 | CWA-11 |  |  | 1 | 2027-02-17 | 2027-03-17 |  | 2027-04-07 | 2027-03-29 | -7 | ALP-EPC-00UCA-CV-FND-0001
ALP-EPC-00UCA-EL-CBL-0001 | Control, Administration and Workshop Buildings - Cable Schedule and Routing |  | EPC | 00UCA | Control building | electrical | CBL | M | information |  |  | 11 | 42 | EWP-11-EL-01 | CWP-11-EL-01 | CWA-11 |  |  | 3 | 2027-04-06 | 2027-05-06 |  | 2027-05-13 | 2027-11-08 | 127 | capacity electrical
ALP-EPC-00UCA-EL-ELY-0001 | Control, Administration and Workshop Buildings - Electrical Layouts | equipment, trays, earthing, lighting | EPC | 00UCA | Control building | electrical | ELY | L | review |  |  | 6 | 180 | EWP-11-EL-01 | CWP-11-EL-01 | CWA-11 |  |  | 3 | 2027-02-08 | 2027-03-15 |  | 2027-04-12 | 2027-11-08 | 150 | ALP-EPC-00000-EL-STU-0003
ALP-EPC-00UCA-EL-ELY-0002 | Control, Administration and Workshop Buildings - Cable Routing, Tray and Trench Layouts |  | EPC | 00UCA | Control building | electrical | ELY | L | review |  |  | 3 | 75 | EWP-11-EL-01 | CWP-11-EL-01 | CWA-11 |  |  | 2 | 2027-07-07 | 2027-08-06 |  | 2027-09-03 | 2027-11-08 | 46 | ALP-EPC-00UCA-PI-PPL-0001
ALP-EPC-00UCA-EL-ELY-0003 | Control Building - Earthing and Lightning Protection Layouts |  | EPC | 00UCA | Control building | electrical | ELY | L | review |  |  | 1 | 20 | EWP-11-EL-01 | CWP-11-EL-01 | CWA-11 |  |  | 3 | 2027-02-17 | 2027-03-29 |  | 2027-04-26 | 2027-11-08 | 140 | capacity electrical
ALP-EPC-00UCA-HS-GAD-0001 | Control Building - Fire Fighting, Escape Route and Safety Signage Layouts |  | EPC | 00UCA | Control building | hse | GAD | L | approval |  |  | 4 | 48 | EWP-11-CV-01 | CWP-11-CV-01 | CWA-11 |  |  | 3 | 2027-02-02 | 2027-03-05 | 2027-04-02 | 2027-04-09 | 2027-03-29 | -9 | ALP-EPC-00UCA-CV-ARC-0001
ALP-EPC-00UCA-HV-GAD-0001 | Control, Administration and Workshop Buildings - HVAC Layouts |  | EPC | 00UCA | Control building | hvac | GAD | L | review |  |  | 4 | 120 | EWP-11-HV-01 | CWP-11-HV-01 | CWA-11 |  |  | 2 | 2027-04-26 | 2027-05-27 |  | 2027-06-24 | 2027-11-08 | 97 | capacity hvac
ALP-EPC-00UCA-HV-GAD-0002 | Control Building - Building Services | plumbing, HVAC ducting, fire fighting | EPC | 00UCA | Control building | hvac | GAD | L | review |  |  | 20 | 500 | EWP-11-CV-01 | CWP-11-CV-01 | CWA-11 |  |  | 2 | 2027-02-02 | 2027-03-29 |  | 2027-04-26 | 2027-03-29 | -20 | ALP-EPC-00UCA-CV-ARC-0001
ALP-EPC-00UCA-IC-ELY-0001 | Control, Administration and Workshop Buildings - Instrument Location and I&C Cable Routing |  | EPC | 00UCA | Control building | i_and_c | ELY | L | review |  |  | 4 | 64 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 |  |  | 2 | 2027-07-06 | 2027-08-06 |  | 2027-09-03 | 2027-11-22 | 56 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UCA-IC-ELY-0002 | Control Building - Fire Detection and Alarm Layouts |  | EPC | 00UCA | Control building | i_and_c | ELY | L | review |  |  | 6 | 84 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 | MR-IC-006 |  | 2 | 2027-02-02 | 2027-03-09 |  | 2027-04-06 | 2027-11-22 | 164 | ALP-EPC-00UCA-CV-ARC-0001
ALP-EPC-00UCA-IC-HUP-0001 | Control, Administration and Workshop Buildings - Instrument Hook-Up Drawings |  | EPC | 00UCA | Control building | i_and_c | HUP | M | information |  |  | 5 | 40 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 | MR-IC-010 |  | 2 | 2027-07-06 | 2027-07-22 |  | 2027-07-29 | 2027-11-22 | 82 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UCA-IC-LOP-0001 | Control, Administration and Workshop Buildings - Loop and Connection Diagrams |  | EPC | 00UCA | Control building | i_and_c | LOP | M | information |  |  | 112 | 168 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 |  |  | 2 | 2027-07-27 | 2027-09-07 |  | 2027-09-14 | 2027-11-22 | 49 | ALP-EPC-00000-IC-IOL-0001
ALP-EPC-00UCA-IC-LOP-0002 | Control, Administration and Workshop Buildings - Junction Box and Cabinet Interconnection Diagrams |  | EPC | 00UCA | Control building | i_and_c | LOP | M | information |  |  | 13 | 32.5 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 |  |  | 2 | 2027-08-06 | 2027-09-09 |  | 2027-09-16 | 2027-11-22 | 47 | ALP-EPC-00UCA-IC-ELY-0001
ALP-EPC-00UCA-PI-LAY-0001 | Control, Administration and Workshop Buildings - Equipment Layout |  | EPC | 00UCA | Control building | piping | LAY | L | approval |  |  | 12 | 480 | EWP-11-CV-01 | CWP-11-CV-01 | CWA-11 |  |  | 1 | 2026-11-02 | 2026-12-15 | 2027-01-12 | 2027-01-19 | 2027-03-29 | 49
ALP-EPC-00UCA-PI-PPL-0001 | Control, Administration and Workshop Buildings - Piping General Arrangement |  | EPC | 00UCA | Control building | piping | PPL | L | review |  |  | 14 | 1260 | EWP-11-HV-01 | CWP-11-HV-01 | CWA-11 |  |  | 3 | 2027-05-10 | 2027-07-07 |  | 2027-08-04 | 2027-11-08 | 68 | capacity piping
ALP-EPC-00UCA-SS-STL-0001 | Control Building - Structural Drawings | concrete / steel | EPC | 00UCA | Control building | structural | STL | L | approval |  |  | 8 | 280 | EWP-11-SS-01 | CWP-11-SS-01 | CWA-11 |  |  | 3 | 2027-04-06 | 2027-05-13 | 2027-06-10 | 2027-06-17 | 2027-05-24 | -18 | ALP-EPC-00UCA-CV-CAL-0001
ALP-EPC-00UCA-SS-STL-0002 | Control Building - Steel Structure Drawings |  | EPC | 00UCA | Control building | structural | STL | L | approval |  |  | 8 | 280 | EWP-11-SS-01 | CWP-11-SS-01 | CWA-11 |  |  | 3 | 2027-04-06 | 2027-05-13 | 2027-06-10 | 2027-06-17 | 2027-05-24 | -18 | ALP-EPC-00UCA-CV-CAL-0001
ALP-EPC-00UEG-CV-CAL-0001 | LDO Tank Farm Structures - Structural and Foundation Calculation |  | EPC | 00UEG | LDO tank farm structures | civil | CAL | E | review |  |  | 2 | 120 | [5 empty] | 2 | 2027-01-25 | 2027-02-16 |  | 2027-03-09 |  |  | capacity civil
ALP-EPC-00UEG-CV-EFD-0001 | LDO Tank Farm Structures - Equipment Foundation Drawings |  | EPC | 00UEG | LDO tank farm structures | civil | EFD | L | approval |  |  | 3 | 150 | EWP-10-CV-01 | CWP-10-CV-01 | CWA-10 |  |  | 2 | 2027-05-06 | 2027-06-03 | 2027-07-01 | 2027-07-08 | 2027-06-03 | -25 | capacity civil
ALP-EPC-00UEG-CV-FND-0001 | LDO Tank Farm Structures - Foundation and Underground Drawings |  | EPC | 00UEG | LDO tank farm structures | civil | FND | L | approval |  |  | 6 | 300 | EWP-10-CV-01 | CWP-10-CV-01 | CWA-10 |  |  | 3 | 2027-03-17 | 2027-04-21 | 2027-05-19 | 2027-05-26 | 2027-06-03 | 6 | capacity civil
ALP-EPC-00UEG-CV-RBR-0001 | LDO Tank Farm Structures - Reinforcement Drawings |  | EPC | 00UEG | LDO tank farm structures | civil | RBR | L | review |  |  | 10 | 350 | EWP-10-CV-01 | CWP-10-CV-01 | CWA-10 |  |  | 1 | 2027-04-21 | 2027-05-21 |  | 2027-06-11 | 2027-06-03 | -6 | ALP-EPC-00UEG-CV-FND-0001
ALP-EPC-00UEG-EL-CBL-0001 | LDO Tank Farm and Unloading - Cable Schedule and Routing |  | EPC | 00UEG | LDO tank farm structures | electrical | CBL | M | information |  |  | 6 | 32 | EWP-10-EL-01 | CWP-10-EL-01 | CWA-10 |  |  | 3 | 2027-09-08 | 2027-10-05 |  | 2027-10-12 | 2028-01-24 | 74 | capacity electrical
ALP-EPC-00UEG-EL-ELY-0001 | LDO Tank Farm and Unloading - Electrical Layouts | equipment, trays, earthing, lighting | EPC | 00UEG | LDO tank farm structures | electrical | ELY | L | review |  |  | 4 | 120 | EWP-10-EL-01 | CWP-10-EL-01 | CWA-10 |  |  | 3 | 2027-06-29 | 2027-07-30 |  | 2027-08-27 | 2028-01-24 | 106 | capacity electrical
ALP-EPC-00UEG-EL-ELY-0002 | LDO Tank Farm and Unloading - Cable Routing, Tray and Trench Layouts |  | EPC | 00UEG | LDO tank farm structures | electrical | ELY | L | review |  |  | 2 | 50 | EWP-10-EL-01 | CWP-10-EL-01 | CWA-10 |  |  | 2 | 2027-08-06 | 2027-09-06 |  | 2027-10-04 | 2028-01-24 | 80 | capacity electrical
ALP-EPC-00UEG-EL-ELY-0003 | LDO Tank Farm Structures - Earthing and Lightning Protection Layouts |  | EPC | 00UEG | LDO tank farm structures | electrical | ELY | L | review |  |  | 2 | 40 | EWP-10-EL-01 | CWP-10-EL-01 | CWA-10 |  |  | 3 | 2027-08-06 | 2027-09-06 |  | 2027-10-04 | 2028-01-24 | 80 | capacity electrical
ALP-EPC-00UEG-IC-ELY-0001 | LDO Tank Farm and Unloading - Instrument Location and I&C Cable Routing |  | EPC | 00UEG | LDO tank farm structures | i_and_c | ELY | L | review |  |  | 4 | 64 | EWP-10-IC-01 | CWP-10-IC-01 | CWA-10 |  |  | 2 | 2027-07-06 | 2027-08-06 |  | 2027-09-03 | 2028-02-21 | 121 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UEG-IC-HUP-0001 | LDO Tank Farm and Unloading - Instrument Hook-Up Drawings |  | EPC | 00UEG | LDO tank farm structures | i_and_c | HUP | M | information |  |  | 5 | 40 | EWP-10-IC-01 | CWP-10-IC-01 | CWA-10 | MR-IC-010 |  | 2 | 2027-07-06 | 2027-07-22 |  | 2027-07-29 | 2028-02-21 | 147 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UEG-IC-LOP-0001 | LDO Tank Farm and Unloading - Loop and Connection Diagrams |  | EPC | 00UEG | LDO tank farm structures | i_and_c | LOP | M | information |  |  | 96 | 144 | EWP-10-IC-01 | CWP-10-IC-01 | CWA-10 |  |  | 2 | 2027-07-27 | 2027-09-07 |  | 2027-09-14 | 2028-02-21 | 114 | ALP-EPC-00000-IC-IOL-0001
ALP-EPC-00UEG-IC-LOP-0002 | LDO Tank Farm and Unloading - Junction Box and Cabinet Interconnection Diagrams |  | EPC | 00UEG | LDO tank farm structures | i_and_c | LOP | M | information |  |  | 11 | 27.5 | EWP-10-IC-01 | CWP-10-IC-01 | CWA-10 |  |  | 2 | 2027-08-06 | 2027-09-07 |  | 2027-09-14 | 2028-02-21 | 114 | ALP-EPC-00UEG-IC-ELY-0001
ALP-EPC-00UEG-PI-LAY-0001 | LDO Tank Farm and Unloading - Equipment Layout |  | EPC | 00UEG | LDO tank farm structures | piping | LAY | L | approval |  |  | 2 | 80 | EWP-10-ME-01 | CWP-10-ME-01 | CWA-10 |  |  | 1 | 2026-11-19 | 2026-12-18 | 2027-01-15 | 2027-01-22 | 2027-10-04 | 181 | capacity piping
ALP-EPC-00UEG-PI-PPL-0001 | LDO Tank Farm and Unloading - Piping General Arrangement |  | EPC | 00UEG | LDO tank farm structures | piping | PPL | L | review |  |  | 30 | 2700 | EWP-10-PI-01 | CWP-10-PI-01 | CWA-10 |  |  | 3 | 2026-12-18 | 2027-02-26 |  | 2027-03-26 | 2027-12-27 | 196 | ALP-EPC-00UEG-PI-LAY-0001
ALP-EPC-00UEG-SS-STL-0001 | LDO Tank Farm Structures - Steel Structure Drawings |  | EPC | 00UEG | LDO tank farm structures | structural | STL | L | approval |  |  | 4 | 140 | EWP-10-CV-01 | CWP-10-CV-01 | CWA-10 |  |  | 3 | 2027-02-16 | 2027-03-19 | 2027-04-16 | 2027-04-23 | 2027-06-03 | 29 | ALP-EPC-00UEG-CV-CAL-0001
ALP-EPC-00UEK-CV-ARC-0001 | Gas Station Structures - Architectural Drawings |  | EPC | 00UEK | Gas station structures | civil | ARC | L | approval |  |  | 2 | 70 | EWP-09-CV-01 | CWP-09-CV-01 | CWA-09 |  |  | 2 | 2026-12-23 | 2027-04-30 | 2027-05-28 | 2027-06-04 | 2027-08-04 | 43 | capacity civil
ALP-EPC-00UEK-CV-CAL-0001 | Gas Station Structures - Structural and Foundation Calculation |  | EPC | 00UEK | Gas station structures | civil | CAL | E | review |  |  | 1 | 80 | [5 empty] | 2 | 2027-03-22 | 2027-04-12 |  | 2027-05-03 |  |  | capacity civil
ALP-EPC-00UEK-CV-EFD-0001 | Gas Station Structures - Equipment Foundation Drawings |  | EPC | 00UEK | Gas station structures | civil | EFD | L | approval |  |  | 2 | 100 | EWP-09-CV-01 | CWP-09-CV-01 | CWA-09 |  |  | 2 | 2027-06-17 | 2027-07-09 | 2027-08-06 | 2027-08-13 | 2027-08-04 | -7 | ALP-EPC-00UEK-CV-FND-0001
ALP-EPC-00UEK-CV-FND-0001 | Gas Station Structures - Foundation and Underground Drawings |  | EPC | 00UEK | Gas station structures | civil | FND | L | approval |  |  | 4 | 200 | EWP-09-CV-01 | CWP-09-CV-01 | CWA-09 |  |  | 3 | 2027-04-15 | 2027-06-17 | 2027-07-15 | 2027-07-22 | 2027-08-04 | 9 | capacity civil
ALP-EPC-00UEK-CV-RBR-0001 | Gas Station Structures - Reinforcement Drawings |  | EPC | 00UEK | Gas station structures | civil | RBR | L | review |  |  | 6 | 210 | EWP-09-CV-01 | CWP-09-CV-01 | CWA-09 |  |  | 1 | 2027-06-17 | 2027-07-14 |  | 2027-08-04 | 2027-08-04 | 0 | ALP-EPC-00UEK-CV-FND-0001
ALP-EPC-00UEK-EL-CBL-0001 | Fuel Gas Station - Cable Schedule and Routing |  | EPC | 00UEK | Gas station structures | electrical | CBL | M | information |  |  | 5 | 30 | EWP-09-EL-01 | CWP-09-EL-01 | CWA-09 |  |  | 3 | 2027-08-06 | 2027-09-01 |  | 2027-09-08 | 2027-12-27 | 78 | capacity electrical
ALP-EPC-00UEK-EL-ELY-0001 | Fuel Gas Station - Electrical Layouts | equipment, trays, earthing, lighting | EPC | 00UEK | Gas station structures | electrical | ELY | L | review |  |  | 4 | 120 | EWP-09-EL-01 | CWP-09-EL-01 | CWA-09 |  |  | 3 | 2027-02-15 | 2027-04-13 |  | 2027-05-11 | 2027-12-27 | 164 | capacity electrical
ALP-EPC-00UEK-EL-ELY-0002 | Fuel Gas Station - Cable Routing, Tray and Trench Layouts |  | EPC | 00UEK | Gas station structures | electrical | ELY | L | review |  |  | 2 | 50 | EWP-09-EL-01 | CWP-09-EL-01 | CWA-09 |  |  | 2 | 2027-05-06 | 2027-07-28 |  | 2027-08-25 | 2027-12-27 | 88 | capacity electrical
ALP-EPC-00UEK-EL-ELY-0003 | Gas Station Structures - Earthing and Lightning Protection Layouts |  | EPC | 00UEK | Gas station structures | electrical | ELY | L | review |  |  | 2 | 40 | EWP-09-EL-01 | CWP-09-EL-01 | CWA-09 |  |  | 3 | 2027-07-02 | 2027-08-10 |  | 2027-09-07 | 2027-12-27 | 79 | capacity electrical
ALP-EPC-00UEK-HS-GAD-0001 | Gas Station Structures - Fire Fighting, Escape Route and Safety Signage Layouts |  | EPC | 00UEK | Gas station structures | hse | GAD | L | approval |  |  | 1 | 12 | EWP-09-CV-01 | CWP-09-CV-01 | CWA-09 |  |  | 3 | 2027-04-30 | 2027-05-28 | 2027-06-25 | 2027-07-02 | 2027-08-04 | 23 | ALP-EPC-00UEK-CV-ARC-0001
ALP-EPC-00UEK-HV-GAD-0001 | Gas Station Structures - Building Services | plumbing, HVAC ducting, fire fighting | EPC | 00UEK | Gas station structures | hvac | GAD | L | review |  |  | 2 | 50 | EWP-09-CV-01 | CWP-09-CV-01 | CWA-09 |  |  | 2 | 2027-04-30 | 2027-05-31 |  | 2027-06-28 | 2027-08-04 | 27 | ALP-EPC-00UEK-CV-ARC-0001
ALP-EPC-00UEK-IC-ELY-0001 | Fuel Gas Station - Instrument Location and I&C Cable Routing |  | EPC | 00UEK | Gas station structures | i_and_c | ELY | L | review |  |  | 4 | 64 | EWP-09-IC-01 | CWP-09-IC-01 | CWA-09 |  |  | 2 | 2027-07-06 | 2027-08-06 |  | 2027-09-03 | 2028-01-24 | 101 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UEK-IC-ELY-0002 | Gas Station Structures - Fire Detection and Alarm Layouts |  | EPC | 00UEK | Gas station structures | i_and_c | ELY | L | review |  |  | 1 | 14 | EWP-09-IC-01 | CWP-09-IC-01 | CWA-09 | MR-IC-006 |  | 2 | 2027-04-30 | 2027-05-28 |  | 2027-06-25 | 2028-01-24 | 151 | ALP-EPC-00UEK-CV-ARC-0001
ALP-EPC-00UEK-IC-HUP-0001 | Fuel Gas Station - Instrument Hook-Up Drawings |  | EPC | 00UEK | Gas station structures | i_and_c | HUP | M | information |  |  | 5 | 40 | EWP-09-IC-01 | CWP-09-IC-01 | CWA-09 | MR-IC-010 |  | 2 | 2027-07-06 | 2027-07-22 |  | 2027-07-29 | 2028-01-24 | 127 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UEK-IC-LOP-0001 | Fuel Gas Station - Loop and Connection Diagrams |  | EPC | 00UEK | Gas station structures | i_and_c | LOP | M | information |  |  | 104 | 156 | EWP-09-IC-01 | CWP-09-IC-01 | CWA-09 |  |  | 2 | 2027-07-27 | 2027-09-07 |  | 2027-09-14 | 2028-01-24 | 94 | ALP-EPC-00000-IC-IOL-0001
ALP-EPC-00UEK-IC-LOP-0002 | Fuel Gas Station - Junction Box and Cabinet Interconnection Diagrams |  | EPC | 00UEK | Gas station structures | i_and_c | LOP | M | information |  |  | 12 | 30 | EWP-09-IC-01 | CWP-09-IC-01 | CWA-09 |  |  | 2 | 2027-08-06 | 2027-09-08 |  | 2027-09-15 | 2028-01-24 | 93 | ALP-EPC-00UEK-IC-ELY-0001
ALP-EPC-00UEK-PI-LAY-0001 | Fuel Gas Station - Equipment Layout |  | EPC | 00UEK | Gas station structures | piping | LAY | L | approval |  |  | 2 | 80 | EWP-09-ME-01 | CWP-09-ME-01 | CWA-09 |  |  | 1 | 2026-11-24 | 2026-12-23 | 2027-01-20 | 2027-01-27 | 2027-11-01 | 198 | capacity piping
ALP-EPC-00UEK-PI-PPL-0001 | Fuel Gas Station - Piping General Arrangement |  | EPC | 00UEK | Gas station structures | piping | PPL | L | review |  |  | 21 | 1890 | EWP-09-PI-01 | CWP-09-PI-01 | CWA-09 |  |  | 3 | 2026-12-23 | 2027-03-03 |  | 2027-03-31 | 2027-11-29 | 173 | ALP-EPC-00UEK-PI-LAY-0001
ALP-EPC-00UEK-SS-STL-0001 | Gas Station Structures - Steel Structure Drawings |  | EPC | 00UEK | Gas station structures | structural | STL | L | approval |  |  | 4 | 140 | EWP-09-CV-01 | CWP-09-CV-01 | CWA-09 |  |  | 3 | 2027-04-12 | 2027-05-13 | 2027-06-10 | 2027-06-17 | 2027-08-04 | 34 | ALP-EPC-00UEK-CV-CAL-0001
ALP-EPC-00UGA-CV-ARC-0001 | Water Treatment Building and Basins - Architectural Drawings |  | EPC | 00UGA | Water treatment building and basins | civil | ARC | L | approval |  |  | 10 | 350 | EWP-07-SS-01 | CWP-07-SS-01 | CWA-07 |  |  | 2 | 2026-12-14 | 2027-01-22 | 2027-02-19 | 2027-02-26 | 2027-06-14 | 76 | ALP-EPC-00000-HV-DBR-0001
ALP-EPC-00UGA-CV-CAL-0001 | Water Treatment Building and Basins - Structural and Foundation Calculation |  | EPC | 00UGA | Water treatment building and basins | civil | CAL | E | review |  |  | 2 | 120 | [5 empty] | 2 | 2027-01-26 | 2027-02-22 |  | 2027-03-15 |  |  | capacity civil
ALP-EPC-00UGA-CV-EFD-0001 | Water Treatment Building and Basins - Equipment Foundation Drawings |  | EPC | 00UGA | Water treatment building and basins | civil | EFD | L | approval |  |  | 4 | 200 | EWP-07-CV-01 | CWP-07-CV-01 | CWA-07 |  |  | 4 | 2027-03-17 | 2027-04-12 | 2027-05-10 | 2027-05-17 | 2027-04-05 | -30 | capacity civil
ALP-EPC-00UGA-CV-FND-0001 | Water Treatment Building and Basins - Foundation and Underground Drawings |  | EPC | 00UGA | Water treatment building and basins | civil | FND | L | approval |  |  | 8 | 400 | EWP-07-CV-01 | CWP-07-CV-01 | CWA-07 |  |  | 3 | 2027-01-18 | 2027-02-24 | 2027-03-24 | 2027-03-31 | 2027-04-05 | 3 | ALP-EPC-00000-CV-CAL-0001
ALP-EPC-00UGA-CV-RBR-0001 | Water Treatment Building and Basins - Reinforcement Drawings |  | EPC | 00UGA | Water treatment building and basins | civil | RBR | L | review |  |  | 20 | 700 | EWP-07-CV-01 | CWP-07-CV-01 | CWA-07 |  |  | 1 | 2027-02-24 | 2027-04-06 |  | 2027-04-27 | 2027-04-05 | -16 | ALP-EPC-00UGA-CV-FND-0001
ALP-EPC-00UGA-EL-CBL-0001 | Water Treatment and Effluents - Cable Schedule and Routing |  | EPC | 00UGA | Water treatment building and basins | electrical | CBL | M | information |  |  | 11 | 42 | EWP-07-EL-01 | CWP-07-EL-01 | CWA-07 |  |  | 3 | 2027-09-10 | 2027-10-12 |  | 2027-10-19 | 2028-02-21 | 89 | capacity electrical
ALP-EPC-00UGA-EL-ELY-0001 | Water Treatment and Effluents - Electrical Layouts | equipment, trays, earthing, lighting | EPC | 00UGA | Water treatment building and basins | electrical | ELY | L | review |  |  | 6 | 180 | EWP-07-EL-01 | CWP-07-EL-01 | CWA-07 |  |  | 3 | 2027-08-05 | 2027-09-09 |  | 2027-10-07 | 2028-02-21 | 97 | capacity electrical
ALP-EPC-00UGA-EL-ELY-0002 | Water Treatment and Effluents - Cable Routing, Tray and Trench Layouts |  | EPC | 00UGA | Water treatment building and basins | electrical | ELY | L | review |  |  | 3 | 75 | EWP-07-EL-01 | CWP-07-EL-01 | CWA-07 |  |  | 2 | 2027-09-09 | 2027-10-11 |  | 2027-11-08 | 2028-02-21 | 75 | ALP-EPC-00UGA-EL-ELY-0001
ALP-EPC-00UGA-EL-ELY-0003 | Water Treatment Building and Basins - Earthing and Lightning Protection Layouts |  | EPC | 00UGA | Water treatment building and basins | electrical | ELY | L | review |  |  | 3 | 60 | EWP-07-EL-01 | CWP-07-EL-01 | CWA-07 |  |  | 3 | 2027-09-08 | 2027-10-08 |  | 2027-11-05 | 2028-02-21 | 76 | capacity electrical
ALP-EPC-00UGA-HS-GAD-0001 | Water Treatment Building and Basins - Fire Fighting, Escape Route and Safety Signage Layouts |  | EPC | 00UGA | Water treatment building and basins | hse | GAD | L | approval |  |  | 3 | 36 | EWP-07-CV-01 | CWP-07-CV-01 | CWA-07 |  |  | 3 | 2027-01-22 | 2027-02-23 | 2027-03-23 | 2027-03-30 | 2027-04-05 | 4 | ALP-EPC-00UGA-CV-ARC-0001
ALP-EPC-00UGA-HV-GAD-0001 | Water Treatment Building and Basins - Building Services | plumbing, HVAC ducting, fire fighting | EPC | 00UGA | Water treatment building and basins | hvac | GAD | L | review |  |  | 12 | 300 | EWP-07-CV-01 | CWP-07-CV-01 | CWA-07 |  |  | 2 | 2027-01-22 | 2027-05-10 |  | 2027-06-07 | 2027-04-05 | -45 | capacity hvac
ALP-EPC-00UGA-IC-ELY-0001 | Water Treatment and Effluents - Instrument Location and I&C Cable Routing |  | EPC | 00UGA | Water treatment building and basins | i_and_c | ELY | L | review |  |  | 6 | 96 | EWP-07-IC-01 | CWP-07-IC-01 | CWA-07 |  |  | 2 | 2027-07-06 | 2027-08-10 |  | 2027-09-07 | 2028-03-20 | 139 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UGA-IC-ELY-0002 | Water Treatment Building and Basins - Fire Detection and Alarm Layouts |  | EPC | 00UGA | Water treatment building and basins | i_and_c | ELY | L | review |  |  | 4 | 56 | EWP-07-IC-01 | CWP-07-IC-01 | CWA-07 | MR-IC-006 |  | 2 | 2027-01-22 | 2027-02-24 |  | 2027-03-24 | 2028-03-20 | 258 | ALP-EPC-00UGA-CV-ARC-0001
ALP-EPC-00UGA-IC-HUP-0001 | Water Treatment and Effluents - Instrument Hook-Up Drawings |  | EPC | 00UGA | Water treatment building and basins | i_and_c | HUP | M | information |  |  | 8 | 64 | EWP-07-IC-01 | CWP-07-IC-01 | CWA-07 | MR-IC-010 |  | 2 | 2027-07-06 | 2027-07-26 |  | 2027-08-02 | 2028-03-20 | 165 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UGA-IC-LOP-0001 | Water Treatment and Effluents - Loop and Connection Diagrams |  | EPC | 00UGA | Water treatment building and basins | i_and_c | LOP | M | information |  |  | 162 | 243 | EWP-07-IC-01 | CWP-07-IC-01 | CWA-07 |  |  | 2 | 2027-08-03 | 2027-09-16 |  | 2027-09-23 | 2028-03-20 | 127 | capacity i_and_c
ALP-EPC-00UGA-IC-LOP-0002 | Water Treatment and Effluents - Junction Box and Cabinet Interconnection Diagrams |  | EPC | 00UGA | Water treatment building and basins | i_and_c | LOP | M | information |  |  | 18 | 45 | EWP-07-IC-01 | CWP-07-IC-01 | CWA-07 |  |  | 2 | 2027-08-10 | 2027-09-17 |  | 2027-09-24 | 2028-03-20 | 126 | ALP-EPC-00UGA-IC-ELY-0001
ALP-EPC-00UGA-PI-LAY-0001 | Water Treatment and Effluents - Equipment Layout |  | EPC | 00UGA | Water treatment building and basins | piping | LAY | L | approval |  |  | 5 | 200 | EWP-07-ME-01 | CWP-07-ME-01 | CWA-07 |  |  | 1 | 2026-11-06 | 2026-12-11 | 2027-01-08 | 2027-01-15 | 2027-12-27 | 246 | capacity piping
ALP-EPC-00UGA-PI-PPL-0001 | Water Treatment and Effluents - Piping General Arrangement |  | EPC | 00UGA | Water treatment building and basins | piping | PPL | L | review |  |  | 49 | 4410 | EWP-07-PI-01 | CWP-07-PI-01 | CWA-07 |  |  | 3 | 2026-12-14 | 2027-03-03 |  | 2027-03-31 | 2028-01-24 | 213 | capacity piping
ALP-EPC-00UGA-SS-STL-0001 | Water Treatment Building and Basins - Structural Drawings | concrete / steel | EPC | 00UGA | Water treatment building and basins | structural | STL | L | approval |  |  | 5 | 175 | EWP-07-SS-01 | CWP-07-SS-01 | CWA-07 |  |  | 3 | 2027-02-22 | 2027-03-26 | 2027-04-23 | 2027-04-30 | 2027-06-14 | 31 | ALP-EPC-00UGA-CV-CAL-0001
ALP-EPC-00UGA-SS-STL-0002 | Water Treatment Building and Basins - Steel Structure Drawings |  | EPC | 00UGA | Water treatment building and basins | structural | STL | L | approval |  |  | 8 | 280 | EWP-07-SS-01 | CWP-07-SS-01 | CWA-07 |  |  | 3 | 2027-02-22 | 2027-03-31 | 2027-04-28 | 2027-05-05 | 2027-06-14 | 28 | ALP-EPC-00UGA-CV-CAL-0001
ALP-EPC-00UPA-CV-CAL-0001 | CW Intake and Outfall Marine Structures - Structural and Foundation Calculation |  | EPC | 00UPA | CW intake and outfall marine structures | civil | CAL | E | review |  |  | 5 | 240 | [5 empty] | 2 | 2027-05-20 | 2027-06-15 |  | 2027-07-06 |  |  | capacity civil
ALP-EPC-00UPA-CV-CAL-0002 | Marine Structures Design: Hydrodynamics, Scour and Rock Protection |  | EPC | 00UPA | CW intake and outfall marine structures | civil | CAL | E | review |  |  | 1 | 240 | [5 empty] | 2 | 2027-06-02 | 2027-06-23 |  | 2027-07-14 |  |  | ALP-EPC-00000-PR-STU-0003
ALP-EPC-00UPA-CV-CVL-0001 | CW Intake and Outfall Marine Structures - Civil Drawings |  | EPC | 00UPA | CW intake and outfall marine structures | civil | CVL | L | approval |  |  | 20 | 800 | EWP-06-CV-01 | CWP-06-CV-01 | CWA-06 |  |  | 3 | 2027-06-23 | 2027-08-17 | 2027-09-14 | 2027-09-21 | 2027-09-03 | -12 | ALP-EPC-00UPA-CV-CAL-0002
ALP-EPC-00UPA-CV-MOS-0001 | Marine Works Construction Method Statement | intake, outfall, dredging | EPC | 00UPA | CW intake and outfall marine structures | civil | MOS | B | review |  |  | 1 | 80 | [5 empty] | 1 | 2027-08-17 | 2027-08-31 |  | 2027-09-21 |  |  | ALP-EPC-00UPA-CV-CVL-0001
ALP-EPC-00UPA-CV-RBR-0001 | CW Intake and Outfall Marine Structures - Reinforcement Drawings |  | EPC | 00UPA | CW intake and outfall marine structures | civil | RBR | L | review |  |  | 10 | 350 | EWP-06-CV-01 | CWP-06-CV-01 | CWA-06 |  |  | 1 | 2027-08-17 | 2027-09-16 |  | 2027-10-07 | 2027-09-03 | -24 | ALP-EPC-00UPA-CV-CVL-0001
ALP-EPC-00UPA-CV-RPT-0001 | Marine Route Survey for Intake and Outfall Pipelines | bathymetry, geophysics | EPC | 00UPA | CW intake and outfall marine structures | civil | RPT | D | review |  |  | 1 | 120 | [5 empty] | 1 | 2027-05-20 | 2027-06-10 |  | 2027-07-01 |  |  | capacity civil
ALP-EPC-00UPA-EL-ELY-0001 | CW Intake and Outfall Marine Structures - Earthing and Lightning Protection Layouts |  | EPC | 00UPA | CW intake and outfall marine structures | electrical | ELY | L | review |  |  | 7 | 140 | EWP-06-CV-01 | CWP-06-CV-01 | CWA-06 |  |  | 3 | 2027-08-17 | 2027-09-22 |  | 2027-10-20 | 2027-09-03 | -33 | ALP-EPC-00UPA-CV-CVL-0001
ALP-EPC-00UPA-EL-ELY-0002 | Marine Works - Electrical Layouts | equipment, trays, earthing, lighting; offshore | EPC | 00UPA | CW intake and outfall marine structures | electrical | ELY | L | review |  |  | 4 | 120 | EWP-06-CV-01 | CWP-06-CV-01 | CWA-06 |  |  | 3 | 2027-02-08 | 2027-03-11 |  | 2027-04-08 | 2027-09-03 | 106 | ALP-EPC-00000-EL-STU-0003
ALP-EPC-00UPA-GE-RPT-0001 | Marine Works - Technical Bid Evaluation |  | EPC | 00UPA | CW intake and outfall marine structures | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-CV-003 |  | 1 | 2027-02-09 | 2027-03-02 |  | 2027-03-09 |  |  | capacity general
ALP-EPC-00UPA-PI-LAY-0001 | Marine Works - Equipment Layout | offshore | EPC | 00UPA | CW intake and outfall marine structures | piping | LAY | L | approval |  |  | 2 | 80 | EWP-06-CV-01 | CWP-06-CV-01 | CWA-06 |  |  | 1 | 2026-11-25 | 2026-12-24 | 2027-01-21 | 2027-01-28 | 2027-09-03 | 156 | capacity piping
ALP-EPC-00UPC-CV-ARC-0001 | CW Pump House - Architectural Drawings |  | EPC | 00UPC | CW pump house | civil | ARC | L | approval |  |  | 4 | 140 | EWP-05-CV-01 | CWP-05-CV-01 | CWA-05 |  |  | 2 | 2026-12-14 | 2027-01-14 | 2027-02-11 | 2027-02-18 | 2027-03-25 | 25 | ALP-EPC-00000-HV-DBR-0001
ALP-EPC-00UPC-CV-CAL-0001 | CW Pump House - Structural and Foundation Calculation |  | EPC | 00UPC | CW pump house | civil | CAL | E | review |  |  | 2 | 120 | [5 empty] | 2 | 2027-01-18 | 2027-02-09 |  | 2027-03-02 |  |  | ALP-EPC-00000-CV-CAL-0001
ALP-EPC-00UPC-CV-EFD-0001 | CW Pump House - Equipment Foundation Drawings |  | EPC | 00UPC | CW pump house | civil | EFD | L | approval |  |  | 4 | 200 | EWP-05-CV-01 | CWP-05-CV-01 | CWA-05 |  |  | 4 | 2027-04-08 | 2027-05-03 | 2027-05-31 | 2027-06-07 | 2027-03-25 | -52 | ALP-EPC-00UPC-CV-FND-0001
ALP-EPC-00UPC-CV-FND-0001 | CW Pump House - Foundation and Underground Drawings |  | EPC | 00UPC | CW pump house | civil | FND | L | approval |  |  | 8 | 400 | EWP-05-CV-01 | CWP-05-CV-01 | CWA-05 |  |  | 4 | 2027-03-02 | 2027-04-08 | 2027-05-06 | 2027-05-13 | 2027-03-25 | -35 | ALP-EPC-00UPC-CV-FND-0002
ALP-EPC-00UPC-CV-FND-0002 | CW Pump House - Piling Layout and Pile Schedule |  | EPC | 00UPC | CW pump house | civil | FND | L | approval |  |  | 2 | 80 | EWP-05-CV-01 | CWP-05-CV-01 | CWA-05 |  |  | 3 | 2027-02-01 | 2027-03-02 | 2027-03-30 | 2027-04-06 | 2027-03-25 | -8 | ALP-EPC-00000-CV-SPC-0002
ALP-EPC-00UPC-CV-RBR-0001 | CW Pump House - Reinforcement Drawings |  | EPC | 00UPC | CW pump house | civil | RBR | L | review |  |  | 24 | 840 | EWP-05-CV-01 | CWP-05-CV-01 | CWA-05 |  |  | 1 | 2027-04-08 | 2027-05-20 |  | 2027-06-10 | 2027-03-25 | -55 | ALP-EPC-00UPC-CV-FND-0001
ALP-EPC-00UPC-EL-CBL-0001 | CW Pump House and Onshore CW - Cable Schedule and Routing |  | EPC | 00UPC | CW pump house | electrical | CBL | M | information |  |  | 7 | 34 | EWP-05-EL-01 | CWP-05-EL-01 | CWA-05 |  |  | 3 | 2027-09-09 | 2027-10-07 |  | 2027-10-14 | 2028-01-31 | 77 | capacity electrical
ALP-EPC-00UPC-EL-ELY-0001 | CW Pump House and Onshore CW - Electrical Layouts | equipment, trays, earthing, lighting | EPC | 00UPC | CW pump house | electrical | ELY | L | review |  |  | 4 | 120 | EWP-05-EL-01 | CWP-05-EL-01 | CWA-05 |  |  | 3 | 2027-07-02 | 2027-08-13 |  | 2027-09-10 | 2028-01-31 | 101 | capacity electrical
ALP-EPC-00UPC-EL-ELY-0002 | CW Pump House and Onshore CW - Cable Routing, Tray and Trench Layouts |  | EPC | 00UPC | CW pump house | electrical | ELY | L | review |  |  | 2 | 50 | EWP-05-EL-01 | CWP-05-EL-01 | CWA-05 |  |  | 2 | 2027-08-13 | 2027-10-01 |  | 2027-10-29 | 2028-01-31 | 66 | capacity electrical
ALP-EPC-00UPC-EL-ELY-0003 | CW Pump House - Earthing and Lightning Protection Layouts |  | EPC | 00UPC | CW pump house | electrical | ELY | L | review |  |  | 3 | 60 | EWP-05-EL-01 | CWP-05-EL-01 | CWA-05 |  |  | 3 | 2027-09-06 | 2027-10-06 |  | 2027-11-03 | 2028-01-31 | 63 | capacity electrical
ALP-EPC-00UPC-HS-GAD-0001 | CW Pump House - Fire Fighting, Escape Route and Safety Signage Layouts |  | EPC | 00UPC | CW pump house | hse | GAD | L | approval |  |  | 1 | 12 | EWP-05-CV-01 | CWP-05-CV-01 | CWA-05 |  |  | 3 | 2027-01-14 | 2027-02-11 | 2027-03-11 | 2027-03-18 | 2027-03-25 | 5 | ALP-EPC-00UPC-CV-ARC-0001
ALP-EPC-00UPC-HV-GAD-0001 | CW Pump House - Building Services | plumbing, HVAC ducting, fire fighting | EPC | 00UPC | CW pump house | hvac | GAD | L | review |  |  | 4 | 100 | EWP-05-CV-01 | CWP-05-CV-01 | CWA-05 |  |  | 2 | 2027-01-14 | 2027-04-26 |  | 2027-05-24 | 2027-03-25 | -42 | capacity hvac
ALP-EPC-00UPC-IC-ELY-0001 | CW Pump House and Onshore CW - Instrument Location and I&C Cable Routing |  | EPC | 00UPC | CW pump house | i_and_c | ELY | L | review |  |  | 4 | 64 | EWP-05-IC-01 | CWP-05-IC-01 | CWA-05 |  |  | 2 | 2027-07-06 | 2027-08-06 |  | 2027-09-03 | 2028-02-28 | 126 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UPC-IC-ELY-0002 | CW Pump House - Fire Detection and Alarm Layouts |  | EPC | 00UPC | CW pump house | i_and_c | ELY | L | review |  |  | 2 | 28 | EWP-05-IC-01 | CWP-05-IC-01 | CWA-05 | MR-IC-006 |  | 2 | 2027-01-14 | 2027-02-12 |  | 2027-03-12 | 2028-02-28 | 251 | ALP-EPC-00UPC-CV-ARC-0001
ALP-EPC-00UPC-IC-HUP-0001 | CW Pump House and Onshore CW - Instrument Hook-Up Drawings |  | EPC | 00UPC | CW pump house | i_and_c | HUP | M | information |  |  | 5 | 40 | EWP-05-IC-01 | CWP-05-IC-01 | CWA-05 | MR-IC-010 |  | 2 | 2027-07-06 | 2027-07-22 |  | 2027-07-29 | 2028-02-28 | 152 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UPC-IC-LOP-0001 | CW Pump House and Onshore CW - Loop and Connection Diagrams |  | EPC | 00UPC | CW pump house | i_and_c | LOP | M | information |  |  | 97 | 145.5 | EWP-05-IC-01 | CWP-05-IC-01 | CWA-05 |  |  | 2 | 2027-07-27 | 2027-09-07 |  | 2027-09-14 | 2028-02-28 | 119 | ALP-EPC-00000-IC-IOL-0001
ALP-EPC-00UPC-IC-LOP-0002 | CW Pump House and Onshore CW - Junction Box and Cabinet Interconnection Diagrams |  | EPC | 00UPC | CW pump house | i_and_c | LOP | M | information |  |  | 11 | 27.5 | EWP-05-IC-01 | CWP-05-IC-01 | CWA-05 |  |  | 2 | 2027-08-06 | 2027-09-07 |  | 2027-09-14 | 2028-02-28 | 119 | ALP-EPC-00UPC-IC-ELY-0001
ALP-EPC-00UPC-PI-LAY-0001 | CW Pump House and Onshore CW - Equipment Layout |  | EPC | 00UPC | CW pump house | piping | LAY | L | approval |  |  | 3 | 120 | EWP-05-ME-01 | CWP-05-ME-01 | CWA-05 |  |  | 1 | 2026-11-02 | 2026-12-02 | 2026-12-30 | 2027-01-06 | 2027-12-20 | 248
ALP-EPC-00UPC-PI-PPL-0001 | CW Pump House and Onshore CW - Piping General Arrangement |  | EPC | 00UPC | CW pump house | piping | PPL | L | review |  |  | 17 | 1530 | EWP-05-PI-01 | CWP-05-PI-01 | CWA-05 |  |  | 3 | 2027-03-03 | 2027-05-11 |  | 2027-06-08 | 2027-09-20 | 74 | capacity piping
ALP-EPC-00UPC-SS-STL-0001 | CW Pump House - Steel Structure Drawings |  | EPC | 00UPC | CW pump house | structural | STL | L | approval |  |  | 6 | 210 | EWP-05-CV-01 | CWP-05-CV-01 | CWA-05 |  |  | 3 | 2027-02-09 | 2027-03-16 | 2027-04-13 | 2027-04-20 | 2027-03-25 | -18 | ALP-EPC-00UPC-CV-CAL-0001
ALP-EPC-00UQA-CV-ARC-0001 | Utility Building - Architectural Drawings |  | EPC | 00UQA | Utility building | civil | ARC | L | approval |  |  | 6 | 210 | EWP-08-SS-01 | CWP-08-SS-01 | CWA-08 |  |  | 2 | 2026-12-21 | 2027-01-25 | 2027-02-22 | 2027-03-01 | 2027-06-29 | 86 | ALP-EPC-00UQA-PI-LAY-0001
ALP-EPC-00UQA-CV-CAL-0001 | Utility Building - Structural and Foundation Calculation |  | EPC | 00UQA | Utility building | civil | CAL | E | review |  |  | 1 | 80 | [5 empty] | 2 | 2027-02-10 | 2027-03-30 |  | 2027-04-20 |  |  | capacity civil
ALP-EPC-00UQA-CV-EFD-0001 | Utility Building - Equipment Foundation Drawings |  | EPC | 00UQA | Utility building | civil | EFD | L | approval |  |  | 2 | 100 | EWP-08-CV-01 | CWP-08-CV-01 | CWA-08 |  |  | 7 | 2027-03-30 | 2027-04-27 | 2027-05-25 | 2027-06-01 | 2027-05-04 | -20 | capacity civil
ALP-EPC-00UQA-CV-FND-0001 | Utility Building - Foundation and Underground Drawings |  | EPC | 00UQA | Utility building | civil | FND | L | approval |  |  | 4 | 200 | EWP-08-CV-01 | CWP-08-CV-01 | CWA-08 |  |  | 3 | 2027-02-08 | 2027-03-16 | 2027-04-13 | 2027-04-20 | 2027-05-04 | 10 | capacity civil
ALP-EPC-00UQA-CV-RBR-0001 | Utility Building - Reinforcement Drawings |  | EPC | 00UQA | Utility building | civil | RBR | L | review |  |  | 10 | 350 | EWP-08-CV-01 | CWP-08-CV-01 | CWA-08 |  |  | 1 | 2027-03-18 | 2027-04-20 |  | 2027-05-11 | 2027-05-04 | -5 | capacity civil
ALP-EPC-00UQA-EL-CBL-0001 | BOP Utilities - Cable Schedule and Routing |  | EPC | 00UQA | Utility building | electrical | CBL | M | information |  |  | 20 | 60 | EWP-08-EL-01 | CWP-08-EL-01 | CWA-08 |  |  | 3 | 2027-09-07 | 2027-10-18 |  | 2027-10-25 | 2028-01-10 | 55 | capacity electrical
ALP-EPC-00UQA-EL-ELY-0001 | BOP Utilities - Electrical Layouts | equipment, trays, earthing, lighting | EPC | 00UQA | Utility building | electrical | ELY | L | review |  |  | 10 | 300 | EWP-08-EL-01 | CWP-08-EL-01 | CWA-08 |  |  | 3 | 2027-03-16 | 2027-05-12 |  | 2027-06-09 | 2028-01-10 | 153 | capacity electrical
ALP-EPC-00UQA-EL-ELY-0002 | BOP Utilities - Cable Routing, Tray and Trench Layouts |  | EPC | 00UQA | Utility building | electrical | ELY | L | review |  |  | 6 | 150 | EWP-08-EL-01 | CWP-08-EL-01 | CWA-08 |  |  | 4 | 2027-08-04 | 2027-09-08 |  | 2027-10-06 | 2028-01-10 | 68 | capacity electrical
ALP-EPC-00UQA-EL-ELY-0003 | Utility Building - Earthing and Lightning Protection Layouts |  | EPC | 00UQA | Utility building | electrical | ELY | L | review |  |  | 2 | 40 | EWP-08-EL-01 | CWP-08-EL-01 | CWA-08 |  |  | 3 | 2027-08-06 | 2027-09-06 |  | 2027-10-04 | 2028-01-10 | 70 | capacity electrical
ALP-EPC-00UQA-HS-GAD-0001 | Utility Building - Fire Fighting, Escape Route and Safety Signage Layouts |  | EPC | 00UQA | Utility building | hse | GAD | L | approval |  |  | 2 | 24 | EWP-08-CV-01 | CWP-08-CV-01 | CWA-08 |  |  | 3 | 2027-01-25 | 2027-02-23 | 2027-03-23 | 2027-03-30 | 2027-05-04 | 25 | ALP-EPC-00UQA-CV-ARC-0001
ALP-EPC-00UQA-HV-GAD-0001 | Utility Building - Building Services | plumbing, HVAC ducting, fire fighting | EPC | 00UQA | Utility building | hvac | GAD | L | review |  |  | 8 | 200 | EWP-08-CV-01 | CWP-08-CV-01 | CWA-08 |  |  | 2 | 2027-04-05 | 2027-05-13 |  | 2027-06-10 | 2027-05-04 | -27 | capacity hvac
ALP-EPC-00UQA-IC-ELY-0001 | BOP Utilities - Instrument Location and I&C Cable Routing |  | EPC | 00UQA | Utility building | i_and_c | ELY | L | review |  |  | 14 | 224 | EWP-08-IC-01 | CWP-08-IC-01 | CWA-08 |  |  | 2 | 2027-07-06 | 2027-08-20 |  | 2027-09-17 | 2028-02-21 | 111 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UQA-IC-ELY-0002 | Utility Building - Fire Detection and Alarm Layouts |  | EPC | 00UQA | Utility building | i_and_c | ELY | L | review |  |  | 2 | 28 | EWP-08-IC-01 | CWP-08-IC-01 | CWA-08 | MR-IC-006 |  | 2 | 2027-01-25 | 2027-02-23 |  | 2027-03-23 | 2028-02-21 | 239 | ALP-EPC-00UQA-CV-ARC-0001
ALP-EPC-00UQA-IC-HUP-0001 | BOP Utilities - Instrument Hook-Up Drawings |  | EPC | 00UQA | Utility building | i_and_c | HUP | M | information |  |  | 19 | 152 | EWP-08-IC-01 | CWP-08-IC-01 | CWA-08 | MR-IC-010 |  | 2 | 2027-07-06 | 2027-08-13 |  | 2027-08-20 | 2028-02-21 | 131 | capacity i_and_c
ALP-EPC-00UQA-IC-LOP-0001 | BOP Utilities - Loop and Connection Diagrams, Part 1 of 2 |  | EPC | 00UQA | Utility building | i_and_c | LOP | M | information |  |  | 208 | 312 | EWP-08-IC-01 | CWP-08-IC-01 | CWA-08 |  |  | 2 | 2027-07-27 | 2027-09-07 |  | 2027-09-14 | 2028-02-21 | 114 | ALP-EPC-00000-IC-IOL-0001
ALP-EPC-00UQA-IC-LOP-0002 | BOP Utilities - Junction Box and Cabinet Interconnection Diagrams |  | EPC | 00UQA | Utility building | i_and_c | LOP | M | information |  |  | 47 | 117.5 | EWP-08-IC-01 | CWP-08-IC-01 | CWA-08 |  |  | 2 | 2027-08-20 | 2027-10-01 |  | 2027-10-08 | 2028-02-21 | 96 | ALP-EPC-00UQA-IC-ELY-0001
ALP-EPC-00UQA-IC-LOP-0003 | BOP Utilities - Loop and Connection Diagrams, Part 2 of 2 |  | EPC | 00UQA | Utility building | i_and_c | LOP | M | information |  |  | 207 | 310.5 | EWP-08-IC-01 | CWP-08-IC-01 | CWA-08 |  |  | 2 | 2027-07-27 | 2027-09-07 |  | 2027-09-14 | 2028-02-21 | 114 | ALP-EPC-00000-IC-IOL-0001
ALP-EPC-00UQA-PI-LAY-0001 | BOP Utilities - Equipment Layout |  | EPC | 00UQA | Utility building | piping | LAY | L | approval |  |  | 7 | 280 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 |  |  | 1 | 2026-11-11 | 2026-12-21 | 2027-01-18 | 2027-01-25 | 2027-11-01 | 200 | capacity piping
ALP-EPC-00UQA-PI-PPL-0001 | BOP Utilities - Piping General Arrangement, Part 1 of 3 |  | EPC | 00UQA | Utility building | piping | PPL | L | review |  |  | 41 | 3690 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 |  |  | 3 | 2027-01-14 | 2027-04-15 |  | 2027-05-13 | 2027-12-13 | 152 | capacity piping
ALP-EPC-00UQA-PI-PPL-0002 | BOP Utilities - Piping General Arrangement, Part 2 of 3 |  | EPC | 00UQA | Utility building | piping | PPL | L | review |  |  | 41 | 3690 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 |  |  | 3 | 2027-04-14 | 2027-06-25 |  | 2027-07-23 | 2027-12-13 | 101 | capacity piping
ALP-EPC-00UQA-PI-PPL-0003 | BOP Utilities - Piping General Arrangement, Part 3 of 3 |  | EPC | 00UQA | Utility building | piping | PPL | L | review |  |  | 41 | 3690 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 |  |  | 3 | 2027-05-07 | 2027-07-19 |  | 2027-08-16 | 2027-12-13 | 85 | capacity piping
ALP-EPC-00UQA-SS-STL-0001 | Utility Building - Steel Structure Drawings |  | EPC | 00UQA | Utility building | structural | STL | L | approval |  |  | 12 | 420 | EWP-08-SS-01 | CWP-08-SS-01 | CWA-08 |  |  | 4 | 2027-03-30 | 2027-05-12 | 2027-06-09 | 2027-06-16 | 2027-06-29 | 9 | ALP-EPC-00UQA-CV-CAL-0001
ALP-EPC-00USA-CV-ARC-0001 | Workshop and Warehouse - Architectural Drawings |  | EPC | 00USA | Workshop and warehouse | civil | ARC | L | approval |  |  | 10 | 350 | EWP-11-SS-01 | CWP-11-SS-01 | CWA-11 |  |  | 2 | 2026-12-15 | 2027-01-25 | 2027-02-22 | 2027-03-01 | 2027-05-24 | 60 | ALP-EPC-00UCA-PI-LAY-0001
ALP-EPC-00USA-CV-CAL-0001 | Workshop and Warehouse - Structural and Foundation Calculation |  | EPC | 00USA | Workshop and warehouse | civil | CAL | E | review |  |  | 1 | 80 | [5 empty] | 2 | 2027-02-16 | 2027-04-05 |  | 2027-04-26 |  |  | capacity civil
ALP-EPC-00USA-CV-FND-0001 | Workshop and Warehouse - Foundation and Underground Drawings |  | EPC | 00USA | Workshop and warehouse | civil | FND | L | approval |  |  | 3 | 150 | EWP-11-CV-01 | CWP-11-CV-01 | CWA-11 |  |  | 3 | 2027-01-18 | 2027-02-17 | 2027-03-17 | 2027-03-24 | 2027-03-29 | 3 | ALP-EPC-00000-CV-CAL-0001
ALP-EPC-00USA-CV-RBR-0001 | Workshop and Warehouse - Reinforcement Drawings |  | EPC | 00USA | Workshop and warehouse | civil | RBR | L | review |  |  | 6 | 210 | EWP-11-CV-01 | CWP-11-CV-01 | CWA-11 |  |  | 1 | 2027-02-17 | 2027-03-16 |  | 2027-04-06 | 2027-03-29 | -6 | ALP-EPC-00USA-CV-FND-0001
ALP-EPC-00USA-EL-ELY-0001 | Workshop and Warehouse - Earthing and Lightning Protection Layouts |  | EPC | 00USA | Workshop and warehouse | electrical | ELY | L | review |  |  | 1 | 20 | EWP-11-EL-01 | CWP-11-EL-01 | CWA-11 |  |  | 3 | 2027-02-17 | 2027-03-29 |  | 2027-04-26 | 2027-11-08 | 140 | capacity electrical
ALP-EPC-00USA-HS-GAD-0001 | Workshop and Warehouse - Fire Fighting, Escape Route and Safety Signage Layouts |  | EPC | 00USA | Workshop and warehouse | hse | GAD | L | approval |  |  | 3 | 36 | EWP-11-CV-01 | CWP-11-CV-01 | CWA-11 |  |  | 3 | 2027-01-25 | 2027-02-24 | 2027-03-24 | 2027-03-31 | 2027-03-29 | -2 | ALP-EPC-00USA-CV-ARC-0001
ALP-EPC-00USA-HV-GAD-0001 | Workshop and Warehouse - Building Services | plumbing, HVAC ducting, fire fighting | EPC | 00USA | Workshop and warehouse | hvac | GAD | L | review |  |  | 10 | 250 | EWP-11-CV-01 | CWP-11-CV-01 | CWA-11 |  |  | 2 | 2027-01-25 | 2027-04-05 |  | 2027-05-03 | 2027-03-29 | -25 | capacity hvac
ALP-EPC-00USA-IC-ELY-0001 | Workshop and Warehouse - Fire Detection and Alarm Layouts |  | EPC | 00USA | Workshop and warehouse | i_and_c | ELY | L | review |  |  | 4 | 56 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 | MR-IC-006 |  | 2 | 2027-01-25 | 2027-02-25 |  | 2027-03-25 | 2027-11-22 | 172 | ALP-EPC-00USA-CV-ARC-0001
ALP-EPC-00USA-SS-STL-0001 | Workshop and Warehouse - Structural Drawings | concrete / steel | EPC | 00USA | Workshop and warehouse | structural | STL | L | approval |  |  | 5 | 175 | EWP-11-SS-01 | CWP-11-SS-01 | CWA-11 |  |  | 3 | 2027-04-05 | 2027-05-07 | 2027-06-04 | 2027-06-11 | 2027-05-24 | -14 | ALP-EPC-00USA-CV-CAL-0001
ALP-EPC-00USA-SS-STL-0002 | Workshop and Warehouse - Steel Structure Drawings |  | EPC | 00USA | Workshop and warehouse | structural | STL | L | approval |  |  | 10 | 350 | EWP-11-SS-01 | CWP-11-SS-01 | CWA-11 |  |  | 3 | 2027-04-05 | 2027-05-14 | 2027-06-11 | 2027-06-18 | 2027-05-24 | -19 | ALP-EPC-00USA-CV-CAL-0001
ALP-EPC-00UYA-CV-ARC-0001 | Administration Building - Architectural Drawings |  | EPC | 00UYA | Administration building | civil | ARC | L | approval |  |  | 16 | 560 | EWP-11-SS-01 | CWP-11-SS-01 | CWA-11 |  |  | 2 | 2026-12-15 | 2027-02-02 | 2027-03-02 | 2027-03-09 | 2027-05-24 | 54 | ALP-EPC-00UCA-PI-LAY-0001
ALP-EPC-00UYA-CV-CAL-0001 | Administration Building - Structural and Foundation Calculation |  | EPC | 00UYA | Administration building | civil | CAL | E | review |  |  | 1 | 80 | [5 empty] | 2 | 2027-03-17 | 2027-04-07 |  | 2027-04-28 |  |  | capacity civil
ALP-EPC-00UYA-CV-FND-0001 | Administration Building - Foundation and Underground Drawings |  | EPC | 00UYA | Administration building | civil | FND | L | approval |  |  | 3 | 150 | EWP-11-CV-01 | CWP-11-CV-01 | CWA-11 |  |  | 3 | 2027-01-18 | 2027-02-17 | 2027-03-17 | 2027-03-24 | 2027-03-29 | 3 | ALP-EPC-00000-CV-CAL-0001
ALP-EPC-00UYA-CV-RBR-0001 | Administration Building - Reinforcement Drawings |  | EPC | 00UYA | Administration building | civil | RBR | L | review |  |  | 6 | 210 | EWP-11-CV-01 | CWP-11-CV-01 | CWA-11 |  |  | 1 | 2027-02-17 | 2027-03-16 |  | 2027-04-06 | 2027-03-29 | -6 | ALP-EPC-00UYA-CV-FND-0001
ALP-EPC-00UYA-EL-ELY-0001 | Administration Building - Earthing and Lightning Protection Layouts |  | EPC | 00UYA | Administration building | electrical | ELY | L | review |  |  | 1 | 20 | EWP-11-EL-01 | CWP-11-EL-01 | CWA-11 |  |  | 3 | 2027-02-17 | 2027-03-29 |  | 2027-04-26 | 2027-11-08 | 140 | capacity electrical
ALP-EPC-00UYA-HS-GAD-0001 | Administration Building - Fire Fighting, Escape Route and Safety Signage Layouts |  | EPC | 00UYA | Administration building | hse | GAD | L | approval |  |  | 4 | 48 | EWP-11-CV-01 | CWP-11-CV-01 | CWA-11 |  |  | 3 | 2027-02-02 | 2027-03-05 | 2027-04-02 | 2027-04-09 | 2027-03-29 | -9 | ALP-EPC-00UYA-CV-ARC-0001
ALP-EPC-00UYA-HV-GAD-0001 | Administration Building - Building Services | plumbing, HVAC ducting, fire fighting | EPC | 00UYA | Administration building | hvac | GAD | L | review |  |  | 20 | 500 | EWP-11-CV-01 | CWP-11-CV-01 | CWA-11 |  |  | 2 | 2027-02-02 | 2027-04-02 |  | 2027-04-30 | 2027-03-29 | -24 | capacity hvac
ALP-EPC-00UYA-IC-ELY-0001 | Administration Building - Fire Detection and Alarm Layouts |  | EPC | 00UYA | Administration building | i_and_c | ELY | L | review |  |  | 6 | 84 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 | MR-IC-006 |  | 2 | 2027-02-02 | 2027-03-09 |  | 2027-04-06 | 2027-11-22 | 164 | ALP-EPC-00UYA-CV-ARC-0001
ALP-EPC-00UYA-SS-STL-0001 | Administration Building - Structural Drawings | concrete / steel | EPC | 00UYA | Administration building | structural | STL | L | approval |  |  | 8 | 280 | EWP-11-SS-01 | CWP-11-SS-01 | CWA-11 |  |  | 3 | 2027-04-07 | 2027-05-14 | 2027-06-11 | 2027-06-18 | 2027-05-24 | -19 | ALP-EPC-00UYA-CV-CAL-0001
ALP-EPC-00UYA-SS-STL-0002 | Administration Building - Steel Structure Drawings |  | EPC | 00UYA | Administration building | structural | STL | L | approval |  |  | 6 | 210 | EWP-11-SS-01 | CWP-11-SS-01 | CWA-11 |  |  | 3 | 2027-04-07 | 2027-05-12 | 2027-06-09 | 2027-06-16 | 2027-05-24 | -17 | ALP-EPC-00UYA-CV-CAL-0001
ALP-EPC-00UZA-CV-CAL-0001 | Roads and Paving - Structural and Foundation Calculation |  | EPC | 00UZA | Roads and paving | civil | CAL | E | review |  |  | 8 | 360 | [5 empty] | 2 | 2027-05-20 | 2027-06-18 |  | 2027-07-09 |  |  | capacity civil
ALP-EPC-00UZA-CV-CVL-0001 | Temporary Facilities and Construction Site Layout | TP-A1 | EPC | 00UZA | Roads and paving | civil | CVL | L | information |  |  | 2 | 50 | EWP-12-CV-01 | CWP-12-CV-01 | CWA-12 |  |  | 1 | 2026-11-02 | 2026-12-01 |  | 2026-12-15 | 2027-01-18 | 24
ALP-EPC-00UZA-CV-CVL-0002 | Roads and Paving - Civil Drawings |  | EPC | 00UZA | Roads and paving | civil | CVL | L | approval |  |  | 30 | 1200 | EWP-12-CV-02 | CWP-12-CV-02 | CWA-12 |  |  | 5 | 2027-01-04 | 2027-03-03 | 2027-03-31 | 2027-04-07 | 2027-03-22 | -12 | capacity civil
ALP-EPC-00UZA-EL-CBL-0001 | Site-Wide Infrastructure - Cable Schedule and Routing |  | EPC | 00UZA | Roads and paving | electrical | CBL | M | information |  |  | 6 | 32 | EWP-12-EL-01 | CWP-12-EL-01 | CWA-12 |  |  | 3 | 2027-03-11 | 2027-04-07 |  | 2027-04-14 | 2027-05-17 | 23 | ALP-EPC-00UZA-EL-ELY-0001
ALP-EPC-00UZA-EL-ELY-0001 | Site-Wide Infrastructure - Electrical Layouts | equipment, trays, earthing, lighting | EPC | 00UZA | Roads and paving | electrical | ELY | L | review |  |  | 4 | 120 | EWP-12-EL-01 | CWP-12-EL-01 | CWA-12 |  |  | 3 | 2027-02-08 | 2027-03-11 |  | 2027-04-08 | 2027-05-17 | 27 | ALP-EPC-00000-EL-STU-0003
ALP-EPC-00UZA-EL-ELY-0002 | Site-Wide Infrastructure - Cable Routing, Tray and Trench Layouts |  | EPC | 00UZA | Roads and paving | electrical | ELY | L | review |  |  | 2 | 50 | EWP-12-EL-01 | CWP-12-EL-01 | CWA-12 |  |  | 2 | 2027-03-11 | 2027-04-09 |  | 2027-05-07 | 2027-05-17 | 6 | ALP-EPC-00UZA-EL-ELY-0001
ALP-EPC-00UZA-EL-ELY-0003 | Roads and Paving - Earthing and Lightning Protection Layouts |  | EPC | 00UZA | Roads and paving | electrical | ELY | L | review |  |  | 10 | 200 | EWP-12-EL-01 | CWP-12-EL-01 | CWA-12 |  |  | 3 | 2027-03-03 | 2027-04-13 |  | 2027-05-11 | 2027-05-17 | 4 | ALP-EPC-00UZA-CV-CVL-0002
ALP-EPC-00UZA-IC-ELY-0001 | Site-Wide Infrastructure - Instrument Location and I&C Cable Routing |  | EPC | 00UZA | Roads and paving | i_and_c | ELY | L | review |  |  | 1 | 16 | EWP-12-PI-01 | CWP-12-PI-01 | CWA-12 |  |  | 2 | 2027-07-06 | 2027-08-03 |  | 2027-08-31 | 2027-07-12 | -36 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UZA-IC-HUP-0001 | Site-Wide Infrastructure - Instrument Hook-Up Drawings |  | EPC | 00UZA | Roads and paving | i_and_c | HUP | M | information |  |  | 2 | 16 | EWP-12-PI-01 | CWP-12-PI-01 | CWA-12 | MR-IC-010 |  | 2 | 2027-07-06 | 2027-07-20 |  | 2027-07-27 | 2027-07-12 | -11 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-00UZA-IC-LOP-0001 | Site-Wide Infrastructure - Junction Box and Cabinet Interconnection Diagrams |  | EPC | 00UZA | Roads and paving | i_and_c | LOP | M | information |  |  | 4 | 10 | EWP-12-PI-01 | CWP-12-PI-01 | CWA-12 |  |  | 2 | 2027-08-03 | 2027-08-26 |  | 2027-09-02 | 2027-07-12 | -38 | ALP-EPC-00UZA-IC-ELY-0001
ALP-EPC-00UZA-IC-LOP-0002 | Site-Wide Infrastructure - Loop and Connection Diagrams |  | EPC | 00UZA | Roads and paving | i_and_c | LOP | M | information |  |  | 30 | 45 | EWP-12-PI-01 | CWP-12-PI-01 | CWA-12 |  |  | 2 | 2027-07-27 | 2027-09-07 |  | 2027-09-14 | 2027-07-12 | -46 | ALP-EPC-00000-IC-IOL-0001
ALP-EPC-00UZA-PI-LAY-0001 | Site-Wide Infrastructure - Equipment Layout |  | EPC | 00UZA | Roads and paving | piping | LAY | L | approval |  |  | 2 | 80 | EWP-12-CV-01 | CWP-12-CV-01 | CWA-12 |  |  | 1 | 2026-11-02 | 2026-12-01 | 2026-12-29 | 2027-01-05 | 2027-01-18 | 9
ALP-EPC-00UZA-PI-PPL-0001 | Site-Wide Infrastructure - Piping General Arrangement |  | EPC | 00UZA | Roads and paving | piping | PPL | L | review |  |  | 14 | 1260 | EWP-12-PI-01 | CWP-12-PI-01 | CWA-12 |  |  | 3 | 2026-12-14 | 2027-02-09 |  | 2027-03-09 | 2027-07-12 | 89 | ALP-EPC-00000-PI-M3D-0001
ALP-EPC-00UZB-CV-CAL-0001 | Fencing and Gates - Structural and Foundation Calculation |  | EPC | 00UZB | Fencing and gates | civil | CAL | E | review |  |  | 2 | 120 | [5 empty] | 2 | 2027-05-21 | 2027-06-14 |  | 2027-07-05 |  |  | capacity civil
ALP-EPC-00UZB-CV-CVL-0001 | Fencing and Gates - Civil Drawings |  | EPC | 00UZB | Fencing and gates | civil | CVL | L | information |  |  | 6 | 240 | EWP-12-CV-01 | CWP-12-CV-01 | CWA-12 |  |  | 4 | 2027-01-04 | 2027-02-08 |  | 2027-02-22 | 2027-01-18 | -25 | ALP-EPC-00000-CV-RPT-0001
ALP-EPC-00UZB-EL-ELY-0001 | Fencing and Gates - Earthing and Lightning Protection Layouts |  | EPC | 00UZB | Fencing and gates | electrical | ELY | L | review |  |  | 2 | 40 | EWP-12-EL-01 | CWP-12-EL-01 | CWA-12 |  |  | 3 | 2027-02-08 | 2027-03-09 |  | 2027-04-06 | 2027-05-17 | 29 | ALP-EPC-00UZB-CV-CVL-0001
ALP-EPC-00UZC-CV-CAL-0001 | Site Drainage and Culverts - Structural and Foundation Calculation |  | EPC | 00UZC | Site drainage and culverts | civil | CAL | E | review |  |  | 8 | 360 | [5 empty] | 2 | 2027-05-21 | 2027-06-18 |  | 2027-07-09 |  |  | capacity civil
ALP-EPC-00UZC-CV-CVL-0001 | Site Drainage and Culverts - Civil Drawings |  | EPC | 00UZC | Site drainage and culverts | civil | CVL | L | approval |  |  | 30 | 1200 | EWP-12-CV-02 | CWP-12-CV-02 | CWA-12 |  |  | 4 | 2027-01-04 | 2027-03-08 | 2027-04-05 | 2027-04-12 | 2027-03-22 | -15 | capacity civil
ALP-EPC-00UZC-CV-RBR-0001 | Site Drainage and Culverts - Reinforcement Drawings |  | EPC | 00UZC | Site drainage and culverts | civil | RBR | L | review |  |  | 6 | 210 | EWP-12-CV-02 | CWP-12-CV-02 | CWA-12 |  |  | 1 | 2027-04-07 | 2027-05-31 |  | 2027-06-21 | 2027-03-22 | -65 | capacity civil
ALP-EPC-00UZC-EL-ELY-0001 | Site Drainage and Culverts - Earthing and Lightning Protection Layouts |  | EPC | 00UZC | Site drainage and culverts | electrical | ELY | L | review |  |  | 10 | 200 | EWP-12-EL-01 | CWP-12-EL-01 | CWA-12 |  |  | 3 | 2027-03-08 | 2027-04-16 |  | 2027-05-14 | 2027-05-17 | 1 | ALP-EPC-00UZC-CV-CVL-0001
ALP-EPC-00UZD-CV-CAL-0001 | Pipe Racks and Pipe Sleepers - Structural and Foundation Calculation |  | EPC | 00UZD | Pipe racks and pipe sleepers | civil | CAL | E | review |  |  | 4 | 200 | [5 empty] | 2 | 2027-01-18 | 2027-02-10 |  | 2027-03-03 |  |  | ALP-EPC-00000-CV-CAL-0001
ALP-EPC-00UZD-CV-FND-0001 | Pipe Racks and Pipe Sleepers - Foundation and Underground Drawings |  | EPC | 00UZD | Pipe racks and pipe sleepers | civil | FND | L | approval |  |  | 14 | 700 | EWP-12-CV-02 | CWP-12-CV-02 | CWA-12 |  |  | 3 | 2027-02-08 | 2027-04-16 | 2027-05-14 | 2027-05-21 | 2027-03-22 | -44 | capacity civil
ALP-EPC-00UZD-CV-RBR-0001 | Pipe Racks and Pipe Sleepers - Reinforcement Drawings |  | EPC | 00UZD | Pipe racks and pipe sleepers | civil | RBR | L | review |  |  | 10 | 350 | EWP-12-CV-02 | CWP-12-CV-02 | CWA-12 |  |  | 1 | 2027-04-16 | 2027-05-28 |  | 2027-06-18 | 2027-03-22 | -64 | capacity civil
ALP-EPC-00UZD-EL-ELY-0001 | Pipe Racks and Pipe Sleepers - Earthing and Lightning Protection Layouts |  | EPC | 00UZD | Pipe racks and pipe sleepers | electrical | ELY | L | review |  |  | 5 | 100 | EWP-12-EL-01 | CWP-12-EL-01 | CWA-12 |  |  | 3 | 2027-04-16 | 2027-05-20 |  | 2027-06-17 | 2027-05-17 | -23 | ALP-EPC-00UZD-CV-FND-0001
ALP-EPC-00UZD-SS-STL-0001 | Pipe Racks and Pipe Sleepers - Steel Structure Drawings |  | EPC | 00UZD | Pipe racks and pipe sleepers | structural | STL | L | approval |  |  | 40 | 1400 | EWP-12-CV-02 | CWP-12-CV-02 | CWA-12 |  |  | 3 | 2027-02-10 | 2027-04-07 | 2027-05-05 | 2027-05-12 | 2027-03-22 | -37 | ALP-EPC-00UZD-CV-CAL-0001
ALP-EPC-00UZE-CV-CAL-0001 | Cable Trenches and Duct Banks - Structural and Foundation Calculation |  | EPC | 00UZE | Cable trenches and duct banks | civil | CAL | E | review |  |  | 5 | 240 | [5 empty] | 2 | 2027-05-27 | 2027-06-22 |  | 2027-07-13 |  |  | capacity civil
ALP-EPC-00UZE-CV-CVL-0001 | Cable Trenches and Duct Banks - Civil Drawings |  | EPC | 00UZE | Cable trenches and duct banks | civil | CVL | L | approval |  |  | 20 | 800 | EWP-12-CV-02 | CWP-12-CV-02 | CWA-12 |  |  | 4 | 2027-01-11 | 2027-03-18 | 2027-04-15 | 2027-04-22 | 2027-03-22 | -23 | capacity civil
ALP-EPC-00UZE-CV-RBR-0001 | Cable Trenches and Duct Banks - Reinforcement Drawings |  | EPC | 00UZE | Cable trenches and duct banks | civil | RBR | L | review |  |  | 10 | 350 | EWP-12-CV-02 | CWP-12-CV-02 | CWA-12 |  |  | 1 | 2027-04-06 | 2027-05-24 |  | 2027-06-14 | 2027-03-22 | -60 | capacity civil
ALP-EPC-00UZE-EL-ELY-0001 | Cable Trenches and Duct Banks - Earthing and Lightning Protection Layouts |  | EPC | 00UZE | Cable trenches and duct banks | electrical | ELY | L | review |  |  | 7 | 140 | EWP-12-EL-01 | CWP-12-EL-01 | CWA-12 |  |  | 3 | 2027-03-18 | 2027-04-23 |  | 2027-05-21 | 2027-05-17 | -4 | ALP-EPC-00UZE-CV-CVL-0001
ALP-EPC-00UZF-CV-CAL-0001 | Temporary Barge Landing - Structural and Foundation Calculation |  | EPC | 00UZF | Temporary barge landing | civil | CAL | E | review |  |  | 2 | 120 | [5 empty] | 2 | 2027-05-18 | 2027-06-09 |  | 2027-06-30 |  |  | capacity civil
ALP-EPC-00UZF-CV-FND-0001 | Temporary Barge Landing - Foundation and Underground Drawings |  | EPC | 00UZF | Temporary barge landing | civil | FND | L | approval |  |  | 8 | 400 | EWP-06-CV-01 | CWP-06-CV-01 | CWA-06 |  |  | 4 | 2027-05-31 | 2027-07-07 | 2027-08-04 | 2027-08-11 | 2027-09-03 | 17 | ALP-EPC-00UZF-CV-FND-0002
ALP-EPC-00UZF-CV-FND-0002 | Temporary Barge Landing - Piling Layout and Pile Schedule |  | EPC | 00UZF | Temporary barge landing | civil | FND | L | approval |  |  | 2 | 80 | EWP-06-CV-01 | CWP-06-CV-01 | CWA-06 |  |  | 3 | 2027-04-07 | 2027-05-31 | 2027-06-28 | 2027-07-05 | 2027-09-03 | 44 | capacity civil
ALP-EPC-00UZF-CV-RBR-0001 | Temporary Barge Landing - Reinforcement Drawings |  | EPC | 00UZF | Temporary barge landing | civil | RBR | L | review |  |  | 6 | 210 | EWP-06-CV-01 | CWP-06-CV-01 | CWA-06 |  |  | 1 | 2027-07-07 | 2027-08-03 |  | 2027-08-24 | 2027-09-03 | 8 | ALP-EPC-00UZF-CV-FND-0001
ALP-EPC-00UZF-CV-RPT-0001 | Temporary Barge Landing Design Report and Removal Plan |  | EPC | 00UZF | Temporary barge landing | civil | RPT | D | review |  |  | 1 | 160 | [5 empty] | 2 | 2027-05-18 | 2027-06-08 |  | 2027-06-29 |  |  | capacity civil
ALP-EPC-00UZF-EL-ELY-0001 | Temporary Barge Landing - Earthing and Lightning Protection Layouts |  | EPC | 00UZF | Temporary barge landing | electrical | ELY | L | review |  |  | 3 | 60 | EWP-06-CV-01 | CWP-06-CV-01 | CWA-06 |  |  | 3 | 2027-07-07 | 2027-08-06 |  | 2027-09-03 | 2027-09-03 | 0 | ALP-EPC-00UZF-CV-FND-0001
ALP-EPC-00UZF-GE-MRQ-0001 | Heavy Transport, Barge Landing and Marine Logistics - Material Requisition | subcontract | EPC | 00UZF | Temporary barge landing | general | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-ME-024 |  | 1 | 2027-07-06 | 2027-07-13 |  | 2027-07-16 |  |  | ALP-EPC-00UZF-GE-SPC-0001
ALP-EPC-00UZF-GE-RPT-0001 | Heavy Transport, Barge Landing and Marine Logistics - Technical Bid Evaluation | subcontract | EPC | 00UZF | Temporary barge landing | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-024 |  | 1 | 2027-08-27 | 2027-09-17 |  | 2027-09-24 |  |  | bids MR-ME-024
ALP-EPC-00UZF-GE-SPC-0001 | Heavy Transport, Barge Landing and Marine Logistics - Technical Specification | subcontract | EPC | 00UZF | Temporary barge landing | general | SPC | E | approval |  |  | 1 | 80 |  |  |  | MR-ME-024 |  | 4 | 2027-06-08 | 2027-07-06 | 2027-08-03 | 2027-08-10 |  |  | ALP-EPC-00UZF-CV-RPT-0001
ALP-EPC-00UZF-SS-STL-0001 | Temporary Barge Landing - Steel Structure Drawings |  | EPC | 00UZF | Temporary barge landing | structural | STL | L | approval |  |  | 4 | 140 | EWP-06-CV-01 | CWP-06-CV-01 | CWA-06 |  |  | 3 | 2027-06-09 | 2027-07-12 | 2027-08-09 | 2027-08-16 | 2027-09-03 | 14 | ALP-EPC-00UZF-CV-CAL-0001
ALP-EPC-00XJA-CM-CMP-0001 | Emergency Diesel Generator - System Commissioning Procedure |  | EPC | 00XJA | Emergency diesel generator | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2026-12-28 | 2027-01-25 | 2027-02-22 | 2027-03-01 |  |  | capacity commissioning
ALP-EPC-00XJA-CM-MDB-0001 | Emergency Diesel Generator - System Turnover Dossier |  | EPC | 00XJA | Emergency diesel generator | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-01-04 | 2028-01-18 |  | 2028-01-25 |  |  | as late as possible (need)
ALP-EPC-00XJA-CM-OMM-0001 | Emergency Diesel Generator - Operating Procedures | English / Turkish | EPC | 00XJA | Emergency diesel generator | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-01-25 | 2027-03-08 |  | 2027-04-05 |  |  | ALP-EPC-00XJA-CM-CMP-0001
ALP-EPC-00XJA-EL-DSH-0001 | Emergency Diesel Generator - Datasheet |  | EPC | 00XJA | Emergency diesel generator | electrical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-EL-006 | 00XJA10 | 2 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-00XJA-EL-ITP-0001 | Emergency Diesel Generator - Inspection and Test Plan |  | EPC | 00XJA | Emergency diesel generator | electrical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-EL-006 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-00XJA-EL-MRQ-0001 | Emergency Diesel Generator - Material Requisition |  | EPC | 00XJA | Emergency diesel generator | electrical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-EL-006 |  | 3 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-00XJA-EL-SPC-0001 | Emergency Diesel Generator - Technical Specification |  | EPC | 00XJA | Emergency diesel generator | electrical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-EL-006 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-00XJA-GE-RPT-0001 | Emergency Diesel Generator - Technical Bid Evaluation |  | EPC | 00XJA | Emergency diesel generator | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-EL-006 |  | 1 | 2026-12-17 | 2027-01-07 |  | 2027-01-14 |  |  | bids MR-EL-006
ALP-EPC-00XJA-IC-DSH-0001 | Emergency Diesel Generator - Instrument Datasheets |  | EPC | 00XJA | Emergency diesel generator | i_and_c | DSH | E | approval |  |  | 20 | 38 |  |  |  | MR-IC-004 |  | 1 | 2027-01-18 | 2027-02-15 | 2027-03-08 | 2027-03-15 |  |  | capacity i_and_c
ALP-EPC-00XJA-IC-LOG-0001 | Emergency Diesel Generator - Logic Diagrams |  | EPC | 00XJA | Emergency diesel generator | i_and_c | LOG | F | approval |  |  | 11 | 104 | [5 empty] | 1 | 2027-01-18 | 2027-10-08 | 2027-11-05 | 2027-11-12 |  |  | capacity i_and_c
ALP-EPC-00XJA-ME-DSH-0001 | Emergency Diesel Generator: Tank - Datasheet |  | EPC | 00XJA | Emergency diesel generator | mechanical | DSH | E | approval |  |  | 1 | 16 |  |  |  | MR-EL-006 | 00XJA10BB001 | 2 | 2027-02-08 | 2027-02-22 | 2027-03-15 | 2027-03-22 |  |  | ALP-EPC-00000-ME-DBR-0001
ALP-EPC-10BAA-CM-MDB-0001 | GT Generator Busduct - System Turnover Dossier |  | EPC | 10BAA | GT generator busduct | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-01-04 | 2028-01-18 |  | 2028-01-25 |  |  | as late as possible (need)
ALP-EPC-10BAC-CM-MDB-0001 | GT Generator Circuit Breaker - System Turnover Dossier |  | EPC | 10BAC | GT generator circuit breaker | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-01-04 | 2028-01-18 |  | 2028-01-25 |  |  | as late as possible (need)
ALP-EPC-10BAT-CM-MDB-0001 | GT Generator Step-Up Transformer - System Turnover Dossier |  | EPC | 10BAT | GT generator step-up transformer | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-01-04 | 2028-01-18 |  | 2028-01-25 |  |  | as late as possible (need)
ALP-EPC-10BBT-CM-CMP-0001 | GT Unit Auxiliary Transformer - System Commissioning Procedure |  | EPC | 10BBT | GT unit auxiliary transformer | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2026-12-28 | 2027-01-25 | 2027-02-22 | 2027-03-01 |  |  | capacity commissioning
ALP-EPC-10BBT-CM-MDB-0001 | GT Unit Auxiliary Transformer - System Turnover Dossier |  | EPC | 10BBT | GT unit auxiliary transformer | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-01-04 | 2028-01-18 |  | 2028-01-25 |  |  | as late as possible (need)
ALP-EPC-10BBT-CM-OMM-0001 | GT Unit Auxiliary Transformer - Operating Procedures | English / Turkish | EPC | 10BBT | GT unit auxiliary transformer | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-01-25 | 2027-03-08 |  | 2027-04-05 |  |  | ALP-EPC-10BBT-CM-CMP-0001
ALP-EPC-10BBT-EL-DSH-0001 | GT Unit Auxiliary Transformer - Datasheet |  | EPC | 10BBT | GT unit auxiliary transformer | electrical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-EL-002 | 10BBT10 | 2 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-10BBT-EL-ITP-0001 | Unit Auxiliary Transformers - Inspection and Test Plan |  | EPC | 10BBT | GT unit auxiliary transformer | electrical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-EL-002 |  | 1 | 2026-11-06 | 2026-11-20 | 2026-12-11 | 2026-12-18 |  |  | capacity electrical
ALP-EPC-10BBT-EL-MRQ-0001 | Unit Auxiliary Transformers - Material Requisition |  | EPC | 10BBT | GT unit auxiliary transformer | electrical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-EL-002 |  | 3 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-10BBT-EL-SPC-0001 | Unit Auxiliary Transformers - Technical Specification |  | EPC | 10BBT | GT unit auxiliary transformer | electrical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-EL-002 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-10BBT-GE-RPT-0001 | Unit Auxiliary Transformers - Technical Bid Evaluation |  | EPC | 10BBT | GT unit auxiliary transformer | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-EL-002 |  | 1 | 2027-01-14 | 2027-02-09 |  | 2027-02-16 |  |  | capacity general
ALP-EPC-10BBT-IC-DSH-0001 | GT Unit Auxiliary Transformer - Instrument Datasheets |  | EPC | 10BBT | GT unit auxiliary transformer | i_and_c | DSH | E | approval |  |  | 10 | 23 |  |  |  | MR-IC-004 |  | 1 | 2027-01-18 | 2027-02-09 | 2027-03-02 | 2027-03-09 |  |  | capacity i_and_c
ALP-EPC-10BBT-IC-LOG-0001 | GT Unit Auxiliary Transformer - Logic Diagrams |  | EPC | 10BBT | GT unit auxiliary transformer | i_and_c | LOG | F | approval |  |  | 8 | 80 | [5 empty] | 1 | 2027-01-25 | 2027-04-21 | 2027-05-19 | 2027-05-26 |  |  | capacity i_and_c
ALP-EPC-10HAA-CM-MDB-0001 | HRSG Pressure System - System Turnover Dossier |  | EPC | 10HAA | HRSG pressure system | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-04-17 | 2028-05-01 |  | 2028-05-08 |  |  | capacity commissioning
ALP-EPC-10HAN-CM-CMP-0001 | HRSG Blowdown and Drains - System Commissioning Procedure | EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-08-05 | 2027-09-02 | 2027-09-30 | 2027-10-07 |  |  | capacity commissioning
ALP-EPC-10HAN-CM-MDB-0001 | HRSG Blowdown and Drains - System Turnover Dossier | EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-05-22 | 2028-06-05 |  | 2028-06-12 |  |  | as late as possible (need)
ALP-EPC-10HAN-CM-OMM-0001 | HRSG Blowdown and Drains - Operating Procedures | English / Turkish; EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-09-07 | 2027-10-19 |  | 2027-11-16 |  |  | capacity commissioning
ALP-EPC-10HAN-GE-RPT-0001 | HRSG Blowdown and Drain Tanks - Technical Bid Evaluation |  | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-019 |  | 1 | 2026-12-03 | 2027-02-05 |  | 2027-02-12 |  |  | capacity general
ALP-EPC-10HAN-IC-CEM-0001 | HRSG Blowdown and Drains - Cause and Effect Matrix | EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | i_and_c | CEM | F | approval |  |  | 1 | 28 | [5 empty] | 2 | 2027-09-07 | 2027-10-15 | 2027-11-12 | 2027-11-19 |  |  | capacity i_and_c
ALP-EPC-10HAN-IC-CNR-0001 | HRSG Blowdown and Drains - Control Narrative | EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-05-27 | 2027-06-17 |  | 2027-07-15 |  |  | ALP-EPC-10HAN-PR-PID-0001
ALP-EPC-10HAN-IC-DSH-0001 | HRSG Blowdown and Drains - Instrument Datasheets | EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | i_and_c | DSH | E | approval |  |  | 25 | 45.5 |  |  |  | MR-IC-004 |  | 2 | 2027-10-05 | 2027-11-02 | 2027-11-23 | 2027-11-30 |  |  | capacity i_and_c
ALP-EPC-10HAN-IC-DSH-0002 | HRSG Blowdown and Drains - Control Valve Sizing and Datasheets | EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | i_and_c | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-IC-005 |  | 3 | 2027-10-05 | 2027-10-19 | 2027-11-09 | 2027-11-16 |  |  | capacity i_and_c
ALP-EPC-10HAN-IC-HMI-0001 | HRSG Blowdown and Drains - Operator Displays | HMI graphics; EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-10-05 | 2027-10-27 |  | 2027-11-17 |  |  | capacity i_and_c
ALP-EPC-10HAN-IC-LOG-0001 | HRSG Blowdown and Drains - Logic Diagrams | EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | i_and_c | LOG | F | approval |  |  | 13 | 120 | [5 empty] | 3 | 2027-10-08 | 2027-11-23 | 2027-12-21 | 2027-12-28 |  |  | capacity i_and_c
ALP-EPC-10HAN-ME-CAL-0001 | HRSG Blowdown and Drains - Sizing and Hydraulic Calculation | EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | CAL | E | review |  |  | 6 | 78 | [5 empty] | 2 | 2027-02-04 | 2027-03-19 |  | 2027-04-09 |  |  | capacity mechanical
ALP-EPC-10HAN-ME-DSH-0001 | HRSG Blowdown and Drains - Datasheet | EPC tanks and headers; 2 items | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | DSH | E | approval |  | yes | 2 | 26 |  |  |  | MR-ME-019 | 10HAN10BB001 10HAN10BB002 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-10HAN-ME-DSH-0002 | HRSG Blowdown and Drains: Pumps - Datasheet | EPC tanks and headers; 2 items | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | DSH | E | approval |  |  | 2 | 26 |  |  |  | MR-ME-019 | 10HAN10AP001 10HAN10AP002 | 3 | 2027-03-19 | 2027-04-02 | 2027-04-23 | 2027-04-30 |  |  | ALP-EPC-10HAN-ME-CAL-0001
ALP-EPC-10HAN-ME-ITP-0001 | HRSG Blowdown and Drain Tanks - Inspection and Test Plan |  | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-019 |  | 1 | 2026-11-11 | 2026-11-25 | 2026-12-16 | 2026-12-23 |  |  | capacity mechanical
ALP-EPC-10HAN-ME-MRQ-0001 | HRSG Blowdown and Drain Tanks - Material Requisition |  | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-019 |  | 3 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-10HAN-ME-SPC-0001 | HRSG Blowdown and Drain Tanks - Technical Specification |  | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-019 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-10HAN-PI-ISO-0001 | HRSG Blowdown and Drains - Isometric Drawings | EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | piping | ISO | L | information |  |  | 80 | 800 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 |  |  | 4 | 2027-10-12 | 2027-12-08 |  | 2027-12-15 | 2027-12-13 | -2 | capacity piping
ALP-EPC-10HAN-PI-STR-0001 | HRSG Blowdown and Drains - Pipe Stress Analysis | EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | piping | STR | E | review |  |  | 2 | 140 | [5 empty] | 2 | 2027-07-19 | 2027-08-17 |  | 2027-09-07 |  |  | capacity piping
ALP-EPC-10HAN-PI-SUP-0001 | HRSG Blowdown and Drains - Pipe Support Drawings | EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | piping | SUP | L | information |  |  | 20 | 120 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 | MR-PI-005 |  | 2 | 2027-12-15 | 2028-01-25 |  | 2028-02-01 | 2027-12-13 | -36 | ALP-EPC-10HAN-PI-ISO-0001
ALP-EPC-10HAN-PR-DSH-0001 | HRSG Blowdown and Drains - Safety / Relief Valve Sizing and Datasheets | EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | process | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-PI-007 |  | 2 | 2027-06-14 | 2027-06-28 | 2027-07-19 | 2027-07-26 |  |  | capacity process
ALP-EPC-10HAN-PR-PID-0001 | HRSG Blowdown and Drains - P&ID | EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | process | PID | F | approval |  |  | 2 | 220 | [5 empty] | 3 | 2027-04-06 | 2027-05-27 | 2027-07-01 | 2027-07-08 |  |  | capacity process
ALP-EPC-10HAN-PR-SDS-0001 | HRSG Blowdown and Drains - System Design Description | EPC tanks and headers | EPC | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-10HNA-CM-MDB-0001 | HRSG Flue Gas Ducting - System Turnover Dossier |  | EPC | 10HNA | HRSG flue gas ducting | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-04-17 | 2028-05-01 |  | 2028-05-08 |  |  | capacity commissioning
ALP-EPC-10HNE-CM-CMP-0001 | Stack 65 m with CEMS Platform and Silencer - System Commissioning Procedure |  | EPC | 10HNE | Stack 65 m with CEMS platform and silencer | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2027-02-08 | 2027-03-08 | 2027-04-05 | 2027-04-12 |  |  | capacity commissioning
ALP-EPC-10HNE-CM-MDB-0001 | Stack 65 m with CEMS Platform and Silencer - System Turnover Dossier |  | EPC | 10HNE | Stack 65 m with CEMS platform and silencer | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-17 | 2028-05-01 |  | 2028-05-08 |  |  | capacity commissioning
ALP-EPC-10HNE-GE-RPT-0001 | Stack 65 m with Silencer - Technical Bid Evaluation |  | EPC | 10HNE | Stack 65 m with CEMS platform and silencer | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-SS-002 |  | 1 | 2027-01-07 | 2027-01-28 |  | 2027-02-04 |  |  | capacity general
ALP-EPC-10HNE-IC-DSH-0001 | Stack 65 m with CEMS Platform and Silencer - Instrument Datasheets |  | EPC | 10HNE | Stack 65 m with CEMS platform and silencer | i_and_c | DSH | E | approval |  |  | 20 | 38 |  |  |  | MR-IC-004 |  | 1 | 2027-01-19 | 2027-02-19 | 2027-03-12 | 2027-03-19 |  |  | capacity i_and_c
ALP-EPC-10HNE-IC-LOG-0001 | Stack 65 m with CEMS Platform and Silencer - Logic Diagrams |  | EPC | 10HNE | Stack 65 m with CEMS platform and silencer | i_and_c | LOG | F | approval |  |  | 11 | 104 | [5 empty] | 1 | 2027-01-25 | 2027-10-22 | 2027-11-19 | 2027-11-26 |  |  | capacity i_and_c
ALP-EPC-10HNE-ME-DSH-0001 | Stack 65 m with CEMS Platform and Silencer - Datasheet |  | EPC | 10HNE | Stack 65 m with CEMS platform and silencer | mechanical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-SS-002 | 10HNE10 | 2 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-10HNE-SS-MRQ-0001 | Stack 65 m with Silencer - Material Requisition |  | EPC | 10HNE | Stack 65 m with CEMS platform and silencer | structural | MRQ | C | information |  |  | 1 | 24 |  |  |  | MR-SS-002 |  | 2 | 2026-11-02 | 2026-11-09 |  | 2026-11-12
ALP-EPC-10HNE-SS-SPC-0001 | Stack 65 m with Silencer - Technical Specification |  | EPC | 10HNE | Stack 65 m with CEMS platform and silencer | structural | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-SS-002 |  | 2 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-10HSA-CM-MDB-0001 | SCR Catalyst and Ammonia Injection - System Turnover Dossier |  | EPC | 10HSA | SCR catalyst and ammonia injection | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-04-17 | 2028-05-01 |  | 2028-05-08 |  |  | capacity commissioning
ALP-EPC-10HSB-CM-CMP-0001 | Ammonia Storage and Supply - System Commissioning Procedure |  | EPC | 10HSB | Ammonia storage and supply | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-07-02 | 2027-07-30 | 2027-08-27 | 2027-09-03 |  |  | ALP-EPC-10HSB-IC-CNR-0001
ALP-EPC-10HSB-CM-MDB-0001 | Ammonia Storage and Supply - System Turnover Dossier |  | EPC | 10HSB | Ammonia storage and supply | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-04-17 | 2028-05-01 |  | 2028-05-08 |  |  | capacity commissioning
ALP-EPC-10HSB-CM-OMM-0001 | Ammonia Storage and Supply - Operating Procedures | English / Turkish | EPC | 10HSB | Ammonia storage and supply | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-07-30 | 2027-09-10 |  | 2027-10-08 |  |  | ALP-EPC-10HSB-CM-CMP-0001
ALP-EPC-10HSB-GE-RPT-0001 | Aqueous Ammonia Storage and Forwarding - Technical Bid Evaluation |  | EPC | 10HSB | Ammonia storage and supply | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-018 |  | 1 | 2027-01-28 | 2027-02-18 |  | 2027-02-25 |  |  | capacity general
ALP-EPC-10HSB-IC-CEM-0001 | Ammonia Storage and Supply - Cause and Effect Matrix |  | EPC | 10HSB | Ammonia storage and supply | i_and_c | CEM | F | approval |  |  | 2 | 40 | [5 empty] | 2 | 2027-10-12 | 2027-11-03 | 2027-12-01 | 2027-12-08 |  |  | capacity i_and_c
ALP-EPC-10HSB-IC-CNR-0001 | Ammonia Storage and Supply - Control Narrative |  | EPC | 10HSB | Ammonia storage and supply | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-06-11 | 2027-07-02 |  | 2027-07-30 |  |  | ALP-EPC-10HSB-PR-PID-0001
ALP-EPC-10HSB-IC-DSH-0001 | Ammonia Storage and Supply - Instrument Datasheets |  | EPC | 10HSB | Ammonia storage and supply | i_and_c | DSH | E | approval |  |  | 40 | 68 |  |  |  | MR-IC-004 |  | 2 | 2027-10-13 | 2027-11-10 | 2027-12-01 | 2027-12-08 |  |  | capacity i_and_c
ALP-EPC-10HSB-IC-DSH-0002 | Ammonia Storage and Supply - Control Valve Sizing and Datasheets |  | EPC | 10HSB | Ammonia storage and supply | i_and_c | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-IC-005 |  | 3 | 2027-10-13 | 2027-10-27 | 2027-11-17 | 2027-11-24 |  |  | capacity i_and_c
ALP-EPC-10HSB-IC-HMI-0001 | Ammonia Storage and Supply - Operator Displays | HMI graphics | EPC | 10HSB | Ammonia storage and supply | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-10-13 | 2027-11-04 |  | 2027-11-25 |  |  | capacity i_and_c
ALP-EPC-10HSB-IC-LOG-0001 | Ammonia Storage and Supply - Logic Diagrams |  | EPC | 10HSB | Ammonia storage and supply | i_and_c | LOG | F | approval |  |  | 23 | 200 | [5 empty] | 3 | 2027-10-14 | 2027-12-09 | 2028-01-06 | 2028-01-13 |  |  | capacity i_and_c
ALP-EPC-10HSB-ME-CAL-0001 | Ammonia Storage and Supply - Sizing and Hydraulic Calculation |  | EPC | 10HSB | Ammonia storage and supply | mechanical | CAL | E | review |  |  | 5 | 70 | [5 empty] | 2 | 2027-02-02 | 2027-02-26 |  | 2027-03-19 |  |  | capacity mechanical
ALP-EPC-10HSB-ME-DSH-0001 | Ammonia Storage and Supply: Tanks - Datasheet | 2 items | EPC | 10HSB | Ammonia storage and supply | mechanical | DSH | E | approval |  | yes | 2 | 26 |  |  |  | MR-ME-018 | 10HSB10BB001 10HSB10BB002 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-10HSB-ME-DSH-0002 | Ammonia Storage and Supply: Pumps - Datasheet | 2 items | EPC | 10HSB | Ammonia storage and supply | mechanical | DSH | E | approval |  | yes | 2 | 26 |  |  |  | MR-ME-018 | 10HSB10AP001 10HSB10AP002 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-10HSB-ME-ITP-0001 | Aqueous Ammonia Storage and Forwarding - Inspection and Test Plan |  | EPC | 10HSB | Ammonia storage and supply | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-018 |  | 1 | 2026-11-06 | 2026-11-20 | 2026-12-11 | 2026-12-18 |  |  | capacity mechanical
ALP-EPC-10HSB-ME-MRQ-0001 | Aqueous Ammonia Storage and Forwarding - Material Requisition |  | EPC | 10HSB | Ammonia storage and supply | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-018 |  | 3 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-10HSB-ME-SPC-0001 | Aqueous Ammonia Storage and Forwarding - Technical Specification |  | EPC | 10HSB | Ammonia storage and supply | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-018 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-10HSB-PI-ISO-0001 | Ammonia Storage and Supply - Isometric Drawings |  | EPC | 10HSB | Ammonia storage and supply | piping | ISO | L | information |  |  | 60 | 600 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 |  |  | 5 | 2027-10-05 | 2027-11-30 |  | 2027-12-07 | 2027-12-13 | 4 | capacity piping
ALP-EPC-10HSB-PI-SUP-0001 | Ammonia Storage and Supply - Pipe Support Drawings |  | EPC | 10HSB | Ammonia storage and supply | piping | SUP | L | information |  |  | 15 | 90 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 | MR-PI-005 |  | 1 | 2027-12-09 | 2028-01-14 |  | 2028-01-21 | 2027-12-13 | -29 | capacity piping
ALP-EPC-10HSB-PR-DSH-0001 | Ammonia Storage and Supply - Safety / Relief Valve Sizing and Datasheets |  | EPC | 10HSB | Ammonia storage and supply | process | DSH | E | approval |  |  | 4 | 32 |  |  |  | MR-PI-007 |  | 2 | 2027-06-14 | 2027-06-30 | 2027-07-21 | 2027-07-28 |  |  | capacity process
ALP-EPC-10HSB-PR-PID-0001 | Ammonia Storage and Supply - P&ID |  | EPC | 10HSB | Ammonia storage and supply | process | PID | F | approval |  |  | 2 | 220 | [5 empty] | 3 | 2027-05-06 | 2027-06-11 | 2027-07-16 | 2027-07-23 |  |  | capacity process
ALP-EPC-10HSB-PR-SDS-0001 | Ammonia Storage and Supply - System Design Description |  | EPC | 10HSB | Ammonia storage and supply | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-10LAB-CM-CMP-0001 | Feedwater Piping - System Commissioning Procedure |  | EPC | 10LAB | Feedwater piping | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-08-06 | 2027-09-03 | 2027-10-01 | 2027-10-08 |  |  | capacity commissioning
ALP-EPC-10LAB-CM-MDB-0001 | Feedwater Piping - System Turnover Dossier |  | EPC | 10LAB | Feedwater piping | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-05-22 | 2028-06-05 |  | 2028-06-12 |  |  | as late as possible (need)
ALP-EPC-10LAB-CM-OMM-0001 | Feedwater Piping - Operating Procedures | English / Turkish | EPC | 10LAB | Feedwater piping | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-09-07 | 2027-10-19 |  | 2027-11-16 |  |  | capacity commissioning
ALP-EPC-10LAB-IC-CEM-0001 | Feedwater Piping - Cause and Effect Matrix |  | EPC | 10LAB | Feedwater piping | i_and_c | CEM | F | approval |  |  | 1 | 28 | [5 empty] | 2 | 2027-10-13 | 2027-11-04 | 2027-12-02 | 2027-12-09 |  |  | capacity i_and_c
ALP-EPC-10LAB-IC-CNR-0001 | Feedwater Piping - Control Narrative |  | EPC | 10LAB | Feedwater piping | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-06-11 | 2027-07-02 |  | 2027-07-30 |  |  | ALP-EPC-10LAB-PR-PID-0001
ALP-EPC-10LAB-IC-DSH-0001 | Feedwater Piping - Instrument Datasheets |  | EPC | 10LAB | Feedwater piping | i_and_c | DSH | E | approval |  |  | 40 | 68 |  |  |  | MR-IC-004 |  | 2 | 2027-10-15 | 2027-11-12 | 2027-12-03 | 2027-12-10 |  |  | capacity i_and_c
ALP-EPC-10LAB-IC-DSH-0002 | Feedwater Piping - Control Valve Sizing and Datasheets |  | EPC | 10LAB | Feedwater piping | i_and_c | DSH | E | approval |  |  | 4 | 32 |  |  |  | MR-IC-005 |  | 3 | 2027-10-18 | 2027-11-03 | 2027-11-24 | 2027-12-01 |  |  | capacity i_and_c
ALP-EPC-10LAB-IC-HMI-0001 | Feedwater Piping - Operator Displays | HMI graphics | EPC | 10LAB | Feedwater piping | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-10-15 | 2027-11-08 |  | 2027-11-29 |  |  | capacity i_and_c
ALP-EPC-10LAB-IC-LOG-0001 | Feedwater Piping - Logic Diagrams |  | EPC | 10LAB | Feedwater piping | i_and_c | LOG | F | approval |  |  | 14 | 128 | [5 empty] | 3 | 2027-10-21 | 2027-12-07 | 2028-01-04 | 2028-01-11 |  |  | capacity i_and_c
ALP-EPC-10LAB-ME-CAL-0001 | Feedwater Piping - Sizing and Hydraulic Calculation |  | EPC | 10LAB | Feedwater piping | mechanical | CAL | E | review |  |  | 3 | 54 | [5 empty] | 2 | 2027-03-04 | 2027-03-26 |  | 2027-04-16 |  |  | capacity mechanical
ALP-EPC-10LAB-PI-ISO-0001 | Feedwater Piping - Isometric Drawings |  | EPC | 10LAB | Feedwater piping | piping | ISO | L | information |  |  | 110 | 1100 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 |  |  | 6 | 2027-08-25 | 2027-10-26 |  | 2027-11-02 | 2027-12-13 | 29 | capacity piping
ALP-EPC-10LAB-PI-STR-0001 | Feedwater Piping - Pipe Stress Analysis |  | EPC | 10LAB | Feedwater piping | piping | STR | E | review |  |  | 4 | 260 | [5 empty] | 5 | 2027-07-19 | 2027-08-19 |  | 2027-09-09 |  |  | ALP-EPC-00UQA-PI-PPL-0003
ALP-EPC-10LAB-PI-SUP-0001 | Feedwater Piping - Pipe Support Drawings |  | EPC | 10LAB | Feedwater piping | piping | SUP | L | information |  |  | 28 | 168 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 | MR-PI-005 |  | 2 | 2027-12-08 | 2028-01-19 |  | 2028-01-26 | 2027-12-13 | -32 | capacity piping
ALP-EPC-10LAB-PR-DSH-0001 | Feedwater Piping - Safety / Relief Valve Sizing and Datasheets |  | EPC | 10LAB | Feedwater piping | process | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-PI-007 |  | 2 | 2027-06-14 | 2027-06-28 | 2027-07-19 | 2027-07-26 |  |  | capacity process
ALP-EPC-10LAB-PR-PID-0001 | Feedwater Piping - P&ID |  | EPC | 10LAB | Feedwater piping | process | PID | F | approval | yes |  | 2 | 220 | [5 empty] | 3 | 2027-05-06 | 2027-06-11 | 2027-07-23 | 2027-07-30 |  |  | capacity process
ALP-EPC-10LAB-PR-SDS-0001 | Feedwater Piping - System Design Description |  | EPC | 10LAB | Feedwater piping | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-10LAC-CM-CMP-0001 | Boiler Feed Pumps - System Commissioning Procedure |  | EPC | 10LAC | Boiler feed pumps | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-08-09 | 2027-09-06 | 2027-10-04 | 2027-10-11 |  |  | capacity commissioning
ALP-EPC-10LAC-CM-MDB-0001 | Boiler Feed Pumps - System Turnover Dossier |  | EPC | 10LAC | Boiler feed pumps | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-05-22 | 2028-06-05 |  | 2028-06-12 |  |  | as late as possible (need)
ALP-EPC-10LAC-CM-OMM-0001 | Boiler Feed Pumps - Operating Procedures | English / Turkish | EPC | 10LAC | Boiler feed pumps | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-09-10 | 2027-10-22 |  | 2027-11-19 |  |  | capacity commissioning
ALP-EPC-10LAC-GE-RPT-0001 | Boiler Feed Pumps - Technical Bid Evaluation |  | EPC | 10LAC | Boiler feed pumps | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-001 |  | 1 | 2026-12-17 | 2027-01-07 |  | 2027-01-14 |  |  | bids MR-ME-001
ALP-EPC-10LAC-IC-CEM-0001 | Boiler Feed Pumps - Cause and Effect Matrix |  | EPC | 10LAC | Boiler feed pumps | i_and_c | CEM | F | approval |  |  | 3 | 52 | [5 empty] | 2 | 2027-10-22 | 2027-11-15 | 2027-12-13 | 2027-12-20 |  |  | capacity i_and_c
ALP-EPC-10LAC-IC-CNR-0001 | Boiler Feed Pumps - Control Narrative |  | EPC | 10LAC | Boiler feed pumps | i_and_c | CNR | F | review |  |  | 2 | 90 | [5 empty] | 2 | 2027-06-11 | 2027-07-05 |  | 2027-08-02 |  |  | ALP-EPC-10LAC-PR-PID-0001
ALP-EPC-10LAC-IC-DSH-0001 | Boiler Feed Pumps - Instrument Datasheets |  | EPC | 10LAC | Boiler feed pumps | i_and_c | DSH | E | approval |  |  | 70 | 113 |  |  |  | MR-IC-004 |  | 2 | 2027-10-22 | 2027-11-19 | 2027-12-10 | 2027-12-17 |  |  | capacity i_and_c
ALP-EPC-10LAC-IC-DSH-0002 | Boiler Feed Pumps - Control Valve Sizing and Datasheets |  | EPC | 10LAC | Boiler feed pumps | i_and_c | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-IC-005 |  | 3 | 2027-10-19 | 2027-11-03 | 2027-11-24 | 2027-12-01 |  |  | capacity i_and_c
ALP-EPC-10LAC-IC-HMI-0001 | Boiler Feed Pumps - Operator Displays | HMI graphics | EPC | 10LAC | Boiler feed pumps | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-10-25 | 2027-11-16 |  | 2027-12-07 |  |  | capacity i_and_c
ALP-EPC-10LAC-IC-LOG-0001 | Boiler Feed Pumps - Logic Diagrams |  | EPC | 10LAC | Boiler feed pumps | i_and_c | LOG | F | approval |  |  | 36 | 304 | [5 empty] | 3 | 2027-10-27 | 2027-12-23 | 2028-01-20 | 2028-01-27 |  |  | capacity i_and_c
ALP-EPC-10LAC-ME-CAL-0001 | Boiler Feed Pumps - Sizing and Hydraulic Calculation |  | EPC | 10LAC | Boiler feed pumps | mechanical | CAL | E | review |  |  | 4 | 62 | [5 empty] | 2 | 2027-01-11 | 2027-02-03 |  | 2027-02-24 |  |  | ALP-EPC-00000-PR-DBR-0001
ALP-EPC-10LAC-ME-DSH-0001 | Boiler Feed Pumps - Datasheet | 2 items | EPC | 10LAC | Boiler feed pumps | mechanical | DSH | E | approval |  | yes | 2 | 26 |  |  |  | MR-ME-001 | 10LAC10AP001 10LAC10AP002 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-10LAC-ME-ITP-0001 | Boiler Feed Pumps - Inspection and Test Plan |  | EPC | 10LAC | Boiler feed pumps | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-001 |  | 1 | 2026-11-02 | 2026-11-16 | 2026-12-07 | 2026-12-14
ALP-EPC-10LAC-ME-MRQ-0001 | Boiler Feed Pumps - Material Requisition |  | EPC | 10LAC | Boiler feed pumps | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-001 |  | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-10LAC-ME-SPC-0001 | Boiler Feed Pumps - Technical Specification |  | EPC | 10LAC | Boiler feed pumps | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-001 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-10LAC-PI-ISO-0001 | Boiler Feed Pumps - Isometric Drawings |  | EPC | 10LAC | Boiler feed pumps | piping | ISO | L | information |  |  | 70 | 700 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 |  |  | 6 | 2027-09-21 | 2027-11-17 |  | 2027-11-24 | 2027-12-13 | 13 | capacity piping
ALP-EPC-10LAC-PI-STR-0001 | Boiler Feed Pumps - Pipe Stress Analysis |  | EPC | 10LAC | Boiler feed pumps | piping | STR | E | review |  |  | 2 | 140 | [5 empty] | 4 | 2027-07-19 | 2027-08-17 |  | 2027-09-07 |  |  | ALP-EPC-00UQA-PI-PPL-0003
ALP-EPC-10LAC-PI-SUP-0001 | Boiler Feed Pumps - Pipe Support Drawings |  | EPC | 10LAC | Boiler feed pumps | piping | SUP | L | information |  |  | 18 | 108 | EWP-08-PI-01 | CWP-08-PI-01 | CWA-08 | MR-PI-005 |  | 2 | 2027-12-08 | 2028-01-17 |  | 2028-01-24 | 2027-12-13 | -30 | capacity piping
ALP-EPC-10LAC-PR-DSH-0001 | Boiler Feed Pumps - Safety / Relief Valve Sizing and Datasheets |  | EPC | 10LAC | Boiler feed pumps | process | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-PI-007 |  | 2 | 2027-06-14 | 2027-06-28 | 2027-07-19 | 2027-07-26 |  |  | capacity process
ALP-EPC-10LAC-PR-PID-0001 | Boiler Feed Pumps - P&ID |  | EPC | 10LAC | Boiler feed pumps | process | PID | F | approval | yes |  | 2 | 220 | [5 empty] | 3 | 2027-05-06 | 2027-06-11 | 2027-07-23 | 2027-07-30 |  |  | capacity process
ALP-EPC-10LAC-PR-SDS-0001 | Boiler Feed Pumps - System Design Description |  | EPC | 10LAC | Boiler feed pumps | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-10LAE-CM-CMP-0001 | HP Attemperation Spray Water - System Commissioning Procedure |  | EPC | 10LAE | HP attemperation spray water | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-08-10 | 2027-09-07 | 2027-10-05 | 2027-10-12 |  |  | capacity commissioning
ALP-EPC-10LAE-CM-MDB-0001 | HP Attemperation Spray Water - System Turnover Dossier |  | EPC | 10LAE | HP attemperation spray water | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-05-22 | 2028-06-05 |  | 2028-06-12 |  |  | as late as possible (need)
ALP-EPC-10LAE-CM-OMM-0001 | HP Attemperation Spray Water - Operating Procedures | English / Turkish | EPC | 10LAE | HP attemperation spray water | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-09-10 | 2027-10-22 |  | 2027-11-19 |  |  | capacity commissioning
ALP-EPC-10LAE-IC-CEM-0001 | HP Attemperation Spray Water - Cause and Effect Matrix |  | EPC | 10LAE | HP attemperation spray water | i_and_c | CEM | F | approval |  |  | 1 | 28 | [5 empty] | 2 | 2027-10-21 | 2027-11-17 | 2027-12-15 | 2027-12-22 |  |  | capacity i_and_c
ALP-EPC-10LAE-IC-CNR-0001 | HP Attemperation Spray Water - Control Narrative |  | EPC | 10LAE | HP attemperation spray water | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-06-14 | 2027-07-05 |  | 2027-08-02 |  |  | ALP-EPC-10LAE-PR-PID-0001
ALP-EPC-10LAE-IC-DSH-0001 | HP Attemperation Spray Water - Instrument Datasheets |  | EPC | 10LAE | HP attemperation spray water | i_and_c | DSH | E | approval |  |  | 12 | 26 |  |  |  | MR-IC-004 |  | 2 | 2027-07-13 | 2027-11-22 | 2027-12-13 | 2027-12-20 |  |  | capacity i_and_c
ALP-EPC-10LAE-IC-DSH-0002 | HP Attemperation Spray Water - Control Valve Sizing and Datasheets |  | EPC | 10LAE | HP attemperation spray water | i_and_c | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-IC-005 |  | 3 | 2027-11-02 | 2027-11-16 | 2027-12-07 | 2027-12-14 |  |  | capacity i_and_c
ALP-EPC-10LAE-IC-HMI-0001 | HP Attemperation Spray Water - Operator Displays | HMI graphics | EPC | 10LAE | HP attemperation spray water | i_and_c | HMI | F | review |  |  | 1 | 20 | [5 empty] | 2 | 2027-09-29 | 2027-11-19 |  | 2027-12-10 |  |  | capacity i_and_c
ALP-EPC-10LAE-IC-LOG-0001 | HP Attemperation Spray Water - Logic Diagrams |  | EPC | 10LAE | HP attemperation spray water | i_and_c | LOG | F | approval |  |  | 5 | 56 | [5 empty] | 3 | 2027-11-02 | 2027-12-06 | 2028-01-03 | 2028-01-10 |  |  | capacity i_and_c
ALP-EPC-10LAE-ME-CAL-0001 | HP Attemperation Spray Water - Sizing and Hydraulic Calculation |  | EPC | 10LAE | HP attemperation spray water | mechanical | CAL | E | review |  |  | 2 | 46 | [5 empty] | 2 | 2027-03-02 | 2027-03-25 |  | 2027-04-15 |  |  | capacity mechanical
ALP-EPC-10LAE-PI-ISO-0001 | HP Attemperation Spray Water - Isometric Drawings |  | EPC | 10LAE | HP attemperation spray water | piping | ISO | L | information |  |  | 30 | 300 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 |  |  | 4 | 2027-11-22 | 2028-01-18 |  | 2028-01-25 | 2027-12-13 | -31 | capacity piping
ALP-EPC-10LAE-PI-STR-0001 | HP Attemperation Spray Water - Pipe Stress Analysis |  | EPC | 10LAE | HP attemperation spray water | piping | STR | E | review |  |  | 1 | 80 | [5 empty] | 3 | 2027-10-05 | 2027-11-02 |  | 2027-11-23 |  |  | capacity piping
ALP-EPC-10LAE-PI-SUP-0001 | HP Attemperation Spray Water - Pipe Support Drawings |  | EPC | 10LAE | HP attemperation spray water | piping | SUP | L | information |  |  | 8 | 48 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 | MR-PI-005 |  | 2 | 2028-01-25 | 2028-02-22 |  | 2028-02-29 | 2027-12-13 | -56 | ALP-EPC-10LAE-PI-ISO-0001
ALP-EPC-10LAE-PR-PID-0001 | HP Attemperation Spray Water - P&ID |  | EPC | 10LAE | HP attemperation spray water | process | PID | F | approval |  |  | 1 | 120 | [5 empty] | 3 | 2027-05-10 | 2027-06-14 | 2027-07-19 | 2027-07-26 |  |  | capacity process
ALP-EPC-10LAE-PR-SDS-0001 | HP Attemperation Spray Water - System Design Description |  | EPC | 10LAE | HP attemperation spray water | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-10LAF-CM-CMP-0001 | Reheat Attemperation Spray Water - System Commissioning Procedure |  | EPC | 10LAF | Reheat attemperation spray water | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-08-16 | 2027-09-13 | 2027-10-11 | 2027-10-18 |  |  | capacity commissioning
ALP-EPC-10LAF-CM-MDB-0001 | Reheat Attemperation Spray Water - System Turnover Dossier |  | EPC | 10LAF | Reheat attemperation spray water | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-05-22 | 2028-06-05 |  | 2028-06-12 |  |  | as late as possible (need)
ALP-EPC-10LAF-CM-OMM-0001 | Reheat Attemperation Spray Water - Operating Procedures | English / Turkish | EPC | 10LAF | Reheat attemperation spray water | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-09-13 | 2027-10-25 |  | 2027-11-22 |  |  | ALP-EPC-10LAF-CM-CMP-0001
ALP-EPC-10LAF-IC-CEM-0001 | Reheat Attemperation Spray Water - Cause and Effect Matrix |  | EPC | 10LAF | Reheat attemperation spray water | i_and_c | CEM | F | approval |  |  | 1 | 28 | [5 empty] | 2 | 2027-11-02 | 2027-11-23 | 2027-12-21 | 2027-12-28 |  |  | capacity i_and_c
ALP-EPC-10LAF-IC-CNR-0001 | Reheat Attemperation Spray Water - Control Narrative |  | EPC | 10LAF | Reheat attemperation spray water | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-06-14 | 2027-07-05 |  | 2027-08-02 |  |  | ALP-EPC-10LAF-PR-PID-0001
ALP-EPC-10LAF-IC-DSH-0001 | Reheat Attemperation Spray Water - Instrument Datasheets |  | EPC | 10LAF | Reheat attemperation spray water | i_and_c | DSH | E | approval |  |  | 10 | 23 |  |  |  | MR-IC-004 |  | 2 | 2027-11-02 | 2027-11-22 | 2027-12-13 | 2027-12-20 |  |  | capacity i_and_c
ALP-EPC-10LAF-IC-DSH-0002 | Reheat Attemperation Spray Water - Control Valve Sizing and Datasheets |  | EPC | 10LAF | Reheat attemperation spray water | i_and_c | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-IC-005 |  | 3 | 2027-11-02 | 2027-11-16 | 2027-12-07 | 2027-12-14 |  |  | capacity i_and_c
ALP-EPC-10LAF-IC-HMI-0001 | Reheat Attemperation Spray Water - Operator Displays | HMI graphics | EPC | 10LAF | Reheat attemperation spray water | i_and_c | HMI | F | review |  |  | 1 | 20 | [5 empty] | 2 | 2027-11-02 | 2027-11-23 |  | 2027-12-14 |  |  | capacity i_and_c
ALP-EPC-10LAF-IC-LOG-0001 | Reheat Attemperation Spray Water - Logic Diagrams |  | EPC | 10LAF | Reheat attemperation spray water | i_and_c | LOG | F | approval |  |  | 4 | 48 | [5 empty] | 3 | 2027-11-03 | 2027-12-06 | 2028-01-03 | 2028-01-10 |  |  | capacity i_and_c
ALP-EPC-10LAF-ME-CAL-0001 | Reheat Attemperation Spray Water - Sizing and Hydraulic Calculation |  | EPC | 10LAF | Reheat attemperation spray water | mechanical | CAL | E | review |  |  | 2 | 46 | [5 empty] | 2 | 2027-03-04 | 2027-03-26 |  | 2027-04-16 |  |  | capacity mechanical
ALP-EPC-10LAF-PI-ISO-0001 | Reheat Attemperation Spray Water - Isometric Drawings |  | EPC | 10LAF | Reheat attemperation spray water | piping | ISO | L | information |  |  | 25 | 250 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 |  |  | 4 | 2027-11-23 | 2028-01-18 |  | 2028-01-25 | 2027-12-13 | -31 | capacity piping
ALP-EPC-10LAF-PI-STR-0001 | Reheat Attemperation Spray Water - Pipe Stress Analysis |  | EPC | 10LAF | Reheat attemperation spray water | piping | STR | E | review |  |  | 1 | 80 | [5 empty] | 2 | 2027-10-11 | 2027-11-08 |  | 2027-11-29 |  |  | capacity piping
ALP-EPC-10LAF-PI-SUP-0001 | Reheat Attemperation Spray Water - Pipe Support Drawings |  | EPC | 10LAF | Reheat attemperation spray water | piping | SUP | L | information |  |  | 7 | 42 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 | MR-PI-005 |  | 2 | 2028-01-25 | 2028-02-22 |  | 2028-02-29 | 2027-12-13 | -56 | ALP-EPC-10LAF-PI-ISO-0001
ALP-EPC-10LAF-PR-PID-0001 | Reheat Attemperation Spray Water - P&ID |  | EPC | 10LAF | Reheat attemperation spray water | process | PID | F | approval |  |  | 1 | 120 | [5 empty] | 3 | 2027-05-10 | 2027-06-14 | 2027-07-19 | 2027-07-26 |  |  | capacity process
ALP-EPC-10LAF-PR-SDS-0001 | Reheat Attemperation Spray Water - System Design Description |  | EPC | 10LAF | Reheat attemperation spray water | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-10LBA-CM-CMP-0001 | Main Steam Piping - System Commissioning Procedure |  | EPC | 10LBA | Main steam piping | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-08-20 | 2027-09-17 | 2027-10-15 | 2027-10-22 |  |  | capacity commissioning
ALP-EPC-10LBA-CM-MDB-0001 | Main Steam Piping - System Turnover Dossier |  | EPC | 10LBA | Main steam piping | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-05-22 | 2028-06-05 |  | 2028-06-12 |  |  | as late as possible (need)
ALP-EPC-10LBA-CM-OMM-0001 | Main Steam Piping - Operating Procedures | English / Turkish | EPC | 10LBA | Main steam piping | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-09-17 | 2027-10-29 |  | 2027-11-26 |  |  | ALP-EPC-10LBA-CM-CMP-0001
ALP-EPC-10LBA-GE-RPT-0001 | Alloy Piping P91 / P22 - Technical Bid Evaluation | main steam, reheat | EPC | 10LBA | Main steam piping | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-PI-002 |  | 1 | 2027-02-25 | 2027-03-18 |  | 2027-03-25 |  |  | bids MR-PI-002
ALP-EPC-10LBA-IC-CEM-0001 | Main Steam Piping - Cause and Effect Matrix |  | EPC | 10LBA | Main steam piping | i_and_c | CEM | F | approval |  |  | 1 | 28 | [5 empty] | 2 | 2027-11-03 | 2027-11-24 | 2027-12-22 | 2027-12-29 |  |  | capacity i_and_c
ALP-EPC-10LBA-IC-CNR-0001 | Main Steam Piping - Control Narrative |  | EPC | 10LBA | Main steam piping | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-06-14 | 2027-07-05 |  | 2027-08-02 |  |  | ALP-EPC-10LBA-PR-PID-0001
ALP-EPC-10LBA-IC-DSH-0001 | Main Steam Piping - Instrument Datasheets |  | EPC | 10LBA | Main steam piping | i_and_c | DSH | E | approval |  |  | 25 | 45.5 |  |  |  | MR-IC-004 |  | 2 | 2027-11-03 | 2027-12-01 | 2027-12-22 | 2027-12-29 |  |  | capacity i_and_c
ALP-EPC-10LBA-IC-HMI-0001 | Main Steam Piping - Operator Displays | HMI graphics | EPC | 10LBA | Main steam piping | i_and_c | HMI | F | review |  |  | 1 | 20 | [5 empty] | 2 | 2027-11-03 | 2027-11-24 |  | 2027-12-15 |  |  | capacity i_and_c
ALP-EPC-10LBA-IC-LOG-0001 | Main Steam Piping - Logic Diagrams |  | EPC | 10LBA | Main steam piping | i_and_c | LOG | F | approval |  |  | 8 | 80 | [5 empty] | 3 | 2027-11-04 | 2027-12-13 | 2028-01-10 | 2028-01-17 |  |  | capacity i_and_c
ALP-EPC-10LBA-ME-CAL-0001 | Main Steam Piping - Sizing and Hydraulic Calculation |  | EPC | 10LBA | Main steam piping | mechanical | CAL | E | review |  |  | 2 | 46 | [5 empty] | 2 | 2027-03-04 | 2027-03-26 |  | 2027-04-16 |  |  | capacity mechanical
ALP-EPC-10LBA-PI-ISO-0001 | Main Steam Piping - Isometric Drawings |  | EPC | 10LBA | Main steam piping | piping | ISO | L | information |  |  | 90 | 900 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 |  |  | 4 | 2027-10-11 | 2027-12-07 |  | 2027-12-14 | 2027-12-13 | -1 | capacity piping
ALP-EPC-10LBA-PI-STR-0001 | Main Steam Piping - Pipe Stress Analysis |  | EPC | 10LBA | Main steam piping | piping | STR | E | review |  |  | 6 | 380 | [5 empty] | 3 | 2027-06-25 | 2027-08-02 |  | 2027-08-23 |  |  | capacity piping
ALP-EPC-10LBA-PI-SUP-0001 | Main Steam Piping - Pipe Support Drawings |  | EPC | 10LBA | Main steam piping | piping | SUP | L | information |  |  | 23 | 138 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 | MR-PI-005 |  | 2 | 2027-12-14 | 2028-01-25 |  | 2028-02-01 | 2027-12-13 | -36 | ALP-EPC-10LBA-PI-ISO-0001
ALP-EPC-10LBA-PR-PID-0001 | Main Steam Piping - P&ID |  | EPC | 10LBA | Main steam piping | process | PID | F | approval | yes |  | 1 | 120 | [5 empty] | 3 | 2027-05-10 | 2027-06-14 | 2027-07-26 | 2027-08-02 |  |  | capacity process
ALP-EPC-10LBA-PR-SDS-0001 | Main Steam Piping - System Design Description |  | EPC | 10LBA | Main steam piping | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-10LBB-CM-CMP-0001 | Hot Reheat Piping - System Commissioning Procedure |  | EPC | 10LBB | Hot reheat piping | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-08-27 | 2027-09-24 | 2027-10-22 | 2027-10-29 |  |  | capacity commissioning
ALP-EPC-10LBB-CM-MDB-0001 | Hot Reheat Piping - System Turnover Dossier |  | EPC | 10LBB | Hot reheat piping | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-05-22 | 2028-06-05 |  | 2028-06-12 |  |  | as late as possible (need)
ALP-EPC-10LBB-CM-OMM-0001 | Hot Reheat Piping - Operating Procedures | English / Turkish | EPC | 10LBB | Hot reheat piping | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-09-24 | 2027-11-05 |  | 2027-12-03 |  |  | ALP-EPC-10LBB-CM-CMP-0001
ALP-EPC-10LBB-IC-CEM-0001 | Hot Reheat Piping - Cause and Effect Matrix |  | EPC | 10LBB | Hot reheat piping | i_and_c | CEM | F | approval |  |  | 1 | 28 | [5 empty] | 2 | 2027-11-08 | 2027-11-29 | 2027-12-27 | 2028-01-03 |  |  | capacity i_and_c
ALP-EPC-10LBB-IC-CNR-0001 | Hot Reheat Piping - Control Narrative |  | EPC | 10LBB | Hot reheat piping | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-06-14 | 2027-07-05 |  | 2027-08-02 |  |  | ALP-EPC-10LBB-PR-PID-0001
ALP-EPC-10LBB-IC-DSH-0001 | Hot Reheat Piping - Instrument Datasheets |  | EPC | 10LBB | Hot reheat piping | i_and_c | DSH | E | approval |  |  | 20 | 38 |  |  |  | MR-IC-004 |  | 2 | 2027-11-08 | 2027-12-06 | 2027-12-27 | 2028-01-03 |  |  | capacity i_and_c
ALP-EPC-10LBB-IC-HMI-0001 | Hot Reheat Piping - Operator Displays | HMI graphics | EPC | 10LBB | Hot reheat piping | i_and_c | HMI | F | review |  |  | 1 | 20 | [5 empty] | 2 | 2027-11-04 | 2027-11-25 |  | 2027-12-16 |  |  | capacity i_and_c
ALP-EPC-10LBB-IC-LOG-0001 | Hot Reheat Piping - Logic Diagrams |  | EPC | 10LBB | Hot reheat piping | i_and_c | LOG | F | approval |  |  | 7 | 72 | [5 empty] | 3 | 2027-11-08 | 2027-12-14 | 2028-01-11 | 2028-01-18 |  |  | capacity i_and_c
ALP-EPC-10LBB-ME-CAL-0001 | Hot Reheat Piping - Sizing and Hydraulic Calculation |  | EPC | 10LBB | Hot reheat piping | mechanical | CAL | E | review |  |  | 2 | 46 | [5 empty] | 2 | 2027-03-05 | 2027-03-29 |  | 2027-04-19 |  |  | capacity mechanical
ALP-EPC-10LBB-PI-ISO-0001 | Hot Reheat Piping - Isometric Drawings |  | EPC | 10LBB | Hot reheat piping | piping | ISO | L | information |  |  | 80 | 800 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 |  |  | 4 | 2027-10-13 | 2027-12-09 |  | 2027-12-16 | 2027-12-13 | -3 | capacity piping
ALP-EPC-10LBB-PI-STR-0001 | Hot Reheat Piping - Pipe Stress Analysis |  | EPC | 10LBB | Hot reheat piping | piping | STR | E | review |  |  | 5 | 320 | [5 empty] | 3 | 2027-06-25 | 2027-08-06 |  | 2027-08-27 |  |  | capacity piping
ALP-EPC-10LBB-PI-SUP-0001 | Hot Reheat Piping - Pipe Support Drawings |  | EPC | 10LBB | Hot reheat piping | piping | SUP | L | information |  |  | 20 | 120 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 | MR-PI-005 |  | 2 | 2027-12-21 | 2028-01-31 |  | 2028-02-07 | 2027-12-13 | -40 | capacity piping
ALP-EPC-10LBB-PR-PID-0001 | Hot Reheat Piping - P&ID |  | EPC | 10LBB | Hot reheat piping | process | PID | F | approval | yes |  | 1 | 120 | [5 empty] | 3 | 2027-05-10 | 2027-06-14 | 2027-07-26 | 2027-08-02 |  |  | capacity process
ALP-EPC-10LBB-PR-SDS-0001 | Hot Reheat Piping - System Design Description |  | EPC | 10LBB | Hot reheat piping | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-10LBC-CM-CMP-0001 | Cold Reheat Piping - System Commissioning Procedure |  | EPC | 10LBC | Cold reheat piping | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-08-27 | 2027-09-24 | 2027-10-22 | 2027-10-29 |  |  | capacity commissioning
ALP-EPC-10LBC-CM-MDB-0001 | Cold Reheat Piping - System Turnover Dossier |  | EPC | 10LBC | Cold reheat piping | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-05-22 | 2028-06-05 |  | 2028-06-12 |  |  | as late as possible (need)
ALP-EPC-10LBC-CM-OMM-0001 | Cold Reheat Piping - Operating Procedures | English / Turkish | EPC | 10LBC | Cold reheat piping | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-09-24 | 2027-11-05 |  | 2027-12-03 |  |  | ALP-EPC-10LBC-CM-CMP-0001
ALP-EPC-10LBC-IC-CEM-0001 | Cold Reheat Piping - Cause and Effect Matrix |  | EPC | 10LBC | Cold reheat piping | i_and_c | CEM | F | approval |  |  | 1 | 28 | [5 empty] | 2 | 2027-11-08 | 2027-11-29 | 2027-12-27 | 2028-01-03 |  |  | capacity i_and_c
ALP-EPC-10LBC-IC-CNR-0001 | Cold Reheat Piping - Control Narrative |  | EPC | 10LBC | Cold reheat piping | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-06-14 | 2027-07-05 |  | 2027-08-02 |  |  | ALP-EPC-10LBC-PR-PID-0001
ALP-EPC-10LBC-IC-DSH-0001 | Cold Reheat Piping - Instrument Datasheets |  | EPC | 10LBC | Cold reheat piping | i_and_c | DSH | E | approval |  |  | 18 | 35 |  |  |  | MR-IC-004 |  | 2 | 2027-11-09 | 2027-12-03 | 2027-12-24 | 2027-12-31 |  |  | capacity i_and_c
ALP-EPC-10LBC-IC-HMI-0001 | Cold Reheat Piping - Operator Displays | HMI graphics | EPC | 10LBC | Cold reheat piping | i_and_c | HMI | F | review |  |  | 1 | 20 | [5 empty] | 2 | 2027-11-09 | 2027-11-30 |  | 2027-12-21 |  |  | capacity i_and_c
ALP-EPC-10LBC-IC-LOG-0001 | Cold Reheat Piping - Logic Diagrams |  | EPC | 10LBC | Cold reheat piping | i_and_c | LOG | F | approval |  |  | 6 | 64 | [5 empty] | 3 | 2027-11-09 | 2027-12-14 | 2028-01-11 | 2028-01-18 |  |  | capacity i_and_c
ALP-EPC-10LBC-ME-CAL-0001 | Cold Reheat Piping - Sizing and Hydraulic Calculation |  | EPC | 10LBC | Cold reheat piping | mechanical | CAL | E | review |  |  | 2 | 46 | [5 empty] | 2 | 2027-03-08 | 2027-03-30 |  | 2027-04-20 |  |  | capacity mechanical
ALP-EPC-10LBC-PI-ISO-0001 | Cold Reheat Piping - Isometric Drawings |  | EPC | 10LBC | Cold reheat piping | piping | ISO | L | information |  |  | 70 | 700 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 |  |  | 4 | 2027-10-14 | 2027-12-15 |  | 2027-12-22 | 2027-12-13 | -7 | capacity piping
ALP-EPC-10LBC-PI-STR-0001 | Cold Reheat Piping - Pipe Stress Analysis |  | EPC | 10LBC | Cold reheat piping | piping | STR | E | review |  |  | 5 | 320 | [5 empty] | 3 | 2027-07-07 | 2027-08-16 |  | 2027-09-06 |  |  | capacity piping
ALP-EPC-10LBC-PI-SUP-0001 | Cold Reheat Piping - Pipe Support Drawings |  | EPC | 10LBC | Cold reheat piping | piping | SUP | L | information |  |  | 18 | 108 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 | MR-PI-005 |  | 2 | 2027-12-22 | 2028-01-31 |  | 2028-02-07 | 2027-12-13 | -40 | ALP-EPC-10LBC-PI-ISO-0001
ALP-EPC-10LBC-PR-PID-0001 | Cold Reheat Piping - P&ID |  | EPC | 10LBC | Cold reheat piping | process | PID | F | approval | yes |  | 1 | 120 | [5 empty] | 3 | 2027-05-10 | 2027-06-14 | 2027-07-26 | 2027-08-02 |  |  | capacity process
ALP-EPC-10LBC-PR-SDS-0001 | Cold Reheat Piping - System Design Description |  | EPC | 10LBC | Cold reheat piping | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-10LBD-CM-CMP-0001 | LP Steam Piping - System Commissioning Procedure |  | EPC | 10LBD | LP steam piping | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-08-30 | 2027-09-27 | 2027-10-25 | 2027-11-01 |  |  | capacity commissioning
ALP-EPC-10LBD-CM-MDB-0001 | LP Steam Piping - System Turnover Dossier |  | EPC | 10LBD | LP steam piping | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-05-22 | 2028-06-05 |  | 2028-06-12 |  |  | as late as possible (need)
ALP-EPC-10LBD-CM-OMM-0001 | LP Steam Piping - Operating Procedures | English / Turkish | EPC | 10LBD | LP steam piping | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-09-27 | 2027-11-08 |  | 2027-12-06 |  |  | ALP-EPC-10LBD-CM-CMP-0001
ALP-EPC-10LBD-IC-CEM-0001 | LP Steam Piping - Cause and Effect Matrix |  | EPC | 10LBD | LP steam piping | i_and_c | CEM | F | approval |  |  | 1 | 28 | [5 empty] | 2 | 2027-11-09 | 2027-11-30 | 2027-12-28 | 2028-01-04 |  |  | capacity i_and_c
ALP-EPC-10LBD-IC-CNR-0001 | LP Steam Piping - Control Narrative |  | EPC | 10LBD | LP steam piping | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-06-14 | 2027-07-05 |  | 2027-08-02 |  |  | ALP-EPC-10LBD-PR-PID-0001
ALP-EPC-10LBD-IC-DSH-0001 | LP Steam Piping - Instrument Datasheets |  | EPC | 10LBD | LP steam piping | i_and_c | DSH | E | approval |  |  | 15 | 30.5 |  |  |  | MR-IC-004 |  | 2 | 2027-11-09 | 2027-12-02 | 2027-12-23 | 2027-12-30 |  |  | capacity i_and_c
ALP-EPC-10LBD-IC-HMI-0001 | LP Steam Piping - Operator Displays | HMI graphics | EPC | 10LBD | LP steam piping | i_and_c | HMI | F | review |  |  | 1 | 20 | [5 empty] | 2 | 2027-11-09 | 2027-11-30 |  | 2027-12-21 |  |  | capacity i_and_c
ALP-EPC-10LBD-IC-LOG-0001 | LP Steam Piping - Logic Diagrams |  | EPC | 10LBD | LP steam piping | i_and_c | LOG | F | approval |  |  | 6 | 64 | [5 empty] | 3 | 2027-11-09 | 2027-12-14 | 2028-01-11 | 2028-01-18 |  |  | capacity i_and_c
ALP-EPC-10LBD-ME-CAL-0001 | LP Steam Piping - Sizing and Hydraulic Calculation |  | EPC | 10LBD | LP steam piping | mechanical | CAL | E | review |  |  | 2 | 46 | [5 empty] | 2 | 2027-03-08 | 2027-03-30 |  | 2027-04-20 |  |  | capacity mechanical
ALP-EPC-10LBD-PI-ISO-0001 | LP Steam Piping - Isometric Drawings |  | EPC | 10LBD | LP steam piping | piping | ISO | L | information |  |  | 50 | 500 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 |  |  | 4 | 2027-11-02 | 2027-12-30 |  | 2028-01-06 | 2027-12-13 | -18 | capacity piping
ALP-EPC-10LBD-PI-STR-0001 | LP Steam Piping - Pipe Stress Analysis |  | EPC | 10LBD | LP steam piping | piping | STR | E | review |  |  | 3 | 200 | [5 empty] | 3 | 2027-07-19 | 2027-08-18 |  | 2027-09-08 |  |  | capacity piping
ALP-EPC-10LBD-PI-SUP-0001 | LP Steam Piping - Pipe Support Drawings |  | EPC | 10LBD | LP steam piping | piping | SUP | L | information |  |  | 13 | 78 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 | MR-PI-005 |  | 2 | 2028-01-06 | 2028-02-09 |  | 2028-02-16 | 2027-12-13 | -47 | ALP-EPC-10LBD-PI-ISO-0001
ALP-EPC-10LBD-PR-PID-0001 | LP Steam Piping - P&ID |  | EPC | 10LBD | LP steam piping | process | PID | F | approval | yes |  | 1 | 120 | [5 empty] | 3 | 2027-05-10 | 2027-06-14 | 2027-07-26 | 2027-08-02 |  |  | capacity process
ALP-EPC-10LBD-PR-SDS-0001 | LP Steam Piping - System Design Description |  | EPC | 10LBD | LP steam piping | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-10MBA-CM-MDB-0001 | Gas Turbine - System Turnover Dossier |  | EPC | 10MBA | Gas turbine | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-04-17 | 2028-05-01 |  | 2028-05-08 |  |  | capacity commissioning
ALP-EPC-10MBL-CM-MDB-0001 | GT Inlet Air System - System Turnover Dossier |  | EPC | 10MBL | GT inlet air system | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-04-17 | 2028-05-01 |  | 2028-05-08 |  |  | capacity commissioning
ALP-EPC-10MBN-CM-MDB-0001 | GT Liquid Fuel and Water Injection - System Turnover Dossier |  | EPC | 10MBN | GT liquid fuel and water injection | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-05-01 | 2028-05-15 |  | 2028-05-22 |  |  | capacity commissioning
ALP-EPC-10MBP-CM-MDB-0001 | GT Fuel Gas System incl. Performance Heater - System Turnover Dossier |  | EPC | 10MBP | GT fuel gas system incl. performance heater | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-05-01 | 2028-05-15 |  | 2028-05-22 |  |  | capacity commissioning
ALP-EPC-10MBU-CM-MDB-0001 | GT Compressor Washing - System Turnover Dossier |  | EPC | 10MBU | GT compressor washing | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-05-01 | 2028-05-15 |  | 2028-05-22 |  |  | capacity commissioning
ALP-EPC-10MBV-CM-MDB-0001 | GT Lube Oil System - System Turnover Dossier |  | EPC | 10MBV | GT lube oil system | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-05-01 | 2028-05-15 |  | 2028-05-22 |  |  | capacity commissioning
ALP-EPC-10MBY-CM-MDB-0001 | GT Control and Protection - System Turnover Dossier | TCS | EPC | 10MBY | GT control and protection (TCS) | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-05-01 | 2028-05-15 |  | 2028-05-22 |  |  | capacity commissioning
ALP-EPC-10MKA-CM-MDB-0001 | GT Generator - System Turnover Dossier |  | EPC | 10MKA | GT generator | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-05-01 | 2028-05-15 |  | 2028-05-22 |  |  | capacity commissioning
ALP-EPC-10MKC-CM-MDB-0001 | GT Excitation and Static Frequency Converter - System Turnover Dossier |  | EPC | 10MKC | GT excitation and static frequency converter | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-05-01 | 2028-05-15 |  | 2028-05-22 |  |  | capacity commissioning
ALP-EPC-10MKG-CM-MDB-0001 | GT Generator Gas System - System Turnover Dossier | H2/CO2 | EPC | 10MKG | GT generator gas system (H2/CO2) | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-05-01 | 2028-05-15 |  | 2028-05-22 |  |  | capacity commissioning
ALP-EPC-10UHA-CV-CAL-0001 | HRSG Foundations and Structures - Structural and Foundation Calculation |  | EPC | 10UHA | HRSG foundations and structures | civil | CAL | E | review |  |  | 2 | 120 | [5 empty] | 4 | 2027-05-28 | 2027-06-22 |  | 2027-07-13 |  |  | capacity civil
ALP-EPC-10UHA-CV-EFD-0001 | HRSG Foundations and Structures - Equipment Foundation Drawings |  | EPC | 10UHA | HRSG foundations and structures | civil | EFD | L | approval |  |  | 4 | 200 | EWP-01-CV-02 | CWP-01-CV-02 | CWA-01 |  |  | 4 | 2027-04-12 | 2027-05-05 | 2027-06-02 | 2027-06-09 | 2027-04-19 | -37 | ALP-EPC-10UHA-CV-FND-0001
ALP-EPC-10UHA-CV-FND-0001 | HRSG Foundations and Structures - Foundation and Underground Drawings |  | EPC | 10UHA | HRSG foundations and structures | civil | FND | L | approval |  |  | 8 | 400 | EWP-01-CV-02 | CWP-01-CV-02 | CWA-01 |  |  | 6 | 2027-03-04 | 2027-04-12 | 2027-05-10 | 2027-05-17 | 2027-04-19 | -20 | ALP-EPC-10UHA-CV-FND-0002
ALP-EPC-10UHA-CV-FND-0002 | HRSG Foundations and Structures - Piling Layout and Pile Schedule |  | EPC | 10UHA | HRSG foundations and structures | civil | FND | L | approval |  |  | 4 | 160 | EWP-01-CV-01 | CWP-01-CV-01 | CWA-01 |  |  | 3 | 2027-02-01 | 2027-03-04 | 2027-04-01 | 2027-04-08 | 2027-03-22 | -13 | ALP-EPC-00000-CV-SPC-0002
ALP-EPC-10UHA-CV-RBR-0001 | HRSG Foundations and Structures - Reinforcement Drawings |  | EPC | 10UHA | HRSG foundations and structures | civil | RBR | L | review |  |  | 16 | 560 | EWP-01-CV-02 | CWP-01-CV-02 | CWA-01 |  |  | 1 | 2027-04-12 | 2027-05-18 |  | 2027-06-08 | 2027-04-19 | -36 | ALP-EPC-10UHA-CV-FND-0001
ALP-EPC-10UHA-EL-ELY-0001 | HRSG Foundations and Structures - Earthing and Lightning Protection Layouts |  | EPC | 10UHA | HRSG foundations and structures | electrical | ELY | L | review |  |  | 3 | 60 | EWP-01-EL-01 | CWP-01-EL-01 | CWA-01 |  |  | 3 | 2027-08-06 | 2027-09-09 |  | 2027-10-07 | 2028-01-10 | 67 | capacity electrical
ALP-EPC-10UHN-CV-CAL-0001 | Stack Foundation - Structural and Foundation Calculation |  | EPC | 10UHN | Stack foundation | civil | CAL | E | review |  |  | 1 | 80 | [5 empty] | 4 | 2027-05-28 | 2027-06-21 |  | 2027-07-12 |  |  | capacity civil
ALP-EPC-10UHN-CV-EFD-0001 | Stack Foundation - Equipment Foundation Drawings |  | EPC | 10UHN | Stack foundation | civil | EFD | L | approval |  |  | 1 | 50 | EWP-01-CV-02 | CWP-01-CV-02 | CWA-01 |  |  | 4 | 2027-04-06 | 2027-04-27 | 2027-05-25 | 2027-06-01 | 2027-04-19 | -31 | capacity civil
ALP-EPC-10UHN-CV-FND-0001 | Stack Foundation - Foundation and Underground Drawings |  | EPC | 10UHN | Stack foundation | civil | FND | L | approval |  |  | 2 | 100 | EWP-01-CV-02 | CWP-01-CV-02 | CWA-01 |  |  | 6 | 2027-03-02 | 2027-03-31 | 2027-04-28 | 2027-05-05 | 2027-04-19 | -12 | ALP-EPC-10UHN-CV-FND-0002
ALP-EPC-10UHN-CV-FND-0002 | Stack Foundation - Piling Layout and Pile Schedule |  | EPC | 10UHN | Stack foundation | civil | FND | L | approval |  |  | 2 | 80 | EWP-01-CV-01 | CWP-01-CV-01 | CWA-01 |  |  | 3 | 2027-02-01 | 2027-03-02 | 2027-03-30 | 2027-04-06 | 2027-03-22 | -11 | ALP-EPC-00000-CV-SPC-0002
ALP-EPC-10UHN-CV-RBR-0001 | Stack Foundation - Reinforcement Drawings |  | EPC | 10UHN | Stack foundation | civil | RBR | L | review |  |  | 4 | 140 | EWP-01-CV-02 | CWP-01-CV-02 | CWA-01 |  |  | 1 | 2027-03-31 | 2027-04-23 |  | 2027-05-14 | 2027-04-19 | -19 | ALP-EPC-10UHN-CV-FND-0001
ALP-EPC-10UHN-EL-ELY-0001 | Stack Foundation - Earthing and Lightning Protection Layouts |  | EPC | 10UHN | Stack foundation | electrical | ELY | L | review |  |  | 1 | 20 | EWP-01-EL-01 | CWP-01-EL-01 | CWA-01 |  |  | 3 | 2027-04-12 | 2027-09-07 |  | 2027-10-05 | 2028-01-10 | 69 | capacity electrical
ALP-EPC-10UMA-CV-ARC-0001 | Gas Turbine Hall - Architectural Drawings |  | EPC | 10UMA | Gas turbine hall | civil | ARC | L | approval |  |  | 8 | 280 | EWP-01-SS-01 | CWP-01-SS-01 | CWA-01 |  |  | 2 | 2026-12-24 | 2027-02-01 | 2027-03-01 | 2027-03-08 | 2027-07-12 | 90 | ALP-EPC-10UMA-PI-LAY-0001
ALP-EPC-10UMA-CV-CAL-0001 | Gas Turbine Hall - Structural and Foundation Calculation |  | EPC | 10UMA | Gas turbine hall | civil | CAL | E | review |  |  | 3 | 160 | [5 empty] | 4 | 2027-03-16 | 2027-04-07 |  | 2027-04-28 |  |  | capacity civil
ALP-EPC-10UMA-CV-EFD-0001 | Gas Turbine Hall - Equipment Foundation Drawings |  | EPC | 10UMA | Gas turbine hall | civil | EFD | L | approval |  |  | 6 | 300 | EWP-01-CV-02 | CWP-01-CV-02 | CWA-01 |  |  | 5 | 2027-04-20 | 2027-05-17 | 2027-06-14 | 2027-06-21 | 2027-04-19 | -45 | ALP-EPC-10UMA-CV-FND-0002
ALP-EPC-10UMA-CV-FND-0001 | Gas Turbine Hall - Piling Layout and Pile Schedule |  | EPC | 10UMA | Gas turbine hall | civil | FND | L | approval |  |  | 6 | 240 | EWP-01-CV-01 | CWP-01-CV-01 | CWA-01 |  |  | 4 | 2027-02-01 | 2027-03-08 | 2027-04-05 | 2027-04-12 | 2027-03-22 | -15 | ALP-EPC-00000-CV-SPC-0002
ALP-EPC-10UMA-CV-FND-0002 | Gas Turbine Hall - Foundation and Underground Drawings |  | EPC | 10UMA | Gas turbine hall | civil | FND | L | approval |  |  | 12 | 600 | EWP-01-CV-02 | CWP-01-CV-02 | CWA-01 |  |  | 6 | 2027-03-08 | 2027-04-20 | 2027-05-18 | 2027-05-25 | 2027-04-19 | -26 | ALP-EPC-10UMA-CV-FND-0001
ALP-EPC-10UMA-CV-RBR-0001 | Gas Turbine Hall - Reinforcement Drawings |  | EPC | 10UMA | Gas turbine hall | civil | RBR | L | review |  |  | 30 | 1050 | EWP-01-CV-02 | CWP-01-CV-02 | CWA-01 |  |  | 1 | 2027-04-20 | 2027-06-01 |  | 2027-06-22 | 2027-04-19 | -46 | ALP-EPC-10UMA-CV-FND-0002
ALP-EPC-10UMA-EL-CBL-0001 | Power Block - GT and HRSG - Cable Schedule and Routing |  | EPC | 10UMA | Gas turbine hall | electrical | CBL | M | information |  |  | 65 | 150 | EWP-01-EL-01 | CWP-01-EL-01 | CWA-01 |  |  | 3 | 2027-09-09 | 2027-10-21 |  | 2027-10-28 | 2028-01-10 | 52 | capacity electrical
ALP-EPC-10UMA-EL-ELY-0001 | Power Block - GT and HRSG - Electrical Layouts | equipment, trays, earthing, lighting | EPC | 10UMA | Gas turbine hall | electrical | ELY | L | review |  |  | 33 | 990 | EWP-01-EL-01 | CWP-01-EL-01 | CWA-01 |  |  | 3 | 2027-02-08 | 2027-04-06 |  | 2027-05-04 | 2028-01-10 | 179 | capacity electrical
ALP-EPC-10UMA-EL-ELY-0002 | Power Block - GT and HRSG - Cable Routing, Tray and Trench Layouts |  | EPC | 10UMA | Gas turbine hall | electrical | ELY | L | review |  |  | 18 | 450 | EWP-01-EL-01 | CWP-01-EL-01 | CWA-01 |  |  | 2 | 2027-07-05 | 2027-09-13 |  | 2027-10-11 | 2028-01-10 | 65 | capacity electrical
ALP-EPC-10UMA-EL-ELY-0003 | Gas Turbine Hall - Earthing and Lightning Protection Layouts |  | EPC | 10UMA | Gas turbine hall | electrical | ELY | L | review |  |  | 4 | 80 | EWP-01-EL-01 | CWP-01-EL-01 | CWA-01 |  |  | 3 | 2027-08-10 | 2027-09-10 |  | 2027-10-08 | 2028-01-10 | 66 | capacity electrical
ALP-EPC-10UMA-HS-GAD-0001 | Gas Turbine Hall - Fire Fighting, Escape Route and Safety Signage Layouts |  | EPC | 10UMA | Gas turbine hall | hse | GAD | L | approval |  |  | 2 | 24 | EWP-01-CV-02 | CWP-01-CV-02 | CWA-01 |  |  | 3 | 2027-02-01 | 2027-03-02 | 2027-03-30 | 2027-04-06 | 2027-04-19 | 9 | ALP-EPC-10UMA-CV-ARC-0001
ALP-EPC-10UMA-HV-GAD-0001 | Power Block - GT and HRSG - HVAC Layouts |  | EPC | 10UMA | Gas turbine hall | hvac | GAD | L | review |  |  | 4 | 120 | EWP-01-HV-01 | CWP-01-HV-01 | CWA-01 |  |  | 2 | 2027-04-13 | 2027-05-14 |  | 2027-06-11 | 2027-11-01 | 101 | capacity hvac
ALP-EPC-10UMA-HV-GAD-0002 | Gas Turbine Hall - Building Services | plumbing, HVAC ducting, fire fighting | EPC | 10UMA | Gas turbine hall | hvac | GAD | L | review |  |  | 10 | 250 | EWP-01-CV-02 | CWP-01-CV-02 | CWA-01 |  |  | 2 | 2027-04-02 | 2027-05-13 |  | 2027-06-10 | 2027-04-19 | -38 | capacity hvac
ALP-EPC-10UMA-IC-ELY-0001 | Power Block - GT and HRSG - Instrument Location and I&C Cable Routing |  | EPC | 10UMA | Gas turbine hall | i_and_c | ELY | L | review |  |  | 11 | 176 | EWP-01-IC-01 | CWP-01-IC-01 | CWA-01 |  |  | 2 | 2027-07-06 | 2027-08-17 |  | 2027-09-14 | 2028-02-07 | 104 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-10UMA-IC-ELY-0002 | Gas Turbine Hall - Fire Detection and Alarm Layouts |  | EPC | 10UMA | Gas turbine hall | i_and_c | ELY | L | review |  |  | 3 | 42 | EWP-01-IC-01 | CWP-01-IC-01 | CWA-01 | MR-IC-006 |  | 2 | 2027-02-01 | 2027-03-03 |  | 2027-03-31 | 2028-02-07 | 223 | ALP-EPC-10UMA-CV-ARC-0001
ALP-EPC-10UMA-IC-HUP-0001 | Power Block - GT and HRSG - Instrument Hook-Up Drawings |  | EPC | 10UMA | Gas turbine hall | i_and_c | HUP | M | information |  |  | 14 | 112 | EWP-01-IC-01 | CWP-01-IC-01 | CWA-01 | MR-IC-010 |  | 2 | 2027-07-06 | 2027-08-16 |  | 2027-08-23 | 2028-02-07 | 120 | capacity i_and_c
ALP-EPC-10UMA-IC-LOP-0001 | Power Block - GT and HRSG - Loop and Connection Diagrams, Part 1 of 2 |  | EPC | 10UMA | Gas turbine hall | i_and_c | LOP | M | information |  |  | 156 | 234 | EWP-01-IC-01 | CWP-01-IC-01 | CWA-01 |  |  | 4 | 2027-07-27 | 2027-09-07 |  | 2027-09-14 | 2028-02-07 | 104 | ALP-EPC-00000-IC-IOL-0001
ALP-EPC-10UMA-IC-LOP-0002 | Power Block - GT and HRSG - Junction Box and Cabinet Interconnection Diagrams |  | EPC | 10UMA | Gas turbine hall | i_and_c | LOP | M | information |  |  | 35 | 87.5 | EWP-01-IC-01 | CWP-01-IC-01 | CWA-01 |  |  | 2 | 2027-08-17 | 2027-09-28 |  | 2027-10-05 | 2028-02-07 | 89 | ALP-EPC-10UMA-IC-ELY-0001
ALP-EPC-10UMA-IC-LOP-0003 | Power Block - GT and HRSG - Loop and Connection Diagrams, Part 2 of 2 |  | EPC | 10UMA | Gas turbine hall | i_and_c | LOP | M | information |  |  | 156 | 234 | EWP-01-IC-01 | CWP-01-IC-01 | CWA-01 |  |  | 2 | 2027-07-27 | 2027-09-07 |  | 2027-09-14 | 2028-02-07 | 104 | ALP-EPC-00000-IC-IOL-0001
ALP-EPC-10UMA-PI-LAY-0001 | Power Block - GT and HRSG - Equipment Layout |  | EPC | 10UMA | Gas turbine hall | piping | LAY | L | approval | yes |  | 19 | 760 | EWP-01-ME-01 | CWP-01-ME-01 | CWA-01 |  |  | 3 | 2026-11-02 | 2026-12-24 | 2027-01-28 | 2027-02-04 | 2027-10-18 | 182
ALP-EPC-10UMA-PI-PPL-0001 | Power Block - GT and HRSG - Piping General Arrangement |  | EPC | 10UMA | Gas turbine hall | piping | PPL | L | review |  |  | 56 | 5040 | EWP-01-PI-01 | CWP-01-PI-01 | CWA-01 |  |  | 3 | 2027-02-26 | 2027-05-11 |  | 2027-06-08 | 2027-12-13 | 134 | capacity piping
ALP-EPC-10UMA-SS-STL-0001 | Gas Turbine Hall - Steel Structure Drawings |  | EPC | 10UMA | Gas turbine hall | structural | STL | L | approval |  |  | 30 | 1050 | EWP-01-SS-01 | CWP-01-SS-01 | CWA-01 |  |  | 4 | 2027-04-07 | 2027-06-02 | 2027-06-30 | 2027-07-07 | 2027-07-12 | 3 | ALP-EPC-10UMA-CV-CAL-0001
ALP-EPC-20BAA-CM-MDB-0001 | ST Generator Busduct - System Turnover Dossier |  | EPC | 20BAA | ST generator busduct | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-01-18 | 2028-02-01 |  | 2028-02-08 |  |  | capacity commissioning
ALP-EPC-20BAC-CM-MDB-0001 | ST Generator Circuit Breaker - System Turnover Dossier |  | EPC | 20BAC | ST generator circuit breaker | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-01-18 | 2028-02-01 |  | 2028-02-08 |  |  | capacity commissioning
ALP-EPC-20BAT-CM-MDB-0001 | ST Generator Step-Up Transformer - System Turnover Dossier |  | EPC | 20BAT | ST generator step-up transformer | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-01-18 | 2028-02-01 |  | 2028-02-08 |  |  | capacity commissioning
ALP-EPC-20BBT-CM-CMP-0001 | ST Unit Auxiliary Transformer - System Commissioning Procedure |  | EPC | 20BBT | ST unit auxiliary transformer | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 1 | 2026-12-28 | 2027-01-25 | 2027-02-22 | 2027-03-01 |  |  | capacity commissioning
ALP-EPC-20BBT-CM-MDB-0001 | ST Unit Auxiliary Transformer - System Turnover Dossier |  | EPC | 20BBT | ST unit auxiliary transformer | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-01-18 | 2028-02-01 |  | 2028-02-08 |  |  | capacity commissioning
ALP-EPC-20BBT-CM-OMM-0001 | ST Unit Auxiliary Transformer - Operating Procedures | English / Turkish | EPC | 20BBT | ST unit auxiliary transformer | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-01-25 | 2027-03-08 |  | 2027-04-05 |  |  | ALP-EPC-20BBT-CM-CMP-0001
ALP-EPC-20BBT-EL-DSH-0001 | ST Unit Auxiliary Transformer - Datasheet |  | EPC | 20BBT | ST unit auxiliary transformer | electrical | DSH | E | approval |  | yes | 1 | 16 |  |  |  | MR-EL-002 | 20BBT10 | 2 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-20BBT-IC-DSH-0001 | ST Unit Auxiliary Transformer - Instrument Datasheets |  | EPC | 20BBT | ST unit auxiliary transformer | i_and_c | DSH | E | approval |  |  | 10 | 23 |  |  |  | MR-IC-004 |  | 1 | 2027-01-25 | 2027-02-12 | 2027-03-05 | 2027-03-12 |  |  | capacity i_and_c
ALP-EPC-20BBT-IC-LOG-0001 | ST Unit Auxiliary Transformer - Logic Diagrams |  | EPC | 20BBT | ST unit auxiliary transformer | i_and_c | LOG | F | approval |  |  | 8 | 80 | [5 empty] | 1 | 2027-01-25 | 2027-11-25 | 2027-12-23 | 2027-12-30 |  |  | capacity i_and_c
ALP-EPC-20LCA-CM-CMP-0001 | Main Condensate Piping - System Commissioning Procedure |  | EPC | 20LCA | Main condensate piping | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-09-02 | 2027-09-30 | 2027-10-28 | 2027-11-04 |  |  | capacity commissioning
ALP-EPC-20LCA-CM-MDB-0001 | Main Condensate Piping - System Turnover Dossier |  | EPC | 20LCA | Main condensate piping | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-05-22 | 2028-06-05 |  | 2028-06-12 |  |  | as late as possible (need)
ALP-EPC-20LCA-CM-OMM-0001 | Main Condensate Piping - Operating Procedures | English / Turkish | EPC | 20LCA | Main condensate piping | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-09-30 | 2027-11-11 |  | 2027-12-09 |  |  | ALP-EPC-20LCA-CM-CMP-0001
ALP-EPC-20LCA-IC-CEM-0001 | Main Condensate Piping - Cause and Effect Matrix |  | EPC | 20LCA | Main condensate piping | i_and_c | CEM | F | approval |  |  | 1 | 28 | [5 empty] | 2 | 2027-11-12 | 2027-12-03 | 2027-12-31 | 2028-01-07 |  |  | capacity i_and_c
ALP-EPC-20LCA-IC-CNR-0001 | Main Condensate Piping - Control Narrative |  | EPC | 20LCA | Main condensate piping | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-06-14 | 2027-07-05 |  | 2027-08-02 |  |  | ALP-EPC-20LCA-PR-PID-0001
ALP-EPC-20LCA-IC-DSH-0001 | Main Condensate Piping - Instrument Datasheets |  | EPC | 20LCA | Main condensate piping | i_and_c | DSH | E | approval |  |  | 45 | 75.5 |  |  |  | MR-IC-004 |  | 2 | 2027-11-15 | 2027-12-13 | 2028-01-03 | 2028-01-10 |  |  | capacity i_and_c
ALP-EPC-20LCA-IC-DSH-0002 | Main Condensate Piping - Control Valve Sizing and Datasheets |  | EPC | 20LCA | Main condensate piping | i_and_c | DSH | E | approval |  |  | 4 | 32 |  |  |  | MR-IC-005 |  | 3 | 2027-11-12 | 2027-12-01 | 2027-12-22 | 2027-12-29 |  |  | capacity i_and_c
ALP-EPC-20LCA-IC-HMI-0001 | Main Condensate Piping - Operator Displays | HMI graphics | EPC | 20LCA | Main condensate piping | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-11-15 | 2027-12-07 |  | 2027-12-28 |  |  | capacity i_and_c
ALP-EPC-20LCA-IC-LOG-0001 | Main Condensate Piping - Logic Diagrams |  | EPC | 20LCA | Main condensate piping | i_and_c | LOG | F | approval |  |  | 15 | 136 | [5 empty] | 3 | 2027-11-16 | 2028-01-04 | 2028-02-01 | 2028-02-08 |  |  | capacity i_and_c
ALP-EPC-20LCA-ME-CAL-0001 | Main Condensate Piping - Sizing and Hydraulic Calculation |  | EPC | 20LCA | Main condensate piping | mechanical | CAL | E | review |  |  | 4 | 62 | [5 empty] | 2 | 2027-03-10 | 2027-04-02 |  | 2027-04-23 |  |  | capacity mechanical
ALP-EPC-20LCA-PI-ISO-0001 | Main Condensate Piping - Isometric Drawings |  | EPC | 20LCA | Main condensate piping | piping | ISO | L | information |  |  | 110 | 1100 | EWP-02-PI-01 | CWP-02-PI-01 | CWA-02 |  |  | 4 | 2028-01-05 | 2028-03-01 |  | 2028-03-08 | 2028-01-31 | -27 | ALP-EPC-20LCA-PI-STR-0001
ALP-EPC-20LCA-PI-STR-0001 | Main Condensate Piping - Pipe Stress Analysis |  | EPC | 20LCA | Main condensate piping | piping | STR | E | review |  |  | 3 | 200 | [5 empty] | 2 | 2027-12-06 | 2028-01-05 |  | 2028-01-26 |  |  | capacity piping
ALP-EPC-20LCA-PI-SUP-0001 | Main Condensate Piping - Pipe Support Drawings |  | EPC | 20LCA | Main condensate piping | piping | SUP | L | information |  |  | 28 | 168 | EWP-02-PI-01 | CWP-02-PI-01 | CWA-02 | MR-PI-005 |  | 2 | 2028-03-08 | 2028-04-19 |  | 2028-04-26 | 2028-01-31 | -62 | ALP-EPC-20LCA-PI-ISO-0001
ALP-EPC-20LCA-PR-DSH-0001 | Main Condensate Piping - Safety / Relief Valve Sizing and Datasheets |  | EPC | 20LCA | Main condensate piping | process | DSH | E | approval |  |  | 1 | 14 |  |  |  | MR-PI-007 |  | 2 | 2027-06-14 | 2027-06-28 | 2027-07-19 | 2027-07-26 |  |  | ALP-EPC-20LCA-PR-PID-0001
ALP-EPC-20LCA-PR-PID-0001 | Main Condensate Piping - P&ID |  | EPC | 20LCA | Main condensate piping | process | PID | F | approval | yes |  | 2 | 220 | [5 empty] | 3 | 2027-05-07 | 2027-06-14 | 2027-07-26 | 2027-08-02 |  |  | capacity process
ALP-EPC-20LCA-PR-SDS-0001 | Main Condensate Piping - System Design Description |  | EPC | 20LCA | Main condensate piping | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-20LCB-CM-CMP-0001 | Condensate Extraction Pumps - System Commissioning Procedure |  | EPC | 20LCB | Condensate extraction pumps | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-09-03 | 2027-10-01 | 2027-10-29 | 2027-11-05 |  |  | capacity commissioning
ALP-EPC-20LCB-CM-MDB-0001 | Condensate Extraction Pumps - System Turnover Dossier |  | EPC | 20LCB | Condensate extraction pumps | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-05-22 | 2028-06-05 |  | 2028-06-12 |  |  | as late as possible (need)
ALP-EPC-20LCB-CM-OMM-0001 | Condensate Extraction Pumps - Operating Procedures | English / Turkish | EPC | 20LCB | Condensate extraction pumps | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-10-01 | 2027-11-12 |  | 2027-12-10 |  |  | ALP-EPC-20LCB-CM-CMP-0001
ALP-EPC-20LCB-GE-RPT-0001 | Condensate Extraction Pumps - Technical Bid Evaluation |  | EPC | 20LCB | Condensate extraction pumps | general | RPT | D | internal |  |  | 1 | 40 |  |  |  | MR-ME-002 |  | 1 | 2027-01-28 | 2027-02-18 |  | 2027-02-25 |  |  | capacity general
ALP-EPC-20LCB-IC-CEM-0001 | Condensate Extraction Pumps - Cause and Effect Matrix |  | EPC | 20LCB | Condensate extraction pumps | i_and_c | CEM | F | approval |  |  | 2 | 40 | [5 empty] | 2 | 2027-11-17 | 2027-12-09 | 2028-01-06 | 2028-01-13 |  |  | capacity i_and_c
ALP-EPC-20LCB-IC-CNR-0001 | Condensate Extraction Pumps - Control Narrative |  | EPC | 20LCB | Condensate extraction pumps | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-06-15 | 2027-07-06 |  | 2027-08-03 |  |  | ALP-EPC-20LCB-PR-PID-0001
ALP-EPC-20LCB-IC-DSH-0001 | Condensate Extraction Pumps - Instrument Datasheets |  | EPC | 20LCB | Condensate extraction pumps | i_and_c | DSH | E | approval |  |  | 40 | 68 |  |  |  | MR-IC-004 |  | 2 | 2027-11-17 | 2027-12-15 | 2028-01-05 | 2028-01-12 |  |  | capacity i_and_c
ALP-EPC-20LCB-IC-DSH-0002 | Condensate Extraction Pumps - Control Valve Sizing and Datasheets |  | EPC | 20LCB | Condensate extraction pumps | i_and_c | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-IC-005 |  | 3 | 2027-11-17 | 2027-12-01 | 2027-12-22 | 2027-12-29 |  |  | capacity i_and_c
ALP-EPC-20LCB-IC-HMI-0001 | Condensate Extraction Pumps - Operator Displays | HMI graphics | EPC | 20LCB | Condensate extraction pumps | i_and_c | HMI | F | review |  |  | 1 | 20 | [5 empty] | 2 | 2027-11-10 | 2027-12-06 |  | 2027-12-27 |  |  | capacity i_and_c
ALP-EPC-20LCB-IC-LOG-0001 | Condensate Extraction Pumps - Logic Diagrams |  | EPC | 20LCB | Condensate extraction pumps | i_and_c | LOG | F | approval |  |  | 21 | 184 | [5 empty] | 3 | 2027-11-19 | 2028-01-14 | 2028-02-11 | 2028-02-18 |  |  | capacity i_and_c
ALP-EPC-20LCB-ME-CAL-0001 | Condensate Extraction Pumps - Sizing and Hydraulic Calculation |  | EPC | 20LCB | Condensate extraction pumps | mechanical | CAL | E | review |  |  | 3 | 54 | [5 empty] | 2 | 2027-01-20 | 2027-03-04 |  | 2027-03-25 |  |  | capacity mechanical
ALP-EPC-20LCB-ME-DSH-0001 | Condensate Extraction Pumps - Datasheet | 2 items | EPC | 20LCB | Condensate extraction pumps | mechanical | DSH | E | approval |  | yes | 2 | 26 |  |  |  | MR-ME-002 | 20LCB10AP001 20LCB10AP002 | 3 | 2026-11-02 | 2026-11-02 | 2026-11-23 | 2026-11-30
ALP-EPC-20LCB-ME-ITP-0001 | Condensate Extraction Pumps - Inspection and Test Plan |  | EPC | 20LCB | Condensate extraction pumps | mechanical | ITP | Q | approval |  |  | 1 | 16 |  |  |  | MR-ME-002 |  | 1 | 2026-11-09 | 2026-11-23 | 2026-12-14 | 2026-12-21 |  |  | capacity mechanical
ALP-EPC-20LCB-ME-MRQ-0001 | Condensate Extraction Pumps - Material Requisition |  | EPC | 20LCB | Condensate extraction pumps | mechanical | MRQ | C | information |  | yes | 1 | 24 |  |  |  | MR-ME-002 |  | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-05
ALP-EPC-20LCB-ME-SPC-0001 | Condensate Extraction Pumps - Technical Specification |  | EPC | 20LCB | Condensate extraction pumps | mechanical | SPC | E | approval |  | yes | 1 | 80 |  |  |  | MR-ME-002 |  | 3 | 2026-11-02 | 2026-11-02 | 2026-11-30 | 2026-12-07
ALP-EPC-20LCB-PI-ISO-0001 | Condensate Extraction Pumps - Isometric Drawings |  | EPC | 20LCB | Condensate extraction pumps | piping | ISO | L | information |  |  | 40 | 400 | EWP-02-PI-01 | CWP-02-PI-01 | CWA-02 |  |  | 4 | 2028-01-03 | 2028-02-28 |  | 2028-03-06 | 2028-01-31 | -25 | ALP-EPC-20LCB-PI-STR-0001
ALP-EPC-20LCB-PI-STR-0001 | Condensate Extraction Pumps - Pipe Stress Analysis |  | EPC | 20LCB | Condensate extraction pumps | piping | STR | E | review |  |  | 1 | 80 | [5 empty] | 2 | 2027-12-06 | 2028-01-03 |  | 2028-01-24 |  |  | capacity piping
ALP-EPC-20LCB-PI-SUP-0001 | Condensate Extraction Pumps - Pipe Support Drawings |  | EPC | 20LCB | Condensate extraction pumps | piping | SUP | L | information |  |  | 10 | 60 | EWP-02-PI-01 | CWP-02-PI-01 | CWA-02 | MR-PI-005 |  | 2 | 2028-03-06 | 2028-04-05 |  | 2028-04-12 | 2028-01-31 | -52 | ALP-EPC-20LCB-PI-ISO-0001
ALP-EPC-20LCB-PR-PID-0001 | Condensate Extraction Pumps - P&ID |  | EPC | 20LCB | Condensate extraction pumps | process | PID | F | approval | yes |  | 1 | 120 | [5 empty] | 3 | 2027-05-11 | 2027-06-15 | 2027-07-27 | 2027-08-03 |  |  | capacity process
ALP-EPC-20LCB-PR-SDS-0001 | Condensate Extraction Pumps - System Design Description |  | EPC | 20LCB | Condensate extraction pumps | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-20MAA-CM-MDB-0001 | HP Turbine - System Turnover Dossier |  | EPC | 20MAA | HP turbine | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-05-22 | 2028-06-05 |  | 2028-06-12 |  |  | as late as possible (need)
ALP-EPC-20MAB-CM-MDB-0001 | IP/LP Turbine - System Turnover Dossier |  | EPC | 20MAB | IP/LP turbine | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-05-22 | 2028-06-05 |  | 2028-06-12 |  |  | as late as possible (need)
ALP-EPC-20MAG-CM-MDB-0001 | Condensing System - System Turnover Dossier |  | EPC | 20MAG | Condensing system | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-06-05 | 2028-06-19 |  | 2028-06-26 |  |  | capacity commissioning
ALP-EPC-20MAJ-CM-MDB-0001 | Condenser Vacuum System - System Turnover Dossier |  | EPC | 20MAJ | Condenser vacuum system | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-06-05 | 2028-06-19 |  | 2028-06-26 |  |  | capacity commissioning
ALP-EPC-20MAN-CM-CMP-0001 | Turbine Bypass Stations and Piping - System Commissioning Procedure |  | EPC | 20MAN | Turbine bypass stations and piping | commissioning | CMP | B | approval |  |  | 1 | 40 | [5 empty] | 3 | 2027-09-06 | 2027-10-04 | 2027-11-01 | 2027-11-08 |  |  | capacity commissioning
ALP-EPC-20MAN-CM-MDB-0001 | Turbine Bypass Stations and Piping - System Turnover Dossier |  | EPC | 20MAN | Turbine bypass stations and piping | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 1 | 2028-06-05 | 2028-06-19 |  | 2028-06-26 |  |  | capacity commissioning
ALP-EPC-20MAN-CM-OMM-0001 | Turbine Bypass Stations and Piping - Operating Procedures | English / Turkish | EPC | 20MAN | Turbine bypass stations and piping | commissioning | OMM | D | review |  |  | 1 | 32 | [5 empty] | 1 | 2027-10-04 | 2027-11-15 |  | 2027-12-13 |  |  | ALP-EPC-20MAN-CM-CMP-0001
ALP-EPC-20MAN-IC-CEM-0001 | Turbine Bypass Stations and Piping - Cause and Effect Matrix |  | EPC | 20MAN | Turbine bypass stations and piping | i_and_c | CEM | F | approval |  |  | 1 | 28 | [5 empty] | 2 | 2027-11-19 | 2027-12-10 | 2028-01-07 | 2028-01-14 |  |  | capacity i_and_c
ALP-EPC-20MAN-IC-CNR-0001 | Turbine Bypass Stations and Piping - Control Narrative |  | EPC | 20MAN | Turbine bypass stations and piping | i_and_c | CNR | F | review |  |  | 1 | 60 | [5 empty] | 2 | 2027-06-14 | 2027-07-05 |  | 2027-08-02 |  |  | ALP-EPC-20MAN-PR-PID-0001
ALP-EPC-20MAN-IC-DSH-0001 | Turbine Bypass Stations and Piping - Instrument Datasheets |  | EPC | 20MAN | Turbine bypass stations and piping | i_and_c | DSH | E | approval |  |  | 30 | 53 |  |  |  | MR-IC-004 |  | 2 | 2027-11-22 | 2027-12-20 | 2028-01-10 | 2028-01-17 |  |  | capacity i_and_c
ALP-EPC-20MAN-IC-DSH-0002 | Turbine Bypass Stations and Piping - Control Valve Sizing and Datasheets |  | EPC | 20MAN | Turbine bypass stations and piping | i_and_c | DSH | E | approval |  |  | 3 | 26 |  |  |  | MR-IC-005 |  | 3 | 2027-11-23 | 2027-12-08 | 2027-12-29 | 2028-01-05 |  |  | capacity i_and_c
ALP-EPC-20MAN-IC-HMI-0001 | Turbine Bypass Stations and Piping - Operator Displays | HMI graphics | EPC | 20MAN | Turbine bypass stations and piping | i_and_c | HMI | F | review |  |  | 2 | 32 | [5 empty] | 2 | 2027-11-23 | 2027-12-15 |  | 2028-01-05 |  |  | capacity i_and_c
ALP-EPC-20MAN-IC-LOG-0001 | Turbine Bypass Stations and Piping - Logic Diagrams |  | EPC | 20MAN | Turbine bypass stations and piping | i_and_c | LOG | F | approval |  |  | 12 | 112 | [5 empty] | 3 | 2027-11-23 | 2028-01-05 | 2028-02-02 | 2028-02-09 |  |  | capacity i_and_c
ALP-EPC-20MAN-ME-CAL-0001 | Turbine Bypass Stations and Piping - Sizing and Hydraulic Calculation |  | EPC | 20MAN | Turbine bypass stations and piping | mechanical | CAL | E | review |  |  | 3 | 54 | [5 empty] | 2 | 2027-03-10 | 2027-04-01 |  | 2027-04-22 |  |  | capacity mechanical
ALP-EPC-20MAN-PI-ISO-0001 | Turbine Bypass Stations and Piping - Isometric Drawings |  | EPC | 20MAN | Turbine bypass stations and piping | piping | ISO | L | information |  |  | 90 | 900 | EWP-02-PI-01 | CWP-02-PI-01 | CWA-02 |  |  | 4 | 2028-01-03 | 2028-02-28 |  | 2028-03-06 | 2028-01-31 | -25 | ALP-EPC-20MAN-PI-STR-0001
ALP-EPC-20MAN-PI-STR-0001 | Turbine Bypass Stations and Piping - Pipe Stress Analysis |  | EPC | 20MAN | Turbine bypass stations and piping | piping | STR | E | review |  |  | 4 | 260 | [5 empty] | 3 | 2027-11-30 | 2028-01-03 |  | 2028-01-24 |  |  | capacity piping
ALP-EPC-20MAN-PI-SUP-0001 | Turbine Bypass Stations and Piping - Pipe Support Drawings |  | EPC | 20MAN | Turbine bypass stations and piping | piping | SUP | L | information |  |  | 23 | 138 | EWP-02-PI-01 | CWP-02-PI-01 | CWA-02 | MR-PI-005 |  | 2 | 2028-03-06 | 2028-04-17 |  | 2028-04-24 | 2028-01-31 | -60 | ALP-EPC-20MAN-PI-ISO-0001
ALP-EPC-20MAN-PR-DSH-0001 | Turbine Bypass Stations and Piping - Safety / Relief Valve Sizing and Datasheets |  | EPC | 20MAN | Turbine bypass stations and piping | process | DSH | E | approval |  |  | 2 | 20 |  |  |  | MR-PI-007 |  | 2 | 2027-06-14 | 2027-06-28 | 2027-07-19 | 2027-07-26 |  |  | ALP-EPC-20MAN-PR-PID-0001
ALP-EPC-20MAN-PR-PID-0001 | Turbine Bypass Stations and Piping - P&ID |  | EPC | 20MAN | Turbine bypass stations and piping | process | PID | F | approval |  |  | 2 | 220 | [5 empty] | 3 | 2027-05-07 | 2027-06-14 | 2027-07-19 | 2027-07-26 |  |  | capacity process
ALP-EPC-20MAN-PR-SDS-0001 | Turbine Bypass Stations and Piping - System Design Description |  | EPC | 20MAN | Turbine bypass stations and piping | process | SDS | D | review |  | yes | 1 | 80 | [5 empty] | 2 | 2026-11-02 | 2026-11-02 |  | 2026-11-30
ALP-EPC-20MAV-CM-MDB-0001 | ST Lube Oil System - System Turnover Dossier |  | EPC | 20MAV | ST lube oil system | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-06-05 | 2028-06-19 |  | 2028-06-26 |  |  | capacity commissioning
ALP-EPC-20MAW-CM-MDB-0001 | Gland Steam System - System Turnover Dossier |  | EPC | 20MAW | Gland steam system | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-06-05 | 2028-06-19 |  | 2028-06-26 |  |  | capacity commissioning
ALP-EPC-20MAX-CM-MDB-0001 | ST Control Fluid System - System Turnover Dossier |  | EPC | 20MAX | ST control fluid system | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-06-05 | 2028-06-19 |  | 2028-06-26 |  |  | capacity commissioning
ALP-EPC-20MAY-CM-MDB-0001 | ST Control and Protection - System Turnover Dossier |  | EPC | 20MAY | ST control and protection | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-05-01 | 2028-05-15 |  | 2028-05-22 |  |  | capacity commissioning
ALP-EPC-20MKA-CM-MDB-0001 | ST Generator - System Turnover Dossier |  | EPC | 20MKA | ST generator | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-05-01 | 2028-05-15 |  | 2028-05-22 |  |  | capacity commissioning
ALP-EPC-20MKC-CM-MDB-0001 | ST Excitation - System Turnover Dossier |  | EPC | 20MKC | ST excitation | commissioning | MDB | Q | information |  |  | 1 | 16 | [5 empty] | 0 | 2028-05-01 | 2028-05-15 |  | 2028-05-22 |  |  | capacity commissioning
ALP-EPC-20UMB-CV-ARC-0001 | Steam Turbine Hall - Architectural Drawings |  | EPC | 20UMB | Steam turbine hall | civil | ARC | L | approval |  |  | 8 | 280 | EWP-02-SS-01 | CWP-02-SS-01 | CWA-02 |  |  | 2 | 2026-12-14 | 2027-01-20 | 2027-02-17 | 2027-02-24 | 2027-07-12 | 98 | ALP-EPC-00000-HV-DBR-0001
ALP-EPC-20UMB-CV-CAL-0001 | Steam Turbine Hall - Structural and Foundation Calculation |  | EPC | 20UMB | Steam turbine hall | civil | CAL | E | review |  |  | 3 | 160 | [5 empty] | 3 | 2027-03-16 | 2027-04-08 |  | 2027-04-29 |  |  | capacity civil
ALP-EPC-20UMB-CV-EFD-0001 | Steam Turbine Hall - Equipment Foundation Drawings |  | EPC | 20UMB | Steam turbine hall | civil | EFD | L | approval |  |  | 6 | 300 | EWP-02-CV-02 | CWP-02-CV-02 | CWA-02 |  |  | 5 | 2027-04-20 | 2027-05-21 | 2027-06-18 | 2027-06-25 | 2027-04-19 | -49 | capacity civil
ALP-EPC-20UMB-CV-FND-0001 | Steam Turbine Hall - Piling Layout and Pile Schedule |  | EPC | 20UMB | Steam turbine hall | civil | FND | L | approval |  |  | 6 | 240 | EWP-02-CV-01 | CWP-02-CV-01 | CWA-02 |  |  | 4 | 2027-02-01 | 2027-03-08 | 2027-04-05 | 2027-04-12 | 2027-03-22 | -15 | ALP-EPC-00000-CV-SPC-0002
ALP-EPC-20UMB-CV-FND-0002 | Steam Turbine Hall - Foundation and Underground Drawings |  | EPC | 20UMB | Steam turbine hall | civil | FND | L | approval |  |  | 12 | 600 | EWP-02-CV-02 | CWP-02-CV-02 | CWA-02 |  |  | 5 | 2027-03-08 | 2027-04-20 | 2027-05-18 | 2027-05-25 | 2027-04-19 | -26 | ALP-EPC-20UMB-CV-FND-0001
ALP-EPC-20UMB-CV-RBR-0001 | Steam Turbine Hall - Reinforcement Drawings |  | EPC | 20UMB | Steam turbine hall | civil | RBR | L | review |  |  | 36 | 1260 | EWP-02-CV-02 | CWP-02-CV-02 | CWA-02 |  |  | 1 | 2027-04-20 | 2027-06-01 |  | 2027-06-22 | 2027-04-19 | -46 | ALP-EPC-20UMB-CV-FND-0002
ALP-EPC-20UMB-EL-CBL-0001 | Power Block - ST and Condenser - Cable Schedule and Routing |  | EPC | 20UMB | Steam turbine hall | electrical | CBL | M | information |  |  | 31 | 82 | EWP-02-EL-01 | CWP-02-EL-01 | CWA-02 |  |  | 3 | 2027-09-17 | 2027-10-29 |  | 2027-11-05 | 2028-02-28 | 81 | ALP-EPC-20UMB-EL-ELY-0001
ALP-EPC-20UMB-EL-ELY-0001 | Power Block - ST and Condenser - Electrical Layouts | equipment, trays, earthing, lighting | EPC | 20UMB | Steam turbine hall | electrical | ELY | L | review |  |  | 16 | 480 | EWP-02-EL-01 | CWP-02-EL-01 | CWA-02 |  |  | 3 | 2027-07-28 | 2027-09-17 |  | 2027-10-15 | 2028-02-28 | 96 | capacity electrical
ALP-EPC-20UMB-EL-ELY-0002 | Power Block - ST and Condenser - Cable Routing, Tray and Trench Layouts |  | EPC | 20UMB | Steam turbine hall | electrical | ELY | L | review |  |  | 9 | 225 | EWP-02-EL-01 | CWP-02-EL-01 | CWA-02 |  |  | 2 | 2027-09-17 | 2027-10-27 |  | 2027-11-24 | 2028-02-28 | 68 | ALP-EPC-20UMB-EL-ELY-0001
ALP-EPC-20UMB-EL-ELY-0003 | Steam Turbine Hall - Earthing and Lightning Protection Layouts |  | EPC | 20UMB | Steam turbine hall | electrical | ELY | L | review |  |  | 4 | 80 | EWP-02-EL-01 | CWP-02-EL-01 | CWA-02 |  |  | 3 | 2027-09-10 | 2027-10-13 |  | 2027-11-10 | 2028-02-28 | 78 | capacity electrical
ALP-EPC-20UMB-HS-GAD-0001 | Steam Turbine Hall - Fire Fighting, Escape Route and Safety Signage Layouts |  | EPC | 20UMB | Steam turbine hall | hse | GAD | L | approval |  |  | 2 | 24 | EWP-02-CV-02 | CWP-02-CV-02 | CWA-02 |  |  | 3 | 2027-01-20 | 2027-02-18 | 2027-03-18 | 2027-03-25 | 2027-04-19 | 17 | ALP-EPC-20UMB-CV-ARC-0001
ALP-EPC-20UMB-HV-GAD-0001 | Steam Turbine Hall - Building Services | plumbing, HVAC ducting, fire fighting | EPC | 20UMB | Steam turbine hall | hvac | GAD | L | review |  |  | 10 | 250 | EWP-02-CV-02 | CWP-02-CV-02 | CWA-02 |  |  | 2 | 2027-01-20 | 2027-05-12 |  | 2027-06-09 | 2027-04-19 | -37 | capacity hvac
ALP-EPC-20UMB-IC-ELY-0001 | Power Block - ST and Condenser - Instrument Location and I&C Cable Routing |  | EPC | 20UMB | Steam turbine hall | i_and_c | ELY | L | review |  |  | 4 | 64 | EWP-02-IC-01 | CWP-02-IC-01 | CWA-02 |  |  | 2 | 2027-07-06 | 2027-08-06 |  | 2027-09-03 | 2028-03-27 | 146 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-20UMB-IC-ELY-0002 | Steam Turbine Hall - Fire Detection and Alarm Layouts |  | EPC | 20UMB | Steam turbine hall | i_and_c | ELY | L | review |  |  | 3 | 42 | EWP-02-IC-01 | CWP-02-IC-01 | CWA-02 | MR-IC-006 |  | 2 | 2027-01-20 | 2027-02-19 |  | 2027-03-19 | 2028-03-27 | 266 | ALP-EPC-20UMB-CV-ARC-0001
ALP-EPC-20UMB-IC-HUP-0001 | Power Block - ST and Condenser - Instrument Hook-Up Drawings |  | EPC | 20UMB | Steam turbine hall | i_and_c | HUP | M | information |  |  | 5 | 40 | EWP-02-IC-01 | CWP-02-IC-01 | CWA-02 | MR-IC-010 |  | 2 | 2027-07-06 | 2027-07-22 |  | 2027-07-29 | 2028-03-27 | 172 | ALP-EPC-00000-IC-LST-0001
ALP-EPC-20UMB-IC-LOP-0001 | Power Block - ST and Condenser - Loop and Connection Diagrams |  | EPC | 20UMB | Steam turbine hall | i_and_c | LOP | M | information |  |  | 109 | 163.5 | EWP-02-IC-01 | CWP-02-IC-01 | CWA-02 |  |  | 4 | 2027-08-13 | 2027-09-24 |  | 2027-10-01 | 2028-03-27 | 126 | capacity i_and_c
ALP-EPC-20UMB-IC-LOP-0002 | Power Block - ST and Condenser - Junction Box and Cabinet Interconnection Diagrams |  | EPC | 20UMB | Steam turbine hall | i_and_c | LOP | M | information |  |  | 13 | 32.5 | EWP-02-IC-01 | CWP-02-IC-01 | CWA-02 |  |  | 2 | 2027-08-16 | 2027-09-17 |  | 2027-09-24 | 2028-03-27 | 131 | capacity i_and_c
ALP-EPC-20UMB-PI-LAY-0001 | Power Block - ST and Condenser - Equipment Layout |  | EPC | 20UMB | Steam turbine hall | piping | LAY | L | approval | yes |  | 7 | 280 | EWP-02-ME-01 | CWP-02-ME-01 | CWA-02 |  |  | 2 | 2026-11-03 | 2026-12-10 | 2027-01-14 | 2027-01-21 | 2027-12-20 | 237 | capacity piping
ALP-EPC-20UMB-PI-PPL-0001 | Power Block - ST and Condenser - Piping General Arrangement |  | EPC | 20UMB | Steam turbine hall | piping | PPL | L | review |  |  | 19 | 1710 | EWP-02-PI-01 | CWP-02-PI-01 | CWA-02 |  |  | 3 | 2027-03-02 | 2027-05-10 |  | 2027-06-07 | 2028-01-31 | 170 | capacity piping
ALP-EPC-20UMB-SS-STL-0001 | Steam Turbine Hall - Steel Structure Drawings |  | EPC | 20UMB | Steam turbine hall | structural | STL | L | approval |  |  | 30 | 1050 | EWP-02-SS-01 | CWP-02-SS-01 | CWA-02 |  |  | 4 | 2027-04-08 | 2027-06-03 | 2027-07-01 | 2027-07-08 | 2027-07-12 | 2 | ALP-EPC-20UMB-CV-CAL-0001
ALP-H01-00SAA-EL-WIR-0001 | HVAC Plant and Equipment - Supplier Electrical Schematics and Wiring Diagrams, Part 1 of 2 |  | H01 | 00SAA | HVAC | electrical | WIR | F | review |  |  | 60 | 34 | EWP-03-HV-01 | CWP-03-HV-01 | CWA-03 | MR-HV-001 |  | 1 | 2027-03-02 | 2027-03-23 |  | 2027-05-04 | 2027-10-11 | 114 | PO MR-HV-001
ALP-H01-00SAA-EL-WIR-0002 | HVAC Plant and Equipment - Supplier Electrical Schematics and Wiring Diagrams, Part 2 of 2 |  | H01 | 00SAA | HVAC | electrical | WIR | F | review |  |  | 60 | 34 | EWP-03-HV-01 | CWP-03-HV-01 | CWA-03 | MR-HV-001 |  | 1 | 2027-03-02 | 2027-03-23 |  | 2027-05-04 | 2027-10-11 | 114 | PO MR-HV-001
ALP-H01-00SAA-IC-DSH-0001 | HVAC Plant and Equipment - Supplier Instrument List and Datasheets |  | H01 | 00SAA | HVAC | i_and_c | DSH | E | review |  |  | 75 | 19 |  |  |  | MR-HV-001 | 00SAA10 00SAA10AN001 00SAA10AN002 00SAA10AN003 00SAA10AP001 00SAA10AP002 00SAA11AN001 00SAA11AN002 00SAA11AN003 00SAA11AN004 00SAA11AN005 00SAA11AN006 00SAA11AN007 00SAA11AN008 00SAA12AN001 00SAA12AN002 00SAA12AN003 00SAA12AN004 00SAA13AN001 00SAA13AN002 00SAA13AN003 00SAA13AN004 00SAA14AN001 00SAA14AN002 | 1 | 2027-03-09 | 2027-03-23 |  | 2027-05-04 |  |  | PO MR-HV-001
ALP-H01-00SAA-IC-IOL-0001 | HVAC Plant and Equipment - Supplier I/O List, Control Philosophy and Interface Signals |  | H01 | 00SAA | HVAC | i_and_c | IOL | P | review |  |  | 4 | 8 |  |  |  | MR-HV-001 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-12 |  |  | PO MR-HV-001
ALP-H01-00SAA-ME-CAL-0001 | HVAC Plant and Equipment - Supplier Design Calculations |  | H01 | 00SAA | HVAC | mechanical | CAL | E | review |  |  | 20 | 24 |  |  |  | MR-HV-001 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-12 |  |  | PO MR-HV-001
ALP-H01-00SAA-ME-DSH-0001 | HVAC Plant and Equipment - Supplier Certified Datasheets and Performance Curves |  | H01 | 00SAA | HVAC | mechanical | DSH | E | review |  |  | 60 | 64 |  |  |  | MR-HV-001 | 00SAA10 00SAA10AN001 00SAA10AN002 00SAA10AN003 00SAA10AP001 00SAA10AP002 00SAA11AN001 00SAA11AN002 00SAA11AN003 00SAA11AN004 00SAA11AN005 00SAA11AN006 00SAA11AN007 00SAA11AN008 00SAA12AN001 00SAA12AN002 00SAA12AN003 00SAA12AN004 00SAA13AN001 00SAA13AN002 00SAA13AN003 00SAA13AN004 00SAA14AN001 00SAA14AN002 | 1 | 2027-02-04 | 2027-02-18 |  | 2027-03-23 |  |  | PO MR-HV-001
ALP-H01-00SAA-ME-GAD-0001 | HVAC Plant and Equipment - Supplier GA Drawings |  | H01 | 00SAA | HVAC | mechanical | GAD | L | review |  |  | 60 | 94 | EWP-03-HV-01 | CWP-03-HV-01 | CWA-03 | MR-HV-001 | 00SAA10 00SAA10AN001 00SAA10AN002 00SAA10AN003 00SAA10AP001 00SAA10AP002 00SAA11AN001 00SAA11AN002 00SAA11AN003 00SAA11AN004 00SAA11AN005 00SAA11AN006 00SAA11AN007 00SAA11AN008 00SAA12AN001 00SAA12AN002 00SAA12AN003 00SAA12AN004 00SAA13AN001 00SAA13AN002 00SAA13AN003 00SAA13AN004 00SAA14AN001 00SAA14AN002 | 1 | 2027-02-01 | 2027-03-01 |  | 2027-04-01 | 2027-10-11 | 137 | PO MR-HV-001
ALP-H01-00SAA-ME-ITP-0001 | HVAC Plant and Equipment - Supplier Inspection and Test Plan |  | H01 | 00SAA | HVAC | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-HV-001 |  | 1 | 2027-02-04 | 2027-02-18 |  | 2027-03-11 |  |  | PO MR-HV-001
ALP-H01-00SAA-ME-LST-0001 | HVAC Plant and Equipment - Spare Parts and Special Tools Lists |  | H01 | 00SAA | HVAC | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-HV-001 |  | 1 | 2027-03-11 | 2027-04-01 |  | 2027-05-13 |  |  | PO MR-HV-001
ALP-H01-00SAA-ME-MDB-0001 | HVAC Plant and Equipment - Manufacturing Record Book and Conformity Certificates |  | H01 | 00SAA | HVAC | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-HV-001 |  | 1 | 2027-07-29 | 2027-08-12 |  | 2027-10-07 |  |  | PO MR-HV-001
ALP-H01-00SAA-ME-OMM-0001 | HVAC Plant and Equipment - Supplier Operation and Maintenance Manual |  | H01 | 00SAA | HVAC | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-HV-001 |  | 1 | 2027-05-20 | 2027-07-01 |  | 2027-11-18 |  |  | PO MR-HV-001
ALP-H01-00SAA-ME-PRC-0001 | HVAC Plant and Equipment - Supplier Installation and Erection Manual |  | H01 | 00SAA | HVAC | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-HV-001 |  | 1 | 2027-05-13 | 2027-06-03 |  | 2027-07-15 |  |  | PO MR-HV-001
ALP-H01-00SAA-ME-TRP-0001 | HVAC Plant and Equipment - Factory Acceptance Test Report |  | H01 | 00SAA | HVAC | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-HV-001 |  | 1 | 2027-07-22 | 2027-07-29 |  | 2027-08-12 |  |  | PO MR-HV-001
ALP-H01-00SAA-ME-TST-0001 | HVAC Plant and Equipment - Factory Acceptance Test Procedure |  | H01 | 00SAA | HVAC | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-HV-001 |  | 1 | 2027-04-15 | 2027-05-06 |  | 2027-06-17 |  |  | PO MR-HV-001
ALP-H01-00SAA-PR-PID-0001 | HVAC Plant and Equipment - Supplier P&IDs |  | H01 | 00SAA | HVAC | process | PID | F | approval |  |  | 10 | 34 |  |  |  | MR-HV-001 |  | 1 | 2027-02-04 | 2027-03-11 |  | 2027-04-12 |  |  | PO MR-HV-001
ALP-I01-00CJA-EL-WIR-0001 | Plant DCS - Supplier Electrical Schematics and Wiring Diagrams |  | I01 | 00CJA | Plant DCS | electrical | WIR | F | review |  |  | 40 | 24 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 | MR-IC-001 |  | 1 | 2027-03-11 | 2027-04-01 |  | 2027-05-27 | 2027-11-22 | 127 | PO MR-IC-001
ALP-I01-00CJA-IC-IOL-0001 | Plant DCS - Supplier I/O List, Control Philosophy and Interface Signals |  | I01 | 00CJA | Plant DCS | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-IC-001 |  | 1 | 2027-02-25 | 2027-03-18 |  | 2027-04-29 |  |  | PO MR-IC-001
ALP-I01-00CJA-ME-CAL-0001 | Plant DCS - Supplier Design Calculations |  | I01 | 00CJA | Plant DCS | mechanical | CAL | E | review |  |  | 7 | 11 |  |  |  | MR-IC-001 |  | 1 | 2027-02-25 | 2027-03-18 |  | 2027-04-29 |  |  | PO MR-IC-001
ALP-I01-00CJA-ME-DSH-0001 | Plant DCS - Supplier Certified Datasheets and Performance Curves |  | I01 | 00CJA | Plant DCS | mechanical | DSH | E | review |  |  | 20 | 24 |  |  |  | MR-IC-001 | 00CJA10 00CJA20 00CJA30 00CJA40 00CJA50 00CJA60 | 1 | 2027-02-04 | 2027-02-18 |  | 2027-04-01 |  |  | PO MR-IC-001
ALP-I01-00CJA-ME-GAD-0001 | Plant DCS - Supplier GA Drawings |  | I01 | 00CJA | Plant DCS | mechanical | GAD | L | review |  |  | 20 | 34 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 | MR-IC-001 | 00CJA10 00CJA20 00CJA30 00CJA40 00CJA50 00CJA60 | 1 | 2027-02-04 | 2027-03-04 |  | 2027-04-15 | 2027-11-22 | 157 | PO MR-IC-001
ALP-I01-00CJA-ME-ITP-0001 | Plant DCS - Supplier Inspection and Test Plan |  | I01 | 00CJA | Plant DCS | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-IC-001 |  | 1 | 2027-02-04 | 2027-02-18 |  | 2027-03-18 |  |  | PO MR-IC-001
ALP-I01-00CJA-ME-LST-0001 | Plant DCS - Spare Parts and Special Tools Lists |  | I01 | 00CJA | Plant DCS | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-IC-001 |  | 1 | 2027-03-25 | 2027-04-15 |  | 2027-06-10 |  |  | PO MR-IC-001
ALP-I01-00CJA-ME-MDB-0001 | Plant DCS - Manufacturing Record Book and Conformity Certificates |  | I01 | 00CJA | Plant DCS | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-IC-001 |  | 1 | 2027-09-30 | 2027-10-14 |  | 2027-12-09 |  |  | PO MR-IC-001
ALP-I01-00CJA-ME-OMM-0001 | Plant DCS - Supplier Operation and Maintenance Manual |  | I01 | 00CJA | Plant DCS | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-IC-001 |  | 1 | 2027-07-22 | 2027-09-02 |  | 2028-01-20 |  |  | PO MR-IC-001
ALP-I01-00CJA-ME-PRC-0001 | Plant DCS - Supplier Installation and Erection Manual |  | I01 | 00CJA | Plant DCS | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-IC-001 |  | 1 | 2027-07-15 | 2027-08-05 |  | 2027-09-16 |  |  | PO MR-IC-001
ALP-I01-00CJA-ME-TRP-0001 | Plant DCS - Factory Acceptance Test Report |  | I01 | 00CJA | Plant DCS | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-IC-001 |  | 1 | 2027-09-23 | 2027-09-30 |  | 2027-10-14 |  |  | PO MR-IC-001
ALP-I01-00CJA-ME-TST-0001 | Plant DCS - Factory Acceptance Test Procedure |  | I01 | 00CJA | Plant DCS | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-IC-001 |  | 1 | 2027-06-17 | 2027-07-08 |  | 2027-08-19 |  |  | PO MR-IC-001
ALP-I02-00CQA-EL-WIR-0001 | Continuous Emission Monitoring System - Supplier Electrical Schematics and Wiring Diagrams |  | I02 | 00CQA | Continuous emission monitoring | electrical | WIR | F | review |  |  | 8 | 8 | EWP-01-IC-01 | CWP-01-IC-01 | CWA-01 | MR-IC-002 |  | 1 | 2027-04-15 | 2027-05-06 |  | 2027-06-17 | 2028-02-07 | 167 | PO MR-IC-002
ALP-I02-00CQA-IC-DSH-0001 | Continuous Emission Monitoring System - Supplier Instrument List and Datasheets |  | I02 | 00CQA | Continuous emission monitoring | i_and_c | DSH | E | review |  |  | 15 | 7 |  |  |  | MR-IC-002 | 00CQA10 | 1 | 2027-04-22 | 2027-05-06 |  | 2027-06-17 |  |  | PO MR-IC-002
ALP-I02-00CQA-IC-IOL-0001 | Continuous Emission Monitoring System - Supplier I/O List, Control Philosophy and Interface Signals |  | I02 | 00CQA | Continuous emission monitoring | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-IC-002 |  | 1 | 2027-04-05 | 2027-04-26 |  | 2027-05-26 |  |  | PO MR-IC-002
ALP-I02-00CQA-ME-CAL-0001 | Continuous Emission Monitoring System - Supplier Design Calculations |  | I02 | 00CQA | Continuous emission monitoring | mechanical | CAL | E | review |  |  | 2 | 6 |  |  |  | MR-IC-002 |  | 1 | 2027-04-05 | 2027-04-26 |  | 2027-05-26 |  |  | PO MR-IC-002
ALP-I02-00CQA-ME-DSH-0001 | Continuous Emission Monitoring System - Supplier Certified Datasheets and Performance Curves |  | I02 | 00CQA | Continuous emission monitoring | mechanical | DSH | E | review |  |  | 4 | 8 |  |  |  | MR-IC-002 | 00CQA10 | 1 | 2027-03-22 | 2027-04-05 |  | 2027-05-06 |  |  | PO MR-IC-002
ALP-I02-00CQA-ME-GAD-0001 | Continuous Emission Monitoring System - Supplier GA Drawings |  | I02 | 00CQA | Continuous emission monitoring | mechanical | GAD | L | review |  |  | 4 | 10 | EWP-01-IC-01 | CWP-01-IC-01 | CWA-01 | MR-IC-002 | 00CQA10 | 1 | 2027-03-17 | 2027-04-14 |  | 2027-05-17 | 2028-02-07 | 190 | PO MR-IC-002
ALP-I02-00CQA-ME-ITP-0001 | Continuous Emission Monitoring System - Supplier Inspection and Test Plan |  | I02 | 00CQA | Continuous emission monitoring | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-IC-002 |  | 1 | 2027-03-22 | 2027-04-05 |  | 2027-04-26 |  |  | PO MR-IC-002
ALP-I02-00CQA-ME-LST-0001 | Continuous Emission Monitoring System - Spare Parts and Special Tools Lists |  | I02 | 00CQA | Continuous emission monitoring | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-IC-002 |  | 1 | 2027-04-26 | 2027-05-17 |  | 2027-06-28 |  |  | PO MR-IC-002
ALP-I02-00CQA-ME-MDB-0001 | Continuous Emission Monitoring System - Manufacturing Record Book and Conformity Certificates |  | I02 | 00CQA | Continuous emission monitoring | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-IC-002 |  | 1 | 2027-09-13 | 2027-09-27 |  | 2027-11-22 |  |  | PO MR-IC-002
ALP-I02-00CQA-ME-OMM-0001 | Continuous Emission Monitoring System - Supplier Operation and Maintenance Manual |  | I02 | 00CQA | Continuous emission monitoring | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-IC-002 |  | 1 | 2027-07-05 | 2027-08-16 |  | 2028-01-03 |  |  | PO MR-IC-002
ALP-I02-00CQA-ME-PRC-0001 | Continuous Emission Monitoring System - Supplier Installation and Erection Manual |  | I02 | 00CQA | Continuous emission monitoring | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-IC-002 |  | 1 | 2027-06-28 | 2027-07-19 |  | 2027-08-30 |  |  | PO MR-IC-002
ALP-I02-00CQA-ME-TRP-0001 | Continuous Emission Monitoring System - Factory Acceptance Test Report |  | I02 | 00CQA | Continuous emission monitoring | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-IC-002 |  | 1 | 2027-09-06 | 2027-09-13 |  | 2027-09-27 |  |  | PO MR-IC-002
ALP-I02-00CQA-ME-TST-0001 | Continuous Emission Monitoring System - Factory Acceptance Test Procedure |  | I02 | 00CQA | Continuous emission monitoring | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-IC-002 |  | 1 | 2027-05-31 | 2027-06-21 |  | 2027-08-02 |  |  | PO MR-IC-002
ALP-I03-00QUA-EL-WIR-0001 | Steam/Water Analysis System - Supplier Electrical Schematics and Wiring Diagrams |  | I03 | 00QUA | Sampling and SWAS | electrical | WIR | F | review |  |  | 8 | 8 | EWP-01-IC-01 | CWP-01-IC-01 | CWA-01 | MR-IC-003 |  | 1 | 2027-04-15 | 2027-05-06 |  | 2027-06-17 | 2028-02-07 | 167 | PO MR-IC-003
ALP-I03-00QUA-IC-DSH-0001 | Steam/Water Analysis System - Supplier Instrument List and Datasheets |  | I03 | 00QUA | Sampling and SWAS | i_and_c | DSH | E | review |  |  | 30 | 10 |  |  |  | MR-IC-003 | 00QUA10 00QUA10AC001 | 1 | 2027-04-22 | 2027-05-06 |  | 2027-06-17 |  |  | PO MR-IC-003
ALP-I03-00QUA-IC-IOL-0001 | Steam/Water Analysis System - Supplier I/O List, Control Philosophy and Interface Signals |  | I03 | 00QUA | Sampling and SWAS | i_and_c | IOL | P | review |  |  | 2 | 6 |  |  |  | MR-IC-003 |  | 1 | 2027-04-05 | 2027-04-26 |  | 2027-05-26 |  |  | PO MR-IC-003
ALP-I03-00QUA-ME-CAL-0001 | Steam/Water Analysis System - Supplier Design Calculations |  | I03 | 00QUA | Sampling and SWAS | mechanical | CAL | E | review |  |  | 1 | 5 |  |  |  | MR-IC-003 |  | 1 | 2027-04-05 | 2027-04-26 |  | 2027-05-26 |  |  | PO MR-IC-003
ALP-I03-00QUA-ME-DSH-0001 | Steam/Water Analysis System - Supplier Certified Datasheets and Performance Curves |  | I03 | 00QUA | Sampling and SWAS | mechanical | DSH | E | review |  |  | 3 | 7 |  |  |  | MR-IC-003 | 00QUA10 00QUA10AC001 | 1 | 2027-03-22 | 2027-04-05 |  | 2027-05-06 |  |  | PO MR-IC-003
ALP-I03-00QUA-ME-GAD-0001 | Steam/Water Analysis System - Supplier GA Drawings |  | I03 | 00QUA | Sampling and SWAS | mechanical | GAD | L | review |  |  | 3 | 8.5 | EWP-01-IC-01 | CWP-01-IC-01 | CWA-01 | MR-IC-003 | 00QUA10 00QUA10AC001 | 1 | 2027-03-17 | 2027-04-14 |  | 2027-05-17 | 2028-02-07 | 190 | PO MR-IC-003
ALP-I03-00QUA-ME-ITP-0001 | Steam/Water Analysis System - Supplier Inspection and Test Plan |  | I03 | 00QUA | Sampling and SWAS | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-IC-003 |  | 1 | 2027-03-22 | 2027-04-05 |  | 2027-04-26 |  |  | PO MR-IC-003
ALP-I03-00QUA-ME-LST-0001 | Steam/Water Analysis System - Spare Parts and Special Tools Lists |  | I03 | 00QUA | Sampling and SWAS | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-IC-003 |  | 1 | 2027-04-26 | 2027-05-17 |  | 2027-06-28 |  |  | PO MR-IC-003
ALP-I03-00QUA-ME-MDB-0001 | Steam/Water Analysis System - Manufacturing Record Book and Conformity Certificates |  | I03 | 00QUA | Sampling and SWAS | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-IC-003 |  | 1 | 2027-09-13 | 2027-09-27 |  | 2027-11-22 |  |  | PO MR-IC-003
ALP-I03-00QUA-ME-OMM-0001 | Steam/Water Analysis System - Supplier Operation and Maintenance Manual |  | I03 | 00QUA | Sampling and SWAS | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-IC-003 |  | 1 | 2027-07-05 | 2027-08-16 |  | 2028-01-03 |  |  | PO MR-IC-003
ALP-I03-00QUA-ME-PRC-0001 | Steam/Water Analysis System - Supplier Installation and Erection Manual |  | I03 | 00QUA | Sampling and SWAS | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-IC-003 |  | 1 | 2027-06-28 | 2027-07-19 |  | 2027-08-30 |  |  | PO MR-IC-003
ALP-I03-00QUA-ME-TRP-0001 | Steam/Water Analysis System - Factory Acceptance Test Report |  | I03 | 00QUA | Sampling and SWAS | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-IC-003 |  | 1 | 2027-09-06 | 2027-09-13 |  | 2027-09-27 |  |  | PO MR-IC-003
ALP-I03-00QUA-ME-TST-0001 | Steam/Water Analysis System - Factory Acceptance Test Procedure |  | I03 | 00QUA | Sampling and SWAS | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-IC-003 |  | 1 | 2027-05-31 | 2027-06-21 |  | 2027-08-02 |  |  | PO MR-IC-003
ALP-I03-00QUA-PR-PID-0001 | Steam/Water Analysis System - Supplier P&IDs |  | I03 | 00QUA | Sampling and SWAS | process | PID | F | approval |  |  | 2 | 10 |  |  |  | MR-IC-003 |  | 1 | 2027-03-22 | 2027-04-26 |  | 2027-05-26 |  |  | PO MR-IC-003
ALP-I04-00000-ME-DSH-0001 | Field Instruments - Supplier Catalogues and Material Datasheets |  | I04 | 00000 | plant general | mechanical | DSH | E | review |  |  | 1 | 6 |  |  |  | MR-IC-004 |  | 1 | 2027-03-30 | 2027-04-13 |  | 2027-04-30 |  |  | PO MR-IC-004
ALP-I04-00000-ME-ITP-0001 | Field Instruments - Supplier Inspection and Test Plan |  | I04 | 00000 | plant general | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-IC-004 |  | 1 | 2027-03-30 | 2027-04-13 |  | 2027-04-30 |  |  | PO MR-IC-004
ALP-I04-00000-ME-MDB-0001 | Field Instruments - Manufacturing Record Book and Conformity Certificates |  | I04 | 00000 | plant general | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-IC-004 |  | 1 | 2027-08-26 | 2027-09-09 |  | 2027-11-04 |  |  | PO MR-IC-004
ALP-I05-00000-ME-DSH-0001 | Control Valves - Supplier Catalogues and Material Datasheets |  | I05 | 00000 | plant general | mechanical | DSH | E | review |  |  | 1 | 6 |  |  |  | MR-IC-005 |  | 1 | 2027-04-01 | 2027-04-15 |  | 2027-05-06 |  |  | PO MR-IC-005
ALP-I05-00000-ME-ITP-0001 | Control Valves - Supplier Inspection and Test Plan |  | I05 | 00000 | plant general | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-IC-005 |  | 1 | 2027-04-01 | 2027-04-15 |  | 2027-05-06 |  |  | PO MR-IC-005
ALP-I05-00000-ME-MDB-0001 | Control Valves - Manufacturing Record Book and Conformity Certificates |  | I05 | 00000 | plant general | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-IC-005 |  | 1 | 2027-09-23 | 2027-10-07 |  | 2027-12-02 |  |  | PO MR-IC-005
ALP-I06-00SGY-EL-WIR-0001 | Fire Detection and Alarm System - Supplier Electrical Schematics and Wiring Diagrams |  | I06 | 00SGY | Fire detection and alarm | electrical | WIR | F | review |  |  | 8 | 8 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 | MR-IC-006 |  | 1 | 2027-06-11 | 2027-07-02 |  | 2027-07-30 | 2027-11-22 | 81 | PO MR-IC-006
ALP-I06-00SGY-IC-IOL-0001 | Fire Detection and Alarm System - Supplier I/O List, Control Philosophy and Interface Signals |  | I06 | 00SGY | Fire detection and alarm | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-IC-006 |  | 1 | 2027-06-04 | 2027-06-25 |  | 2027-07-16 |  |  | PO MR-IC-006
ALP-I06-00SGY-ME-CAL-0001 | Fire Detection and Alarm System - Supplier Design Calculations |  | I06 | 00SGY | Fire detection and alarm | mechanical | CAL | E | review |  |  | 10 | 14 |  |  |  | MR-IC-006 |  | 1 | 2027-06-04 | 2027-06-25 |  | 2027-07-16 |  |  | PO MR-IC-006
ALP-I06-00SGY-ME-DSH-0001 | Fire Detection and Alarm System - Supplier Certified Datasheets and Performance Curves |  | I06 | 00SGY | Fire detection and alarm | mechanical | DSH | E | review |  |  | 30 | 34 |  |  |  | MR-IC-006 | 00SGY10 | 1 | 2027-05-28 | 2027-06-11 |  | 2027-07-02 |  |  | PO MR-IC-006
ALP-I06-00SGY-ME-GAD-0001 | Fire Detection and Alarm System - Supplier GA Drawings |  | I06 | 00SGY | Fire detection and alarm | mechanical | GAD | L | review |  |  | 30 | 49 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 | MR-IC-006 | 00SGY10 | 1 | 2027-05-21 | 2027-06-18 |  | 2027-07-09 | 2027-11-22 | 96 | PO MR-IC-006
ALP-I06-00SGY-ME-ITP-0001 | Fire Detection and Alarm System - Supplier Inspection and Test Plan |  | I06 | 00SGY | Fire detection and alarm | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-IC-006 |  | 1 | 2027-05-28 | 2027-06-11 |  | 2027-06-25 |  |  | PO MR-IC-006
ALP-I06-00SGY-ME-LST-0001 | Fire Detection and Alarm System - Spare Parts and Special Tools Lists |  | I06 | 00SGY | Fire detection and alarm | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-IC-006 |  | 1 | 2027-06-18 | 2027-07-09 |  | 2027-08-06 |  |  | PO MR-IC-006
ALP-I06-00SGY-ME-MDB-0001 | Fire Detection and Alarm System - Manufacturing Record Book and Conformity Certificates |  | I06 | 00SGY | Fire detection and alarm | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-IC-006 |  | 1 | 2027-09-17 | 2027-10-01 |  | 2027-11-26 |  |  | PO MR-IC-006
ALP-I06-00SGY-ME-OMM-0001 | Fire Detection and Alarm System - Supplier Operation and Maintenance Manual |  | I06 | 00SGY | Fire detection and alarm | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-IC-006 |  | 1 | 2027-07-09 | 2027-08-20 |  | 2028-01-07 |  |  | PO MR-IC-006
ALP-I06-00SGY-ME-PRC-0001 | Fire Detection and Alarm System - Supplier Installation and Erection Manual |  | I06 | 00SGY | Fire detection and alarm | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-IC-006 |  | 1 | 2027-07-02 | 2027-07-23 |  | 2027-09-03 |  |  | PO MR-IC-006
ALP-I06-00SGY-ME-TRP-0001 | Fire Detection and Alarm System - Factory Acceptance Test Report |  | I06 | 00SGY | Fire detection and alarm | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-IC-006 |  | 1 | 2027-09-10 | 2027-09-17 |  | 2027-10-01 |  |  | PO MR-IC-006
ALP-I06-00SGY-ME-TST-0001 | Fire Detection and Alarm System - Factory Acceptance Test Procedure |  | I06 | 00SGY | Fire detection and alarm | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-IC-006 |  | 1 | 2027-06-04 | 2027-06-25 |  | 2027-08-06 |  |  | PO MR-IC-006
ALP-I07-00CYA-EL-WIR-0001 | Telecom, CCTV, Access Control and Perimeter Security - Supplier Electrical Schematics and Wiring Diagrams |  | I07 | 00CYA | Telecom, CCTV, access control, security | electrical | WIR | F | review |  |  | 12 | 10 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 | MR-IC-007 |  | 1 | 2027-06-08 | 2027-06-29 |  | 2027-07-27 | 2027-11-22 | 84 | PO MR-IC-007
ALP-I07-00CYA-IC-IOL-0001 | Telecom, CCTV, Access Control and Perimeter Security - Supplier I/O List, Control Philosophy and Interface Signals |  | I07 | 00CYA | Telecom, CCTV, access control, security | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-IC-007 |  | 1 | 2027-06-01 | 2027-06-22 |  | 2027-07-13 |  |  | PO MR-IC-007
ALP-I07-00CYA-ME-CAL-0001 | Telecom, CCTV, Access Control and Perimeter Security - Supplier Design Calculations |  | I07 | 00CYA | Telecom, CCTV, access control, security | mechanical | CAL | E | review |  |  | 7 | 11 |  |  |  | MR-IC-007 |  | 1 | 2027-06-01 | 2027-06-22 |  | 2027-07-13 |  |  | PO MR-IC-007
ALP-I07-00CYA-ME-DSH-0001 | Telecom, CCTV, Access Control and Perimeter Security - Supplier Certified Datasheets and Performance Curves |  | I07 | 00CYA | Telecom, CCTV, access control, security | mechanical | DSH | E | review |  |  | 20 | 24 |  |  |  | MR-IC-007 | 00CYA10 | 1 | 2027-05-25 | 2027-06-08 |  | 2027-06-29 |  |  | PO MR-IC-007
ALP-I07-00CYA-ME-GAD-0001 | Telecom, CCTV, Access Control and Perimeter Security - Supplier GA Drawings |  | I07 | 00CYA | Telecom, CCTV, access control, security | mechanical | GAD | L | review |  |  | 20 | 34 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 | MR-IC-007 | 00CYA10 | 1 | 2027-05-18 | 2027-06-15 |  | 2027-07-06 | 2027-11-22 | 99 | PO MR-IC-007
ALP-I07-00CYA-ME-ITP-0001 | Telecom, CCTV, Access Control and Perimeter Security - Supplier Inspection and Test Plan |  | I07 | 00CYA | Telecom, CCTV, access control, security | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-IC-007 |  | 1 | 2027-05-25 | 2027-06-08 |  | 2027-06-22 |  |  | PO MR-IC-007
ALP-I07-00CYA-ME-LST-0001 | Telecom, CCTV, Access Control and Perimeter Security - Spare Parts and Special Tools Lists |  | I07 | 00CYA | Telecom, CCTV, access control, security | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-IC-007 |  | 1 | 2027-06-15 | 2027-07-06 |  | 2027-08-03 |  |  | PO MR-IC-007
ALP-I07-00CYA-ME-MDB-0001 | Telecom, CCTV, Access Control and Perimeter Security - Manufacturing Record Book and Conformity Certificates |  | I07 | 00CYA | Telecom, CCTV, access control, security | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-IC-007 |  | 1 | 2027-09-14 | 2027-09-28 |  | 2027-11-23 |  |  | PO MR-IC-007
ALP-I07-00CYA-ME-OMM-0001 | Telecom, CCTV, Access Control and Perimeter Security - Supplier Operation and Maintenance Manual |  | I07 | 00CYA | Telecom, CCTV, access control, security | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-IC-007 |  | 1 | 2027-07-06 | 2027-08-17 |  | 2028-01-04 |  |  | PO MR-IC-007
ALP-I07-00CYA-ME-PRC-0001 | Telecom, CCTV, Access Control and Perimeter Security - Supplier Installation and Erection Manual |  | I07 | 00CYA | Telecom, CCTV, access control, security | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-IC-007 |  | 1 | 2027-06-29 | 2027-07-20 |  | 2027-08-31 |  |  | PO MR-IC-007
ALP-I07-00CYA-ME-TRP-0001 | Telecom, CCTV, Access Control and Perimeter Security - Factory Acceptance Test Report |  | I07 | 00CYA | Telecom, CCTV, access control, security | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-IC-007 |  | 1 | 2027-09-07 | 2027-09-14 |  | 2027-09-28 |  |  | PO MR-IC-007
ALP-I07-00CYA-ME-TST-0001 | Telecom, CCTV, Access Control and Perimeter Security - Factory Acceptance Test Procedure |  | I07 | 00CYA | Telecom, CCTV, access control, security | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-IC-007 |  | 1 | 2027-06-01 | 2027-06-22 |  | 2027-08-03 |  |  | PO MR-IC-007
ALP-I08-00CJG-EL-WIR-0001 | BOP Safety Instrumented System - Supplier Electrical Schematics and Wiring Diagrams | IEC 61511 | I08 | 00CJG | Safety instrumented systems (BOP) | electrical | WIR | F | review |  |  | 4 | 6 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 | MR-IC-008 |  | 1 | 2027-06-14 | 2027-07-05 |  | 2027-08-11 | 2027-11-22 | 73 | PO MR-IC-008
ALP-I08-00CJG-IC-IOL-0001 | BOP Safety Instrumented System - Supplier I/O List, Control Philosophy and Interface Signals | IEC 61511 | I08 | 00CJG | Safety instrumented systems (BOP) | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-IC-008 |  | 1 | 2027-06-04 | 2027-06-25 |  | 2027-07-23 |  |  | PO MR-IC-008
ALP-I08-00CJG-IC-LOG-0001 | BOP Safety Instrumented System - Supplier Logic Diagrams | IEC 61511 | I08 | 00CJG | Safety instrumented systems (BOP) | i_and_c | LOG | F | review |  |  | 150 | 83 |  |  |  | MR-IC-008 |  | 1 | 2027-07-22 | 2027-08-19 |  | 2027-10-13 |  |  | PO MR-IC-008
ALP-I08-00CJG-ME-CAL-0001 | BOP Safety Instrumented System - Supplier Design Calculations | IEC 61511 | I08 | 00CJG | Safety instrumented systems (BOP) | mechanical | CAL | E | review |  |  | 2 | 6 |  |  |  | MR-IC-008 |  | 1 | 2027-06-04 | 2027-06-25 |  | 2027-07-23 |  |  | PO MR-IC-008
ALP-I08-00CJG-ME-DSH-0001 | BOP Safety Instrumented System - Supplier Certified Datasheets and Performance Curves | IEC 61511 | I08 | 00CJG | Safety instrumented systems (BOP) | mechanical | DSH | E | review |  |  | 4 | 8 |  |  |  | MR-IC-008 | 00CJG10 | 1 | 2027-05-25 | 2027-06-08 |  | 2027-07-05 |  |  | PO MR-IC-008
ALP-I08-00CJG-ME-GAD-0001 | BOP Safety Instrumented System - Supplier GA Drawings | IEC 61511 | I08 | 00CJG | Safety instrumented systems (BOP) | mechanical | GAD | L | review |  |  | 4 | 10 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 | MR-IC-008 | 00CJG10 | 1 | 2027-05-20 | 2027-06-17 |  | 2027-07-14 | 2027-11-22 | 93 | PO MR-IC-008
ALP-I08-00CJG-ME-ITP-0001 | BOP Safety Instrumented System - Supplier Inspection and Test Plan | IEC 61511 | I08 | 00CJG | Safety instrumented systems (BOP) | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-IC-008 |  | 1 | 2027-05-25 | 2027-06-08 |  | 2027-06-25 |  |  | PO MR-IC-008
ALP-I08-00CJG-ME-LST-0001 | BOP Safety Instrumented System - Spare Parts and Special Tools Lists | IEC 61511 | I08 | 00CJG | Safety instrumented systems (BOP) | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-IC-008 |  | 1 | 2027-06-23 | 2027-07-14 |  | 2027-08-19 |  |  | PO MR-IC-008
ALP-I08-00CJG-ME-MDB-0001 | BOP Safety Instrumented System - Manufacturing Record Book and Conformity Certificates | IEC 61511 | I08 | 00CJG | Safety instrumented systems (BOP) | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-IC-008 |  | 1 | 2027-10-21 | 2027-11-04 |  | 2027-12-30 |  |  | PO MR-IC-008
ALP-I08-00CJG-ME-OMM-0001 | BOP Safety Instrumented System - Supplier Operation and Maintenance Manual | IEC 61511 | I08 | 00CJG | Safety instrumented systems (BOP) | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-IC-008 |  | 1 | 2027-08-12 | 2027-09-23 |  | 2028-02-10 |  |  | PO MR-IC-008
ALP-I08-00CJG-ME-PRC-0001 | BOP Safety Instrumented System - Supplier Installation and Erection Manual | IEC 61511 | I08 | 00CJG | Safety instrumented systems (BOP) | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-IC-008 |  | 1 | 2027-08-05 | 2027-08-26 |  | 2027-10-07 |  |  | PO MR-IC-008
ALP-I08-00CJG-ME-TRP-0001 | BOP Safety Instrumented System - Factory Acceptance Test Report | IEC 61511 | I08 | 00CJG | Safety instrumented systems (BOP) | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-IC-008 |  | 1 | 2027-10-14 | 2027-10-21 |  | 2027-11-04 |  |  | PO MR-IC-008
ALP-I08-00CJG-ME-TST-0001 | BOP Safety Instrumented System - Factory Acceptance Test Procedure | IEC 61511 | I08 | 00CJG | Safety instrumented systems (BOP) | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-IC-008 |  | 1 | 2027-07-08 | 2027-07-29 |  | 2027-09-09 |  |  | PO MR-IC-008
ALP-I09-00CKA-EL-WIR-0001 | Operator Training Simulator, Historian and Performance Monitoring - Supplier Electrical Schematics and Wiring Diagrams |  | I09 | 00CKA | Historian, performance monitoring and operator training simulator | electrical | WIR | F | review |  |  | 4 | 6 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 | MR-IC-009 |  | 1 | 2027-07-22 | 2027-08-12 |  | 2027-10-07 | 2027-11-22 | 32 | PO MR-IC-009
ALP-I09-00CKA-IC-IOL-0001 | Operator Training Simulator, Historian and Performance Monitoring - Supplier I/O List, Control Philosophy and Interface Signals |  | I09 | 00CKA | Historian, performance monitoring and operator training simulator | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-IC-009 |  | 1 | 2027-07-08 | 2027-07-29 |  | 2027-09-09 |  |  | PO MR-IC-009
ALP-I09-00CKA-ME-CAL-0001 | Operator Training Simulator, Historian and Performance Monitoring - Supplier Design Calculations |  | I09 | 00CKA | Historian, performance monitoring and operator training simulator | mechanical | CAL | E | review |  |  | 2 | 6 |  |  |  | MR-IC-009 |  | 1 | 2027-07-08 | 2027-07-29 |  | 2027-09-09 |  |  | PO MR-IC-009
ALP-I09-00CKA-ME-DSH-0001 | Operator Training Simulator, Historian and Performance Monitoring - Supplier Certified Datasheets and Performance Curves |  | I09 | 00CKA | Historian, performance monitoring and operator training simulator | mechanical | DSH | E | review |  |  | 6 | 10 |  |  |  | MR-IC-009 | 00CKA10 | 1 | 2027-06-17 | 2027-07-01 |  | 2027-08-12 |  |  | PO MR-IC-009
ALP-I09-00CKA-ME-GAD-0001 | Operator Training Simulator, Historian and Performance Monitoring - Supplier GA Drawings |  | I09 | 00CKA | Historian, performance monitoring and operator training simulator | mechanical | GAD | L | review |  |  | 6 | 13 | EWP-11-IC-01 | CWP-11-IC-01 | CWA-11 | MR-IC-009 | 00CKA10 | 1 | 2027-06-17 | 2027-07-15 |  | 2027-08-26 | 2027-11-22 | 62 | PO MR-IC-009
ALP-I09-00CKA-ME-ITP-0001 | Operator Training Simulator, Historian and Performance Monitoring - Supplier Inspection and Test Plan |  | I09 | 00CKA | Historian, performance monitoring and operator training simulator | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-IC-009 |  | 1 | 2027-06-17 | 2027-07-01 |  | 2027-07-29 |  |  | PO MR-IC-009
ALP-I09-00CKA-ME-LST-0001 | Operator Training Simulator, Historian and Performance Monitoring - Spare Parts and Special Tools Lists |  | I09 | 00CKA | Historian, performance monitoring and operator training simulator | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-IC-009 |  | 1 | 2027-08-05 | 2027-08-26 |  | 2027-10-21 |  |  | PO MR-IC-009
ALP-I09-00CKA-ME-MDB-0001 | Operator Training Simulator, Historian and Performance Monitoring - Manufacturing Record Book and Conformity Certificates |  | I09 | 00CKA | Historian, performance monitoring and operator training simulator | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-IC-009 |  | 1 | 2028-02-10 | 2028-02-24 |  | 2028-04-20 |  |  | PO MR-IC-009
ALP-I09-00CKA-ME-OMM-0001 | Operator Training Simulator, Historian and Performance Monitoring - Supplier Operation and Maintenance Manual |  | I09 | 00CKA | Historian, performance monitoring and operator training simulator | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-IC-009 |  | 1 | 2027-12-02 | 2028-01-13 |  | 2028-06-01 |  |  | PO MR-IC-009
ALP-I09-00CKA-ME-PRC-0001 | Operator Training Simulator, Historian and Performance Monitoring - Supplier Installation and Erection Manual |  | I09 | 00CKA | Historian, performance monitoring and operator training simulator | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-IC-009 |  | 1 | 2027-11-25 | 2027-12-16 |  | 2028-01-27 |  |  | PO MR-IC-009
ALP-I09-00CKA-ME-TRP-0001 | Operator Training Simulator, Historian and Performance Monitoring - Factory Acceptance Test Report |  | I09 | 00CKA | Historian, performance monitoring and operator training simulator | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-IC-009 |  | 1 | 2028-02-03 | 2028-02-10 |  | 2028-02-24 |  |  | PO MR-IC-009
ALP-I09-00CKA-ME-TST-0001 | Operator Training Simulator, Historian and Performance Monitoring - Factory Acceptance Test Procedure |  | I09 | 00CKA | Historian, performance monitoring and operator training simulator | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-IC-009 |  | 1 | 2027-10-28 | 2027-11-18 |  | 2027-12-30 |  |  | PO MR-IC-009
ALP-I10-00000-ME-DSH-0001 | Instrument Installation Materials - Supplier Catalogues and Material Datasheets | tubing, fittings, junction boxes, supports | I10 | 00000 | plant general | mechanical | DSH | E | review |  |  | 1 | 6 |  |  |  | MR-IC-010 |  | 1 | 2027-06-14 | 2027-06-28 |  | 2027-07-12 |  |  | PO MR-IC-010
ALP-I10-00000-ME-ITP-0001 | Instrument Installation Materials - Supplier Inspection and Test Plan | tubing, fittings, junction boxes, supports | I10 | 00000 | plant general | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-IC-010 |  | 1 | 2027-06-14 | 2027-06-28 |  | 2027-07-12 |  |  | PO MR-IC-010
ALP-I10-00000-ME-MDB-0001 | Instrument Installation Materials - Manufacturing Record Book and Conformity Certificates | tubing, fittings, junction boxes, supports | I10 | 00000 | plant general | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-IC-010 |  | 1 | 2027-08-09 | 2027-08-23 |  | 2027-10-18 |  |  | PO MR-IC-010
ALP-IEC-00000-GE-LST-0001 | Power Island - Terminal Points and Interface Data |  | IEC | 00000 | plant general | general | LST | P | review |  |  |  | 80 | [5 empty] | 0 | 2026-09-07 | 2026-09-28 |  | 2026-11-02 |  |  |  | IEC-ALP-IF-001 | A IFR 2026-09-28
ALP-IEC-00000-GE-RPT-0001 | Power Island and Balance of Plant - Division of Responsibility |  | IEC | 00000 | plant general | general | RPT | D | review |  |  |  | 60 | [5 empty] | 0 | 2026-09-07 | 2026-09-28 |  | 2026-11-02 |  |  |  | IEC-ALP-DOR-001 | 0 IFR 2026-09-27
ALP-IEC-00000-GE-SPC-0001 | Power Island Interface Requirements to the EPC |  | IEC | 00000 | plant general | general | SPC | E | approval |  |  |  | 80 | [5 empty] | 0 | 2026-08-31 | 2026-09-28 |  | 2026-11-02 |  |  |  | IEC-ALP-REQ-001 | 0 IFR 2026-09-27
ALP-IEC-00000-PI-LST-0001 | Terminal Point Nozzle Loads | IF-001 attachment A | IEC | 00000 | plant general | piping | LST | P | review |  |  |  | 80 | [5 empty] | 0 | 2026-12-07 | 2026-12-28 |  | 2027-01-25 |  |  |  | IEC-ALP-IF-001-A
ALP-IEC-10BAA-EL-SLD-0001 | Power Island Single Line Diagram | generators, GCB, GSU, UAT tap-offs, SFC | IEC | 10BAA | GT generator busduct | electrical | SLD | F | approval |  |  | 2 | 75 | [5 empty] | 0 | 2026-12-07 | 2026-12-28 |  | 2027-02-08 |  |  |  | IEC-ALP-SLD-101
ALP-IEC-10BAT-CM-CMP-0001 | Generator Step-Up Transformers - Supplier Commissioning Procedures | IEC | IEC | 10BAT | GT generator step-up transformer | commissioning | CMP | B | approval |  |  | 1 | 10 |  |  |  | MR-EL-102 |  | 0 | 2027-05-03 | 2027-05-31 |  | 2027-08-23 |  |  | PO MR-EL-102
ALP-IEC-10BAT-CV-CAL-0001 | Generator Step-Up Transformers - Supplier Foundation Loads and Anchor Bolt Drawings | IEC | IEC | 10BAT | GT generator step-up transformer | civil | CAL | E | review |  |  | 1 | 5 |  |  |  | MR-EL-102 |  | 0 | 2026-11-23 | 2026-12-14 |  | 2027-01-11 |  |  | PO MR-EL-102
ALP-IEC-10BAT-EL-DSH-0001 | Generator Step-Up Transformers - Supplier Certified Datasheets and Performance Curves | IEC | IEC | 10BAT | GT generator step-up transformer | electrical | DSH | E | review |  |  | 2 | 6 |  |  |  | MR-EL-102 | 10BAT10 20BAT10 | 0 | 2026-09-14 | 2026-09-28 |  | 2026-12-28 |  |  |  | IEC-ALP-DS-106 | 0 IFR 2026-09-27
ALP-IEC-10BAT-EL-GAD-0001 | Generator Step-Up Transformers - Supplier GA Drawings | IEC | IEC | 10BAT | GT generator step-up transformer | electrical | GAD | L | review |  |  | 2 | 7 | EWP-01-EL-01 | CWP-01-EL-01 | CWA-01 | MR-EL-102 | 10BAT10 20BAT10 | 0 | 2026-08-31 | 2026-09-28 |  | 2027-01-11 | 2028-01-10 | 260 |  | IEC-ALP-GA-104 | 0 IFR 2026-09-28
ALP-IEC-10BAT-EL-WIR-0001 | Generator Step-Up Transformers - Supplier Electrical Schematics and Wiring Diagrams | IEC | IEC | 10BAT | GT generator step-up transformer | electrical | WIR | F | review |  |  | 24 | 16 | EWP-01-EL-01 | CWP-01-EL-01 | CWA-01 | MR-EL-102 |  | 0 | 2026-12-21 | 2027-01-11 |  | 2027-03-08 | 2028-01-10 | 220 | PO MR-EL-102
ALP-IEC-10BAT-IC-DSH-0001 | Generator Step-Up Transformers - Supplier Instrument List and Datasheets | IEC | IEC | 10BAT | GT generator step-up transformer | i_and_c | DSH | E | review |  |  | 25 | 9 |  |  |  | MR-EL-102 | 10BAT10 20BAT10 | 0 | 2026-12-28 | 2027-01-11 |  | 2027-03-08 |  |  | PO MR-EL-102
ALP-IEC-10BAT-IC-IOL-0001 | Generator Step-Up Transformers - Supplier I/O List, Control Philosophy and Interface Signals | IEC | IEC | 10BAT | GT generator step-up transformer | i_and_c | IOL | P | review |  |  | 2 | 6 |  |  |  | MR-EL-102 |  | 0 | 2026-12-07 | 2026-12-28 |  | 2027-02-08 |  |  | PO MR-EL-102
ALP-IEC-10BAT-ME-CAL-0001 | Generator Step-Up Transformers - Supplier Design Calculations | IEC | IEC | 10BAT | GT generator step-up transformer | mechanical | CAL | E | review |  |  | 1 | 5 |  |  |  | MR-EL-102 |  | 0 | 2026-12-07 | 2026-12-28 |  | 2027-02-08 |  |  | PO MR-EL-102
ALP-IEC-10BAT-ME-ITP-0001 | Generator Step-Up Transformers - Supplier Inspection and Test Plan | IEC | IEC | 10BAT | GT generator step-up transformer | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-EL-102 |  | 0 | 2026-11-16 | 2026-11-30 |  | 2026-12-28 |  |  | PO MR-EL-102
ALP-IEC-10BAT-ME-LST-0001 | Generator Step-Up Transformers - Spare Parts and Special Tools Lists | IEC | IEC | 10BAT | GT generator step-up transformer | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-EL-102 |  | 0 | 2027-01-04 | 2027-01-25 |  | 2027-03-22 |  |  | PO MR-EL-102
ALP-IEC-10BAT-ME-MDB-0001 | Generator Step-Up Transformers - Manufacturing Record Book and Conformity Certificates | IEC | IEC | 10BAT | GT generator step-up transformer | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-EL-102 |  | 0 | 2027-09-20 | 2027-10-04 |  | 2027-11-29 |  |  | PO MR-EL-102
ALP-IEC-10BAT-ME-OMM-0001 | Generator Step-Up Transformers - Supplier Operation and Maintenance Manual | IEC | IEC | 10BAT | GT generator step-up transformer | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-EL-102 |  | 0 | 2027-07-12 | 2027-08-23 |  | 2028-01-10 |  |  | PO MR-EL-102
ALP-IEC-10BAT-ME-PRC-0001 | Generator Step-Up Transformers - Supplier Installation and Erection Manual | IEC | IEC | 10BAT | GT generator step-up transformer | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-EL-102 |  | 0 | 2027-07-05 | 2027-07-26 |  | 2027-09-06 |  |  | PO MR-EL-102
ALP-IEC-10BAT-ME-TRP-0001 | Generator Step-Up Transformers - Factory Acceptance Test Report | IEC | IEC | 10BAT | GT generator step-up transformer | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-EL-102 |  | 0 | 2027-09-13 | 2027-09-20 |  | 2027-10-04 |  |  | PO MR-EL-102
ALP-IEC-10BAT-ME-TST-0001 | Generator Step-Up Transformers - Factory Acceptance Test Procedure | IEC | IEC | 10BAT | GT generator step-up transformer | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-EL-102 |  | 0 | 2027-06-07 | 2027-06-28 |  | 2027-08-09 |  |  | PO MR-EL-102
ALP-IEC-10HAA-CM-CMP-0001 | HRSG incl. SCR - Supplier Commissioning Procedures | IEC | IEC | 10HAA | HRSG pressure system | commissioning | CMP | B | approval |  |  | 8 | 24 |  |  |  | MR-ME-102 |  | 0 | 2027-04-19 | 2027-05-17 |  | 2027-08-09 |  |  | PO MR-ME-102
ALP-IEC-10HAA-CV-CAL-0001 | HRSG incl. SCR - Supplier Foundation Loads and Anchor Bolt Drawings | IEC | IEC | 10HAA | HRSG pressure system | civil | CAL | E | review |  |  | 10 | 14 |  |  |  | MR-ME-102 |  | 0 | 2026-11-23 | 2026-12-14 |  | 2027-01-11 |  |  |  | IEC-ALP-FL-102
ALP-IEC-10HAA-EL-WIR-0001 | HRSG incl. SCR - Supplier Electrical Schematics and Wiring Diagrams | IEC | IEC | 10HAA | HRSG pressure system | electrical | WIR | F | review |  |  | 80 | 44 | EWP-01-ME-01 | CWP-01-ME-01 | CWA-01 | MR-ME-102 |  | 0 | 2026-12-21 | 2027-01-11 |  | 2027-03-08 | 2027-10-18 | 160 | PO MR-ME-102
ALP-IEC-10HAA-IC-DSH-0001 | HRSG incl. SCR - Supplier Instrument List and Datasheets, Part 1 of 2 | IEC | IEC | 10HAA | HRSG pressure system | i_and_c | DSH | E | review |  |  | 138 | 31.6 |  |  |  | MR-ME-102 | 10HAA10 10HAA10AP001 10HAA10AP002 10HNA10 10HSA10 | 0 | 2026-12-28 | 2027-01-11 |  | 2027-03-08 |  |  | PO MR-ME-102
ALP-IEC-10HAA-IC-DSH-0002 | HRSG incl. SCR - Supplier Instrument List and Datasheets, Part 2 of 2 | IEC | IEC | 10HAA | HRSG pressure system | i_and_c | DSH | E | review |  |  | 137 | 31.4 |  |  |  | MR-ME-102 | 10HAA10 10HAA10AP001 10HAA10AP002 10HNA10 10HSA10 | 0 | 2026-12-28 | 2027-01-11 |  | 2027-03-08 |  |  | PO MR-ME-102
ALP-IEC-10HAA-IC-IOL-0001 | HRSG incl. SCR - Supplier I/O List, Control Philosophy and Interface Signals | IEC | IEC | 10HAA | HRSG pressure system | i_and_c | IOL | P | review |  |  | 14 | 18 |  |  |  | MR-ME-102 |  | 0 | 2026-12-07 | 2026-12-28 |  | 2027-02-08 |  |  | PO MR-ME-102
ALP-IEC-10HAA-ME-CAL-0001 | HRSG incl. SCR - Supplier Design Calculations | IEC | IEC | 10HAA | HRSG pressure system | mechanical | CAL | E | review |  |  | 17 | 21 |  |  |  | MR-ME-102 |  | 0 | 2026-12-07 | 2026-12-28 |  | 2027-02-08 |  |  | PO MR-ME-102
ALP-IEC-10HAA-ME-DSH-0001 | HRSG incl. SCR - Supplier Certified Datasheets and Performance Curves | IEC | IEC | 10HAA | HRSG pressure system | mechanical | DSH | E | review |  |  | 50 | 54 |  |  |  | MR-ME-102 | 10HAA10 10HAA10AP001 10HAA10AP002 10HNA10 10HSA10 | 0 | 2026-09-14 | 2026-09-28 |  | 2026-12-28 |  |  |  | IEC-ALP-DS-104 | C IFR 2026-12-04
ALP-IEC-10HAA-ME-GAD-0001 | HRSG incl. SCR - Supplier GA Drawings | IEC | IEC | 10HAA | HRSG pressure system | mechanical | GAD | L | review |  |  | 50 | 79 | EWP-01-ME-01 | CWP-01-ME-01 | CWA-01 | MR-ME-102 | 10HAA10 10HAA10AP001 10HAA10AP002 10HNA10 10HSA10 | 0 | 2026-08-31 | 2026-09-28 |  | 2027-01-11 | 2027-10-18 | 200 |  | IEC-ALP-GA-103 | 0 IFR 2026-09-28
ALP-IEC-10HAA-ME-ITP-0001 | HRSG incl. SCR - Supplier Inspection and Test Plan | IEC | IEC | 10HAA | HRSG pressure system | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-102 |  | 0 | 2026-11-16 | 2026-11-30 |  | 2026-12-28 |  |  | PO MR-ME-102
ALP-IEC-10HAA-ME-LST-0001 | HRSG incl. SCR - Spare Parts and Special Tools Lists | IEC | IEC | 10HAA | HRSG pressure system | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-102 |  | 0 | 2027-01-04 | 2027-01-25 |  | 2027-03-22 |  |  | PO MR-ME-102
ALP-IEC-10HAA-ME-MDB-0001 | HRSG incl. SCR - Manufacturing Record Book and Conformity Certificates | IEC | IEC | 10HAA | HRSG pressure system | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-102 |  | 0 | 2027-09-06 | 2027-09-20 |  | 2027-11-15 |  |  | PO MR-ME-102
ALP-IEC-10HAA-ME-OMM-0001 | HRSG incl. SCR - Supplier Operation and Maintenance Manual | IEC | IEC | 10HAA | HRSG pressure system | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-102 |  | 0 | 2027-06-28 | 2027-08-09 |  | 2027-12-27 |  |  | PO MR-ME-102
ALP-IEC-10HAA-ME-PRC-0001 | HRSG incl. SCR - Supplier Installation and Erection Manual | IEC | IEC | 10HAA | HRSG pressure system | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-102 |  | 0 | 2027-06-21 | 2027-07-12 |  | 2027-08-23 |  |  | PO MR-ME-102
ALP-IEC-10HAA-ME-TRP-0001 | HRSG incl. SCR - Factory Acceptance Test Report | IEC | IEC | 10HAA | HRSG pressure system | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-102 |  | 0 | 2027-08-30 | 2027-09-06 |  | 2027-09-20 |  |  | PO MR-ME-102
ALP-IEC-10HAA-ME-TST-0001 | HRSG incl. SCR - Factory Acceptance Test Procedure | IEC | IEC | 10HAA | HRSG pressure system | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-102 |  | 0 | 2027-05-24 | 2027-06-14 |  | 2027-07-26 |  |  | PO MR-ME-102
ALP-IEC-10HAA-PR-PID-0001 | HRSG incl. SCR - Supplier P&IDs | IEC | IEC | 10HAA | HRSG pressure system | process | PID | F | approval |  |  | 15 | 49 |  |  |  | MR-ME-102 |  | 0 | 2026-12-07 | 2027-01-11 |  | 2027-03-08 |  |  |  | IEC-ALP-PID-102
ALP-IEC-10MBA-CM-CMP-0001 | Gas Turbine Package incl. Auxiliaries - Supplier Commissioning Procedures | IEC | IEC | 10MBA | Gas turbine | commissioning | CMP | B | approval |  |  | 9 | 26 |  |  |  | MR-ME-101 |  | 0 | 2027-05-03 | 2027-05-31 |  | 2027-08-23 |  |  | PO MR-ME-101
ALP-IEC-10MBA-CV-CAL-0001 | Gas Turbine Package incl. Auxiliaries - Supplier Foundation Loads and Anchor Bolt Drawings | IEC | IEC | 10MBA | Gas turbine | civil | CAL | E | review |  |  | 12 | 16 |  |  |  | MR-ME-101 |  | 0 | 2026-11-23 | 2026-12-14 |  | 2027-01-11 |  |  |  | IEC-ALP-FL-101
ALP-IEC-10MBA-EL-LST-0001 | Power Island Electrical Load List |  | IEC | 10MBA | Gas turbine | electrical | LST | P | review |  |  |  | 80 | [5 empty] | 0 | 2026-12-07 | 2026-12-28 |  | 2027-02-08 |  |  |  | IEC-ALP-EL-101
ALP-IEC-10MBA-EL-WIR-0001 | Gas Turbine Package incl. Auxiliaries - Supplier Electrical Schematics and Wiring Diagrams, Part 1 of 2 | IEC | IEC | 10MBA | Gas turbine | electrical | WIR | F | review |  |  | 49 | 28.5 | EWP-01-ME-01 | CWP-01-ME-01 | CWA-01 | MR-ME-101 |  | 0 | 2026-12-21 | 2027-01-11 |  | 2027-03-08 | 2027-10-18 | 160 | PO MR-ME-101
ALP-IEC-10MBA-EL-WIR-0002 | Gas Turbine Package incl. Auxiliaries - Supplier Electrical Schematics and Wiring Diagrams, Part 2 of 2 | IEC | IEC | 10MBA | Gas turbine | electrical | WIR | F | review |  |  | 49 | 28.5 | EWP-01-ME-01 | CWP-01-ME-01 | CWA-01 | MR-ME-101 |  | 0 | 2026-12-21 | 2027-01-11 |  | 2027-03-08 | 2027-10-18 | 160 | PO MR-ME-101
ALP-IEC-10MBA-HS-RPT-0001 | Power Island Noise Data | ISO 10494 | IEC | 10MBA | Gas turbine | hse | RPT | D | review |  |  |  | 60 | [5 empty] | 0 | 2026-12-21 | 2027-01-11 |  | 2027-02-22 |  |  |  | IEC-ALP-HS-101
ALP-IEC-10MBA-IC-DSH-0001 | Gas Turbine Package incl. Auxiliaries - Supplier Instrument List and Datasheets, Part 1 of 3 | IEC | IEC | 10MBA | Gas turbine | i_and_c | DSH | E | review |  |  | 112 | 26.4 |  |  |  | MR-ME-101 | 10MBA10 10MBL10 10MBN10 10MBP10 10MBU10 10MBV10 | 0 | 2026-12-28 | 2027-01-11 |  | 2027-03-08 |  |  | PO MR-ME-101
ALP-IEC-10MBA-IC-DSH-0002 | Gas Turbine Package incl. Auxiliaries - Supplier Instrument List and Datasheets, Part 2 of 3 | IEC | IEC | 10MBA | Gas turbine | i_and_c | DSH | E | review |  |  | 112 | 26.4 |  |  |  | MR-ME-101 | 10MBA10 10MBL10 10MBN10 10MBP10 10MBU10 10MBV10 | 0 | 2026-12-28 | 2027-01-11 |  | 2027-03-08 |  |  | PO MR-ME-101
ALP-IEC-10MBA-IC-DSH-0003 | Gas Turbine Package incl. Auxiliaries - Supplier Instrument List and Datasheets, Part 3 of 3 | IEC | IEC | 10MBA | Gas turbine | i_and_c | DSH | E | review |  |  | 111 | 26.2 |  |  |  | MR-ME-101 | 10MBA10 10MBL10 10MBN10 10MBP10 10MBU10 10MBV10 | 0 | 2026-12-28 | 2027-01-11 |  | 2027-03-08 |  |  | PO MR-ME-101
ALP-IEC-10MBA-IC-IOL-0001 | Gas Turbine Package incl. Auxiliaries - Supplier I/O List, Control Philosophy and Interface Signals | IEC | IEC | 10MBA | Gas turbine | i_and_c | IOL | P | review |  |  | 17 | 21 |  |  |  | MR-ME-101 |  | 0 | 2026-12-07 | 2026-12-28 |  | 2027-02-08 |  |  | PO MR-ME-101
ALP-IEC-10MBA-ME-CAL-0001 | Gas Turbine Package incl. Auxiliaries - Supplier Design Calculations | IEC | IEC | 10MBA | Gas turbine | mechanical | CAL | E | review |  |  | 19 | 23 |  |  |  | MR-ME-101 |  | 0 | 2026-12-07 | 2026-12-28 |  | 2027-02-08 |  |  | PO MR-ME-101
ALP-IEC-10MBA-ME-DSH-0001 | Gas Turbine Package incl. Auxiliaries - Supplier Certified Datasheets and Performance Curves | IEC | IEC | 10MBA | Gas turbine | mechanical | DSH | E | review |  |  | 57 | 61 |  |  |  | MR-ME-101 | 10MBA10 10MBL10 10MBN10 10MBP10 10MBU10 10MBV10 | 0 | 2026-09-14 | 2026-09-28 |  | 2026-12-28 |  |  |  | IEC-ALP-DS-101 | B IFR 2026-12-04
ALP-IEC-10MBA-ME-GAD-0001 | Gas Turbine Package incl. Auxiliaries - Supplier GA Drawings | IEC | IEC | 10MBA | Gas turbine | mechanical | GAD | L | review |  |  | 57 | 89.5 | EWP-01-ME-01 | CWP-01-ME-01 | CWA-01 | MR-ME-101 | 10MBA10 10MBL10 10MBN10 10MBP10 10MBU10 10MBV10 | 0 | 2026-08-31 | 2026-09-28 |  | 2027-01-11 | 2027-10-18 | 200 |  | IEC-ALP-GA-101 | 0 IFR 2026-09-28
ALP-IEC-10MBA-ME-ITP-0001 | Gas Turbine Package incl. Auxiliaries - Supplier Inspection and Test Plan | IEC | IEC | 10MBA | Gas turbine | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-101 |  | 0 | 2027-01-11 | 2027-01-25 |  | 2027-02-22 |  |  |  | IEC-ALP-QA-101
ALP-IEC-10MBA-ME-LAY-0001 | Power Island Arrangement - Installation and Maintenance Spaces |  | IEC | 10MBA | Gas turbine | mechanical | LAY | L | approval |  |  |  | 80 | EWP-01-ME-01 | CWP-01-ME-01 | CWA-01 |  |  | 0 | 2026-08-31 | 2026-09-28 |  | 2027-01-11 | 2027-10-18 | 200 |  | IEC-ALP-GA-100 | 0 IFR 2026-09-28
ALP-IEC-10MBA-ME-LST-0001 | Gas Turbine Package incl. Auxiliaries - Spare Parts and Special Tools Lists | IEC | IEC | 10MBA | Gas turbine | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-101 |  | 0 | 2027-01-04 | 2027-01-25 |  | 2027-03-22 |  |  | PO MR-ME-101
ALP-IEC-10MBA-ME-MDB-0001 | Gas Turbine Package incl. Auxiliaries - Manufacturing Record Book and Conformity Certificates | IEC | IEC | 10MBA | Gas turbine | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-101 |  | 0 | 2027-09-20 | 2027-10-04 |  | 2027-11-29 |  |  | PO MR-ME-101
ALP-IEC-10MBA-ME-OMM-0001 | Gas Turbine Package incl. Auxiliaries - Supplier Operation and Maintenance Manual | IEC | IEC | 10MBA | Gas turbine | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-101 |  | 0 | 2028-01-24 | 2028-03-06 |  | 2028-07-24 |  |  |  | IEC-ALP-OM-101
ALP-IEC-10MBA-ME-PRC-0001 | Gas Turbine Package incl. Auxiliaries - Supplier Installation and Erection Manual | IEC | IEC | 10MBA | Gas turbine | mechanical | PRC | B | review |  |  | 1 | 6 | EWP-01-ME-01 | CWP-01-ME-01 | CWA-01 | MR-ME-101 |  | 0 | 2027-06-21 | 2027-07-12 |  | 2027-09-06 | 2027-10-18 | 30 |  | IEC-ALP-ER-101
ALP-IEC-10MBA-ME-RPT-0001 | Maintenance Concept and Long-Term Service Offer |  | IEC | 10MBA | Gas turbine | mechanical | RPT | D | review |  |  |  | 60 | [5 empty] | 0 | 2027-07-19 | 2027-08-09 |  | 2027-10-04 |  |  |  | IEC-ALP-OM-102
ALP-IEC-10MBA-ME-TRP-0001 | Gas Turbine Package incl. Auxiliaries - Factory Acceptance Test Report | IEC | IEC | 10MBA | Gas turbine | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-101 |  | 0 | 2027-09-13 | 2027-09-20 |  | 2027-10-04 |  |  | PO MR-ME-101
ALP-IEC-10MBA-ME-TST-0001 | Gas Turbine Package incl. Auxiliaries - Factory Acceptance Test Procedure | IEC | IEC | 10MBA | Gas turbine | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-101 |  | 0 | 2027-06-07 | 2027-06-28 |  | 2027-08-09 |  |  | PO MR-ME-101
ALP-IEC-10MBA-PI-M3D-0001 | Power Island 3D Model Export | for the plant model | IEC | 10MBA | Gas turbine | piping | M3D | L | review |  |  |  | 80 | [5 empty] | 0 | 2027-02-01 | 2027-02-22 |  | 2027-04-19 |  |  |  | IEC-ALP-M3D-101
ALP-IEC-10MBA-PR-HMB-0001 | Power Island Thermal Performance Data | heat balance | IEC | 10MBA | Gas turbine | process | HMB | F | approval |  |  |  | 160 | [5 empty] | 0 | 2026-09-07 | 2026-09-28 |  | 2026-11-02 |  |  |  | IEC-ALP-PER-001 | B IFR 2026-09-28
ALP-IEC-10MBA-PR-HMB-0002 | Power Island Off-Design Heat Balances | case book | IEC | 10MBA | Gas turbine | process | HMB | F | approval |  |  | 9 | 480 | [5 empty] | 0 | 2026-09-07 | 2026-09-28 |  | 2026-11-02 |  |  |  | IEC-ALP-PER-003 | A IFR 2026-09-28
ALP-IEC-10MBA-PR-PID-0001 | Gas Turbine Package incl. Auxiliaries - Supplier P&IDs | IEC | IEC | 10MBA | Gas turbine | process | PID | F | approval |  |  | 17 | 55 |  |  |  | MR-ME-101 |  | 0 | 2026-12-07 | 2027-01-11 |  | 2027-03-08 |  |  |  | IEC-ALP-PID-101
ALP-IEC-10MBY-CM-CMP-0001 | Turbine Control System - Supplier Commissioning Procedures | IEC | IEC | 10MBY | GT control and protection (TCS) | commissioning | CMP | B | approval |  |  | 1 | 10 |  |  |  | MR-IC-101 |  | 0 | 2027-02-22 | 2027-03-22 |  | 2027-06-14 |  |  | PO MR-IC-101
ALP-IEC-10MBY-EL-WIR-0001 | Turbine Control System - Supplier Electrical Schematics and Wiring Diagrams | IEC | IEC | 10MBY | GT control and protection (TCS) | electrical | WIR | F | review |  |  | 28 | 18 | EWP-01-IC-01 | CWP-01-IC-01 | CWA-01 | MR-IC-101 |  | 0 | 2026-12-21 | 2027-01-11 |  | 2027-03-08 | 2028-02-07 | 240 | PO MR-IC-101
ALP-IEC-10MBY-IC-BLK-0001 | TCS Architecture and DCS Integration | OPC UA, IEC 62443 zone | IEC | 10MBY | GT control and protection (TCS) | i_and_c | BLK | F | approval |  |  |  | 40 | [5 empty] | 0 | 2026-12-21 | 2027-01-11 |  | 2027-02-22 |  |  |  | IEC-ALP-IC-101
ALP-IEC-10MBY-IC-CBL-0001 | Power Island Cable List | IEC scope and interfaces | IEC | 10MBY | GT control and protection (TCS) | i_and_c | CBL | M | information |  |  |  | 60 | EWP-01-IC-01 | CWP-01-IC-01 | CWA-01 |  |  | 0 | 2027-05-10 | 2027-05-31 |  | 2027-07-26 | 2028-02-07 | 140 |  | IEC-ALP-IC-104
ALP-IEC-10MBY-IC-CNR-0001 | Power Island Operating and Control Description | start-up, load, trips | IEC | 10MBY | GT control and protection (TCS) | i_and_c | CNR | F | review |  |  |  | 60 | [5 empty] | 0 | 2027-01-18 | 2027-02-08 |  | 2027-04-05 |  |  |  | IEC-ALP-IC-103
ALP-IEC-10MBY-IC-IOL-0001 | Turbine Control System - Supplier I/O List, Control Philosophy and Interface Signals | IEC | IEC | 10MBY | GT control and protection (TCS) | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-IC-101 |  | 0 | 2027-02-01 | 2027-02-22 |  | 2027-04-19 |  |  |  | IEC-ALP-IC-102
ALP-IEC-10MBY-IC-LOG-0001 | Turbine Control System - Supplier Logic Diagrams, Part 1 of 6 | IEC | IEC | 10MBY | GT control and protection (TCS) | i_and_c | LOG | F | review |  |  | 250 | 133 |  |  |  | MR-IC-101 |  | 0 | 2027-02-22 | 2027-03-22 |  | 2027-06-14 |  |  | PO MR-IC-101
ALP-IEC-10MBY-IC-LOG-0002 | Turbine Control System - Supplier Logic Diagrams, Part 2 of 6 | IEC | IEC | 10MBY | GT control and protection (TCS) | i_and_c | LOG | F | review |  |  | 250 | 133 |  |  |  | MR-IC-101 |  | 0 | 2027-02-22 | 2027-03-22 |  | 2027-06-14 |  |  | PO MR-IC-101
ALP-IEC-10MBY-IC-LOG-0003 | Turbine Control System - Supplier Logic Diagrams, Part 3 of 6 | IEC | IEC | 10MBY | GT control and protection (TCS) | i_and_c | LOG | F | review |  |  | 250 | 133 |  |  |  | MR-IC-101 |  | 0 | 2027-02-22 | 2027-03-22 |  | 2027-06-14 |  |  | PO MR-IC-101
ALP-IEC-10MBY-IC-LOG-0004 | Turbine Control System - Supplier Logic Diagrams, Part 4 of 6 | IEC | IEC | 10MBY | GT control and protection (TCS) | i_and_c | LOG | F | review |  |  | 250 | 133 |  |  |  | MR-IC-101 |  | 0 | 2027-02-22 | 2027-03-22 |  | 2027-06-14 |  |  | PO MR-IC-101
ALP-IEC-10MBY-IC-LOG-0005 | Turbine Control System - Supplier Logic Diagrams, Part 5 of 6 | IEC | IEC | 10MBY | GT control and protection (TCS) | i_and_c | LOG | F | review |  |  | 250 | 133 |  |  |  | MR-IC-101 |  | 0 | 2027-02-22 | 2027-03-22 |  | 2027-06-14 |  |  | PO MR-IC-101
ALP-IEC-10MBY-IC-LOG-0006 | Turbine Control System - Supplier Logic Diagrams, Part 6 of 6 | IEC | IEC | 10MBY | GT control and protection (TCS) | i_and_c | LOG | F | review |  |  | 250 | 133 |  |  |  | MR-IC-101 |  | 0 | 2027-02-22 | 2027-03-22 |  | 2027-06-14 |  |  | PO MR-IC-101
ALP-IEC-10MBY-ME-CAL-0001 | Turbine Control System - Supplier Design Calculations | IEC | IEC | 10MBY | GT control and protection (TCS) | mechanical | CAL | E | review |  |  | 7 | 11 |  |  |  | MR-IC-101 |  | 0 | 2026-12-07 | 2026-12-28 |  | 2027-02-08 |  |  | PO MR-IC-101
ALP-IEC-10MBY-ME-DSH-0001 | Turbine Control System - Supplier Certified Datasheets and Performance Curves | IEC | IEC | 10MBY | GT control and protection (TCS) | mechanical | DSH | E | review |  |  | 20 | 24 |  |  |  | MR-IC-101 | 10MBY10 20MAY10 | 0 | 2026-11-16 | 2026-11-30 |  | 2027-01-11 |  |  | PO MR-IC-101
ALP-IEC-10MBY-ME-GAD-0001 | Turbine Control System - Supplier GA Drawings | IEC | IEC | 10MBY | GT control and protection (TCS) | mechanical | GAD | L | review |  |  | 20 | 34 | EWP-01-IC-01 | CWP-01-IC-01 | CWA-01 | MR-IC-101 | 10MBY10 20MAY10 | 0 | 2026-11-16 | 2026-12-14 |  | 2027-01-25 | 2028-02-07 | 270 | PO MR-IC-101
ALP-IEC-10MBY-ME-ITP-0001 | Turbine Control System - Supplier Inspection and Test Plan | IEC | IEC | 10MBY | GT control and protection (TCS) | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-IC-101 |  | 0 | 2026-11-16 | 2026-11-30 |  | 2026-12-28 |  |  | PO MR-IC-101
ALP-IEC-10MBY-ME-LST-0001 | Turbine Control System - Spare Parts and Special Tools Lists | IEC | IEC | 10MBY | GT control and protection (TCS) | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-IC-101 |  | 0 | 2027-01-04 | 2027-01-25 |  | 2027-03-22 |  |  | PO MR-IC-101
ALP-IEC-10MBY-ME-MDB-0001 | Turbine Control System - Manufacturing Record Book and Conformity Certificates | IEC | IEC | 10MBY | GT control and protection (TCS) | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-IC-101 |  | 0 | 2027-07-12 | 2027-07-26 |  | 2027-09-20 |  |  | PO MR-IC-101
ALP-IEC-10MBY-ME-OMM-0001 | Turbine Control System - Supplier Operation and Maintenance Manual | IEC | IEC | 10MBY | GT control and protection (TCS) | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-IC-101 |  | 0 | 2027-05-03 | 2027-06-14 |  | 2027-11-01 |  |  | PO MR-IC-101
ALP-IEC-10MBY-ME-PRC-0001 | Turbine Control System - Supplier Installation and Erection Manual | IEC | IEC | 10MBY | GT control and protection (TCS) | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-IC-101 |  | 0 | 2027-04-26 | 2027-05-17 |  | 2027-06-28 |  |  | PO MR-IC-101
ALP-IEC-10MBY-ME-TRP-0001 | Turbine Control System - Factory Acceptance Test Report | IEC | IEC | 10MBY | GT control and protection (TCS) | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-IC-101 |  | 0 | 2027-07-05 | 2027-07-12 |  | 2027-07-26 |  |  | PO MR-IC-101
ALP-IEC-10MBY-ME-TST-0001 | Turbine Control System - Factory Acceptance Test Procedure | IEC | IEC | 10MBY | GT control and protection (TCS) | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-IC-101 |  | 0 | 2027-03-29 | 2027-04-19 |  | 2027-05-31 |  |  | PO MR-IC-101
ALP-IEC-10MKA-CM-CMP-0001 | Generators, Excitation, GCB and Busducts - Supplier Commissioning Procedures | IEC | IEC | 10MKA | GT generator | commissioning | CMP | B | approval |  |  | 2 | 12 |  |  |  | MR-EL-101 |  | 0 | 2027-04-26 | 2027-05-24 |  | 2027-08-16 |  |  | PO MR-EL-101
ALP-IEC-10MKA-CV-CAL-0001 | Generators, Excitation, GCB and Busducts - Supplier Foundation Loads and Anchor Bolt Drawings | IEC | IEC | 10MKA | GT generator | civil | CAL | E | review |  |  | 5 | 9 |  |  |  | MR-EL-101 |  | 0 | 2026-11-23 | 2026-12-14 |  | 2027-01-11 |  |  | PO MR-EL-101
ALP-IEC-10MKA-EL-DSH-0001 | Generators, Excitation, GCB and Busducts - Supplier Certified Datasheets and Performance Curves | IEC | IEC | 10MKA | GT generator | electrical | DSH | E | review |  |  | 25 | 29 |  |  |  | MR-EL-101 | 10BAA10 10BAC10 10MKA10 10MKA20 10MKA30 10MKC10 10MKC20 10MKC30 10MKG10 20BAA10 20BAC10 20MKA10 20MKA20 20MKA30 20MKC10 20MKC20 | 0 | 2026-09-14 | 2026-09-28 |  | 2026-12-28 |  |  |  | IEC-ALP-DS-102 | A IFR 2026-12-04
ALP-IEC-10MKA-EL-RPT-0001 | Generator Capability Curves and Dynamic Models | Grid Code | IEC | 10MKA | GT generator | electrical | RPT | D | review |  |  |  | 60 | [5 empty] | 0 | 2027-01-04 | 2027-01-25 |  | 2027-03-22 |  |  |  | IEC-ALP-EL-102
ALP-IEC-10MKA-EL-WIR-0001 | Generators, Excitation, GCB and Busducts - Supplier Electrical Schematics and Wiring Diagrams | IEC | IEC | 10MKA | GT generator | electrical | WIR | F | review |  |  | 46 | 27 | EWP-01-ME-01 | CWP-01-ME-01 | CWA-01 | MR-EL-101 |  | 0 | 2026-12-21 | 2027-01-11 |  | 2027-03-08 | 2027-10-18 | 160 | PO MR-EL-101
ALP-IEC-10MKA-IC-DSH-0001 | Generators, Excitation, GCB and Busducts - Supplier Instrument List and Datasheets | IEC | IEC | 10MKA | GT generator | i_and_c | DSH | E | review |  |  | 143 | 32.6 |  |  |  | MR-EL-101 | 10BAA10 10BAC10 10MKA10 10MKA20 10MKA30 10MKC10 10MKC20 10MKC30 10MKG10 20BAA10 20BAC10 20MKA10 20MKA20 20MKA30 20MKC10 20MKC20 | 0 | 2026-12-28 | 2027-01-11 |  | 2027-03-08 |  |  | PO MR-EL-101
ALP-IEC-10MKA-IC-IOL-0001 | Generators, Excitation, GCB and Busducts - Supplier I/O List, Control Philosophy and Interface Signals | IEC | IEC | 10MKA | GT generator | i_and_c | IOL | P | review |  |  | 8 | 12 |  |  |  | MR-EL-101 |  | 0 | 2026-12-07 | 2026-12-28 |  | 2027-02-08 |  |  | PO MR-EL-101
ALP-IEC-10MKA-ME-CAL-0001 | Generators, Excitation, GCB and Busducts - Supplier Design Calculations | IEC | IEC | 10MKA | GT generator | mechanical | CAL | E | review |  |  | 9 | 13 |  |  |  | MR-EL-101 |  | 0 | 2026-12-07 | 2026-12-28 |  | 2027-02-08 |  |  | PO MR-EL-101
ALP-IEC-10MKA-ME-GAD-0001 | Generators, Excitation, GCB and Busducts - Supplier GA Drawings | IEC | IEC | 10MKA | GT generator | mechanical | GAD | L | review |  |  | 25 | 41.5 | EWP-01-ME-01 | CWP-01-ME-01 | CWA-01 | MR-EL-101 | 10BAA10 10BAC10 10MKA10 10MKA20 10MKA30 10MKC10 10MKC20 10MKC30 10MKG10 20BAA10 20BAC10 20MKA10 20MKA20 20MKA30 20MKC10 20MKC20 | 0 | 2026-11-16 | 2026-12-14 |  | 2027-01-25 | 2027-10-18 | 190 | PO MR-EL-101
ALP-IEC-10MKA-ME-ITP-0001 | Generators, Excitation, GCB and Busducts - Supplier Inspection and Test Plan | IEC | IEC | 10MKA | GT generator | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-EL-101 |  | 0 | 2026-11-16 | 2026-11-30 |  | 2026-12-28 |  |  | PO MR-EL-101
ALP-IEC-10MKA-ME-LST-0001 | Generators, Excitation, GCB and Busducts - Spare Parts and Special Tools Lists | IEC | IEC | 10MKA | GT generator | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-EL-101 |  | 0 | 2027-01-04 | 2027-01-25 |  | 2027-03-22 |  |  | PO MR-EL-101
ALP-IEC-10MKA-ME-MDB-0001 | Generators, Excitation, GCB and Busducts - Manufacturing Record Book and Conformity Certificates | IEC | IEC | 10MKA | GT generator | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-EL-101 |  | 0 | 2027-09-13 | 2027-09-27 |  | 2027-11-22 |  |  | PO MR-EL-101
ALP-IEC-10MKA-ME-OMM-0001 | Generators, Excitation, GCB and Busducts - Supplier Operation and Maintenance Manual | IEC | IEC | 10MKA | GT generator | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-EL-101 |  | 0 | 2027-07-05 | 2027-08-16 |  | 2028-01-03 |  |  | PO MR-EL-101
ALP-IEC-10MKA-ME-PRC-0001 | Generators, Excitation, GCB and Busducts - Supplier Installation and Erection Manual | IEC | IEC | 10MKA | GT generator | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-EL-101 |  | 0 | 2027-06-28 | 2027-07-19 |  | 2027-08-30 |  |  | PO MR-EL-101
ALP-IEC-10MKA-ME-TRP-0001 | Generators, Excitation, GCB and Busducts - Factory Acceptance Test Report | IEC | IEC | 10MKA | GT generator | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-EL-101 |  | 0 | 2027-09-06 | 2027-09-13 |  | 2027-09-27 |  |  | PO MR-EL-101
ALP-IEC-10MKA-ME-TST-0001 | Generators, Excitation, GCB and Busducts - Factory Acceptance Test Procedure | IEC | IEC | 10MKA | GT generator | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-EL-101 |  | 0 | 2027-05-31 | 2027-06-21 |  | 2027-08-02 |  |  | PO MR-EL-101
ALP-IEC-10MKA-PR-PID-0001 | Generators, Excitation, GCB and Busducts - Supplier P&IDs | IEC | IEC | 10MKA | GT generator | process | PID | F | approval |  |  | 4 | 16 |  |  |  | MR-EL-101 |  | 0 | 2026-12-21 | 2027-01-25 |  | 2027-03-22 |  |  |  | IEC-ALP-PID-104
ALP-IEC-20MAA-CM-CMP-0001 | Steam Turbine and Condenser - Supplier Commissioning Procedures | IEC | IEC | 20MAA | HP turbine | commissioning | CMP | B | approval |  |  | 10 | 28 |  |  |  | MR-ME-103 |  | 0 | 2027-06-14 | 2027-07-12 |  | 2027-10-04 |  |  | PO MR-ME-103
ALP-IEC-20MAA-CV-CAL-0001 | Steam Turbine and Condenser - Supplier Foundation Loads and Anchor Bolt Drawings | IEC | IEC | 20MAA | HP turbine | civil | CAL | E | review |  |  | 10 | 14 |  |  |  | MR-ME-103 |  | 0 | 2026-12-07 | 2026-12-28 |  | 2027-01-25 |  |  |  | IEC-ALP-FL-103
ALP-IEC-20MAA-EL-WIR-0001 | Steam Turbine and Condenser - Supplier Electrical Schematics and Wiring Diagrams | IEC | IEC | 20MAA | HP turbine | electrical | WIR | F | review |  |  | 70 | 39 | EWP-02-ME-01 | CWP-02-ME-01 | CWA-02 | MR-ME-103 |  | 0 | 2026-12-21 | 2027-01-11 |  | 2027-03-08 | 2027-12-20 | 205 | PO MR-ME-103
ALP-IEC-20MAA-IC-DSH-0001 | Steam Turbine and Condenser - Supplier Instrument List and Datasheets, Part 1 of 3 | IEC | IEC | 20MAA | HP turbine | i_and_c | DSH | E | review |  |  | 104 | 24.8 |  |  |  | MR-ME-103 | 10LBA10AA501 10LBB10AA501 10LBD10AA501 20MAA10 20MAB10 20MAG10 20MAJ10AP001 20MAJ10AP002 20MAV10 20MAW10 20MAX10 | 0 | 2026-12-28 | 2027-01-11 |  | 2027-03-08 |  |  | PO MR-ME-103
ALP-IEC-20MAA-IC-DSH-0002 | Steam Turbine and Condenser - Supplier Instrument List and Datasheets, Part 2 of 3 | IEC | IEC | 20MAA | HP turbine | i_and_c | DSH | E | review |  |  | 103 | 24.6 |  |  |  | MR-ME-103 | 10LBA10AA501 10LBB10AA501 10LBD10AA501 20MAA10 20MAB10 20MAG10 20MAJ10AP001 20MAJ10AP002 20MAV10 20MAW10 20MAX10 | 0 | 2026-12-28 | 2027-01-11 |  | 2027-03-08 |  |  | PO MR-ME-103
ALP-IEC-20MAA-IC-DSH-0003 | Steam Turbine and Condenser - Supplier Instrument List and Datasheets, Part 3 of 3 | IEC | IEC | 20MAA | HP turbine | i_and_c | DSH | E | review |  |  | 103 | 24.6 |  |  |  | MR-ME-103 | 10LBA10AA501 10LBB10AA501 10LBD10AA501 20MAA10 20MAB10 20MAG10 20MAJ10AP001 20MAJ10AP002 20MAV10 20MAW10 20MAX10 | 0 | 2026-12-28 | 2027-01-11 |  | 2027-03-08 |  |  | PO MR-ME-103
ALP-IEC-20MAA-IC-IOL-0001 | Steam Turbine and Condenser - Supplier I/O List, Control Philosophy and Interface Signals | IEC | IEC | 20MAA | HP turbine | i_and_c | IOL | P | review |  |  | 16 | 20 |  |  |  | MR-ME-103 |  | 0 | 2026-12-07 | 2026-12-28 |  | 2027-02-08 |  |  | PO MR-ME-103
ALP-IEC-20MAA-ME-CAL-0001 | Steam Turbine and Condenser - Supplier Design Calculations | IEC | IEC | 20MAA | HP turbine | mechanical | CAL | E | review |  |  | 17 | 21 |  |  |  | MR-ME-103 |  | 0 | 2026-12-07 | 2026-12-28 |  | 2027-02-08 |  |  | PO MR-ME-103
ALP-IEC-20MAA-ME-DSH-0001 | Steam Turbine and Condenser - Supplier Certified Datasheets and Performance Curves | IEC | IEC | 20MAA | HP turbine | mechanical | DSH | E | review |  |  | 49 | 53 |  |  |  | MR-ME-103 | 10LBA10AA501 10LBB10AA501 10LBD10AA501 20MAA10 20MAB10 20MAG10 20MAJ10AP001 20MAJ10AP002 20MAV10 20MAW10 20MAX10 | 0 | 2026-09-14 | 2026-09-28 |  | 2026-12-28 |  |  |  | IEC-ALP-DS-103 | A IFR 2026-12-04
ALP-IEC-20MAA-ME-GAD-0001 | Steam Turbine and Condenser - Supplier GA Drawings | IEC | IEC | 20MAA | HP turbine | mechanical | GAD | L | review |  |  | 49 | 77.5 | EWP-02-ME-01 | CWP-02-ME-01 | CWA-02 | MR-ME-103 | 10LBA10AA501 10LBB10AA501 10LBD10AA501 20MAA10 20MAB10 20MAG10 20MAJ10AP001 20MAJ10AP002 20MAV10 20MAW10 20MAX10 | 0 | 2026-08-31 | 2026-09-28 |  | 2027-01-11 | 2027-12-20 | 245 |  | IEC-ALP-GA-102 | 0 IFR 2026-09-28
ALP-IEC-20MAA-ME-ITP-0001 | Steam Turbine and Condenser - Supplier Inspection and Test Plan | IEC | IEC | 20MAA | HP turbine | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-103 |  | 0 | 2026-11-16 | 2026-11-30 |  | 2026-12-28 |  |  | PO MR-ME-103
ALP-IEC-20MAA-ME-LST-0001 | Steam Turbine and Condenser - Spare Parts and Special Tools Lists | IEC | IEC | 20MAA | HP turbine | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-103 |  | 0 | 2027-01-04 | 2027-01-25 |  | 2027-03-22 |  |  | PO MR-ME-103
ALP-IEC-20MAA-ME-MDB-0001 | Steam Turbine and Condenser - Manufacturing Record Book and Conformity Certificates | IEC | IEC | 20MAA | HP turbine | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-103 |  | 0 | 2027-11-01 | 2027-11-15 |  | 2028-01-10 |  |  | PO MR-ME-103
ALP-IEC-20MAA-ME-OMM-0001 | Steam Turbine and Condenser - Supplier Operation and Maintenance Manual | IEC | IEC | 20MAA | HP turbine | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-103 |  | 0 | 2027-08-23 | 2027-10-04 |  | 2028-02-21 |  |  | PO MR-ME-103
ALP-IEC-20MAA-ME-PRC-0001 | Steam Turbine and Condenser - Supplier Installation and Erection Manual | IEC | IEC | 20MAA | HP turbine | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-103 |  | 0 | 2027-08-16 | 2027-09-06 |  | 2027-10-18 |  |  | PO MR-ME-103
ALP-IEC-20MAA-ME-TRP-0001 | Steam Turbine and Condenser - Factory Acceptance Test Report | IEC | IEC | 20MAA | HP turbine | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-103 |  | 0 | 2027-10-25 | 2027-11-01 |  | 2027-11-15 |  |  | PO MR-ME-103
ALP-IEC-20MAA-ME-TST-0001 | Steam Turbine and Condenser - Factory Acceptance Test Procedure | IEC | IEC | 20MAA | HP turbine | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-103 |  | 0 | 2027-07-19 | 2027-08-09 |  | 2027-09-20 |  |  | PO MR-ME-103
ALP-IEC-20MAA-PR-PID-0001 | Steam Turbine and Condenser - Supplier P&IDs | IEC | IEC | 20MAA | HP turbine | process | PID | F | approval |  |  | 19 | 61 |  |  |  | MR-ME-103 |  | 0 | 2026-12-21 | 2027-01-25 |  | 2027-03-22 |  |  |  | IEC-ALP-PID-103
ALP-IEC-20MAG-ME-DSH-0001 | Seawater-Cooled Surface Condenser - Datasheet |  | IEC | 20MAG | Condensing system | mechanical | DSH | E | approval |  |  |  | 16 |  |  |  |  | 20MAG10 | 0 | 2026-09-14 | 2026-09-28 |  | 2026-12-28 |  |  |  | IEC-ALP-DS-105 | A IFR 2026-12-04
ALP-M01-10LAC-CV-CAL-0001 | Boiler Feed Pumps - Supplier Foundation Loads and Anchor Bolt Drawings |  | M01 | 10LAC | Boiler feed pumps | civil | CAL | E | review |  |  | 1 | 5 |  |  |  | MR-ME-001 |  | 1 | 2027-02-04 | 2027-02-25 |  | 2027-03-25 |  |  | PO MR-ME-001
ALP-M01-10LAC-EL-WIR-0001 | Boiler Feed Pumps - Supplier Electrical Schematics and Wiring Diagrams |  | M01 | 10LAC | Boiler feed pumps | electrical | WIR | F | review |  |  | 16 | 12 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-001 |  | 1 | 2027-03-04 | 2027-03-25 |  | 2027-05-20 | 2027-11-01 | 117 | PO MR-ME-001
ALP-M01-10LAC-IC-DSH-0001 | Boiler Feed Pumps - Supplier Instrument List and Datasheets |  | M01 | 10LAC | Boiler feed pumps | i_and_c | DSH | E | review |  |  | 35 | 11 |  |  |  | MR-ME-001 | 10LAC10AP001 10LAC10AP002 | 1 | 2027-03-11 | 2027-03-25 |  | 2027-05-20 |  |  | PO MR-ME-001
ALP-M01-10LAC-IC-IOL-0001 | Boiler Feed Pumps - Supplier I/O List, Control Philosophy and Interface Signals |  | M01 | 10LAC | Boiler feed pumps | i_and_c | IOL | P | review |  |  | 2 | 6 |  |  |  | MR-ME-001 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-22 |  |  | PO MR-ME-001
ALP-M01-10LAC-ME-CAL-0001 | Boiler Feed Pumps - Supplier Design Calculations |  | M01 | 10LAC | Boiler feed pumps | mechanical | CAL | E | review |  |  | 2 | 6 |  |  |  | MR-ME-001 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-22 |  |  | PO MR-ME-001
ALP-M01-10LAC-ME-DSH-0001 | Boiler Feed Pumps - Supplier Certified Datasheets and Performance Curves |  | M01 | 10LAC | Boiler feed pumps | mechanical | DSH | E | review |  |  | 4 | 8 |  |  |  | MR-ME-001 | 10LAC10AP001 10LAC10AP002 | 1 | 2027-01-28 | 2027-02-11 |  | 2027-03-25 |  |  | PO MR-ME-001
ALP-M01-10LAC-ME-GAD-0001 | Boiler Feed Pumps - Supplier GA Drawings |  | M01 | 10LAC | Boiler feed pumps | mechanical | GAD | L | review |  |  | 4 | 10 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-001 | 10LAC10AP001 10LAC10AP002 | 1 | 2027-01-28 | 2027-02-25 |  | 2027-04-08 | 2027-11-01 | 147 | PO MR-ME-001
ALP-M01-10LAC-ME-ITP-0001 | Boiler Feed Pumps - Supplier Inspection and Test Plan |  | M01 | 10LAC | Boiler feed pumps | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-001 |  | 1 | 2027-01-28 | 2027-02-11 |  | 2027-03-11 |  |  | PO MR-ME-001
ALP-M01-10LAC-ME-LST-0001 | Boiler Feed Pumps - Spare Parts and Special Tools Lists |  | M01 | 10LAC | Boiler feed pumps | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-001 |  | 1 | 2027-03-18 | 2027-04-08 |  | 2027-06-03 |  |  | PO MR-ME-001
ALP-M01-10LAC-ME-MDB-0001 | Boiler Feed Pumps - Manufacturing Record Book and Conformity Certificates |  | M01 | 10LAC | Boiler feed pumps | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-001 |  | 1 | 2027-09-23 | 2027-10-07 |  | 2027-12-02 |  |  | PO MR-ME-001
ALP-M01-10LAC-ME-OMM-0001 | Boiler Feed Pumps - Supplier Operation and Maintenance Manual |  | M01 | 10LAC | Boiler feed pumps | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-001 |  | 1 | 2027-07-15 | 2027-08-26 |  | 2028-01-13 |  |  | PO MR-ME-001
ALP-M01-10LAC-ME-PRC-0001 | Boiler Feed Pumps - Supplier Installation and Erection Manual |  | M01 | 10LAC | Boiler feed pumps | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-001 |  | 1 | 2027-07-08 | 2027-07-29 |  | 2027-09-09 |  |  | PO MR-ME-001
ALP-M01-10LAC-ME-TRP-0001 | Boiler Feed Pumps - Factory Acceptance Test Report |  | M01 | 10LAC | Boiler feed pumps | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-001 |  | 1 | 2027-09-16 | 2027-09-23 |  | 2027-10-07 |  |  | PO MR-ME-001
ALP-M01-10LAC-ME-TST-0001 | Boiler Feed Pumps - Factory Acceptance Test Procedure |  | M01 | 10LAC | Boiler feed pumps | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-001 |  | 1 | 2027-06-10 | 2027-07-01 |  | 2027-08-12 |  |  | PO MR-ME-001
ALP-M01-10LAC-PR-PID-0001 | Boiler Feed Pumps - Supplier P&IDs |  | M01 | 10LAC | Boiler feed pumps | process | PID | F | approval |  |  | 2 | 10 |  |  |  | MR-ME-001 |  | 1 | 2027-02-04 | 2027-03-11 |  | 2027-04-22 |  |  | PO MR-ME-001
ALP-M02-20LCB-CV-CAL-0001 | Condensate Extraction Pumps - Supplier Foundation Loads and Anchor Bolt Drawings |  | M02 | 20LCB | Condensate extraction pumps | civil | CAL | E | review |  |  | 1 | 5 |  |  |  | MR-ME-002 |  | 1 | 2027-03-08 | 2027-03-29 |  | 2027-04-22 |  |  | PO MR-ME-002
ALP-M02-20LCB-EL-WIR-0001 | Condensate Extraction Pumps - Supplier Electrical Schematics and Wiring Diagrams |  | M02 | 20LCB | Condensate extraction pumps | electrical | WIR | F | review |  |  | 8 | 8 | EWP-02-ME-01 | CWP-02-ME-01 | CWA-02 | MR-ME-002 |  | 1 | 2027-04-01 | 2027-04-22 |  | 2027-06-11 | 2027-12-20 | 136 | PO MR-ME-002
ALP-M02-20LCB-IC-DSH-0001 | Condensate Extraction Pumps - Supplier Instrument List and Datasheets |  | M02 | 20LCB | Condensate extraction pumps | i_and_c | DSH | E | review |  |  | 20 | 8 |  |  |  | MR-ME-002 | 20LCB10AP001 20LCB10AP002 | 1 | 2027-04-08 | 2027-04-22 |  | 2027-06-11 |  |  | PO MR-ME-002
ALP-M02-20LCB-IC-IOL-0001 | Condensate Extraction Pumps - Supplier I/O List, Control Philosophy and Interface Signals |  | M02 | 20LCB | Condensate extraction pumps | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-ME-002 |  | 1 | 2027-03-19 | 2027-04-09 |  | 2027-05-18 |  |  | PO MR-ME-002
ALP-M02-20LCB-ME-CAL-0001 | Condensate Extraction Pumps - Supplier Design Calculations |  | M02 | 20LCB | Condensate extraction pumps | mechanical | CAL | E | review |  |  | 1 | 5 |  |  |  | MR-ME-002 |  | 1 | 2027-03-19 | 2027-04-09 |  | 2027-05-18 |  |  | PO MR-ME-002
ALP-M02-20LCB-ME-DSH-0001 | Condensate Extraction Pumps - Supplier Certified Datasheets and Performance Curves |  | M02 | 20LCB | Condensate extraction pumps | mechanical | DSH | E | review |  |  | 3 | 7 |  |  |  | MR-ME-002 | 20LCB10AP001 20LCB10AP002 | 1 | 2027-03-02 | 2027-03-16 |  | 2027-04-22 |  |  | PO MR-ME-002
ALP-M02-20LCB-ME-GAD-0001 | Condensate Extraction Pumps - Supplier GA Drawings |  | M02 | 20LCB | Condensate extraction pumps | mechanical | GAD | L | review |  |  | 3 | 8.5 | EWP-02-ME-01 | CWP-02-ME-01 | CWA-02 | MR-ME-002 | 20LCB10AP001 20LCB10AP002 | 1 | 2027-03-01 | 2027-03-29 |  | 2027-05-05 | 2027-12-20 | 163 | PO MR-ME-002
ALP-M02-20LCB-ME-ITP-0001 | Condensate Extraction Pumps - Supplier Inspection and Test Plan |  | M02 | 20LCB | Condensate extraction pumps | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-002 |  | 1 | 2027-03-02 | 2027-03-16 |  | 2027-04-09 |  |  | PO MR-ME-002
ALP-M02-20LCB-ME-LST-0001 | Condensate Extraction Pumps - Spare Parts and Special Tools Lists |  | M02 | 20LCB | Condensate extraction pumps | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-002 |  | 1 | 2027-04-14 | 2027-05-05 |  | 2027-06-24 |  |  | PO MR-ME-002
ALP-M02-20LCB-ME-MDB-0001 | Condensate Extraction Pumps - Manufacturing Record Book and Conformity Certificates |  | M02 | 20LCB | Condensate extraction pumps | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-002 |  | 1 | 2027-09-30 | 2027-10-14 |  | 2027-12-09 |  |  | PO MR-ME-002
ALP-M02-20LCB-ME-OMM-0001 | Condensate Extraction Pumps - Supplier Operation and Maintenance Manual |  | M02 | 20LCB | Condensate extraction pumps | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-002 |  | 1 | 2027-07-22 | 2027-09-02 |  | 2028-01-20 |  |  | PO MR-ME-002
ALP-M02-20LCB-ME-PRC-0001 | Condensate Extraction Pumps - Supplier Installation and Erection Manual |  | M02 | 20LCB | Condensate extraction pumps | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-002 |  | 1 | 2027-07-15 | 2027-08-05 |  | 2027-09-16 |  |  | PO MR-ME-002
ALP-M02-20LCB-ME-TRP-0001 | Condensate Extraction Pumps - Factory Acceptance Test Report |  | M02 | 20LCB | Condensate extraction pumps | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-002 |  | 1 | 2027-09-23 | 2027-09-30 |  | 2027-10-14 |  |  | PO MR-ME-002
ALP-M02-20LCB-ME-TST-0001 | Condensate Extraction Pumps - Factory Acceptance Test Procedure |  | M02 | 20LCB | Condensate extraction pumps | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-002 |  | 1 | 2027-06-17 | 2027-07-08 |  | 2027-08-19 |  |  | PO MR-ME-002
ALP-M02-20LCB-PR-PID-0001 | Condensate Extraction Pumps - Supplier P&IDs |  | M02 | 20LCB | Condensate extraction pumps | process | PID | F | approval |  |  | 1 | 7 |  |  |  | MR-ME-002 |  | 1 | 2027-03-05 | 2027-04-09 |  | 2027-05-18 |  |  | PO MR-ME-002
ALP-M03-00PAC-CV-CAL-0001 | CW Pumps - Supplier Foundation Loads and Anchor Bolt Drawings |  | M03 | 00PAC | CW pumps | civil | CAL | E | review |  |  | 1 | 5 |  |  |  | MR-ME-003 |  | 1 | 2027-02-04 | 2027-02-25 |  | 2027-03-25 |  |  | PO MR-ME-003
ALP-M03-00PAC-EL-WIR-0001 | CW Pumps - Supplier Electrical Schematics and Wiring Diagrams |  | M03 | 00PAC | CW pumps | electrical | WIR | F | review |  |  | 12 | 10 | EWP-05-ME-01 | CWP-05-ME-01 | CWA-05 | MR-ME-003 |  | 1 | 2027-03-04 | 2027-03-25 |  | 2027-05-20 | 2027-12-20 | 152 | PO MR-ME-003
ALP-M03-00PAC-IC-DSH-0001 | CW Pumps - Supplier Instrument List and Datasheets |  | M03 | 00PAC | CW pumps | i_and_c | DSH | E | review |  |  | 15 | 7 |  |  |  | MR-ME-003 | 00PAC10AP001 00PAC10AP002 | 1 | 2027-03-11 | 2027-03-25 |  | 2027-05-20 |  |  | PO MR-ME-003
ALP-M03-00PAC-IC-IOL-0001 | CW Pumps - Supplier I/O List, Control Philosophy and Interface Signals |  | M03 | 00PAC | CW pumps | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-ME-003 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-22 |  |  | PO MR-ME-003
ALP-M03-00PAC-ME-CAL-0001 | CW Pumps - Supplier Design Calculations |  | M03 | 00PAC | CW pumps | mechanical | CAL | E | review |  |  | 1 | 5 |  |  |  | MR-ME-003 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-22 |  |  | PO MR-ME-003
ALP-M03-00PAC-ME-DSH-0001 | CW Pumps - Supplier Certified Datasheets and Performance Curves |  | M03 | 00PAC | CW pumps | mechanical | DSH | E | review |  |  | 3 | 7 |  |  |  | MR-ME-003 | 00PAC10AP001 00PAC10AP002 | 1 | 2027-01-28 | 2027-02-11 |  | 2027-03-25 |  |  | PO MR-ME-003
ALP-M03-00PAC-ME-GAD-0001 | CW Pumps - Supplier GA Drawings |  | M03 | 00PAC | CW pumps | mechanical | GAD | L | review |  |  | 3 | 8.5 | EWP-05-ME-01 | CWP-05-ME-01 | CWA-05 | MR-ME-003 | 00PAC10AP001 00PAC10AP002 | 1 | 2027-01-28 | 2027-02-25 |  | 2027-04-08 | 2027-12-20 | 182 | PO MR-ME-003
ALP-M03-00PAC-ME-ITP-0001 | CW Pumps - Supplier Inspection and Test Plan |  | M03 | 00PAC | CW pumps | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-003 |  | 1 | 2027-01-28 | 2027-02-11 |  | 2027-03-11 |  |  | PO MR-ME-003
ALP-M03-00PAC-ME-LST-0001 | CW Pumps - Spare Parts and Special Tools Lists |  | M03 | 00PAC | CW pumps | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-003 |  | 1 | 2027-03-18 | 2027-04-08 |  | 2027-06-03 |  |  | PO MR-ME-003
ALP-M03-00PAC-ME-MDB-0001 | CW Pumps - Manufacturing Record Book and Conformity Certificates |  | M03 | 00PAC | CW pumps | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-003 |  | 1 | 2027-10-21 | 2027-11-04 |  | 2027-12-30 |  |  | PO MR-ME-003
ALP-M03-00PAC-ME-OMM-0001 | CW Pumps - Supplier Operation and Maintenance Manual |  | M03 | 00PAC | CW pumps | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-003 |  | 1 | 2027-08-12 | 2027-09-23 |  | 2028-02-10 |  |  | PO MR-ME-003
ALP-M03-00PAC-ME-PRC-0001 | CW Pumps - Supplier Installation and Erection Manual |  | M03 | 00PAC | CW pumps | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-003 |  | 1 | 2027-08-05 | 2027-08-26 |  | 2027-10-07 |  |  | PO MR-ME-003
ALP-M03-00PAC-ME-TRP-0001 | CW Pumps - Factory Acceptance Test Report |  | M03 | 00PAC | CW pumps | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-003 |  | 1 | 2027-10-14 | 2027-10-21 |  | 2027-11-04 |  |  | PO MR-ME-003
ALP-M03-00PAC-ME-TST-0001 | CW Pumps - Factory Acceptance Test Procedure |  | M03 | 00PAC | CW pumps | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-003 |  | 1 | 2027-07-08 | 2027-07-29 |  | 2027-09-09 |  |  | PO MR-ME-003
ALP-M03-00PAC-PR-PID-0001 | CW Pumps - Supplier P&IDs |  | M03 | 00PAC | CW pumps | process | PID | F | approval |  |  | 2 | 10 |  |  |  | MR-ME-003 |  | 1 | 2027-02-04 | 2027-03-11 |  | 2027-04-22 |  |  | PO MR-ME-003
ALP-M04-00PAA-CV-CAL-0001 | Travelling Band Screens and Trash Rakes - Supplier Foundation Loads and Anchor Bolt Drawings |  | M04 | 00PAA | CW intake, screens and outfall | civil | CAL | E | review |  |  | 2 | 6 |  |  |  | MR-ME-004 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-06 |  |  | PO MR-ME-004
ALP-M04-00PAA-EL-WIR-0001 | Travelling Band Screens and Trash Rakes - Supplier Electrical Schematics and Wiring Diagrams |  | M04 | 00PAA | CW intake, screens and outfall | electrical | WIR | F | review |  |  | 40 | 24 | EWP-05-ME-01 | CWP-05-ME-01 | CWA-05 | MR-ME-004 |  | 1 | 2027-03-16 | 2027-04-06 |  | 2027-05-26 | 2027-12-20 | 148 | PO MR-ME-004
ALP-M04-00PAA-IC-DSH-0001 | Travelling Band Screens and Trash Rakes - Supplier Instrument List and Datasheets |  | M04 | 00PAA | CW intake, screens and outfall | i_and_c | DSH | E | review |  |  | 20 | 8 |  |  |  | MR-ME-004 | 00PAA10AA001 00PAA10AA002 00PAA10AP001 00PAA10AP002 00PAA10AT001 00PAA10AT002 00PAA10AT003 00PAA10AT004 | 1 | 2027-03-23 | 2027-04-06 |  | 2027-05-26 |  |  | PO MR-ME-004
ALP-M04-00PAA-IC-IOL-0001 | Travelling Band Screens and Trash Rakes - Supplier I/O List, Control Philosophy and Interface Signals |  | M04 | 00PAA | CW intake, screens and outfall | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-ME-004 |  | 1 | 2027-03-03 | 2027-03-24 |  | 2027-04-30 |  |  | PO MR-ME-004
ALP-M04-00PAA-ME-CAL-0001 | Travelling Band Screens and Trash Rakes - Supplier Design Calculations |  | M04 | 00PAA | CW intake, screens and outfall | mechanical | CAL | E | review |  |  | 4 | 8 |  |  |  | MR-ME-004 |  | 1 | 2027-03-03 | 2027-03-24 |  | 2027-04-30 |  |  | PO MR-ME-004
ALP-M04-00PAA-ME-DSH-0001 | Travelling Band Screens and Trash Rakes - Supplier Certified Datasheets and Performance Curves |  | M04 | 00PAA | CW intake, screens and outfall | mechanical | DSH | E | review |  |  | 10 | 14 |  |  |  | MR-ME-004 | 00PAA10AA001 00PAA10AA002 00PAA10AP001 00PAA10AP002 00PAA10AT001 00PAA10AT002 00PAA10AT003 00PAA10AT004 | 1 | 2027-02-12 | 2027-02-26 |  | 2027-04-06 |  |  | PO MR-ME-004
ALP-M04-00PAA-ME-GAD-0001 | Travelling Band Screens and Trash Rakes - Supplier GA Drawings |  | M04 | 00PAA | CW intake, screens and outfall | mechanical | GAD | L | review |  |  | 10 | 19 | EWP-05-ME-01 | CWP-05-ME-01 | CWA-05 | MR-ME-004 | 00PAA10AA001 00PAA10AA002 00PAA10AP001 00PAA10AP002 00PAA10AT001 00PAA10AT002 00PAA10AT003 00PAA10AT004 | 1 | 2027-02-11 | 2027-03-11 |  | 2027-04-19 | 2027-12-20 | 175 | PO MR-ME-004
ALP-M04-00PAA-ME-ITP-0001 | Travelling Band Screens and Trash Rakes - Supplier Inspection and Test Plan |  | M04 | 00PAA | CW intake, screens and outfall | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-004 |  | 1 | 2027-02-12 | 2027-02-26 |  | 2027-03-24 |  |  | PO MR-ME-004
ALP-M04-00PAA-ME-LST-0001 | Travelling Band Screens and Trash Rakes - Spare Parts and Special Tools Lists |  | M04 | 00PAA | CW intake, screens and outfall | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-004 |  | 1 | 2027-03-29 | 2027-04-19 |  | 2027-06-08 |  |  | PO MR-ME-004
ALP-M04-00PAA-ME-MDB-0001 | Travelling Band Screens and Trash Rakes - Manufacturing Record Book and Conformity Certificates |  | M04 | 00PAA | CW intake, screens and outfall | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-004 |  | 1 | 2027-09-14 | 2027-09-28 |  | 2027-11-23 |  |  | PO MR-ME-004
ALP-M04-00PAA-ME-OMM-0001 | Travelling Band Screens and Trash Rakes - Supplier Operation and Maintenance Manual |  | M04 | 00PAA | CW intake, screens and outfall | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-004 |  | 1 | 2027-07-06 | 2027-08-17 |  | 2028-01-04 |  |  | PO MR-ME-004
ALP-M04-00PAA-ME-PRC-0001 | Travelling Band Screens and Trash Rakes - Supplier Installation and Erection Manual |  | M04 | 00PAA | CW intake, screens and outfall | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-004 |  | 1 | 2027-06-29 | 2027-07-20 |  | 2027-08-31 |  |  | PO MR-ME-004
ALP-M04-00PAA-ME-TRP-0001 | Travelling Band Screens and Trash Rakes - Factory Acceptance Test Report |  | M04 | 00PAA | CW intake, screens and outfall | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-004 |  | 1 | 2027-09-07 | 2027-09-14 |  | 2027-09-28 |  |  | PO MR-ME-004
ALP-M04-00PAA-ME-TST-0001 | Travelling Band Screens and Trash Rakes - Factory Acceptance Test Procedure |  | M04 | 00PAA | CW intake, screens and outfall | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-004 |  | 1 | 2027-06-01 | 2027-06-22 |  | 2027-08-03 |  |  | PO MR-ME-004
ALP-M04-00PAA-PR-PID-0001 | Travelling Band Screens and Trash Rakes - Supplier P&IDs |  | M04 | 00PAA | CW intake, screens and outfall | process | PID | F | approval |  |  | 3 | 13 |  |  |  | MR-ME-004 |  | 1 | 2027-02-17 | 2027-03-24 |  | 2027-04-30 |  |  | PO MR-ME-004
ALP-M05-00PBA-CV-CAL-0001 | Electro-Chlorination Package - Supplier Foundation Loads and Anchor Bolt Drawings |  | M05 | 00PBA | Electro-chlorination | civil | CAL | E | review |  |  | 3 | 7 |  |  |  | MR-ME-005 |  | 1 | 2027-02-19 | 2027-03-12 |  | 2027-04-07 |  |  | PO MR-ME-005
ALP-M05-00PBA-EL-WIR-0001 | Electro-Chlorination Package - Supplier Electrical Schematics and Wiring Diagrams |  | M05 | 00PBA | Electro-chlorination | electrical | WIR | F | review |  |  | 20 | 14 | EWP-05-ME-01 | CWP-05-ME-01 | CWA-05 | MR-ME-005 |  | 1 | 2027-03-17 | 2027-04-07 |  | 2027-05-27 | 2027-12-20 | 147 | PO MR-ME-005
ALP-M05-00PBA-IC-DSH-0001 | Electro-Chlorination Package - Supplier Instrument List and Datasheets |  | M05 | 00PBA | Electro-chlorination | i_and_c | DSH | E | review |  |  | 20 | 8 |  |  |  | MR-ME-005 | 00PBA10 00PBA10AN001 00PBA10AN002 00PBA10AP001 00PBA10AP002 00PBA10AP003 00PBA10AP004 00PBA10AT001 00PBA10AT002 00PBA10BB001 00PBA10BB002 | 1 | 2027-03-24 | 2027-04-07 |  | 2027-05-27 |  |  | PO MR-ME-005
ALP-M05-00PBA-IC-IOL-0001 | Electro-Chlorination Package - Supplier I/O List, Control Philosophy and Interface Signals |  | M05 | 00PBA | Electro-chlorination | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-ME-005 |  | 1 | 2027-03-04 | 2027-03-25 |  | 2027-05-03 |  |  | PO MR-ME-005
ALP-M05-00PBA-IC-LOG-0001 | Electro-Chlorination Package - Supplier Logic Diagrams |  | M05 | 00PBA | Electro-chlorination | i_and_c | LOG | F | review |  |  | 31 | 23.5 |  |  |  | MR-ME-005 |  | 1 | 2027-05-12 | 2027-06-09 |  | 2027-08-24 |  |  | PO MR-ME-005
ALP-M05-00PBA-ME-CAL-0001 | Electro-Chlorination Package - Supplier Design Calculations |  | M05 | 00PBA | Electro-chlorination | mechanical | CAL | E | review |  |  | 4 | 8 |  |  |  | MR-ME-005 |  | 1 | 2027-03-04 | 2027-03-25 |  | 2027-05-03 |  |  | PO MR-ME-005
ALP-M05-00PBA-ME-DSH-0001 | Electro-Chlorination Package - Supplier Certified Datasheets and Performance Curves |  | M05 | 00PBA | Electro-chlorination | mechanical | DSH | E | review |  |  | 11 | 15 |  |  |  | MR-ME-005 | 00PBA10 00PBA10AN001 00PBA10AN002 00PBA10AP001 00PBA10AP002 00PBA10AP003 00PBA10AP004 00PBA10AT001 00PBA10AT002 00PBA10BB001 00PBA10BB002 | 1 | 2027-02-15 | 2027-03-01 |  | 2027-04-07 |  |  | PO MR-ME-005
ALP-M05-00PBA-ME-GAD-0001 | Electro-Chlorination Package - Supplier GA Drawings |  | M05 | 00PBA | Electro-chlorination | mechanical | GAD | L | review |  |  | 11 | 20.5 | EWP-05-ME-01 | CWP-05-ME-01 | CWA-05 | MR-ME-005 | 00PBA10 00PBA10AN001 00PBA10AN002 00PBA10AP001 00PBA10AP002 00PBA10AP003 00PBA10AP004 00PBA10AT001 00PBA10AT002 00PBA10BB001 00PBA10BB002 | 1 | 2027-02-12 | 2027-03-12 |  | 2027-04-20 | 2027-12-20 | 174 | PO MR-ME-005
ALP-M05-00PBA-ME-ITP-0001 | Electro-Chlorination Package - Supplier Inspection and Test Plan |  | M05 | 00PBA | Electro-chlorination | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-005 |  | 1 | 2027-02-15 | 2027-03-01 |  | 2027-03-25 |  |  | PO MR-ME-005
ALP-M05-00PBA-ME-LST-0001 | Electro-Chlorination Package - Spare Parts and Special Tools Lists |  | M05 | 00PBA | Electro-chlorination | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-005 |  | 1 | 2027-03-30 | 2027-04-20 |  | 2027-06-09 |  |  | PO MR-ME-005
ALP-M05-00PBA-ME-MDB-0001 | Electro-Chlorination Package - Manufacturing Record Book and Conformity Certificates |  | M05 | 00PBA | Electro-chlorination | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-005 |  | 1 | 2027-09-15 | 2027-09-29 |  | 2027-11-24 |  |  | PO MR-ME-005
ALP-M05-00PBA-ME-OMM-0001 | Electro-Chlorination Package - Supplier Operation and Maintenance Manual |  | M05 | 00PBA | Electro-chlorination | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-005 |  | 1 | 2027-07-07 | 2027-08-18 |  | 2028-01-05 |  |  | PO MR-ME-005
ALP-M05-00PBA-ME-PRC-0001 | Electro-Chlorination Package - Supplier Installation and Erection Manual |  | M05 | 00PBA | Electro-chlorination | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-005 |  | 1 | 2027-06-30 | 2027-07-21 |  | 2027-09-01 |  |  | PO MR-ME-005
ALP-M05-00PBA-ME-TRP-0001 | Electro-Chlorination Package - Factory Acceptance Test Report |  | M05 | 00PBA | Electro-chlorination | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-005 |  | 1 | 2027-09-08 | 2027-09-15 |  | 2027-09-29 |  |  | PO MR-ME-005
ALP-M05-00PBA-ME-TST-0001 | Electro-Chlorination Package - Factory Acceptance Test Procedure |  | M05 | 00PBA | Electro-chlorination | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-005 |  | 1 | 2027-06-02 | 2027-06-23 |  | 2027-08-04 |  |  | PO MR-ME-005
ALP-M05-00PBA-PR-PID-0001 | Electro-Chlorination Package - Supplier P&IDs |  | M05 | 00PBA | Electro-chlorination | process | PID | F | approval |  |  | 3 | 13 |  |  |  | MR-ME-005 |  | 1 | 2027-02-18 | 2027-03-25 |  | 2027-05-03 |  |  | PO MR-ME-005
ALP-M06-00PAH-EL-WIR-0001 | Condenser Tube Cleaning System - Supplier Electrical Schematics and Wiring Diagrams |  | M06 | 00PAH | Condenser tube cleaning | electrical | WIR | F | review |  |  | 12 | 10 | EWP-02-PI-01 | CWP-02-PI-01 | CWA-02 | MR-ME-006 |  | 1 | 2027-04-14 | 2027-05-05 |  | 2027-06-16 | 2028-01-31 | 163 | PO MR-ME-006
ALP-M06-00PAH-IC-DSH-0001 | Condenser Tube Cleaning System - Supplier Instrument List and Datasheets |  | M06 | 00PAH | Condenser tube cleaning | i_and_c | DSH | E | review |  |  | 10 | 6 |  |  |  | MR-ME-006 | 00PAH10 00PAH10AP001 00PAH10AP002 00PAH10AT001 00PAH10AT002 | 1 | 2027-04-21 | 2027-05-05 |  | 2027-06-16 |  |  | PO MR-ME-006
ALP-M06-00PAH-IC-IOL-0001 | Condenser Tube Cleaning System - Supplier I/O List, Control Philosophy and Interface Signals |  | M06 | 00PAH | Condenser tube cleaning | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-ME-006 |  | 1 | 2027-04-02 | 2027-04-23 |  | 2027-05-25 |  |  | PO MR-ME-006
ALP-M06-00PAH-ME-CAL-0001 | Condenser Tube Cleaning System - Supplier Design Calculations |  | M06 | 00PAH | Condenser tube cleaning | mechanical | CAL | E | review |  |  | 2 | 6 |  |  |  | MR-ME-006 |  | 1 | 2027-04-02 | 2027-04-23 |  | 2027-05-25 |  |  | PO MR-ME-006
ALP-M06-00PAH-ME-DSH-0001 | Condenser Tube Cleaning System - Supplier Certified Datasheets and Performance Curves |  | M06 | 00PAH | Condenser tube cleaning | mechanical | DSH | E | review |  |  | 6 | 10 |  |  |  | MR-ME-006 | 00PAH10 00PAH10AP001 00PAH10AP002 00PAH10AT001 00PAH10AT002 | 1 | 2027-03-19 | 2027-04-02 |  | 2027-05-05 |  |  | PO MR-ME-006
ALP-M06-00PAH-ME-GAD-0001 | Condenser Tube Cleaning System - Supplier GA Drawings |  | M06 | 00PAH | Condenser tube cleaning | mechanical | GAD | L | review |  |  | 6 | 13 | EWP-02-PI-01 | CWP-02-PI-01 | CWA-02 | MR-ME-006 | 00PAH10 00PAH10AP001 00PAH10AP002 00PAH10AT001 00PAH10AT002 | 1 | 2027-03-16 | 2027-04-13 |  | 2027-05-14 | 2028-01-31 | 186 | PO MR-ME-006
ALP-M06-00PAH-ME-ITP-0001 | Condenser Tube Cleaning System - Supplier Inspection and Test Plan |  | M06 | 00PAH | Condenser tube cleaning | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-006 |  | 1 | 2027-03-19 | 2027-04-02 |  | 2027-04-23 |  |  | PO MR-ME-006
ALP-M06-00PAH-ME-LST-0001 | Condenser Tube Cleaning System - Spare Parts and Special Tools Lists |  | M06 | 00PAH | Condenser tube cleaning | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-006 |  | 1 | 2027-04-23 | 2027-05-14 |  | 2027-06-25 |  |  | PO MR-ME-006
ALP-M06-00PAH-ME-MDB-0001 | Condenser Tube Cleaning System - Manufacturing Record Book and Conformity Certificates |  | M06 | 00PAH | Condenser tube cleaning | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-006 |  | 1 | 2027-09-10 | 2027-09-24 |  | 2027-11-19 |  |  | PO MR-ME-006
ALP-M06-00PAH-ME-OMM-0001 | Condenser Tube Cleaning System - Supplier Operation and Maintenance Manual |  | M06 | 00PAH | Condenser tube cleaning | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-006 |  | 1 | 2027-07-02 | 2027-08-13 |  | 2027-12-31 |  |  | PO MR-ME-006
ALP-M06-00PAH-ME-PRC-0001 | Condenser Tube Cleaning System - Supplier Installation and Erection Manual |  | M06 | 00PAH | Condenser tube cleaning | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-006 |  | 1 | 2027-06-25 | 2027-07-16 |  | 2027-08-27 |  |  | PO MR-ME-006
ALP-M06-00PAH-ME-TRP-0001 | Condenser Tube Cleaning System - Factory Acceptance Test Report |  | M06 | 00PAH | Condenser tube cleaning | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-006 |  | 1 | 2027-09-03 | 2027-09-10 |  | 2027-09-24 |  |  | PO MR-ME-006
ALP-M06-00PAH-ME-TST-0001 | Condenser Tube Cleaning System - Factory Acceptance Test Procedure |  | M06 | 00PAH | Condenser tube cleaning | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-006 |  | 1 | 2027-05-28 | 2027-06-18 |  | 2027-07-30 |  |  | PO MR-ME-006
ALP-M06-00PAH-PR-PID-0001 | Condenser Tube Cleaning System - Supplier P&IDs |  | M06 | 00PAH | Condenser tube cleaning | process | PID | F | approval |  |  | 2 | 10 |  |  |  | MR-ME-006 |  | 1 | 2027-03-19 | 2027-04-23 |  | 2027-05-25 |  |  | PO MR-ME-006
ALP-M07-00PGA-CV-CAL-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Supplier Foundation Loads and Anchor Bolt Drawings |  | M07 | 00PGA | Closed cooling water | civil | CAL | E | review |  |  | 2 | 6 |  |  |  | MR-ME-007 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-02 |  |  | PO MR-ME-007
ALP-M07-00PGA-EL-WIR-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Supplier Electrical Schematics and Wiring Diagrams |  | M07 | 00PGA | Closed cooling water | electrical | WIR | F | review |  |  | 16 | 12 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-007 |  | 1 | 2027-03-12 | 2027-04-02 |  | 2027-05-14 | 2027-11-01 | 121 | PO MR-ME-007
ALP-M07-00PGA-IC-DSH-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Supplier Instrument List and Datasheets |  | M07 | 00PGA | Closed cooling water | i_and_c | DSH | E | review |  |  | 35 | 11 |  |  |  | MR-ME-007 | 00PGA10AC001 00PGA10AC002 00PGA10AP001 00PGA10AP002 00PGA10AT001 00PGA10BB001 00PGA10BB002 | 1 | 2027-03-19 | 2027-04-02 |  | 2027-05-14 |  |  | PO MR-ME-007
ALP-M07-00PGA-IC-IOL-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Supplier I/O List, Control Philosophy and Interface Signals |  | M07 | 00PGA | Closed cooling water | i_and_c | IOL | P | review |  |  | 2 | 6 |  |  |  | MR-ME-007 |  | 1 | 2027-03-02 | 2027-03-23 |  | 2027-04-22 |  |  | PO MR-ME-007
ALP-M07-00PGA-ME-CAL-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Supplier Design Calculations |  | M07 | 00PGA | Closed cooling water | mechanical | CAL | E | review |  |  | 3 | 7 |  |  |  | MR-ME-007 |  | 1 | 2027-03-02 | 2027-03-23 |  | 2027-04-22 |  |  | PO MR-ME-007
ALP-M07-00PGA-ME-DSH-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Supplier Certified Datasheets and Performance Curves |  | M07 | 00PGA | Closed cooling water | mechanical | DSH | E | review |  |  | 8 | 12 |  |  |  | MR-ME-007 | 00PGA10AC001 00PGA10AC002 00PGA10AP001 00PGA10AP002 00PGA10AT001 00PGA10BB001 00PGA10BB002 | 1 | 2027-02-16 | 2027-03-02 |  | 2027-04-02 |  |  | PO MR-ME-007
ALP-M07-00PGA-ME-GAD-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Supplier GA Drawings |  | M07 | 00PGA | Closed cooling water | mechanical | GAD | L | review |  |  | 8 | 16 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-007 | 00PGA10AC001 00PGA10AC002 00PGA10AP001 00PGA10AP002 00PGA10AT001 00PGA10BB001 00PGA10BB002 | 1 | 2027-02-11 | 2027-03-11 |  | 2027-04-13 | 2027-11-01 | 144 | PO MR-ME-007
ALP-M07-00PGA-ME-ITP-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Supplier Inspection and Test Plan |  | M07 | 00PGA | Closed cooling water | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-007 |  | 1 | 2027-02-16 | 2027-03-02 |  | 2027-03-23 |  |  | PO MR-ME-007
ALP-M07-00PGA-ME-LST-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Spare Parts and Special Tools Lists |  | M07 | 00PGA | Closed cooling water | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-007 |  | 1 | 2027-03-23 | 2027-04-13 |  | 2027-05-25 |  |  | PO MR-ME-007
ALP-M07-00PGA-ME-MDB-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Manufacturing Record Book and Conformity Certificates |  | M07 | 00PGA | Closed cooling water | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-007 |  | 1 | 2027-08-10 | 2027-08-24 |  | 2027-10-19 |  |  | PO MR-ME-007
ALP-M07-00PGA-ME-OMM-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Supplier Operation and Maintenance Manual |  | M07 | 00PGA | Closed cooling water | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-007 |  | 1 | 2027-06-01 | 2027-07-13 |  | 2027-11-30 |  |  | PO MR-ME-007
ALP-M07-00PGA-ME-PRC-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Supplier Installation and Erection Manual |  | M07 | 00PGA | Closed cooling water | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-007 |  | 1 | 2027-05-25 | 2027-06-15 |  | 2027-07-27 |  |  | PO MR-ME-007
ALP-M07-00PGA-ME-TRP-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Factory Acceptance Test Report |  | M07 | 00PGA | Closed cooling water | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-007 |  | 1 | 2027-08-03 | 2027-08-10 |  | 2027-08-24 |  |  | PO MR-ME-007
ALP-M07-00PGA-ME-TST-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Factory Acceptance Test Procedure |  | M07 | 00PGA | Closed cooling water | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-007 |  | 1 | 2027-04-27 | 2027-05-18 |  | 2027-06-29 |  |  | PO MR-ME-007
ALP-M07-00PGA-PR-PID-0001 | Closed Cooling Water Heat Exchangers, Pumps, Tank - Supplier P&IDs |  | M07 | 00PGA | Closed cooling water | process | PID | F | approval |  |  | 4 | 16 |  |  |  | MR-ME-007 |  | 1 | 2027-02-16 | 2027-03-23 |  | 2027-04-22 |  |  | PO MR-ME-007
ALP-M08-00QEA-CV-CAL-0001 | Air Compressors and Dryers - Supplier Foundation Loads and Anchor Bolt Drawings |  | M08 | 00QEA | Compressed air | civil | CAL | E | review |  |  | 2 | 6 |  |  |  | MR-ME-008 |  | 1 | 2027-02-24 | 2027-03-17 |  | 2027-04-08 |  |  | PO MR-ME-008
ALP-M08-00QEA-EL-WIR-0001 | Air Compressors and Dryers - Supplier Electrical Schematics and Wiring Diagrams |  | M08 | 00QEA | Compressed air | electrical | WIR | F | review |  |  | 16 | 12 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-008 |  | 1 | 2027-03-18 | 2027-04-08 |  | 2027-05-20 | 2027-11-01 | 117 | PO MR-ME-008
ALP-M08-00QEA-IC-DSH-0001 | Air Compressors and Dryers - Supplier Instrument List and Datasheets |  | M08 | 00QEA | Compressed air | i_and_c | DSH | E | review |  |  | 23 | 8.6 |  |  |  | MR-ME-008 | 00QEA10AN001 00QEA10AN002 00QEA10AN003 00QEA10AT001 00QEA10AT002 00QEA10AT003 00QEA10BB001 00QEA10BB002 | 1 | 2027-03-25 | 2027-04-08 |  | 2027-05-20 |  |  | PO MR-ME-008
ALP-M08-00QEA-IC-IOL-0001 | Air Compressors and Dryers - Supplier I/O List, Control Philosophy and Interface Signals |  | M08 | 00QEA | Compressed air | i_and_c | IOL | P | review |  |  | 2 | 6 |  |  |  | MR-ME-008 |  | 1 | 2027-03-08 | 2027-03-29 |  | 2027-04-28 |  |  | PO MR-ME-008
ALP-M08-00QEA-IC-LOG-0001 | Air Compressors and Dryers - Supplier Logic Diagrams |  | M08 | 00QEA | Compressed air | i_and_c | LOG | F | review |  |  | 29 | 22.5 |  |  |  | MR-ME-008 |  | 1 | 2027-05-03 | 2027-05-31 |  | 2027-08-02 |  |  | PO MR-ME-008
ALP-M08-00QEA-ME-CAL-0001 | Air Compressors and Dryers - Supplier Design Calculations |  | M08 | 00QEA | Compressed air | mechanical | CAL | E | review |  |  | 4 | 8 |  |  |  | MR-ME-008 |  | 1 | 2027-03-08 | 2027-03-29 |  | 2027-04-28 |  |  | PO MR-ME-008
ALP-M08-00QEA-ME-DSH-0001 | Air Compressors and Dryers - Supplier Certified Datasheets and Performance Curves |  | M08 | 00QEA | Compressed air | mechanical | DSH | E | review |  |  | 10 | 14 |  |  |  | MR-ME-008 | 00QEA10AN001 00QEA10AN002 00QEA10AN003 00QEA10AT001 00QEA10AT002 00QEA10AT003 00QEA10BB001 00QEA10BB002 | 1 | 2027-02-22 | 2027-03-08 |  | 2027-04-08 |  |  | PO MR-ME-008
ALP-M08-00QEA-ME-GAD-0001 | Air Compressors and Dryers - Supplier GA Drawings |  | M08 | 00QEA | Compressed air | mechanical | GAD | L | review |  |  | 10 | 19 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-008 | 00QEA10AN001 00QEA10AN002 00QEA10AN003 00QEA10AT001 00QEA10AT002 00QEA10AT003 00QEA10BB001 00QEA10BB002 | 1 | 2027-02-17 | 2027-03-17 |  | 2027-04-19 | 2027-11-01 | 140 | PO MR-ME-008
ALP-M08-00QEA-ME-ITP-0001 | Air Compressors and Dryers - Supplier Inspection and Test Plan |  | M08 | 00QEA | Compressed air | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-008 |  | 1 | 2027-02-22 | 2027-03-08 |  | 2027-03-29 |  |  | PO MR-ME-008
ALP-M08-00QEA-ME-LST-0001 | Air Compressors and Dryers - Spare Parts and Special Tools Lists |  | M08 | 00QEA | Compressed air | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-008 |  | 1 | 2027-03-29 | 2027-04-19 |  | 2027-05-31 |  |  | PO MR-ME-008
ALP-M08-00QEA-ME-MDB-0001 | Air Compressors and Dryers - Manufacturing Record Book and Conformity Certificates |  | M08 | 00QEA | Compressed air | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-008 |  | 1 | 2027-08-16 | 2027-08-30 |  | 2027-10-25 |  |  | PO MR-ME-008
ALP-M08-00QEA-ME-OMM-0001 | Air Compressors and Dryers - Supplier Operation and Maintenance Manual |  | M08 | 00QEA | Compressed air | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-008 |  | 1 | 2027-06-07 | 2027-07-19 |  | 2027-12-06 |  |  | PO MR-ME-008
ALP-M08-00QEA-ME-PRC-0001 | Air Compressors and Dryers - Supplier Installation and Erection Manual |  | M08 | 00QEA | Compressed air | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-008 |  | 1 | 2027-05-31 | 2027-06-21 |  | 2027-08-02 |  |  | PO MR-ME-008
ALP-M08-00QEA-ME-TRP-0001 | Air Compressors and Dryers - Factory Acceptance Test Report |  | M08 | 00QEA | Compressed air | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-008 |  | 1 | 2027-08-09 | 2027-08-16 |  | 2027-08-30 |  |  | PO MR-ME-008
ALP-M08-00QEA-ME-TST-0001 | Air Compressors and Dryers - Factory Acceptance Test Procedure |  | M08 | 00QEA | Compressed air | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-008 |  | 1 | 2027-05-03 | 2027-05-24 |  | 2027-07-05 |  |  | PO MR-ME-008
ALP-M08-00QEA-PR-PID-0001 | Air Compressors and Dryers - Supplier P&IDs |  | M08 | 00QEA | Compressed air | process | PID | F | approval |  |  | 3 | 13 |  |  |  | MR-ME-008 |  | 1 | 2027-02-22 | 2027-03-29 |  | 2027-04-28 |  |  | PO MR-ME-008
ALP-M09-00QHA-CV-CAL-0001 | Auxiliary Boiler - Supplier Foundation Loads and Anchor Bolt Drawings |  | M09 | 00QHA | Auxiliary boiler | civil | CAL | E | review |  |  | 2 | 6 |  |  |  | MR-ME-009 |  | 1 | 2027-02-04 | 2027-02-25 |  | 2027-03-25 |  |  | PO MR-ME-009
ALP-M09-00QHA-EL-WIR-0001 | Auxiliary Boiler - Supplier Electrical Schematics and Wiring Diagrams |  | M09 | 00QHA | Auxiliary boiler | electrical | WIR | F | review |  |  | 20 | 14 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-009 |  | 1 | 2027-03-04 | 2027-03-25 |  | 2027-05-20 | 2027-11-01 | 117 | PO MR-ME-009
ALP-M09-00QHA-IC-DSH-0001 | Auxiliary Boiler - Supplier Instrument List and Datasheets |  | M09 | 00QHA | Auxiliary boiler | i_and_c | DSH | E | review |  |  | 30 | 10 |  |  |  | MR-ME-009 | 00QHA10 00QHA10AN001 00QHA10AP001 00QHA10AP002 00QHA10BB001 00QHA10BB002 | 1 | 2027-03-11 | 2027-03-25 |  | 2027-05-20 |  |  | PO MR-ME-009
ALP-M09-00QHA-IC-IOL-0001 | Auxiliary Boiler - Supplier I/O List, Control Philosophy and Interface Signals |  | M09 | 00QHA | Auxiliary boiler | i_and_c | IOL | P | review |  |  | 2 | 6 |  |  |  | MR-ME-009 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-22 |  |  | PO MR-ME-009
ALP-M09-00QHA-IC-LOG-0001 | Auxiliary Boiler - Supplier Logic Diagrams |  | M09 | 00QHA | Auxiliary boiler | i_and_c | LOG | F | review |  |  | 36 | 26 |  |  |  | MR-ME-009 |  | 1 | 2027-05-06 | 2027-06-03 |  | 2027-08-26 |  |  | PO MR-ME-009
ALP-M09-00QHA-ME-CAL-0001 | Auxiliary Boiler - Supplier Design Calculations |  | M09 | 00QHA | Auxiliary boiler | mechanical | CAL | E | review |  |  | 3 | 7 |  |  |  | MR-ME-009 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-22 |  |  | PO MR-ME-009
ALP-M09-00QHA-ME-DSH-0001 | Auxiliary Boiler - Supplier Certified Datasheets and Performance Curves |  | M09 | 00QHA | Auxiliary boiler | mechanical | DSH | E | review |  |  | 8 | 12 |  |  |  | MR-ME-009 | 00QHA10 00QHA10AN001 00QHA10AP001 00QHA10AP002 00QHA10BB001 00QHA10BB002 | 1 | 2027-01-28 | 2027-02-11 |  | 2027-03-25 |  |  | PO MR-ME-009
ALP-M09-00QHA-ME-GAD-0001 | Auxiliary Boiler - Supplier GA Drawings |  | M09 | 00QHA | Auxiliary boiler | mechanical | GAD | L | review |  |  | 8 | 16 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-009 | 00QHA10 00QHA10AN001 00QHA10AP001 00QHA10AP002 00QHA10BB001 00QHA10BB002 | 1 | 2027-01-28 | 2027-02-25 |  | 2027-04-08 | 2027-11-01 | 147 | PO MR-ME-009
ALP-M09-00QHA-ME-ITP-0001 | Auxiliary Boiler - Supplier Inspection and Test Plan |  | M09 | 00QHA | Auxiliary boiler | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-009 |  | 1 | 2027-01-28 | 2027-02-11 |  | 2027-03-11 |  |  | PO MR-ME-009
ALP-M09-00QHA-ME-LST-0001 | Auxiliary Boiler - Spare Parts and Special Tools Lists |  | M09 | 00QHA | Auxiliary boiler | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-009 |  | 1 | 2027-03-18 | 2027-04-08 |  | 2027-06-03 |  |  | PO MR-ME-009
ALP-M09-00QHA-ME-MDB-0001 | Auxiliary Boiler - Manufacturing Record Book and Conformity Certificates |  | M09 | 00QHA | Auxiliary boiler | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-009 |  | 1 | 2027-09-23 | 2027-10-07 |  | 2027-12-02 |  |  | PO MR-ME-009
ALP-M09-00QHA-ME-OMM-0001 | Auxiliary Boiler - Supplier Operation and Maintenance Manual |  | M09 | 00QHA | Auxiliary boiler | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-009 |  | 1 | 2027-07-15 | 2027-08-26 |  | 2028-01-13 |  |  | PO MR-ME-009
ALP-M09-00QHA-ME-PRC-0001 | Auxiliary Boiler - Supplier Installation and Erection Manual |  | M09 | 00QHA | Auxiliary boiler | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-009 |  | 1 | 2027-07-08 | 2027-07-29 |  | 2027-09-09 |  |  | PO MR-ME-009
ALP-M09-00QHA-ME-TRP-0001 | Auxiliary Boiler - Factory Acceptance Test Report |  | M09 | 00QHA | Auxiliary boiler | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-009 |  | 1 | 2027-09-16 | 2027-09-23 |  | 2027-10-07 |  |  | PO MR-ME-009
ALP-M09-00QHA-ME-TST-0001 | Auxiliary Boiler - Factory Acceptance Test Procedure |  | M09 | 00QHA | Auxiliary boiler | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-009 |  | 1 | 2027-06-10 | 2027-07-01 |  | 2027-08-12 |  |  | PO MR-ME-009
ALP-M09-00QHA-PR-PID-0001 | Auxiliary Boiler - Supplier P&IDs |  | M09 | 00QHA | Auxiliary boiler | process | PID | F | approval |  |  | 3 | 13 |  |  |  | MR-ME-009 |  | 1 | 2027-02-04 | 2027-03-11 |  | 2027-04-22 |  |  | PO MR-ME-009
ALP-M10-00QJA-EL-WIR-0001 | Nitrogen, Hydrogen and CO2 Supply - Supplier Electrical Schematics and Wiring Diagrams |  | M10 | 00QJA | Nitrogen supply | electrical | WIR | F | review |  |  | 4 | 6 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-010 |  | 1 | 2027-06-17 | 2027-07-08 |  | 2027-08-05 | 2027-11-01 | 62 | PO MR-ME-010
ALP-M10-00QJA-IC-DSH-0001 | Nitrogen, Hydrogen and CO2 Supply - Supplier Instrument List and Datasheets |  | M10 | 00QJA | Nitrogen supply | i_and_c | DSH | E | review |  |  | 20 | 8 |  |  |  | MR-ME-010 | 00QJA10 00QJA10BB001 00QJB10 | 1 | 2027-06-24 | 2027-07-08 |  | 2027-08-05 |  |  | PO MR-ME-010
ALP-M10-00QJA-IC-IOL-0001 | Nitrogen, Hydrogen and CO2 Supply - Supplier I/O List, Control Philosophy and Interface Signals |  | M10 | 00QJA | Nitrogen supply | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-ME-010 |  | 1 | 2027-06-10 | 2027-07-01 |  | 2027-07-22 |  |  | PO MR-ME-010
ALP-M10-00QJA-ME-CAL-0001 | Nitrogen, Hydrogen and CO2 Supply - Supplier Design Calculations |  | M10 | 00QJA | Nitrogen supply | mechanical | CAL | E | review |  |  | 3 | 7 |  |  |  | MR-ME-010 |  | 1 | 2027-06-10 | 2027-07-01 |  | 2027-07-22 |  |  | PO MR-ME-010
ALP-M10-00QJA-ME-DSH-0001 | Nitrogen, Hydrogen and CO2 Supply - Supplier Certified Datasheets and Performance Curves |  | M10 | 00QJA | Nitrogen supply | mechanical | DSH | E | review |  |  | 8 | 12 |  |  |  | MR-ME-010 | 00QJA10 00QJA10BB001 00QJB10 | 1 | 2027-06-03 | 2027-06-17 |  | 2027-07-08 |  |  | PO MR-ME-010
ALP-M10-00QJA-ME-GAD-0001 | Nitrogen, Hydrogen and CO2 Supply - Supplier GA Drawings |  | M10 | 00QJA | Nitrogen supply | mechanical | GAD | L | review |  |  | 8 | 16 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-010 | 00QJA10 00QJA10BB001 00QJB10 | 1 | 2027-05-27 | 2027-06-24 |  | 2027-07-15 | 2027-11-01 | 77 | PO MR-ME-010
ALP-M10-00QJA-ME-ITP-0001 | Nitrogen, Hydrogen and CO2 Supply - Supplier Inspection and Test Plan |  | M10 | 00QJA | Nitrogen supply | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-010 |  | 1 | 2027-06-03 | 2027-06-17 |  | 2027-07-01 |  |  | PO MR-ME-010
ALP-M10-00QJA-ME-LST-0001 | Nitrogen, Hydrogen and CO2 Supply - Spare Parts and Special Tools Lists |  | M10 | 00QJA | Nitrogen supply | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-010 |  | 1 | 2027-06-24 | 2027-07-15 |  | 2027-08-12 |  |  | PO MR-ME-010
ALP-M10-00QJA-ME-MDB-0001 | Nitrogen, Hydrogen and CO2 Supply - Manufacturing Record Book and Conformity Certificates |  | M10 | 00QJA | Nitrogen supply | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-010 |  | 1 | 2027-09-23 | 2027-10-07 |  | 2027-12-02 |  |  | PO MR-ME-010
ALP-M10-00QJA-ME-OMM-0001 | Nitrogen, Hydrogen and CO2 Supply - Supplier Operation and Maintenance Manual |  | M10 | 00QJA | Nitrogen supply | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-010 |  | 1 | 2027-07-15 | 2027-08-26 |  | 2028-01-13 |  |  | PO MR-ME-010
ALP-M10-00QJA-ME-PRC-0001 | Nitrogen, Hydrogen and CO2 Supply - Supplier Installation and Erection Manual |  | M10 | 00QJA | Nitrogen supply | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-010 |  | 1 | 2027-07-08 | 2027-07-29 |  | 2027-09-09 |  |  | PO MR-ME-010
ALP-M10-00QJA-ME-TRP-0001 | Nitrogen, Hydrogen and CO2 Supply - Factory Acceptance Test Report |  | M10 | 00QJA | Nitrogen supply | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-010 |  | 1 | 2027-09-16 | 2027-09-23 |  | 2027-10-07 |  |  | PO MR-ME-010
ALP-M10-00QJA-ME-TST-0001 | Nitrogen, Hydrogen and CO2 Supply - Factory Acceptance Test Procedure |  | M10 | 00QJA | Nitrogen supply | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-010 |  | 1 | 2027-06-10 | 2027-07-01 |  | 2027-08-12 |  |  | PO MR-ME-010
ALP-M10-00QJA-PR-PID-0001 | Nitrogen, Hydrogen and CO2 Supply - Supplier P&IDs |  | M10 | 00QJA | Nitrogen supply | process | PID | F | approval |  |  | 4 | 16 |  |  |  | MR-ME-010 |  | 1 | 2027-05-27 | 2027-07-01 |  | 2027-07-22 |  |  | PO MR-ME-010
ALP-M11-00QCA-EL-WIR-0001 | Chemical Dosing Skid - Supplier Electrical Schematics and Wiring Diagrams |  | M11 | 00QCA | Chemical dosing | electrical | WIR | F | review |  |  | 28 | 18 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-011 |  | 1 | 2027-06-22 | 2027-07-13 |  | 2027-08-19 | 2027-11-01 | 52 | PO MR-ME-011
ALP-M11-00QCA-IC-DSH-0001 | Chemical Dosing Skid - Supplier Instrument List and Datasheets |  | M11 | 00QCA | Chemical dosing | i_and_c | DSH | E | review |  |  | 20 | 8 |  |  |  | MR-ME-011 | 00QCA10 00QCA10AP001 00QCA10AP002 00QCA10AP003 00QCA10AP004 00QCA10AP005 00QCA10AP006 00QCA10BB001 00QCA10BB002 00QCA10BB003 | 1 | 2027-06-29 | 2027-07-13 |  | 2027-08-19 |  |  | PO MR-ME-011
ALP-M11-00QCA-IC-IOL-0001 | Chemical Dosing Skid - Supplier I/O List, Control Philosophy and Interface Signals |  | M11 | 00QCA | Chemical dosing | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-ME-011 |  | 1 | 2027-06-14 | 2027-07-05 |  | 2027-08-02 |  |  | PO MR-ME-011
ALP-M11-00QCA-ME-CAL-0001 | Chemical Dosing Skid - Supplier Design Calculations |  | M11 | 00QCA | Chemical dosing | mechanical | CAL | E | review |  |  | 4 | 8 |  |  |  | MR-ME-011 |  | 1 | 2027-06-14 | 2027-07-05 |  | 2027-08-02 |  |  | PO MR-ME-011
ALP-M11-00QCA-ME-DSH-0001 | Chemical Dosing Skid - Supplier Certified Datasheets and Performance Curves |  | M11 | 00QCA | Chemical dosing | mechanical | DSH | E | review |  |  | 12 | 16 |  |  |  | MR-ME-011 | 00QCA10 00QCA10AP001 00QCA10AP002 00QCA10AP003 00QCA10AP004 00QCA10AP005 00QCA10AP006 00QCA10BB001 00QCA10BB002 00QCA10BB003 | 1 | 2027-06-02 | 2027-06-16 |  | 2027-07-13 |  |  | PO MR-ME-011
ALP-M11-00QCA-ME-GAD-0001 | Chemical Dosing Skid - Supplier GA Drawings |  | M11 | 00QCA | Chemical dosing | mechanical | GAD | L | review |  |  | 12 | 22 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-011 | 00QCA10 00QCA10AP001 00QCA10AP002 00QCA10AP003 00QCA10AP004 00QCA10AP005 00QCA10AP006 00QCA10BB001 00QCA10BB002 00QCA10BB003 | 1 | 2027-05-28 | 2027-06-25 |  | 2027-07-22 | 2027-11-01 | 72 | PO MR-ME-011
ALP-M11-00QCA-ME-ITP-0001 | Chemical Dosing Skid - Supplier Inspection and Test Plan |  | M11 | 00QCA | Chemical dosing | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-011 |  | 1 | 2027-06-02 | 2027-06-16 |  | 2027-07-05 |  |  | PO MR-ME-011
ALP-M11-00QCA-ME-LST-0001 | Chemical Dosing Skid - Spare Parts and Special Tools Lists |  | M11 | 00QCA | Chemical dosing | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-011 |  | 1 | 2027-07-01 | 2027-07-22 |  | 2027-08-27 |  |  | PO MR-ME-011
ALP-M11-00QCA-ME-MDB-0001 | Chemical Dosing Skid - Manufacturing Record Book and Conformity Certificates |  | M11 | 00QCA | Chemical dosing | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-011 |  | 1 | 2027-10-29 | 2027-11-12 |  | 2028-01-07 |  |  | PO MR-ME-011
ALP-M11-00QCA-ME-OMM-0001 | Chemical Dosing Skid - Supplier Operation and Maintenance Manual |  | M11 | 00QCA | Chemical dosing | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-011 |  | 1 | 2027-08-20 | 2027-10-01 |  | 2028-02-18 |  |  | PO MR-ME-011
ALP-M11-00QCA-ME-PRC-0001 | Chemical Dosing Skid - Supplier Installation and Erection Manual |  | M11 | 00QCA | Chemical dosing | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-011 |  | 1 | 2027-08-13 | 2027-09-03 |  | 2027-10-15 |  |  | PO MR-ME-011
ALP-M11-00QCA-ME-TRP-0001 | Chemical Dosing Skid - Factory Acceptance Test Report |  | M11 | 00QCA | Chemical dosing | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-011 |  | 1 | 2027-10-22 | 2027-10-29 |  | 2027-11-12 |  |  | PO MR-ME-011
ALP-M11-00QCA-ME-TST-0001 | Chemical Dosing Skid - Factory Acceptance Test Procedure |  | M11 | 00QCA | Chemical dosing | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-011 |  | 1 | 2027-07-16 | 2027-08-06 |  | 2027-09-17 |  |  | PO MR-ME-011
ALP-M11-00QCA-PR-PID-0001 | Chemical Dosing Skid - Supplier P&IDs |  | M11 | 00QCA | Chemical dosing | process | PID | F | approval |  |  | 3 | 13 |  |  |  | MR-ME-011 |  | 1 | 2027-05-31 | 2027-07-05 |  | 2027-08-02 |  |  | PO MR-ME-011
ALP-M12-00GBA-CV-CAL-0001 | Water Treatment Package - Supplier Foundation Loads and Anchor Bolt Drawings | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | civil | CAL | E | review |  |  | 6 | 10 |  |  |  | MR-ME-012 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-08 |  |  | PO MR-ME-012
ALP-M12-00GBA-EL-WIR-0001 | Water Treatment Package - Supplier Electrical Schematics and Wiring Diagrams | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | electrical | WIR | F | review |  |  | 72 | 40 | EWP-07-ME-01 | CWP-07-ME-01 | CWA-07 | MR-ME-012 |  | 1 | 2027-03-18 | 2027-04-08 |  | 2027-06-03 | 2027-12-27 | 147 | PO MR-ME-012
ALP-M12-00GBA-IC-DSH-0001 | Water Treatment Package - Supplier Instrument List and Datasheets | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | i_and_c | DSH | E | review |  |  | 70 | 18 |  |  |  | MR-ME-012 | 00GBA10 00GBA10AP001 00GBA10AP002 00GBA10AP003 00GBA10AP004 00GBA10AP005 00GBA10AP006 00GBA10AT001 00GBA10AT002 00GBA10AT003 00GBA10AT004 00GBA10AT005 00GBA10BB001 00GCA10 00GCA10AP001 00GCA10AP002 00GCA10AT001 00GCA10AT002 00GCA10AT003 00GCA10AT004 00LDA10 00LDA10AT001 00LDA10AT002 | 1 | 2027-03-25 | 2027-04-08 |  | 2027-06-03 |  |  | PO MR-ME-012
ALP-M12-00GBA-IC-IOL-0001 | Water Treatment Package - Supplier I/O List, Control Philosophy and Interface Signals | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | i_and_c | IOL | P | review |  |  | 4 | 8 |  |  |  | MR-ME-012 |  | 1 | 2027-03-04 | 2027-03-25 |  | 2027-05-06 |  |  | PO MR-ME-012
ALP-M12-00GBA-IC-LOG-0001 | Water Treatment Package - Supplier Logic Diagrams | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | i_and_c | LOG | F | review |  |  | 103 | 59.5 |  |  |  | MR-ME-012 |  | 1 | 2027-05-20 | 2027-06-17 |  | 2027-09-09 |  |  | PO MR-ME-012
ALP-M12-00GBA-ME-CAL-0001 | Water Treatment Package - Supplier Design Calculations | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | mechanical | CAL | E | review |  |  | 9 | 13 |  |  |  | MR-ME-012 |  | 1 | 2027-03-04 | 2027-03-25 |  | 2027-05-06 |  |  | PO MR-ME-012
ALP-M12-00GBA-ME-DSH-0001 | Water Treatment Package - Supplier Certified Datasheets and Performance Curves | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | mechanical | DSH | E | review |  |  | 27 | 31 |  |  |  | MR-ME-012 | 00GBA10 00GBA10AP001 00GBA10AP002 00GBA10AP003 00GBA10AP004 00GBA10AP005 00GBA10AP006 00GBA10AT001 00GBA10AT002 00GBA10AT003 00GBA10AT004 00GBA10AT005 00GBA10BB001 00GCA10 00GCA10AP001 00GCA10AP002 00GCA10AT001 00GCA10AT002 00GCA10AT003 00GCA10AT004 00LDA10 00LDA10AT001 00LDA10AT002 | 1 | 2027-02-11 | 2027-02-25 |  | 2027-04-08 |  |  | PO MR-ME-012
ALP-M12-00GBA-ME-GAD-0001 | Water Treatment Package - Supplier GA Drawings | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | mechanical | GAD | L | review |  |  | 27 | 44.5 | EWP-07-ME-01 | CWP-07-ME-01 | CWA-07 | MR-ME-012 | 00GBA10 00GBA10AP001 00GBA10AP002 00GBA10AP003 00GBA10AP004 00GBA10AP005 00GBA10AP006 00GBA10AT001 00GBA10AT002 00GBA10AT003 00GBA10AT004 00GBA10AT005 00GBA10BB001 00GCA10 00GCA10AP001 00GCA10AP002 00GCA10AT001 00GCA10AT002 00GCA10AT003 00GCA10AT004 00LDA10 00LDA10AT001 00LDA10AT002 | 1 | 2027-02-11 | 2027-03-11 |  | 2027-04-22 | 2027-12-27 | 177 | PO MR-ME-012
ALP-M12-00GBA-ME-ITP-0001 | Water Treatment Package - Supplier Inspection and Test Plan | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-012 |  | 1 | 2027-02-11 | 2027-02-25 |  | 2027-03-25 |  |  | PO MR-ME-012
ALP-M12-00GBA-ME-LST-0001 | Water Treatment Package - Spare Parts and Special Tools Lists | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-012 |  | 1 | 2027-04-01 | 2027-04-22 |  | 2027-06-17 |  |  | PO MR-ME-012
ALP-M12-00GBA-ME-MDB-0001 | Water Treatment Package - Manufacturing Record Book and Conformity Certificates | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-012 |  | 1 | 2027-11-04 | 2027-11-18 |  | 2028-01-13 |  |  | PO MR-ME-012
ALP-M12-00GBA-ME-OMM-0001 | Water Treatment Package - Supplier Operation and Maintenance Manual | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-012 |  | 1 | 2027-08-26 | 2027-10-07 |  | 2028-02-24 |  |  | PO MR-ME-012
ALP-M12-00GBA-ME-PRC-0001 | Water Treatment Package - Supplier Installation and Erection Manual | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-012 |  | 1 | 2027-08-19 | 2027-09-09 |  | 2027-10-21 |  |  | PO MR-ME-012
ALP-M12-00GBA-ME-TRP-0001 | Water Treatment Package - Factory Acceptance Test Report | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-012 |  | 1 | 2027-10-28 | 2027-11-04 |  | 2027-11-18 |  |  | PO MR-ME-012
ALP-M12-00GBA-ME-TST-0001 | Water Treatment Package - Factory Acceptance Test Procedure | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-012 |  | 1 | 2027-07-22 | 2027-08-12 |  | 2027-09-23 |  |  | PO MR-ME-012
ALP-M12-00GBA-PR-PID-0001 | Water Treatment Package - Supplier P&IDs | SWRO, demin, condensate polishing | M12 | 00GBA | Seawater reverse osmosis | process | PID | F | approval |  |  | 7 | 25 |  |  |  | MR-ME-012 |  | 1 | 2027-02-18 | 2027-03-25 |  | 2027-05-06 |  |  | PO MR-ME-012
ALP-M13-00GHA-CV-CAL-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Supplier Foundation Loads and Anchor Bolt Drawings |  | M13 | 00GHA | Demineralised water storage and distribution | civil | CAL | E | review |  |  | 3 | 7 |  |  |  | MR-ME-013 |  | 1 | 2027-01-21 | 2027-02-11 |  | 2027-03-01 |  |  | PO MR-ME-013
ALP-M13-00GHA-EL-WIR-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Supplier Electrical Schematics and Wiring Diagrams |  | M13 | 00GHA | Demineralised water storage and distribution | electrical | WIR | F | review |  |  | 20 | 14 | EWP-07-ME-01 | CWP-07-ME-01 | CWA-07 | MR-ME-013 |  | 1 | 2027-02-08 | 2027-03-01 |  | 2027-04-07 | 2027-12-27 | 188 | PO MR-ME-013
ALP-M13-00GHA-IC-DSH-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Supplier Instrument List and Datasheets |  | M13 | 00GHA | Demineralised water storage and distribution | i_and_c | DSH | E | review |  |  | 18 | 7.6 |  |  |  | MR-ME-013 | 00GHA10AP001 00GHA10AP002 00GHA10BB001 00GHA10BB002 00GKA10AP001 00GKA10AP002 00GKA10AP003 00GKA10AT001 00GKA10AT002 00GKA10BB001 00SGA10BB001 | 1 | 2027-02-15 | 2027-03-01 |  | 2027-04-07 |  |  | PO MR-ME-013
ALP-M13-00GHA-IC-IOL-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Supplier I/O List, Control Philosophy and Interface Signals |  | M13 | 00GHA | Demineralised water storage and distribution | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-ME-013 |  | 1 | 2027-01-29 | 2027-02-19 |  | 2027-03-19 |  |  | PO MR-ME-013
ALP-M13-00GHA-ME-CAL-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Supplier Design Calculations |  | M13 | 00GHA | Demineralised water storage and distribution | mechanical | CAL | E | review |  |  | 4 | 8 |  |  |  | MR-ME-013 |  | 1 | 2027-01-29 | 2027-02-19 |  | 2027-03-19 |  |  | PO MR-ME-013
ALP-M13-00GHA-ME-DSH-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Supplier Certified Datasheets and Performance Curves |  | M13 | 00GHA | Demineralised water storage and distribution | mechanical | DSH | E | review |  |  | 12 | 16 |  |  |  | MR-ME-013 | 00GHA10AP001 00GHA10AP002 00GHA10BB001 00GHA10BB002 00GKA10AP001 00GKA10AP002 00GKA10AP003 00GKA10AT001 00GKA10AT002 00GKA10BB001 00SGA10BB001 | 1 | 2027-01-19 | 2027-02-02 |  | 2027-03-01 |  |  | PO MR-ME-013
ALP-M13-00GHA-ME-GAD-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Supplier GA Drawings |  | M13 | 00GHA | Demineralised water storage and distribution | mechanical | GAD | L | review |  |  | 12 | 22 | EWP-07-ME-01 | CWP-07-ME-01 | CWA-07 | MR-ME-013 | 00GHA10AP001 00GHA10AP002 00GHA10BB001 00GHA10BB002 00GKA10AP001 00GKA10AP002 00GKA10AP003 00GKA10AT001 00GKA10AT002 00GKA10BB001 00SGA10BB001 | 1 | 2027-01-14 | 2027-02-11 |  | 2027-03-10 | 2027-12-27 | 208 | PO MR-ME-013
ALP-M13-00GHA-ME-ITP-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Supplier Inspection and Test Plan |  | M13 | 00GHA | Demineralised water storage and distribution | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-013 |  | 1 | 2027-01-19 | 2027-02-02 |  | 2027-02-19 |  |  | PO MR-ME-013
ALP-M13-00GHA-ME-LST-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Spare Parts and Special Tools Lists |  | M13 | 00GHA | Demineralised water storage and distribution | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-013 |  | 1 | 2027-02-17 | 2027-03-10 |  | 2027-04-15 |  |  | PO MR-ME-013
ALP-M13-00GHA-ME-MDB-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Manufacturing Record Book and Conformity Certificates |  | M13 | 00GHA | Demineralised water storage and distribution | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-013 |  | 1 | 2027-06-17 | 2027-07-01 |  | 2027-08-26 |  |  | PO MR-ME-013
ALP-M13-00GHA-ME-OMM-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Supplier Operation and Maintenance Manual |  | M13 | 00GHA | Demineralised water storage and distribution | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-013 |  | 1 | 2027-04-08 | 2027-05-20 |  | 2027-10-07 |  |  | PO MR-ME-013
ALP-M13-00GHA-ME-PRC-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Supplier Installation and Erection Manual |  | M13 | 00GHA | Demineralised water storage and distribution | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-013 |  | 1 | 2027-04-01 | 2027-04-22 |  | 2027-06-03 |  |  | PO MR-ME-013
ALP-M13-00GHA-ME-TRP-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Factory Acceptance Test Report |  | M13 | 00GHA | Demineralised water storage and distribution | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-013 |  | 1 | 2027-06-10 | 2027-06-17 |  | 2027-07-01 |  |  | PO MR-ME-013
ALP-M13-00GHA-ME-TST-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Factory Acceptance Test Procedure |  | M13 | 00GHA | Demineralised water storage and distribution | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-013 |  | 1 | 2027-03-04 | 2027-03-25 |  | 2027-05-06 |  |  | PO MR-ME-013
ALP-M13-00GHA-PR-PID-0001 | Shop-Built Tanks and Demin Forwarding Pumps - Supplier P&IDs |  | M13 | 00GHA | Demineralised water storage and distribution | process | PID | F | approval |  |  | 3 | 13 |  |  |  | MR-ME-013 |  | 1 | 2027-01-15 | 2027-02-19 |  | 2027-03-19 |  |  | PO MR-ME-013
ALP-M14-00GNA-CV-CAL-0001 | Waste Water and Sanitary Treatment Packages - Supplier Foundation Loads and Anchor Bolt Drawings |  | M14 | 00GNA | Waste water treatment | civil | CAL | E | review |  |  | 6 | 10 |  |  |  | MR-ME-014 |  | 1 | 2027-02-08 | 2027-03-01 |  | 2027-03-23 |  |  | PO MR-ME-014
ALP-M14-00GNA-EL-WIR-0001 | Waste Water and Sanitary Treatment Packages - Supplier Electrical Schematics and Wiring Diagrams |  | M14 | 00GNA | Waste water treatment | electrical | WIR | F | review |  |  | 76 | 42 | EWP-07-ME-01 | CWP-07-ME-01 | CWA-07 | MR-ME-014 |  | 1 | 2027-03-02 | 2027-03-23 |  | 2027-05-04 | 2027-12-27 | 169 | PO MR-ME-014
ALP-M14-00GNA-IC-DSH-0001 | Waste Water and Sanitary Treatment Packages - Supplier Instrument List and Datasheets |  | M14 | 00GNA | Waste water treatment | i_and_c | DSH | E | review |  |  | 40 | 12 |  |  |  | MR-ME-014 | 00GMA10AP001 00GMA10AP002 00GMA10AP003 00GMA10AP004 00GMA10AP005 00GMA10AP006 00GMA10AT001 00GMA10BB001 00GNA10 00GNA10AP001 00GNA10AP002 00GNA10AP003 00GNA10AP004 00GNA10AP005 00GNA10AP006 00GNA10BB001 00GNA10BB002 00GNA10BB003 00GNA10BB004 00GUA10 00GUA10AP001 00GUA10AP002 | 1 | 2027-03-09 | 2027-03-23 |  | 2027-05-04 |  |  | PO MR-ME-014
ALP-M14-00GNA-IC-IOL-0001 | Waste Water and Sanitary Treatment Packages - Supplier I/O List, Control Philosophy and Interface Signals |  | M14 | 00GNA | Waste water treatment | i_and_c | IOL | P | review |  |  | 2 | 6 |  |  |  | MR-ME-014 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-12 |  |  | PO MR-ME-014
ALP-M14-00GNA-IC-LOG-0001 | Waste Water and Sanitary Treatment Packages - Supplier Logic Diagrams |  | M14 | 00GNA | Waste water treatment | i_and_c | LOG | F | review |  |  | 91 | 53.5 |  |  |  | MR-ME-014 |  | 1 | 2027-04-15 | 2027-05-13 |  | 2027-07-15 |  |  | PO MR-ME-014
ALP-M14-00GNA-ME-CAL-0001 | Waste Water and Sanitary Treatment Packages - Supplier Design Calculations |  | M14 | 00GNA | Waste water treatment | mechanical | CAL | E | review |  |  | 9 | 13 |  |  |  | MR-ME-014 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-12 |  |  | PO MR-ME-014
ALP-M14-00GNA-ME-DSH-0001 | Waste Water and Sanitary Treatment Packages - Supplier Certified Datasheets and Performance Curves |  | M14 | 00GNA | Waste water treatment | mechanical | DSH | E | review |  |  | 26 | 30 |  |  |  | MR-ME-014 | 00GMA10AP001 00GMA10AP002 00GMA10AP003 00GMA10AP004 00GMA10AP005 00GMA10AP006 00GMA10AT001 00GMA10BB001 00GNA10 00GNA10AP001 00GNA10AP002 00GNA10AP003 00GNA10AP004 00GNA10AP005 00GNA10AP006 00GNA10BB001 00GNA10BB002 00GNA10BB003 00GNA10BB004 00GUA10 00GUA10AP001 00GUA10AP002 | 1 | 2027-02-04 | 2027-02-18 |  | 2027-03-23 |  |  | PO MR-ME-014
ALP-M14-00GNA-ME-GAD-0001 | Waste Water and Sanitary Treatment Packages - Supplier GA Drawings |  | M14 | 00GNA | Waste water treatment | mechanical | GAD | L | review |  |  | 26 | 43 | EWP-07-ME-01 | CWP-07-ME-01 | CWA-07 | MR-ME-014 | 00GMA10AP001 00GMA10AP002 00GMA10AP003 00GMA10AP004 00GMA10AP005 00GMA10AP006 00GMA10AT001 00GMA10BB001 00GNA10 00GNA10AP001 00GNA10AP002 00GNA10AP003 00GNA10AP004 00GNA10AP005 00GNA10AP006 00GNA10BB001 00GNA10BB002 00GNA10BB003 00GNA10BB004 00GUA10 00GUA10AP001 00GUA10AP002 | 1 | 2027-02-01 | 2027-03-01 |  | 2027-04-01 | 2027-12-27 | 192 | PO MR-ME-014
ALP-M14-00GNA-ME-ITP-0001 | Waste Water and Sanitary Treatment Packages - Supplier Inspection and Test Plan |  | M14 | 00GNA | Waste water treatment | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-014 |  | 1 | 2027-02-04 | 2027-02-18 |  | 2027-03-11 |  |  | PO MR-ME-014
ALP-M14-00GNA-ME-LST-0001 | Waste Water and Sanitary Treatment Packages - Spare Parts and Special Tools Lists |  | M14 | 00GNA | Waste water treatment | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-014 |  | 1 | 2027-03-11 | 2027-04-01 |  | 2027-05-13 |  |  | PO MR-ME-014
ALP-M14-00GNA-ME-MDB-0001 | Waste Water and Sanitary Treatment Packages - Manufacturing Record Book and Conformity Certificates |  | M14 | 00GNA | Waste water treatment | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-014 |  | 1 | 2027-07-29 | 2027-08-12 |  | 2027-10-07 |  |  | PO MR-ME-014
ALP-M14-00GNA-ME-OMM-0001 | Waste Water and Sanitary Treatment Packages - Supplier Operation and Maintenance Manual |  | M14 | 00GNA | Waste water treatment | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-014 |  | 1 | 2027-05-20 | 2027-07-01 |  | 2027-11-18 |  |  | PO MR-ME-014
ALP-M14-00GNA-ME-PRC-0001 | Waste Water and Sanitary Treatment Packages - Supplier Installation and Erection Manual |  | M14 | 00GNA | Waste water treatment | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-014 |  | 1 | 2027-05-13 | 2027-06-03 |  | 2027-07-15 |  |  | PO MR-ME-014
ALP-M14-00GNA-ME-TRP-0001 | Waste Water and Sanitary Treatment Packages - Factory Acceptance Test Report |  | M14 | 00GNA | Waste water treatment | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-014 |  | 1 | 2027-07-22 | 2027-07-29 |  | 2027-08-12 |  |  | PO MR-ME-014
ALP-M14-00GNA-ME-TST-0001 | Waste Water and Sanitary Treatment Packages - Factory Acceptance Test Procedure |  | M14 | 00GNA | Waste water treatment | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-014 |  | 1 | 2027-04-15 | 2027-05-06 |  | 2027-06-17 |  |  | PO MR-ME-014
ALP-M14-00GNA-PR-PID-0001 | Waste Water and Sanitary Treatment Packages - Supplier P&IDs |  | M14 | 00GNA | Waste water treatment | process | PID | F | approval |  |  | 7 | 25 |  |  |  | MR-ME-014 |  | 1 | 2027-02-04 | 2027-03-11 |  | 2027-04-12 |  |  | PO MR-ME-014
ALP-M15-00EKA-CV-CAL-0001 | Gas Receiving and Metering Station - Supplier Foundation Loads and Anchor Bolt Drawings |  | M15 | 00EKA | Gas receiving, filtration and fiscal metering station | civil | CAL | E | review |  |  | 3 | 7 |  |  |  | MR-ME-015 |  | 1 | 2027-02-04 | 2027-02-25 |  | 2027-03-25 |  |  | PO MR-ME-015
ALP-M15-00EKA-EL-WIR-0001 | Gas Receiving and Metering Station - Supplier Electrical Schematics and Wiring Diagrams |  | M15 | 00EKA | Gas receiving, filtration and fiscal metering station | electrical | WIR | F | review |  |  | 20 | 14 | EWP-09-ME-01 | CWP-09-ME-01 | CWA-09 | MR-ME-015 |  | 1 | 2027-03-04 | 2027-03-25 |  | 2027-05-20 | 2027-11-01 | 117 | PO MR-ME-015
ALP-M15-00EKA-IC-DSH-0001 | Gas Receiving and Metering Station - Supplier Instrument List and Datasheets |  | M15 | 00EKA | Gas receiving, filtration and fiscal metering station | i_and_c | DSH | E | review |  |  | 55 | 15 |  |  |  | MR-ME-015 | 00EKA10 00EKA10AC001 00EKA10AC002 00EKA10AT001 00EKA10AT002 00EKA10BB001 | 1 | 2027-03-11 | 2027-03-25 |  | 2027-05-20 |  |  | PO MR-ME-015
ALP-M15-00EKA-IC-IOL-0001 | Gas Receiving and Metering Station - Supplier I/O List, Control Philosophy and Interface Signals |  | M15 | 00EKA | Gas receiving, filtration and fiscal metering station | i_and_c | IOL | P | review |  |  | 3 | 7 |  |  |  | MR-ME-015 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-22 |  |  | PO MR-ME-015
ALP-M15-00EKA-ME-CAL-0001 | Gas Receiving and Metering Station - Supplier Design Calculations |  | M15 | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | CAL | E | review |  |  | 5 | 9 |  |  |  | MR-ME-015 |  | 1 | 2027-02-18 | 2027-03-11 |  | 2027-04-22 |  |  | PO MR-ME-015
ALP-M15-00EKA-ME-DSH-0001 | Gas Receiving and Metering Station - Supplier Certified Datasheets and Performance Curves |  | M15 | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | DSH | E | review |  |  | 14 | 18 |  |  |  | MR-ME-015 | 00EKA10 00EKA10AC001 00EKA10AC002 00EKA10AT001 00EKA10AT002 00EKA10BB001 | 1 | 2027-01-28 | 2027-02-11 |  | 2027-03-25 |  |  | PO MR-ME-015
ALP-M15-00EKA-ME-GAD-0001 | Gas Receiving and Metering Station - Supplier GA Drawings |  | M15 | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | GAD | L | review |  |  | 14 | 25 | EWP-09-ME-01 | CWP-09-ME-01 | CWA-09 | MR-ME-015 | 00EKA10 00EKA10AC001 00EKA10AC002 00EKA10AT001 00EKA10AT002 00EKA10BB001 | 1 | 2027-01-28 | 2027-02-25 |  | 2027-04-08 | 2027-11-01 | 147 | PO MR-ME-015
ALP-M15-00EKA-ME-ITP-0001 | Gas Receiving and Metering Station - Supplier Inspection and Test Plan |  | M15 | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-015 |  | 1 | 2027-01-28 | 2027-02-11 |  | 2027-03-11 |  |  | PO MR-ME-015
ALP-M15-00EKA-ME-LST-0001 | Gas Receiving and Metering Station - Spare Parts and Special Tools Lists |  | M15 | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-015 |  | 1 | 2027-03-18 | 2027-04-08 |  | 2027-06-03 |  |  | PO MR-ME-015
ALP-M15-00EKA-ME-MDB-0001 | Gas Receiving and Metering Station - Manufacturing Record Book and Conformity Certificates |  | M15 | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-015 |  | 1 | 2027-09-23 | 2027-10-07 |  | 2027-12-02 |  |  | PO MR-ME-015
ALP-M15-00EKA-ME-OMM-0001 | Gas Receiving and Metering Station - Supplier Operation and Maintenance Manual |  | M15 | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-015 |  | 1 | 2027-07-15 | 2027-08-26 |  | 2028-01-13 |  |  | PO MR-ME-015
ALP-M15-00EKA-ME-PRC-0001 | Gas Receiving and Metering Station - Supplier Installation and Erection Manual |  | M15 | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-015 |  | 1 | 2027-07-08 | 2027-07-29 |  | 2027-09-09 |  |  | PO MR-ME-015
ALP-M15-00EKA-ME-TRP-0001 | Gas Receiving and Metering Station - Factory Acceptance Test Report |  | M15 | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-015 |  | 1 | 2027-09-16 | 2027-09-23 |  | 2027-10-07 |  |  | PO MR-ME-015
ALP-M15-00EKA-ME-TST-0001 | Gas Receiving and Metering Station - Factory Acceptance Test Procedure |  | M15 | 00EKA | Gas receiving, filtration and fiscal metering station | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-015 |  | 1 | 2027-06-10 | 2027-07-01 |  | 2027-08-12 |  |  | PO MR-ME-015
ALP-M15-00EKA-PR-PID-0001 | Gas Receiving and Metering Station - Supplier P&IDs |  | M15 | 00EKA | Gas receiving, filtration and fiscal metering station | process | PID | F | approval |  |  | 5 | 19 |  |  |  | MR-ME-015 |  | 1 | 2027-02-04 | 2027-03-11 |  | 2027-04-22 |  |  | PO MR-ME-015
ALP-M16-00EGA-CV-CAL-0001 | LDO Unloading and Forwarding / Treatment Skids - Supplier Foundation Loads and Anchor Bolt Drawings |  | M16 | 00EGA | LDO unloading | civil | CAL | E | review |  |  | 4 | 8 |  |  |  | MR-ME-016 |  | 1 | 2027-02-01 | 2027-02-22 |  | 2027-03-18 |  |  | PO MR-ME-016
ALP-M16-00EGA-EL-WIR-0001 | LDO Unloading and Forwarding / Treatment Skids - Supplier Electrical Schematics and Wiring Diagrams |  | M16 | 00EGA | LDO unloading | electrical | WIR | F | review |  |  | 40 | 24 | EWP-10-ME-01 | CWP-10-ME-01 | CWA-10 | MR-ME-016 |  | 1 | 2027-02-25 | 2027-03-18 |  | 2027-05-07 | 2027-10-04 | 106 | PO MR-ME-016
ALP-M16-00EGA-IC-DSH-0001 | LDO Unloading and Forwarding / Treatment Skids - Supplier Instrument List and Datasheets |  | M16 | 00EGA | LDO unloading | i_and_c | DSH | E | review |  |  | 50 | 14 |  |  |  | MR-ME-016 | 00EGA10 00EGA10AP001 00EGA10AP002 00EGA10AP003 00EGA10AP004 00EGA10AT001 00EGA10AT002 00EGA10BB001 00EGC10 00EGC10AP001 00EGC10AP002 00EGC10AP003 00EGC10AT001 00EGC10AT002 00EGC10AT003 | 1 | 2027-03-04 | 2027-03-18 |  | 2027-05-07 |  |  | PO MR-ME-016
ALP-M16-00EGA-IC-IOL-0001 | LDO Unloading and Forwarding / Treatment Skids - Supplier I/O List, Control Philosophy and Interface Signals |  | M16 | 00EGA | LDO unloading | i_and_c | IOL | P | review |  |  | 3 | 7 |  |  |  | MR-ME-016 |  | 1 | 2027-02-12 | 2027-03-05 |  | 2027-04-13 |  |  | PO MR-ME-016
ALP-M16-00EGA-ME-CAL-0001 | LDO Unloading and Forwarding / Treatment Skids - Supplier Design Calculations |  | M16 | 00EGA | LDO unloading | mechanical | CAL | E | review |  |  | 6 | 10 |  |  |  | MR-ME-016 |  | 1 | 2027-02-12 | 2027-03-05 |  | 2027-04-13 |  |  | PO MR-ME-016
ALP-M16-00EGA-ME-DSH-0001 | LDO Unloading and Forwarding / Treatment Skids - Supplier Certified Datasheets and Performance Curves |  | M16 | 00EGA | LDO unloading | mechanical | DSH | E | review |  |  | 18 | 22 |  |  |  | MR-ME-016 | 00EGA10 00EGA10AP001 00EGA10AP002 00EGA10AP003 00EGA10AP004 00EGA10AT001 00EGA10AT002 00EGA10BB001 00EGC10 00EGC10AP001 00EGC10AP002 00EGC10AP003 00EGC10AT001 00EGC10AT002 00EGC10AT003 | 1 | 2027-01-26 | 2027-02-09 |  | 2027-03-18 |  |  | PO MR-ME-016
ALP-M16-00EGA-ME-GAD-0001 | LDO Unloading and Forwarding / Treatment Skids - Supplier GA Drawings |  | M16 | 00EGA | LDO unloading | mechanical | GAD | L | review |  |  | 18 | 31 | EWP-10-ME-01 | CWP-10-ME-01 | CWA-10 | MR-ME-016 | 00EGA10 00EGA10AP001 00EGA10AP002 00EGA10AP003 00EGA10AP004 00EGA10AT001 00EGA10AT002 00EGA10BB001 00EGC10 00EGC10AP001 00EGC10AP002 00EGC10AP003 00EGC10AT001 00EGC10AT002 00EGC10AT003 | 1 | 2027-01-25 | 2027-02-22 |  | 2027-03-31 | 2027-10-04 | 133 | PO MR-ME-016
ALP-M16-00EGA-ME-ITP-0001 | LDO Unloading and Forwarding / Treatment Skids - Supplier Inspection and Test Plan |  | M16 | 00EGA | LDO unloading | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-016 |  | 1 | 2027-01-26 | 2027-02-09 |  | 2027-03-05 |  |  | PO MR-ME-016
ALP-M16-00EGA-ME-LST-0001 | LDO Unloading and Forwarding / Treatment Skids - Spare Parts and Special Tools Lists |  | M16 | 00EGA | LDO unloading | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-016 |  | 1 | 2027-03-10 | 2027-03-31 |  | 2027-05-20 |  |  | PO MR-ME-016
ALP-M16-00EGA-ME-MDB-0001 | LDO Unloading and Forwarding / Treatment Skids - Manufacturing Record Book and Conformity Certificates |  | M16 | 00EGA | LDO unloading | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-016 |  | 1 | 2027-08-26 | 2027-09-09 |  | 2027-11-04 |  |  | PO MR-ME-016
ALP-M16-00EGA-ME-OMM-0001 | LDO Unloading and Forwarding / Treatment Skids - Supplier Operation and Maintenance Manual |  | M16 | 00EGA | LDO unloading | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-016 |  | 1 | 2027-06-17 | 2027-07-29 |  | 2027-12-16 |  |  | PO MR-ME-016
ALP-M16-00EGA-ME-PRC-0001 | LDO Unloading and Forwarding / Treatment Skids - Supplier Installation and Erection Manual |  | M16 | 00EGA | LDO unloading | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-016 |  | 1 | 2027-06-10 | 2027-07-01 |  | 2027-08-12 |  |  | PO MR-ME-016
ALP-M16-00EGA-ME-TRP-0001 | LDO Unloading and Forwarding / Treatment Skids - Factory Acceptance Test Report |  | M16 | 00EGA | LDO unloading | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-016 |  | 1 | 2027-08-19 | 2027-08-26 |  | 2027-09-09 |  |  | PO MR-ME-016
ALP-M16-00EGA-ME-TST-0001 | LDO Unloading and Forwarding / Treatment Skids - Factory Acceptance Test Procedure |  | M16 | 00EGA | LDO unloading | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-016 |  | 1 | 2027-05-13 | 2027-06-03 |  | 2027-07-15 |  |  | PO MR-ME-016
ALP-M16-00EGA-PR-PID-0001 | LDO Unloading and Forwarding / Treatment Skids - Supplier P&IDs |  | M16 | 00EGA | LDO unloading | process | PID | F | approval |  |  | 6 | 22 |  |  |  | MR-ME-016 |  | 1 | 2027-01-29 | 2027-03-05 |  | 2027-04-13 |  |  | PO MR-ME-016
ALP-M17-00EGB-GE-ITP-0001 | Field-Erected Storage Tanks: LDO Storage and Fire Water - Subcontractor Inspection and Test Plans | API 650 | M17 | 00EGB | LDO storage | general | ITP | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-017 |  | 1 | 2027-03-24 | 2027-04-07 |  | 2027-04-21 |  |  | PO MR-ME-017
ALP-M17-00EGB-GE-MOS-0001 | Field-Erected Storage Tanks: LDO Storage and Fire Water - Subcontractor Method Statements, Part 1 of 6 | API 650 | M17 | 00EGB | LDO storage | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-017 |  | 1 | 2027-03-24 | 2027-04-07 |  | 2027-04-21 |  |  | PO MR-ME-017
ALP-M17-00EGB-GE-MOS-0002 | Field-Erected Storage Tanks: LDO Storage and Fire Water - Subcontractor Method Statements, Part 2 of 6 | API 650 | M17 | 00EGB | LDO storage | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-017 |  | 1 | 2027-03-24 | 2027-04-07 |  | 2027-04-21 |  |  | PO MR-ME-017
ALP-M17-00EGB-GE-MOS-0003 | Field-Erected Storage Tanks: LDO Storage and Fire Water - Subcontractor Method Statements, Part 3 of 6 | API 650 | M17 | 00EGB | LDO storage | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-017 |  | 1 | 2027-03-24 | 2027-04-07 |  | 2027-04-21 |  |  | PO MR-ME-017
ALP-M17-00EGB-GE-MOS-0004 | Field-Erected Storage Tanks: LDO Storage and Fire Water - Subcontractor Method Statements, Part 4 of 6 | API 650 | M17 | 00EGB | LDO storage | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-017 |  | 1 | 2027-03-24 | 2027-04-07 |  | 2027-04-21 |  |  | PO MR-ME-017
ALP-M17-00EGB-GE-MOS-0005 | Field-Erected Storage Tanks: LDO Storage and Fire Water - Subcontractor Method Statements, Part 5 of 6 | API 650 | M17 | 00EGB | LDO storage | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-017 |  | 1 | 2027-03-24 | 2027-04-07 |  | 2027-04-21 |  |  | PO MR-ME-017
ALP-M17-00EGB-GE-MOS-0006 | Field-Erected Storage Tanks: LDO Storage and Fire Water - Subcontractor Method Statements, Part 6 of 6 | API 650 | M17 | 00EGB | LDO storage | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-017 |  | 1 | 2027-03-24 | 2027-04-07 |  | 2027-04-21 |  |  | PO MR-ME-017
ALP-M18-10HSB-CV-CAL-0001 | Aqueous Ammonia Storage and Forwarding - Supplier Foundation Loads and Anchor Bolt Drawings |  | M18 | 10HSB | Ammonia storage and supply | civil | CAL | E | review |  |  | 2 | 6 |  |  |  | MR-ME-018 |  | 1 | 2027-03-01 | 2027-03-22 |  | 2027-04-13 |  |  | PO MR-ME-018
ALP-M18-10HSB-EL-WIR-0001 | Aqueous Ammonia Storage and Forwarding - Supplier Electrical Schematics and Wiring Diagrams |  | M18 | 10HSB | Ammonia storage and supply | electrical | WIR | F | review |  |  | 12 | 10 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-018 |  | 1 | 2027-03-23 | 2027-04-13 |  | 2027-05-25 | 2027-11-01 | 114 | PO MR-ME-018
ALP-M18-10HSB-IC-DSH-0001 | Aqueous Ammonia Storage and Forwarding - Supplier Instrument List and Datasheets |  | M18 | 10HSB | Ammonia storage and supply | i_and_c | DSH | E | review |  |  | 20 | 8 |  |  |  | MR-ME-018 | 10HSB10AP001 10HSB10AP002 10HSB10BB001 10HSB10BB002 | 1 | 2027-03-30 | 2027-04-13 |  | 2027-05-25 |  |  | PO MR-ME-018
ALP-M18-10HSB-IC-IOL-0001 | Aqueous Ammonia Storage and Forwarding - Supplier I/O List, Control Philosophy and Interface Signals |  | M18 | 10HSB | Ammonia storage and supply | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-ME-018 |  | 1 | 2027-03-11 | 2027-04-01 |  | 2027-05-03 |  |  | PO MR-ME-018
ALP-M18-10HSB-ME-CAL-0001 | Aqueous Ammonia Storage and Forwarding - Supplier Design Calculations |  | M18 | 10HSB | Ammonia storage and supply | mechanical | CAL | E | review |  |  | 3 | 7 |  |  |  | MR-ME-018 |  | 1 | 2027-03-11 | 2027-04-01 |  | 2027-05-03 |  |  | PO MR-ME-018
ALP-M18-10HSB-ME-DSH-0001 | Aqueous Ammonia Storage and Forwarding - Supplier Certified Datasheets and Performance Curves |  | M18 | 10HSB | Ammonia storage and supply | mechanical | DSH | E | review |  |  | 8 | 12 |  |  |  | MR-ME-018 | 10HSB10AP001 10HSB10AP002 10HSB10BB001 10HSB10BB002 | 1 | 2027-02-25 | 2027-03-11 |  | 2027-04-13 |  |  | PO MR-ME-018
ALP-M18-10HSB-ME-GAD-0001 | Aqueous Ammonia Storage and Forwarding - Supplier GA Drawings |  | M18 | 10HSB | Ammonia storage and supply | mechanical | GAD | L | review |  |  | 8 | 16 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-018 | 10HSB10AP001 10HSB10AP002 10HSB10BB001 10HSB10BB002 | 1 | 2027-02-22 | 2027-03-22 |  | 2027-04-22 | 2027-11-01 | 137 | PO MR-ME-018
ALP-M18-10HSB-ME-ITP-0001 | Aqueous Ammonia Storage and Forwarding - Supplier Inspection and Test Plan |  | M18 | 10HSB | Ammonia storage and supply | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-018 |  | 1 | 2027-02-25 | 2027-03-11 |  | 2027-04-01 |  |  | PO MR-ME-018
ALP-M18-10HSB-ME-LST-0001 | Aqueous Ammonia Storage and Forwarding - Spare Parts and Special Tools Lists |  | M18 | 10HSB | Ammonia storage and supply | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-018 |  | 1 | 2027-04-01 | 2027-04-22 |  | 2027-06-03 |  |  | PO MR-ME-018
ALP-M18-10HSB-ME-MDB-0001 | Aqueous Ammonia Storage and Forwarding - Manufacturing Record Book and Conformity Certificates |  | M18 | 10HSB | Ammonia storage and supply | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-018 |  | 1 | 2027-08-19 | 2027-09-02 |  | 2027-10-28 |  |  | PO MR-ME-018
ALP-M18-10HSB-ME-OMM-0001 | Aqueous Ammonia Storage and Forwarding - Supplier Operation and Maintenance Manual |  | M18 | 10HSB | Ammonia storage and supply | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-018 |  | 1 | 2027-06-10 | 2027-07-22 |  | 2027-12-09 |  |  | PO MR-ME-018
ALP-M18-10HSB-ME-PRC-0001 | Aqueous Ammonia Storage and Forwarding - Supplier Installation and Erection Manual |  | M18 | 10HSB | Ammonia storage and supply | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-018 |  | 1 | 2027-06-03 | 2027-06-24 |  | 2027-08-05 |  |  | PO MR-ME-018
ALP-M18-10HSB-ME-TRP-0001 | Aqueous Ammonia Storage and Forwarding - Factory Acceptance Test Report |  | M18 | 10HSB | Ammonia storage and supply | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-018 |  | 1 | 2027-08-12 | 2027-08-19 |  | 2027-09-02 |  |  | PO MR-ME-018
ALP-M18-10HSB-ME-TST-0001 | Aqueous Ammonia Storage and Forwarding - Factory Acceptance Test Procedure |  | M18 | 10HSB | Ammonia storage and supply | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-018 |  | 1 | 2027-05-06 | 2027-05-27 |  | 2027-07-08 |  |  | PO MR-ME-018
ALP-M18-10HSB-PR-PID-0001 | Aqueous Ammonia Storage and Forwarding - Supplier P&IDs |  | M18 | 10HSB | Ammonia storage and supply | process | PID | F | approval |  |  | 2 | 10 |  |  |  | MR-ME-018 |  | 1 | 2027-02-25 | 2027-04-01 |  | 2027-05-03 |  |  | PO MR-ME-018
ALP-M19-10HAN-CV-CAL-0001 | HRSG Blowdown and Drain Tanks - Supplier Foundation Loads and Anchor Bolt Drawings |  | M19 | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | civil | CAL | E | review |  |  | 1 | 5 |  |  |  | MR-ME-019 |  | 1 | 2027-02-12 | 2027-03-05 |  | 2027-03-23 |  |  | PO MR-ME-019
ALP-M19-10HAN-EL-WIR-0001 | HRSG Blowdown and Drain Tanks - Supplier Electrical Schematics and Wiring Diagrams |  | M19 | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | electrical | WIR | F | review |  |  | 4 | 6 | EWP-01-ME-01 | CWP-01-ME-01 | CWA-01 | MR-ME-019 |  | 1 | 2027-03-02 | 2027-03-23 |  | 2027-04-29 | 2027-10-18 | 122 | PO MR-ME-019
ALP-M19-10HAN-IC-DSH-0001 | HRSG Blowdown and Drain Tanks - Supplier Instrument List and Datasheets |  | M19 | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | i_and_c | DSH | E | review |  |  | 13 | 6.6 |  |  |  | MR-ME-019 | 10HAN10AP001 10HAN10AP002 10HAN10BB001 10HAN10BB002 | 1 | 2027-03-09 | 2027-03-23 |  | 2027-04-29 |  |  | PO MR-ME-019
ALP-M19-10HAN-IC-IOL-0001 | HRSG Blowdown and Drain Tanks - Supplier I/O List, Control Philosophy and Interface Signals |  | M19 | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-ME-019 |  | 1 | 2027-02-22 | 2027-03-15 |  | 2027-04-12 |  |  | PO MR-ME-019
ALP-M19-10HAN-ME-CAL-0001 | HRSG Blowdown and Drain Tanks - Supplier Design Calculations |  | M19 | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | CAL | E | review |  |  | 2 | 6 |  |  |  | MR-ME-019 |  | 1 | 2027-02-22 | 2027-03-15 |  | 2027-04-12 |  |  | PO MR-ME-019
ALP-M19-10HAN-ME-DSH-0001 | HRSG Blowdown and Drain Tanks - Supplier Certified Datasheets and Performance Curves |  | M19 | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | DSH | E | review |  |  | 4 | 8 |  |  |  | MR-ME-019 | 10HAN10AP001 10HAN10AP002 10HAN10BB001 10HAN10BB002 | 1 | 2027-02-10 | 2027-02-24 |  | 2027-03-23 |  |  | PO MR-ME-019
ALP-M19-10HAN-ME-GAD-0001 | HRSG Blowdown and Drain Tanks - Supplier GA Drawings |  | M19 | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | GAD | L | review |  |  | 4 | 10 | EWP-01-ME-01 | CWP-01-ME-01 | CWA-01 | MR-ME-019 | 10HAN10AP001 10HAN10AP002 10HAN10BB001 10HAN10BB002 | 1 | 2027-02-05 | 2027-03-05 |  | 2027-04-01 | 2027-10-18 | 142 | PO MR-ME-019
ALP-M19-10HAN-ME-ITP-0001 | HRSG Blowdown and Drain Tanks - Supplier Inspection and Test Plan |  | M19 | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-019 |  | 1 | 2027-02-10 | 2027-02-24 |  | 2027-03-15 |  |  | PO MR-ME-019
ALP-M19-10HAN-ME-LST-0001 | HRSG Blowdown and Drain Tanks - Spare Parts and Special Tools Lists |  | M19 | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-019 |  | 1 | 2027-03-11 | 2027-04-01 |  | 2027-05-07 |  |  | PO MR-ME-019
ALP-M19-10HAN-ME-MDB-0001 | HRSG Blowdown and Drain Tanks - Manufacturing Record Book and Conformity Certificates |  | M19 | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-019 |  | 1 | 2027-07-09 | 2027-07-23 |  | 2027-09-17 |  |  | PO MR-ME-019
ALP-M19-10HAN-ME-OMM-0001 | HRSG Blowdown and Drain Tanks - Supplier Operation and Maintenance Manual |  | M19 | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-019 |  | 1 | 2027-04-30 | 2027-06-11 |  | 2027-10-29 |  |  | PO MR-ME-019
ALP-M19-10HAN-ME-PRC-0001 | HRSG Blowdown and Drain Tanks - Supplier Installation and Erection Manual |  | M19 | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-019 |  | 1 | 2027-04-23 | 2027-05-14 |  | 2027-06-25 |  |  | PO MR-ME-019
ALP-M19-10HAN-ME-TRP-0001 | HRSG Blowdown and Drain Tanks - Factory Acceptance Test Report |  | M19 | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-019 |  | 1 | 2027-07-02 | 2027-07-09 |  | 2027-07-23 |  |  | PO MR-ME-019
ALP-M19-10HAN-ME-TST-0001 | HRSG Blowdown and Drain Tanks - Factory Acceptance Test Procedure |  | M19 | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-019 |  | 1 | 2027-03-26 | 2027-04-16 |  | 2027-05-28 |  |  | PO MR-ME-019
ALP-M19-10HAN-PR-PID-0001 | HRSG Blowdown and Drain Tanks - Supplier P&IDs |  | M19 | 10HAN | HRSG blowdown and drains (EPC tanks and headers) | process | PID | F | approval |  |  | 2 | 10 |  |  |  | MR-ME-019 |  | 1 | 2027-02-08 | 2027-03-15 |  | 2027-04-12 |  |  | PO MR-ME-019
ALP-M20-00SGA-CV-CAL-0001 | Fire Pumps and Fire Protection Systems - Supplier Foundation Loads and Anchor Bolt Drawings |  | M20 | 00SGA | Fire water system | civil | CAL | E | review |  |  | 6 | 10 |  |  |  | MR-ME-020 |  | 1 | 2027-02-10 | 2027-03-03 |  | 2027-03-25 |  |  | PO MR-ME-020
ALP-M20-00SGA-EL-WIR-0001 | Fire Pumps and Fire Protection Systems - Supplier Electrical Schematics and Wiring Diagrams |  | M20 | 00SGA | Fire water system | electrical | WIR | F | review |  |  | 24 | 16 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-020 |  | 1 | 2027-03-04 | 2027-03-25 |  | 2027-05-10 | 2027-11-01 | 125 | PO MR-ME-020
ALP-M20-00SGA-IC-DSH-0001 | Fire Pumps and Fire Protection Systems - Supplier Instrument List and Datasheets |  | M20 | 00SGA | Fire water system | i_and_c | DSH | E | review |  |  | 70 | 18 |  |  |  | MR-ME-020 | 00SGA10AP001 00SGA10AP002 00SGA10AP003 00SGA10BB002 00SGC10AA001 00SGC10AA002 00SGC10AA003 00SGC10AA004 00SGC10AA005 00SGC10AA006 00SGC10AA007 00SGC10AA008 00SGC10AA009 00SGC10AA010 00SGC10BB001 | 1 | 2027-03-11 | 2027-03-25 |  | 2027-05-10 |  |  | PO MR-ME-020
ALP-M20-00SGA-IC-IOL-0001 | Fire Pumps and Fire Protection Systems - Supplier I/O List, Control Philosophy and Interface Signals |  | M20 | 00SGA | Fire water system | i_and_c | IOL | P | review |  |  | 4 | 8 |  |  |  | MR-ME-020 |  | 1 | 2027-02-22 | 2027-03-15 |  | 2027-04-16 |  |  | PO MR-ME-020
ALP-M20-00SGA-ME-CAL-0001 | Fire Pumps and Fire Protection Systems - Supplier Design Calculations |  | M20 | 00SGA | Fire water system | mechanical | CAL | E | review |  |  | 10 | 14 |  |  |  | MR-ME-020 |  | 1 | 2027-02-22 | 2027-03-15 |  | 2027-04-16 |  |  | PO MR-ME-020
ALP-M20-00SGA-ME-DSH-0001 | Fire Pumps and Fire Protection Systems - Supplier Certified Datasheets and Performance Curves |  | M20 | 00SGA | Fire water system | mechanical | DSH | E | review |  |  | 28 | 32 |  |  |  | MR-ME-020 | 00SGA10AP001 00SGA10AP002 00SGA10AP003 00SGA10BB002 00SGC10AA001 00SGC10AA002 00SGC10AA003 00SGC10AA004 00SGC10AA005 00SGC10AA006 00SGC10AA007 00SGC10AA008 00SGC10AA009 00SGC10AA010 00SGC10BB001 | 1 | 2027-02-05 | 2027-02-19 |  | 2027-03-25 |  |  | PO MR-ME-020
ALP-M20-00SGA-ME-GAD-0001 | Fire Pumps and Fire Protection Systems - Supplier GA Drawings |  | M20 | 00SGA | Fire water system | mechanical | GAD | L | review |  |  | 28 | 46 | EWP-08-ME-01 | CWP-08-ME-01 | CWA-08 | MR-ME-020 | 00SGA10AP001 00SGA10AP002 00SGA10AP003 00SGA10BB002 00SGC10AA001 00SGC10AA002 00SGC10AA003 00SGC10AA004 00SGC10AA005 00SGC10AA006 00SGC10AA007 00SGC10AA008 00SGC10AA009 00SGC10AA010 00SGC10BB001 | 1 | 2027-02-03 | 2027-03-03 |  | 2027-04-06 | 2027-11-01 | 149 | PO MR-ME-020
ALP-M20-00SGA-ME-ITP-0001 | Fire Pumps and Fire Protection Systems - Supplier Inspection and Test Plan |  | M20 | 00SGA | Fire water system | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-020 |  | 1 | 2027-02-05 | 2027-02-19 |  | 2027-03-15 |  |  | PO MR-ME-020
ALP-M20-00SGA-ME-LST-0001 | Fire Pumps and Fire Protection Systems - Spare Parts and Special Tools Lists |  | M20 | 00SGA | Fire water system | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-020 |  | 1 | 2027-03-16 | 2027-04-06 |  | 2027-05-20 |  |  | PO MR-ME-020
ALP-M20-00SGA-ME-MDB-0001 | Fire Pumps and Fire Protection Systems - Manufacturing Record Book and Conformity Certificates |  | M20 | 00SGA | Fire water system | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-020 |  | 1 | 2027-08-12 | 2027-08-26 |  | 2027-10-21 |  |  | PO MR-ME-020
ALP-M20-00SGA-ME-OMM-0001 | Fire Pumps and Fire Protection Systems - Supplier Operation and Maintenance Manual |  | M20 | 00SGA | Fire water system | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-020 |  | 1 | 2027-06-03 | 2027-07-15 |  | 2027-12-02 |  |  | PO MR-ME-020
ALP-M20-00SGA-ME-PRC-0001 | Fire Pumps and Fire Protection Systems - Supplier Installation and Erection Manual |  | M20 | 00SGA | Fire water system | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-020 |  | 1 | 2027-05-27 | 2027-06-17 |  | 2027-07-29 |  |  | PO MR-ME-020
ALP-M20-00SGA-ME-TRP-0001 | Fire Pumps and Fire Protection Systems - Factory Acceptance Test Report |  | M20 | 00SGA | Fire water system | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-020 |  | 1 | 2027-08-05 | 2027-08-12 |  | 2027-08-26 |  |  | PO MR-ME-020
ALP-M20-00SGA-ME-TST-0001 | Fire Pumps and Fire Protection Systems - Factory Acceptance Test Procedure |  | M20 | 00SGA | Fire water system | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-020 |  | 1 | 2027-04-29 | 2027-05-20 |  | 2027-07-01 |  |  | PO MR-ME-020
ALP-M20-00SGA-PR-PID-0001 | Fire Pumps and Fire Protection Systems - Supplier P&IDs |  | M20 | 00SGA | Fire water system | process | PID | F | approval |  |  | 12 | 40 |  |  |  | MR-ME-020 |  | 1 | 2027-02-08 | 2027-03-15 |  | 2027-04-16 |  |  | PO MR-ME-020
ALP-M21-00SMA-CV-CAL-0001 | EOT Cranes - Supplier Foundation Loads and Anchor Bolt Drawings |  | M21 | 00SMA | Cranes and hoists | civil | CAL | E | review |  |  | 2 | 6 |  |  |  | MR-ME-021 |  | 1 | 2027-02-01 | 2027-02-22 |  | 2027-03-18 |  |  | PO MR-ME-021
ALP-M21-00SMA-EL-WIR-0001 | EOT Cranes - Supplier Electrical Schematics and Wiring Diagrams |  | M21 | 00SMA | Cranes and hoists | electrical | WIR | F | review |  |  | 16 | 12 | EWP-01-ME-01 | CWP-01-ME-01 | CWA-01 | MR-ME-021 |  | 1 | 2027-02-25 | 2027-03-18 |  | 2027-05-07 | 2027-10-18 | 116 | PO MR-ME-021
ALP-M21-00SMA-IC-IOL-0001 | EOT Cranes - Supplier I/O List, Control Philosophy and Interface Signals |  | M21 | 00SMA | Cranes and hoists | i_and_c | IOL | P | review |  |  | 1 | 5 |  |  |  | MR-ME-021 |  | 1 | 2027-02-12 | 2027-03-05 |  | 2027-04-13 |  |  | PO MR-ME-021
ALP-M21-00SMA-ME-CAL-0001 | EOT Cranes - Supplier Design Calculations |  | M21 | 00SMA | Cranes and hoists | mechanical | CAL | E | review |  |  | 3 | 7 |  |  |  | MR-ME-021 |  | 1 | 2027-02-12 | 2027-03-05 |  | 2027-04-13 |  |  | PO MR-ME-021
ALP-M21-00SMA-ME-DSH-0001 | EOT Cranes - Supplier Certified Datasheets and Performance Curves |  | M21 | 00SMA | Cranes and hoists | mechanical | DSH | E | review |  |  | 8 | 12 |  |  |  | MR-ME-021 | 00SMA10 00SMA20 00SMA30 00SMA40 00SMA50 00SMA60 | 1 | 2027-01-26 | 2027-02-09 |  | 2027-03-18 |  |  | PO MR-ME-021
ALP-M21-00SMA-ME-GAD-0001 | EOT Cranes - Supplier GA Drawings |  | M21 | 00SMA | Cranes and hoists | mechanical | GAD | L | review |  |  | 8 | 16 | EWP-01-ME-01 | CWP-01-ME-01 | CWA-01 | MR-ME-021 | 00SMA10 00SMA20 00SMA30 00SMA40 00SMA50 00SMA60 | 1 | 2027-01-25 | 2027-02-22 |  | 2027-03-31 | 2027-10-18 | 143 | PO MR-ME-021
ALP-M21-00SMA-ME-ITP-0001 | EOT Cranes - Supplier Inspection and Test Plan |  | M21 | 00SMA | Cranes and hoists | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-ME-021 |  | 1 | 2027-01-26 | 2027-02-09 |  | 2027-03-05 |  |  | PO MR-ME-021
ALP-M21-00SMA-ME-LST-0001 | EOT Cranes - Spare Parts and Special Tools Lists |  | M21 | 00SMA | Cranes and hoists | mechanical | LST | P | review |  |  | 1 | 6 |  |  |  | MR-ME-021 |  | 1 | 2027-03-10 | 2027-03-31 |  | 2027-05-20 |  |  | PO MR-ME-021
ALP-M21-00SMA-ME-MDB-0001 | EOT Cranes - Manufacturing Record Book and Conformity Certificates |  | M21 | 00SMA | Cranes and hoists | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-ME-021 |  | 1 | 2027-08-26 | 2027-09-09 |  | 2027-11-04 |  |  | PO MR-ME-021
ALP-M21-00SMA-ME-OMM-0001 | EOT Cranes - Supplier Operation and Maintenance Manual |  | M21 | 00SMA | Cranes and hoists | mechanical | OMM | D | review |  |  | 1 | 12 |  |  |  | MR-ME-021 |  | 1 | 2027-06-17 | 2027-07-29 |  | 2027-12-16 |  |  | PO MR-ME-021
ALP-M21-00SMA-ME-PRC-0001 | EOT Cranes - Supplier Installation and Erection Manual |  | M21 | 00SMA | Cranes and hoists | mechanical | PRC | B | review |  |  | 1 | 6 |  |  |  | MR-ME-021 |  | 1 | 2027-06-10 | 2027-07-01 |  | 2027-08-12 |  |  | PO MR-ME-021
ALP-M21-00SMA-ME-TRP-0001 | EOT Cranes - Factory Acceptance Test Report |  | M21 | 00SMA | Cranes and hoists | mechanical | TRP | Q | review |  |  | 1 | 4 |  |  |  | MR-ME-021 |  | 1 | 2027-08-19 | 2027-08-26 |  | 2027-09-09 |  |  | PO MR-ME-021
ALP-M21-00SMA-ME-TST-0001 | EOT Cranes - Factory Acceptance Test Procedure |  | M21 | 00SMA | Cranes and hoists | mechanical | TST | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-021 |  | 1 | 2027-05-13 | 2027-06-03 |  | 2027-07-15 |  |  | PO MR-ME-021
ALP-M22-00000-GE-ITP-0001 | Painting and Insulation - Subcontractor Inspection and Test Plans | subcontract | M22 | 00000 | plant general | general | ITP | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-022 |  | 1 | 2027-06-29 | 2027-07-13 |  | 2027-07-27 |  |  | PO MR-ME-022
ALP-M22-00000-GE-MOS-0001 | Painting and Insulation - Subcontractor Method Statements, Part 1 of 6 | subcontract | M22 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-022 |  | 1 | 2027-06-29 | 2027-07-13 |  | 2027-07-27 |  |  | PO MR-ME-022
ALP-M22-00000-GE-MOS-0002 | Painting and Insulation - Subcontractor Method Statements, Part 2 of 6 | subcontract | M22 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-022 |  | 1 | 2027-06-29 | 2027-07-13 |  | 2027-07-27 |  |  | PO MR-ME-022
ALP-M22-00000-GE-MOS-0003 | Painting and Insulation - Subcontractor Method Statements, Part 3 of 6 | subcontract | M22 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-022 |  | 1 | 2027-06-29 | 2027-07-13 |  | 2027-07-27 |  |  | PO MR-ME-022
ALP-M22-00000-GE-MOS-0004 | Painting and Insulation - Subcontractor Method Statements, Part 4 of 6 | subcontract | M22 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-022 |  | 1 | 2027-06-29 | 2027-07-13 |  | 2027-07-27 |  |  | PO MR-ME-022
ALP-M22-00000-GE-MOS-0005 | Painting and Insulation - Subcontractor Method Statements, Part 5 of 6 | subcontract | M22 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-022 |  | 1 | 2027-06-29 | 2027-07-13 |  | 2027-07-27 |  |  | PO MR-ME-022
ALP-M22-00000-GE-MOS-0006 | Painting and Insulation - Subcontractor Method Statements, Part 6 of 6 | subcontract | M22 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-022 |  | 1 | 2027-06-29 | 2027-07-13 |  | 2027-07-27 |  |  | PO MR-ME-022
ALP-M23-00000-GE-ITP-0001 | Mechanical and Piping Erection - Subcontractor Inspection and Test Plans | subcontract | M23 | 00000 | plant general | general | ITP | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-023 |  | 1 | 2027-09-15 | 2027-09-29 |  | 2027-10-13 |  |  | PO MR-ME-023
ALP-M23-00000-GE-MOS-0001 | Mechanical and Piping Erection - Subcontractor Method Statements, Part 1 of 6 | subcontract | M23 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-023 |  | 1 | 2027-09-15 | 2027-09-29 |  | 2027-10-13 |  |  | PO MR-ME-023
ALP-M23-00000-GE-MOS-0002 | Mechanical and Piping Erection - Subcontractor Method Statements, Part 2 of 6 | subcontract | M23 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-023 |  | 1 | 2027-09-15 | 2027-09-29 |  | 2027-10-13 |  |  | PO MR-ME-023
ALP-M23-00000-GE-MOS-0003 | Mechanical and Piping Erection - Subcontractor Method Statements, Part 3 of 6 | subcontract | M23 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-023 |  | 1 | 2027-09-15 | 2027-09-29 |  | 2027-10-13 |  |  | PO MR-ME-023
ALP-M23-00000-GE-MOS-0004 | Mechanical and Piping Erection - Subcontractor Method Statements, Part 4 of 6 | subcontract | M23 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-023 |  | 1 | 2027-09-15 | 2027-09-29 |  | 2027-10-13 |  |  | PO MR-ME-023
ALP-M23-00000-GE-MOS-0005 | Mechanical and Piping Erection - Subcontractor Method Statements, Part 5 of 6 | subcontract | M23 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-023 |  | 1 | 2027-09-15 | 2027-09-29 |  | 2027-10-13 |  |  | PO MR-ME-023
ALP-M23-00000-GE-MOS-0006 | Mechanical and Piping Erection - Subcontractor Method Statements, Part 6 of 6 | subcontract | M23 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-023 |  | 1 | 2027-09-15 | 2027-09-29 |  | 2027-10-13 |  |  | PO MR-ME-023
ALP-M24-00UZF-GE-ITP-0001 | Heavy Transport, Barge Landing and Marine Logistics - Subcontractor Inspection and Test Plans | subcontract | M24 | 00UZF | Temporary barge landing | general | ITP | Q | approval |  |  | 1 | 8 |  |  |  | MR-ME-024 |  | 1 | 2027-09-17 | 2027-10-01 |  | 2027-10-15 |  |  | PO MR-ME-024
ALP-M24-00UZF-GE-MOS-0001 | Heavy Transport, Barge Landing and Marine Logistics - Subcontractor Method Statements, Part 1 of 6 | subcontract | M24 | 00UZF | Temporary barge landing | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-024 |  | 1 | 2027-09-17 | 2027-10-01 |  | 2027-10-15 |  |  | PO MR-ME-024
ALP-M24-00UZF-GE-MOS-0002 | Heavy Transport, Barge Landing and Marine Logistics - Subcontractor Method Statements, Part 2 of 6 | subcontract | M24 | 00UZF | Temporary barge landing | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-024 |  | 1 | 2027-09-17 | 2027-10-01 |  | 2027-10-15 |  |  | PO MR-ME-024
ALP-M24-00UZF-GE-MOS-0003 | Heavy Transport, Barge Landing and Marine Logistics - Subcontractor Method Statements, Part 3 of 6 | subcontract | M24 | 00UZF | Temporary barge landing | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-024 |  | 1 | 2027-09-17 | 2027-10-01 |  | 2027-10-15 |  |  | PO MR-ME-024
ALP-M24-00UZF-GE-MOS-0004 | Heavy Transport, Barge Landing and Marine Logistics - Subcontractor Method Statements, Part 4 of 6 | subcontract | M24 | 00UZF | Temporary barge landing | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-024 |  | 1 | 2027-09-17 | 2027-10-01 |  | 2027-10-15 |  |  | PO MR-ME-024
ALP-M24-00UZF-GE-MOS-0005 | Heavy Transport, Barge Landing and Marine Logistics - Subcontractor Method Statements, Part 5 of 6 | subcontract | M24 | 00UZF | Temporary barge landing | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-024 |  | 1 | 2027-09-17 | 2027-10-01 |  | 2027-10-15 |  |  | PO MR-ME-024
ALP-M24-00UZF-GE-MOS-0006 | Heavy Transport, Barge Landing and Marine Logistics - Subcontractor Method Statements, Part 6 of 6 | subcontract | M24 | 00UZF | Temporary barge landing | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-ME-024 |  | 1 | 2027-09-17 | 2027-10-01 |  | 2027-10-15 |  |  | PO MR-ME-024
ALP-P01-00000-ME-DSH-0001 | Piping Bulk Materials - Supplier Catalogues and Material Datasheets | carbon steel, stainless | P01 | 00000 | plant general | mechanical | DSH | E | review |  |  | 1 | 6 |  |  |  | MR-PI-001 |  | 1 | 2027-01-28 | 2027-02-11 |  | 2027-02-25 |  |  | PO MR-PI-001
ALP-P01-00000-ME-ITP-0001 | Piping Bulk Materials - Supplier Inspection and Test Plan | carbon steel, stainless | P01 | 00000 | plant general | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-PI-001 |  | 1 | 2027-01-28 | 2027-02-11 |  | 2027-02-25 |  |  | PO MR-PI-001
ALP-P01-00000-ME-MDB-0001 | Piping Bulk Materials - Manufacturing Record Book and Conformity Certificates | carbon steel, stainless | P01 | 00000 | plant general | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-PI-001 |  | 1 | 2027-05-20 | 2027-06-03 |  | 2027-07-29 |  |  | PO MR-PI-001
ALP-P02-10LBA-ME-DSH-0001 | Alloy Piping P91 / P22 - Supplier Catalogues and Material Datasheets | main steam, reheat | P02 | 10LBA | Main steam piping | mechanical | DSH | E | review |  |  | 1 | 6 |  |  |  | MR-PI-002 |  | 1 | 2027-04-08 | 2027-04-22 |  | 2027-05-20 |  |  | PO MR-PI-002
ALP-P02-10LBA-ME-ITP-0001 | Alloy Piping P91 / P22 - Supplier Inspection and Test Plan | main steam, reheat | P02 | 10LBA | Main steam piping | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-PI-002 |  | 1 | 2027-04-08 | 2027-04-22 |  | 2027-05-20 |  |  | PO MR-PI-002
ALP-P02-10LBA-ME-MDB-0001 | Alloy Piping P91 / P22 - Manufacturing Record Book and Conformity Certificates | main steam, reheat | P02 | 10LBA | Main steam piping | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-PI-002 |  | 1 | 2027-12-02 | 2027-12-16 |  | 2028-02-10 |  |  | PO MR-PI-002
ALP-P03-00000-ME-DSH-0001 | Valves - Supplier Catalogues and Material Datasheets | manual and check | P03 | 00000 | plant general | mechanical | DSH | E | review |  |  | 1 | 6 |  |  |  | MR-PI-003 |  | 1 | 2027-03-11 | 2027-03-25 |  | 2027-04-13 |  |  | PO MR-PI-003
ALP-P03-00000-ME-ITP-0001 | Valves - Supplier Inspection and Test Plan | manual and check | P03 | 00000 | plant general | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-PI-003 |  | 1 | 2027-03-11 | 2027-03-25 |  | 2027-04-13 |  |  | PO MR-PI-003
ALP-P03-00000-ME-MDB-0001 | Valves - Manufacturing Record Book and Conformity Certificates | manual and check | P03 | 00000 | plant general | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-PI-003 |  | 1 | 2027-08-09 | 2027-08-23 |  | 2027-10-18 |  |  | PO MR-PI-003
ALP-P04-00PAB-ME-DSH-0001 | GRP CW Pipes and Fittings - Supplier Catalogues and Material Datasheets |  | P04 | 00PAB | CW piping | mechanical | DSH | E | review |  |  | 1 | 6 |  |  |  | MR-PI-004 | 00PAB10AA001 00PAB10AA002 | 1 | 2027-01-20 | 2027-02-03 |  | 2027-02-24 |  |  | PO MR-PI-004
ALP-P04-00PAB-ME-ITP-0001 | GRP CW Pipes and Fittings - Supplier Inspection and Test Plan |  | P04 | 00PAB | CW piping | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-PI-004 |  | 1 | 2027-01-20 | 2027-02-03 |  | 2027-02-24 |  |  | PO MR-PI-004
ALP-P04-00PAB-ME-MDB-0001 | GRP CW Pipes and Fittings - Manufacturing Record Book and Conformity Certificates |  | P04 | 00PAB | CW piping | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-PI-004 |  | 1 | 2027-07-14 | 2027-07-28 |  | 2027-09-22 |  |  | PO MR-PI-004
ALP-P05-00000-ME-DSH-0001 | Pipe Supports, Spring Hangers and Snubbers - Supplier Catalogues and Material Datasheets |  | P05 | 00000 | plant general | mechanical | DSH | E | review |  |  | 1 | 6 |  |  |  | MR-PI-005 |  | 1 | 2027-05-25 | 2027-06-08 |  | 2027-06-22 |  |  | PO MR-PI-005
ALP-P05-00000-ME-ITP-0001 | Pipe Supports, Spring Hangers and Snubbers - Supplier Inspection and Test Plan |  | P05 | 00000 | plant general | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-PI-005 |  | 1 | 2027-05-25 | 2027-06-08 |  | 2027-06-22 |  |  | PO MR-PI-005
ALP-P05-00000-ME-MDB-0001 | Pipe Supports, Spring Hangers and Snubbers - Manufacturing Record Book and Conformity Certificates |  | P05 | 00000 | plant general | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-PI-005 |  | 1 | 2027-08-17 | 2027-08-31 |  | 2027-10-26 |  |  | PO MR-PI-005
ALP-P06-00000-ME-DSH-0001 | Piping Specialty Items - Supplier Catalogues and Material Datasheets | strainers, steam traps, expansion joints, sight glasses | P06 | 00000 | plant general | mechanical | DSH | E | review |  |  | 1 | 6 |  |  |  | MR-PI-006 |  | 1 | 2027-04-05 | 2027-04-19 |  | 2027-05-03 |  |  | PO MR-PI-006
ALP-P06-00000-ME-ITP-0001 | Piping Specialty Items - Supplier Inspection and Test Plan | strainers, steam traps, expansion joints, sight glasses | P06 | 00000 | plant general | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-PI-006 |  | 1 | 2027-04-05 | 2027-04-19 |  | 2027-05-03 |  |  | PO MR-PI-006
ALP-P06-00000-ME-MDB-0001 | Piping Specialty Items - Manufacturing Record Book and Conformity Certificates | strainers, steam traps, expansion joints, sight glasses | P06 | 00000 | plant general | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-PI-006 |  | 1 | 2027-06-28 | 2027-07-12 |  | 2027-09-06 |  |  | PO MR-PI-006
ALP-P07-00000-ME-DSH-0001 | Safety and Relief Valves - Supplier Catalogues and Material Datasheets |  | P07 | 00000 | plant general | mechanical | DSH | E | review |  |  | 1 | 6 |  |  |  | MR-PI-007 |  | 1 | 2027-04-01 | 2027-04-15 |  | 2027-04-29 |  |  | PO MR-PI-007
ALP-P07-00000-ME-ITP-0001 | Safety and Relief Valves - Supplier Inspection and Test Plan |  | P07 | 00000 | plant general | mechanical | ITP | Q | approval |  |  | 1 | 6 |  |  |  | MR-PI-007 |  | 1 | 2027-04-01 | 2027-04-15 |  | 2027-04-29 |  |  | PO MR-PI-007
ALP-P07-00000-ME-MDB-0001 | Safety and Relief Valves - Manufacturing Record Book and Conformity Certificates |  | P07 | 00000 | plant general | mechanical | MDB | Q | information |  |  | 1 | 6 |  |  |  | MR-PI-007 |  | 1 | 2027-07-22 | 2027-08-05 |  | 2027-09-30 |  |  | PO MR-PI-007
ALP-S01-00000-GE-ITP-0001 | Structural Steel Supply and Fabrication - Subcontractor Inspection and Test Plans |  | S01 | 00000 | plant general | general | ITP | Q | approval |  |  | 1 | 8 |  |  |  | MR-SS-001 |  | 1 | 2027-01-28 | 2027-02-11 |  | 2027-02-25 |  |  | PO MR-SS-001
ALP-S01-00000-GE-MOS-0001 | Structural Steel Supply and Fabrication - Subcontractor Method Statements, Part 1 of 6 |  | S01 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-SS-001 |  | 1 | 2027-01-28 | 2027-02-11 |  | 2027-02-25 |  |  | PO MR-SS-001
ALP-S01-00000-GE-MOS-0002 | Structural Steel Supply and Fabrication - Subcontractor Method Statements, Part 2 of 6 |  | S01 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-SS-001 |  | 1 | 2027-01-28 | 2027-02-11 |  | 2027-02-25 |  |  | PO MR-SS-001
ALP-S01-00000-GE-MOS-0003 | Structural Steel Supply and Fabrication - Subcontractor Method Statements, Part 3 of 6 |  | S01 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-SS-001 |  | 1 | 2027-01-28 | 2027-02-11 |  | 2027-02-25 |  |  | PO MR-SS-001
ALP-S01-00000-GE-MOS-0004 | Structural Steel Supply and Fabrication - Subcontractor Method Statements, Part 4 of 6 |  | S01 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-SS-001 |  | 1 | 2027-01-28 | 2027-02-11 |  | 2027-02-25 |  |  | PO MR-SS-001
ALP-S01-00000-GE-MOS-0005 | Structural Steel Supply and Fabrication - Subcontractor Method Statements, Part 5 of 6 |  | S01 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-SS-001 |  | 1 | 2027-01-28 | 2027-02-11 |  | 2027-02-25 |  |  | PO MR-SS-001
ALP-S01-00000-GE-MOS-0006 | Structural Steel Supply and Fabrication - Subcontractor Method Statements, Part 6 of 6 |  | S01 | 00000 | plant general | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-SS-001 |  | 1 | 2027-01-28 | 2027-02-11 |  | 2027-02-25 |  |  | PO MR-SS-001
ALP-S01-00UAC-SS-STL-0001 | GIS Building - Steel Fabrication and Erection Drawings |  | S01 | 00UAC | GIS building | structural | STL | L | information |  |  | 40 | 20 | EWP-04-SS-01 | CWP-04-SS-01 | CWA-04 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-05-31 | 47 | PO MR-SS-001
ALP-S01-00UBA-SS-STL-0001 | Electrical Building - Steel Fabrication and Erection Drawings |  | S01 | 00UBA | Electrical building | structural | STL | L | information |  |  | 32 | 16 | EWP-03-SS-01 | CWP-03-SS-01 | CWA-03 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-05-24 | 42 | PO MR-SS-001
ALP-S01-00UBF-SS-STL-0001 | Transformer Bays - Steel Fabrication and Erection Drawings |  | S01 | 00UBF | Transformer bays | structural | STL | L | information |  |  | 8 | 4 | EWP-01-SS-01 | CWP-01-SS-01 | CWA-01 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-07-12 | 77 | PO MR-SS-001
ALP-S01-00UCA-SS-STL-0001 | Control Building - Steel Fabrication and Erection Drawings |  | S01 | 00UCA | Control building | structural | STL | L | information |  |  | 32 | 16 | EWP-11-SS-01 | CWP-11-SS-01 | CWA-11 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-05-24 | 42 | PO MR-SS-001
ALP-S01-00UEG-SS-STL-0001 | LDO Tank Farm Structures - Steel Fabrication and Erection Drawings |  | S01 | 00UEG | LDO tank farm structures | structural | STL | L | information |  |  | 16 | 8 | EWP-10-CV-01 | CWP-10-CV-01 | CWA-10 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-06-03 | 50 | PO MR-SS-001
ALP-S01-00UEK-SS-STL-0001 | Gas Station Structures - Steel Fabrication and Erection Drawings |  | S01 | 00UEK | Gas station structures | structural | STL | L | information |  |  | 16 | 8 | EWP-09-CV-01 | CWP-09-CV-01 | CWA-09 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-08-04 | 94 | PO MR-SS-001
ALP-S01-00UGA-SS-STL-0001 | Water Treatment Building and Basins - Steel Fabrication and Erection Drawings |  | S01 | 00UGA | Water treatment building and basins | structural | STL | L | information |  |  | 32 | 16 | EWP-07-SS-01 | CWP-07-SS-01 | CWA-07 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-06-14 | 57 | PO MR-SS-001
ALP-S01-00UPC-SS-STL-0001 | CW Pump House - Steel Fabrication and Erection Drawings |  | S01 | 00UPC | CW pump house | structural | STL | L | information |  |  | 24 | 12 | EWP-05-CV-01 | CWP-05-CV-01 | CWA-05 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-03-25 | 0 | PO MR-SS-001
ALP-S01-00UQA-SS-STL-0001 | Utility Building - Steel Fabrication and Erection Drawings |  | S01 | 00UQA | Utility building | structural | STL | L | information |  |  | 48 | 24 | EWP-08-SS-01 | CWP-08-SS-01 | CWA-08 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-06-29 | 68 | PO MR-SS-001
ALP-S01-00USA-SS-STL-0001 | Workshop and Warehouse - Steel Fabrication and Erection Drawings |  | S01 | 00USA | Workshop and warehouse | structural | STL | L | information |  |  | 40 | 20 | EWP-11-SS-01 | CWP-11-SS-01 | CWA-11 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-05-24 | 42 | PO MR-SS-001
ALP-S01-00UYA-SS-STL-0001 | Administration Building - Steel Fabrication and Erection Drawings |  | S01 | 00UYA | Administration building | structural | STL | L | information |  |  | 24 | 12 | EWP-11-SS-01 | CWP-11-SS-01 | CWA-11 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-05-24 | 42 | PO MR-SS-001
ALP-S01-00UZD-SS-STL-0001 | Pipe Racks and Pipe Sleepers - Steel Fabrication and Erection Drawings, Part 1 of 2 |  | S01 | 00UZD | Pipe racks and pipe sleepers | structural | STL | L | information |  |  | 80 | 40 | EWP-12-CV-02 | CWP-12-CV-02 | CWA-12 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-03-22 | -3 | PO MR-SS-001
ALP-S01-00UZD-SS-STL-0002 | Pipe Racks and Pipe Sleepers - Steel Fabrication and Erection Drawings, Part 2 of 2 |  | S01 | 00UZD | Pipe racks and pipe sleepers | structural | STL | L | information |  |  | 80 | 40 | EWP-12-CV-02 | CWP-12-CV-02 | CWA-12 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-03-22 | -3 | PO MR-SS-001
ALP-S01-00UZF-SS-STL-0001 | Temporary Barge Landing - Steel Fabrication and Erection Drawings |  | S01 | 00UZF | Temporary barge landing | structural | STL | L | information |  |  | 16 | 8 | EWP-06-CV-01 | CWP-06-CV-01 | CWA-06 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-09-03 | 116 | PO MR-SS-001
ALP-S01-10UMA-SS-STL-0001 | Gas Turbine Hall - Steel Fabrication and Erection Drawings |  | S01 | 10UMA | Gas turbine hall | structural | STL | L | information |  |  | 120 | 60 | EWP-01-SS-01 | CWP-01-SS-01 | CWA-01 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-07-12 | 77 | PO MR-SS-001
ALP-S01-20UMB-SS-STL-0001 | Steam Turbine Hall - Steel Fabrication and Erection Drawings |  | S01 | 20UMB | Steam turbine hall | structural | STL | L | information |  |  | 120 | 60 | EWP-02-SS-01 | CWP-02-SS-01 | CWA-02 | MR-SS-001 |  | 1 | 2027-02-04 | 2027-03-04 |  | 2027-03-25 | 2027-07-12 | 77 | PO MR-SS-001
ALP-S02-10HNE-CV-CAL-0001 | Stack 65 m with Silencer - Supplier Foundation Loads and Anchor Bolt Drawings |  | S02 | 10HNE | Stack 65 m with CEMS platform and silencer | civil | CAL | E | review |  |  | 1 | 5 |  |  |  | MR-SS-002 |  | 1 | 2027-02-08 | 2027-03-01 |  | 2027-03-23 |  |  | PO MR-SS-002
ALP-S02-10HNE-GE-ITP-0001 | Stack 65 m with Silencer - Subcontractor Inspection and Test Plans |  | S02 | 10HNE | Stack 65 m with CEMS platform and silencer | general | ITP | Q | approval |  |  | 1 | 8 |  |  |  | MR-SS-002 |  | 1 | 2027-02-04 | 2027-02-18 |  | 2027-03-11 |  |  | PO MR-SS-002
ALP-S02-10HNE-GE-MOS-0001 | Stack 65 m with Silencer - Subcontractor Method Statements, Part 1 of 6 |  | S02 | 10HNE | Stack 65 m with CEMS platform and silencer | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-SS-002 |  | 1 | 2027-02-04 | 2027-02-18 |  | 2027-03-11 |  |  | PO MR-SS-002
ALP-S02-10HNE-GE-MOS-0002 | Stack 65 m with Silencer - Subcontractor Method Statements, Part 2 of 6 |  | S02 | 10HNE | Stack 65 m with CEMS platform and silencer | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-SS-002 |  | 1 | 2027-02-04 | 2027-02-18 |  | 2027-03-11 |  |  | PO MR-SS-002
ALP-S02-10HNE-GE-MOS-0003 | Stack 65 m with Silencer - Subcontractor Method Statements, Part 3 of 6 |  | S02 | 10HNE | Stack 65 m with CEMS platform and silencer | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-SS-002 |  | 1 | 2027-02-04 | 2027-02-18 |  | 2027-03-11 |  |  | PO MR-SS-002
ALP-S02-10HNE-GE-MOS-0004 | Stack 65 m with Silencer - Subcontractor Method Statements, Part 4 of 6 |  | S02 | 10HNE | Stack 65 m with CEMS platform and silencer | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-SS-002 |  | 1 | 2027-02-04 | 2027-02-18 |  | 2027-03-11 |  |  | PO MR-SS-002
ALP-S02-10HNE-GE-MOS-0005 | Stack 65 m with Silencer - Subcontractor Method Statements, Part 5 of 6 |  | S02 | 10HNE | Stack 65 m with CEMS platform and silencer | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-SS-002 |  | 1 | 2027-02-04 | 2027-02-18 |  | 2027-03-11 |  |  | PO MR-SS-002
ALP-S02-10HNE-GE-MOS-0006 | Stack 65 m with Silencer - Subcontractor Method Statements, Part 6 of 6 |  | S02 | 10HNE | Stack 65 m with CEMS platform and silencer | general | MOS | B | review |  |  | 1 | 8 |  |  |  | MR-SS-002 |  | 1 | 2027-02-04 | 2027-02-18 |  | 2027-03-11 |  |  | PO MR-SS-002

## Workflow
Alpilla 600 MW Combined Cycle Power Plant - Workflow network (document <- input)
engine engineering_plan v1.6.0 ¦ generated 2026-09-29T03:49:44Z by EPCE ¦ data 73eaa92ce7c1ff26 ¦ dates computed from the workflow network and the CPM (working days)
Document | Type | Input | Input type | Needs input at | Input ready | Driving
ALP-C01-00000-GE-ITP-0001 | ITP | ALP-EPC-00000-CV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-C01-00000-GE-MOS-0001 | MOS | ALP-EPC-00000-CV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-C01-00000-GE-MOS-0002 | MOS | ALP-EPC-00000-CV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-C01-00000-GE-MOS-0003 | MOS | ALP-EPC-00000-CV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-C01-00000-GE-MOS-0004 | MOS | ALP-EPC-00000-CV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-C01-00000-GE-MOS-0005 | MOS | ALP-EPC-00000-CV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-C01-00000-GE-MOS-0006 | MOS | ALP-EPC-00000-CV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-C02-00000-GE-ITP-0001 | ITP | ALP-EPC-00000-CV-MRQ-0002 | MRQ | IFR | 2026-11-02
ALP-C02-00000-GE-MOS-0001 | MOS | ALP-EPC-00000-CV-MRQ-0002 | MRQ | IFR | 2026-11-02
ALP-C02-00000-GE-MOS-0002 | MOS | ALP-EPC-00000-CV-MRQ-0002 | MRQ | IFR | 2026-11-02
ALP-C02-00000-GE-MOS-0003 | MOS | ALP-EPC-00000-CV-MRQ-0002 | MRQ | IFR | 2026-11-02
ALP-C02-00000-GE-MOS-0004 | MOS | ALP-EPC-00000-CV-MRQ-0002 | MRQ | IFR | 2026-11-02
ALP-C02-00000-GE-MOS-0005 | MOS | ALP-EPC-00000-CV-MRQ-0002 | MRQ | IFR | 2026-11-02
ALP-C02-00000-GE-MOS-0006 | MOS | ALP-EPC-00000-CV-MRQ-0002 | MRQ | IFR | 2026-11-02
ALP-C03-00UPA-GE-ITP-0001 | ITP | ALP-EPC-00000-CV-MRQ-0003 | MRQ | IFR | 2026-11-02
ALP-C03-00UPA-GE-MOS-0001 | MOS | ALP-EPC-00000-CV-MRQ-0003 | MRQ | IFR | 2026-11-02
ALP-C03-00UPA-GE-MOS-0002 | MOS | ALP-EPC-00000-CV-MRQ-0003 | MRQ | IFR | 2026-11-02
ALP-C03-00UPA-GE-MOS-0003 | MOS | ALP-EPC-00000-CV-MRQ-0003 | MRQ | IFR | 2026-11-02
ALP-C03-00UPA-GE-MOS-0004 | MOS | ALP-EPC-00000-CV-MRQ-0003 | MRQ | IFR | 2026-11-02
ALP-C03-00UPA-GE-MOS-0005 | MOS | ALP-EPC-00000-CV-MRQ-0003 | MRQ | IFR | 2026-11-02
ALP-C03-00UPA-GE-MOS-0006 | MOS | ALP-EPC-00000-CV-MRQ-0003 | MRQ | IFR | 2026-11-02
ALP-E01-00ACA-CV-CAL-0001 | CAL | ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E01-00ACA-EL-WIR-0001 | WIR | ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-E01-00ACA-IC-DSH-0001 | DSH | ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E01-00ACA-IC-IOL-0001 | IOL | ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E01-00ACA-ME-CAL-0001 | CAL | ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E01-00ACA-ME-DSH-0001 | DSH | ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E01-00ACA-ME-GAD-0001 | GAD | ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E01-00ACA-ME-ITP-0001 | ITP | ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E01-00ACA-ME-LST-0001 | LST | ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E01-00ACA-ME-MDB-0001 | MDB | ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E01-00ACA-ME-OMM-0001 | OMM | ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E01-00ACA-ME-PRC-0001 | PRC | ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E01-00ACA-ME-TRP-0001 | TRP | ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E01-00ACA-ME-TST-0001 | TST | ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E02-10BBT-CV-CAL-0001 | CAL | ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E02-10BBT-EL-WIR-0001 | WIR | ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-E02-10BBT-IC-DSH-0001 | DSH | ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E02-10BBT-IC-IOL-0001 | IOL | ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E02-10BBT-ME-CAL-0001 | CAL | ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E02-10BBT-ME-DSH-0001 | DSH | ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E02-10BBT-ME-GAD-0001 | GAD | ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E02-10BBT-ME-ITP-0001 | ITP | ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E02-10BBT-ME-LST-0001 | LST | ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E02-10BBT-ME-MDB-0001 | MDB | ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E02-10BBT-ME-OMM-0001 | OMM | ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E02-10BBT-ME-PRC-0001 | PRC | ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E02-10BBT-ME-TRP-0001 | TRP | ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E02-10BBT-ME-TST-0001 | TST | ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E03-00BBA-IC-IOL-0001 | IOL | ALP-EPC-00BBA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E03-00BBA-ME-CAL-0001 | CAL | ALP-EPC-00BBA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E03-00BBA-ME-DSH-0001 | DSH | ALP-EPC-00BBA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E03-00BBA-ME-GAD-0001 | GAD | ALP-EPC-00BBA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E03-00BBA-ME-ITP-0001 | ITP | ALP-EPC-00BBA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E03-00BBA-ME-LST-0001 | LST | ALP-EPC-00BBA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E03-00BBA-ME-MDB-0001 | MDB | ALP-EPC-00BBA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E03-00BBA-ME-OMM-0001 | OMM | ALP-EPC-00BBA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E03-00BBA-ME-PRC-0001 | PRC | ALP-EPC-00BBA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E03-00BBA-ME-TRP-0001 | TRP | ALP-EPC-00BBA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E03-00BBA-ME-TST-0001 | TST | ALP-EPC-00BBA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E04-00BFT-IC-IOL-0001 | IOL | ALP-EPC-00BFT-EL-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-E04-00BFT-ME-CAL-0001 | CAL | ALP-EPC-00BFT-EL-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-E04-00BFT-ME-DSH-0001 | DSH | ALP-EPC-00BFT-EL-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-E04-00BFT-ME-GAD-0001 | GAD | ALP-EPC-00BFT-EL-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-E04-00BFT-ME-ITP-0001 | ITP | ALP-EPC-00BFT-EL-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-E04-00BFT-ME-LST-0001 | LST | ALP-EPC-00BFT-EL-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-E04-00BFT-ME-MDB-0001 | MDB | ALP-EPC-00BFT-EL-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-E04-00BFT-ME-OMM-0001 | OMM | ALP-EPC-00BFT-EL-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-E04-00BFT-ME-PRC-0001 | PRC | ALP-EPC-00BFT-EL-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-E04-00BFT-ME-TRP-0001 | TRP | ALP-EPC-00BFT-EL-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-E04-00BFT-ME-TST-0001 | TST | ALP-EPC-00BFT-EL-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-E05-00BFA-EL-WIR-0001 | WIR | ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-E05-00BFA-IC-IOL-0001 | IOL | ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E05-00BFA-ME-CAL-0001 | CAL | ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E05-00BFA-ME-DSH-0001 | DSH | ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E05-00BFA-ME-GAD-0001 | GAD | ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E05-00BFA-ME-ITP-0001 | ITP | ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E05-00BFA-ME-LST-0001 | LST | ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E05-00BFA-ME-MDB-0001 | MDB | ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E05-00BFA-ME-OMM-0001 | OMM | ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E05-00BFA-ME-PRC-0001 | PRC | ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E05-00BFA-ME-TRP-0001 | TRP | ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E05-00BFA-ME-TST-0001 | TST | ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E06-00XJA-CV-CAL-0001 | CAL | ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E06-00XJA-EL-WIR-0001 | WIR | ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-E06-00XJA-IC-DSH-0001 | DSH | ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E06-00XJA-IC-IOL-0001 | IOL | ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E06-00XJA-ME-CAL-0001 | CAL | ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E06-00XJA-ME-DSH-0001 | DSH | ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E06-00XJA-ME-GAD-0001 | GAD | ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E06-00XJA-ME-ITP-0001 | ITP | ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E06-00XJA-ME-LST-0001 | LST | ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E06-00XJA-ME-MDB-0001 | MDB | ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E06-00XJA-ME-OMM-0001 | OMM | ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E06-00XJA-ME-PRC-0001 | PRC | ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E06-00XJA-ME-TRP-0001 | TRP | ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E06-00XJA-ME-TST-0001 | TST | ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E07-00BRA-EL-WIR-0001 | WIR | ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | IFC | 2026-11-26
ALP-E07-00BRA-IC-IOL-0001 | IOL | ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-E07-00BRA-ME-CAL-0001 | CAL | ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-E07-00BRA-ME-DSH-0001 | DSH | ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-E07-00BRA-ME-GAD-0001 | GAD | ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-E07-00BRA-ME-ITP-0001 | ITP | ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-E07-00BRA-ME-LST-0001 | LST | ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-E07-00BRA-ME-MDB-0001 | MDB | ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-E07-00BRA-ME-OMM-0001 | OMM | ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-E07-00BRA-ME-PRC-0001 | PRC | ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-E07-00BRA-ME-TRP-0001 | TRP | ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-E07-00BRA-ME-TST-0001 | TST | ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-E08-00000-ME-DSH-0001 | DSH | ALP-EPC-00000-EL-MRQ-0001 | MRQ | IFR | 2027-02-15
ALP-E08-00000-ME-ITP-0001 | ITP | ALP-EPC-00000-EL-MRQ-0001 | MRQ | IFR | 2027-02-15
ALP-E08-00000-ME-MDB-0001 | MDB | ALP-EPC-00000-EL-MRQ-0001 | MRQ | IFR | 2027-02-15
ALP-E09-00BLA-ME-DSH-0001 | DSH | ALP-EPC-00000-EL-MRQ-0002 | MRQ | IFR | 2027-01-18
ALP-E09-00BLA-ME-ITP-0001 | ITP | ALP-EPC-00000-EL-MRQ-0002 | MRQ | IFR | 2027-01-18
ALP-E09-00BLA-ME-MDB-0001 | MDB | ALP-EPC-00000-EL-MRQ-0002 | MRQ | IFR | 2027-01-18
ALP-E10-00BXA-IC-IOL-0001 | IOL | ALP-EPC-00BXA-GE-MRQ-0001 | MRQ | IFR | 2027-02-18
ALP-E10-00BXA-ME-ITP-0001 | ITP | ALP-EPC-00BXA-GE-MRQ-0001 | MRQ | IFR | 2027-02-18
ALP-E10-00BXA-ME-LST-0001 | LST | ALP-EPC-00BXA-GE-MRQ-0001 | MRQ | IFR | 2027-02-18
ALP-E10-00BXA-ME-MDB-0001 | MDB | ALP-EPC-00BXA-GE-MRQ-0001 | MRQ | IFR | 2027-02-18
ALP-E10-00BXA-ME-OMM-0001 | OMM | ALP-EPC-00BXA-GE-MRQ-0001 | MRQ | IFR | 2027-02-18
ALP-E10-00BXA-ME-PRC-0001 | PRC | ALP-EPC-00BXA-GE-MRQ-0001 | MRQ | IFR | 2027-02-18
ALP-E10-00BXA-ME-TRP-0001 | TRP | ALP-EPC-00BXA-GE-MRQ-0001 | MRQ | IFR | 2027-02-18
ALP-E10-00BXA-ME-TST-0001 | TST | ALP-EPC-00BXA-GE-MRQ-0001 | MRQ | IFR | 2027-02-18
ALP-E11-00000-IC-IOL-0001 | IOL | ALP-EPC-00000-GE-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E11-00000-ME-ITP-0001 | ITP | ALP-EPC-00000-GE-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E11-00000-ME-LST-0001 | LST | ALP-EPC-00000-GE-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E11-00000-ME-MDB-0001 | MDB | ALP-EPC-00000-GE-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E11-00000-ME-OMM-0001 | OMM | ALP-EPC-00000-GE-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E11-00000-ME-PRC-0001 | PRC | ALP-EPC-00000-GE-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E11-00000-ME-TRP-0001 | TRP | ALP-EPC-00000-GE-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E11-00000-ME-TST-0001 | TST | ALP-EPC-00000-GE-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-E12-00000-GE-ITP-0001 | ITP | ALP-EPC-00000-GE-MRQ-0002 | MRQ | IFR | 2027-04-14
ALP-E12-00000-GE-MOS-0001 | MOS | ALP-EPC-00000-GE-MRQ-0002 | MRQ | IFR | 2027-04-14
ALP-E12-00000-GE-MOS-0002 | MOS | ALP-EPC-00000-GE-MRQ-0002 | MRQ | IFR | 2027-04-14
ALP-E12-00000-GE-MOS-0003 | MOS | ALP-EPC-00000-GE-MRQ-0002 | MRQ | IFR | 2027-04-14
ALP-E12-00000-GE-MOS-0004 | MOS | ALP-EPC-00000-GE-MRQ-0002 | MRQ | IFR | 2027-04-14
ALP-E12-00000-GE-MOS-0005 | MOS | ALP-EPC-00000-GE-MRQ-0002 | MRQ | IFR | 2027-04-14
ALP-E12-00000-GE-MOS-0006 | MOS | ALP-EPC-00000-GE-MRQ-0002 | MRQ | IFR | 2027-04-14
ALP-EPC-00000-CM-CMP-0001 | CMP | ALP-EPC-00LBG-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-CM-CMP-0001 | CMP | ALP-EPC-00LDA-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-CM-CMP-0001 | CMP | ALP-EPC-10HAN-PR-PID-0001 | PID | IFR | 2027-05-27
ALP-EPC-00000-CM-CMP-0001 | CMP | ALP-EPC-10LAB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-CM-CMP-0001 | CMP | ALP-EPC-10LAC-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-CM-CMP-0001 | CMP | ALP-EPC-10LAE-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-CMP-0001 | CMP | ALP-EPC-10LAF-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-CMP-0001 | CMP | ALP-EPC-10LBA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-CMP-0001 | CMP | ALP-EPC-10LBB-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-CMP-0001 | CMP | ALP-EPC-10LBC-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-CMP-0001 | CMP | ALP-EPC-10LBD-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-CMP-0001 | CMP | ALP-EPC-20LCA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-CMP-0001 | CMP | ALP-EPC-20LCB-PR-PID-0001 | PID | IFR | 2027-06-15
ALP-EPC-00000-CM-CMP-0001 | CMP | ALP-EPC-20MAN-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-CMP-0001 | CMP | ALP-IEC-10HAA-PR-PID-0001 | PID | IFR | 2027-01-11
ALP-EPC-00000-CM-CMP-0002 | CMP | ALP-EPC-00000-PR-CAL-0001 | CAL | IFR | 2027-01-04
ALP-EPC-00000-CM-CMP-0002 | CMP | ALP-IEC-10MBA-PR-HMB-0001 | HMB | IFR | 2026-09-28
ALP-EPC-00000-CM-CMP-0003 | CMP | ALP-EPC-00000-EL-STU-0006 | STU | IFR | 2027-01-06
ALP-EPC-00000-CM-CMP-0003 | CMP | ALP-IEC-10MKA-EL-RPT-0001 | RPT | IFR | 2027-01-25
ALP-EPC-00000-CM-CMP-0004 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00000-CM-CMP-0004 | CMP | ALP-EPC-00000-IC-CNR-0001 | CNR | IFR | 2027-03-01
ALP-EPC-00000-CM-CMP-0005 | CMP | ALP-EPC-00EGC-PR-PID-0001 | PID | IFR | 2027-02-19
ALP-EPC-00000-CM-CMP-0005 | CMP | ALP-IEC-10MBA-PR-PID-0001 | PID | IFR | 2027-01-11
ALP-EPC-00000-CM-CMP-0005 | CMP | ALP-IEC-10MBY-IC-CNR-0001 | CNR | IFR | 2027-02-08
ALP-EPC-00000-CM-CMP-0006 | CMP | ALP-EPC-00000-HS-STU-0001 | STU | IFR | 2027-02-15
ALP-EPC-00000-CM-CMP-0006 | CMP | ALP-EPC-00CQA-IC-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00EGA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00EGB-PR-PID-0001 | PID | IFR | 2027-04-06
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00EGC-PR-PID-0001 | PID | IFR | 2027-02-19
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00EKA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00EKC-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00GBA-PR-PID-0001 | PID | IFR | 2027-03-01
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00GCA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00GHA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00GKA-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00GMA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00GNA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00GUA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00LBG-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00LDA-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00PAA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00PAB-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00PAC-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00PAH-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00PBA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00PGA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00QCA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00QEA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00QHA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00QJA-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00QJB-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00QUA-PR-PID-0001 | PID | IFR | 2027-05-11
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00SAA-HV-PID-0001 | PID | IFR | 2027-03-02
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00SGA-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-00SGC-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-10HAN-PR-PID-0001 | PID | IFR | 2027-05-27
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-10HSB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-10LAB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-10LAC-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-10LAE-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-10LAF-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-10LBA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-10LBB-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-10LBC-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-10LBD-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-20LCA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-20LCB-PR-PID-0001 | PID | IFR | 2027-06-15
ALP-EPC-00000-CM-LST-0001 | LST | ALP-EPC-20MAN-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00000-PR-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00ACA-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00BBA-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00BFA-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00BFT-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00BMA-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00BRA-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00BTA-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00CJA-IC-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00CQA-IC-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00EGA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00EGB-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00EGC-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00EKA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00GBA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00GCA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00GHA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00GHA-ME-DSH-0002 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00GKA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00GNA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00GUA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00LDA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00PAA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00PAC-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00PAH-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00PBA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00PGA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00PGA-ME-DSH-0002 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00PGA-ME-DSH-0003 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00QCA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00QEA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00QEA-ME-DSH-0002 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00QEA-ME-DSH-0003 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00QHA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00QJA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00QJB-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00QUA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00SAA-HV-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00SGA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00SGA-ME-DSH-0002 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00SMA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-00XJA-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-10BBT-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-10HAN-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-10HNE-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-10HSB-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-10HSB-ME-DSH-0002 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-10LAC-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-20BBT-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0002 | LST | ALP-EPC-20LCB-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00000-CM-LST-0003 | LST | ALP-EPC-00000-CM-PRC-0001 | PRC | IFR | 2027-10-20
ALP-EPC-00000-CM-LST-0004 | LST | ALP-EPC-00000-CM-LST-0002 | LST | IFR | 2027-05-26
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00EGA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00EGB-PR-PID-0001 | PID | IFR | 2027-04-06
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00EGC-PR-PID-0001 | PID | IFR | 2027-02-19
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00EKA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00EKC-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00GBA-PR-PID-0001 | PID | IFR | 2027-03-01
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00GCA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00GHA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00GKA-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00GMA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00GNA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00GUA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00LBG-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00LDA-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00PAA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00PAB-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00PAC-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00PAH-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00PBA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00PGA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00QCA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00QEA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00QHA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00QJA-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00QJB-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00QUA-PR-PID-0001 | PID | IFR | 2027-05-11
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00SAA-HV-PID-0001 | PID | IFR | 2027-03-02
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00SGA-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-00SGC-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-10HAN-PR-PID-0001 | PID | IFR | 2027-05-27
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-10HSB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-10LAB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-10LAC-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-10LAE-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-10LAF-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-10LBA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-10LBB-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-10LBC-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-10LBD-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-20LCA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-20LCB-PR-PID-0001 | PID | IFR | 2027-06-15
ALP-EPC-00000-CM-OMM-0001 | OMM | ALP-EPC-20MAN-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-CM-OMM-0002 | OMM | ALP-EPC-00000-CM-PLN-0002 | PLN | IFR | 2027-12-02
ALP-EPC-00000-CM-PLN-0001 | PLN | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00000-CM-PLN-0002 | PLN | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00000-CM-PRC-0001 | PRC | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00000-CM-PRC-0002 | PRC | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00000-CM-TRP-0001 | TRP | ALP-EPC-00000-CM-CMP-0001 | CMP | IFR | 2027-08-27
ALP-EPC-00000-CM-TRP-0002 | TRP | ALP-EPC-00000-CM-CMP-0002 | CMP | IFR | 2027-03-16
ALP-EPC-00000-CM-TRP-0003 | TRP | ALP-EPC-00000-CM-CMP-0003 | CMP | IFR | 2027-03-22
ALP-EPC-00000-CM-TRP-0004 | TRP | ALP-EPC-00000-CM-CMP-0004 | CMP | IFR | 2027-04-05
ALP-EPC-00000-CM-TRP-0005 | TRP | ALP-EPC-00000-CM-CMP-0005 | CMP | IFR | 2027-04-21
ALP-EPC-00000-CM-TRP-0006 | TRP | ALP-EPC-00000-CM-CMP-0006 | CMP | IFR | 2027-05-24
ALP-EPC-00000-CM-TRP-0007 | TRP | ALP-EPC-00SGA-CM-CMP-0001 | CMP | IFR | 2027-04-14
ALP-EPC-00000-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-CV-CAL-0001 | CAL | ALP-IEC-10HAA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-00000-CV-CAL-0001 | CAL | ALP-IEC-10MBA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-00000-CV-CAL-0001 | CAL | ALP-IEC-20MAA-CV-CAL-0001 | CAL | IFR | 2026-12-28 | driving
ALP-EPC-00000-CV-DBR-0001 | DBR | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-CV-MRQ-0001 | MRQ | ALP-EPC-00000-CV-SPC-0003 | SPC | IFR | 2026-11-02
ALP-EPC-00000-CV-MRQ-0002 | MRQ | ALP-EPC-00000-CV-SPC-0004 | SPC | IFR | 2026-11-02
ALP-EPC-00000-CV-MRQ-0003 | MRQ | ALP-EPC-00000-CV-SPC-0005 | SPC | IFR | 2026-11-02
ALP-EPC-00000-CV-RPT-0001 | RPT | ALP-EPC-00000-CV-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00000-CV-RPT-0002 | RPT | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00000-CV-SPC-0001 | SPC | ALP-EPC-00000-CV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-CV-SPC-0002 | SPC | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00000-CV-SPC-0003 | SPC | ALP-EPC-00000-CV-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00000-CV-SPC-0003 | SPC | ALP-EPC-00000-CV-SPC-0002 | SPC | IFR | 2027-02-01
ALP-EPC-00000-CV-SPC-0003 | SPC | ALP-EPC-00000-CV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-CV-SPC-0004 | SPC | ALP-EPC-00000-CV-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00000-CV-SPC-0004 | SPC | ALP-EPC-00000-CV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-CV-SPC-0005 | SPC | ALP-EPC-00000-CV-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00000-CV-SPC-0005 | SPC | ALP-EPC-00000-PR-STU-0003 | STU | IFR | 2027-06-02
ALP-EPC-00000-CV-SPC-0005 | SPC | ALP-EPC-00000-CV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-CV-STU-0001 | STU | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00000-CV-TRP-0001 | TRP | ALP-EPC-00000-CV-TST-0001 | TST | IFR | 2027-06-03 | driving
ALP-EPC-00000-CV-TST-0001 | TST | ALP-EPC-00000-CV-SPC-0002 | SPC | IFR | 2027-02-01
ALP-EPC-00000-EL-BLK-0001 | BLK | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00000-EL-BLK-0001 | BLK | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-00000-EL-BLK-0002 | BLK | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00000-EL-BLK-0002 | BLK | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-00000-EL-CAL-0001 | CAL | ALP-EPC-00000-EL-STU-0001 | STU | IFR | 2026-12-24 | driving
ALP-EPC-00000-EL-CAL-0002 | CAL | ALP-EPC-00000-EL-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00000-EL-CAL-0003 | CAL | ALP-EPC-00000-EL-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00000-EL-CAL-0004 | CAL | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-EL-CAL-0005 | CAL | ALP-EPC-00000-ME-RPT-0002 | RPT | IFR | 2026-12-14 | driving
ALP-EPC-00000-EL-DBR-0001 | DBR | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-EL-LST-0001 | LST | ALP-EPC-00000-PR-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00000-EL-LST-0001 | LST | ALP-IEC-10MBA-EL-LST-0001 | LST | IFR | 2026-12-28
ALP-EPC-00000-EL-LST-0002 | LST | ALP-EPC-00UZA-CV-CVL-0001 | CVL | IFR | 2026-12-01
ALP-EPC-00000-EL-LST-0003 | LST | ALP-EPC-00000-EL-STU-0002 | STU | IFR | 2027-01-28
ALP-EPC-00000-EL-LST-0004 | LST | ALP-EPC-00000-HS-HAZ-0008 | HAZ | IFR | 2027-08-17
ALP-EPC-00000-EL-MRQ-0001 | MRQ | ALP-EPC-00000-EL-SPC-0004 | SPC | IFR | 2027-02-08 | driving
ALP-EPC-00000-EL-MRQ-0002 | MRQ | ALP-EPC-00000-EL-SPC-0005 | SPC | IFR | 2027-01-11 | driving
ALP-EPC-00000-EL-RPT-0001 | RPT | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-EL-SLD-0001 | SLD | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-EL-SLD-0001 | SLD | ALP-EPC-00000-EL-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00000-EL-SLD-0001 | SLD | ALP-IEC-10BAA-EL-SLD-0001 | SLD | IFR | 2026-12-28
ALP-EPC-00000-EL-SLD-0002 | SLD | ALP-EPC-00000-EL-LST-0002 | LST | IFR | 2026-11-02
ALP-EPC-00000-EL-SLD-0002 | SLD | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00000-EL-SPC-0002 | SPC | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-EL-SPC-0003 | SPC | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00000-EL-SPC-0004 | SPC | ALP-EPC-00000-EL-SPC-0001 | SPC | IFR | 2027-01-11 | driving
ALP-EPC-00000-EL-SPC-0004 | SPC | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-EL-SPC-0005 | SPC | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00000-EL-STU-0001 | STU | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00000-EL-STU-0002 | STU | ALP-EPC-00000-EL-STU-0001 | STU | IFR | 2026-12-24 | driving
ALP-EPC-00000-EL-STU-0003 | STU | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00000-EL-STU-0003 | STU | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00000-EL-STU-0004 | STU | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00000-EL-STU-0005 | STU | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00000-EL-STU-0006 | STU | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00000-EL-STU-0006 | STU | ALP-IEC-10MKA-EL-DSH-0001 | DSH | IFR | 2026-09-28
ALP-EPC-00000-EL-TRP-0001 | TRP | ALP-EPC-00000-EL-SPC-0003 | SPC | IFR | 2027-01-05
ALP-EPC-00000-GE-ITP-0001 | ITP | ALP-EPC-00000-GE-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00000-GE-LST-0001 | LST | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-GE-LST-0002 | LST | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-GE-LST-0003 | LST | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-GE-LST-0003 | LST | ALP-IEC-00000-GE-LST-0001 | LST | IFR | 2026-09-28
ALP-EPC-00000-GE-LST-0004 | LST | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-GE-LST-0005 | LST | ALP-EPC-00000-GE-PRC-0003 | PRC | IFR | 2026-12-09
ALP-EPC-00000-GE-MDL-0001 | MDL | ALP-EPC-00000-GE-PLN-0001 | PLN | IFR | 2027-05-03 | driving
ALP-EPC-00000-GE-MRQ-0001 | MRQ | ALP-EPC-00000-GE-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00000-GE-MRQ-0002 | MRQ | ALP-EPC-00000-GE-SPC-0002 | SPC | IFR | 2027-04-07 | driving
ALP-EPC-00000-GE-MRQ-0003 | MRQ | ALP-EPC-00000-GE-SPC-0003 | SPC | IFR | 2027-04-14 | driving
ALP-EPC-00000-GE-MRQ-0004 | MRQ | ALP-EPC-00000-GE-SPC-0004 | SPC | IFR | 2027-04-15 | driving
ALP-EPC-00000-GE-MRQ-0005 | MRQ | ALP-EPC-00000-GE-SPC-0005 | SPC | IFR | 2027-06-18 | driving
ALP-EPC-00000-GE-MRQ-0006 | MRQ | ALP-EPC-00000-GE-SPC-0006 | SPC | IFR | 2027-03-18 | driving
ALP-EPC-00000-GE-MRQ-0007 | MRQ | ALP-EPC-00000-GE-SPC-0007 | SPC | IFR | 2026-11-30 | driving
ALP-EPC-00000-GE-MRQ-0008 | MRQ | ALP-EPC-00000-GE-SPC-0008 | SPC | IFR | 2026-11-30 | driving
ALP-EPC-00000-GE-PLN-0001 | PLN | ALP-EPC-00000-GE-PRC-0001 | PRC | IFR | 2026-11-20
ALP-EPC-00000-GE-PLN-0001 | PLN | ALP-EPC-00000-GE-PRC-0002 | PRC | IFR | 2026-11-13
ALP-EPC-00000-GE-PLN-0002 | PLN | ALP-EPC-00000-GE-PLN-0001 | PLN | IFR | 2027-05-03 | driving
ALP-EPC-00000-GE-PLN-0003 | PLN | ALP-EPC-00000-GE-PRC-0002 | PRC | IFR | 2026-11-13
ALP-EPC-00000-GE-PLN-0004 | PLN | ALP-EPC-00000-GE-LST-0003 | LST | IFR | 2027-04-15 | driving
ALP-EPC-00000-GE-PLN-0005 | PLN | ALP-EPC-00000-GE-PLN-0003 | PLN | IFR | 2027-05-10
ALP-EPC-00000-GE-PRC-0003 | PRC | ALP-EPC-00000-GE-PRC-0002 | PRC | IFR | 2026-11-13
ALP-EPC-00000-GE-RPT-0001 | RPT | ALP-EPC-00000-CV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00000-GE-RPT-0002 | RPT | ALP-EPC-00000-CV-MRQ-0002 | MRQ | IFR | 2026-11-02
ALP-EPC-00000-GE-RPT-0003 | RPT | ALP-EPC-00000-EL-MRQ-0001 | MRQ | IFR | 2027-02-15
ALP-EPC-00000-GE-RPT-0004 | RPT | ALP-EPC-00000-GE-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00000-GE-RPT-0005 | RPT | ALP-EPC-00000-GE-MRQ-0002 | MRQ | IFR | 2027-04-14
ALP-EPC-00000-GE-RPT-0006 | RPT | ALP-EPC-00000-IC-MRQ-0001 | MRQ | IFR | 2027-01-18
ALP-EPC-00000-GE-RPT-0007 | RPT | ALP-EPC-00000-IC-MRQ-0002 | MRQ | IFR | 2027-01-18
ALP-EPC-00000-GE-RPT-0008 | RPT | ALP-EPC-00000-GE-MRQ-0003 | MRQ | IFR | 2027-04-21
ALP-EPC-00000-GE-RPT-0009 | RPT | ALP-EPC-00000-GE-MRQ-0004 | MRQ | IFR | 2027-04-22
ALP-EPC-00000-GE-RPT-0010 | RPT | ALP-EPC-00000-GE-MRQ-0005 | MRQ | IFR | 2027-06-25
ALP-EPC-00000-GE-RPT-0011 | RPT | ALP-EPC-00000-PI-MRQ-0001 | MRQ | IFR | 2026-12-07
ALP-EPC-00000-GE-RPT-0012 | RPT | ALP-EPC-00000-PI-MRQ-0003 | MRQ | IFR | 2026-12-22
ALP-EPC-00000-GE-RPT-0013 | RPT | ALP-EPC-00000-GE-MRQ-0006 | MRQ | IFR | 2027-03-25
ALP-EPC-00000-GE-RPT-0014 | RPT | ALP-EPC-00000-GE-MRQ-0007 | MRQ | IFR | 2026-12-07
ALP-EPC-00000-GE-RPT-0015 | RPT | ALP-EPC-00000-GE-MRQ-0008 | MRQ | IFR | 2026-12-07
ALP-EPC-00000-GE-RPT-0016 | RPT | ALP-EPC-00000-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-EPC-00000-GE-SPC-0001 | SPC | ALP-EPC-00000-EL-SLD-0002 | SLD | IFR | 2026-11-02
ALP-EPC-00000-GE-SPC-0001 | SPC | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-GE-SPC-0002 | SPC | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00000-GE-SPC-0002 | SPC | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-GE-SPC-0003 | SPC | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00000-GE-SPC-0003 | SPC | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-GE-SPC-0004 | SPC | ALP-EPC-00000-ME-SPC-0002 | SPC | IFR | 2026-12-14
ALP-EPC-00000-GE-SPC-0004 | SPC | ALP-EPC-00000-ME-SPC-0003 | SPC | IFR | 2026-12-14
ALP-EPC-00000-GE-SPC-0004 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00000-GE-SPC-0005 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00000-GE-SPC-0005 | SPC | ALP-EPC-00000-PI-SPC-0003 | SPC | IFR | 2027-05-21 | driving
ALP-EPC-00000-GE-SPC-0005 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00000-GE-SPC-0006 | SPC | ALP-EPC-00000-PI-SPC-0002 | SPC | IFR | 2026-12-14
ALP-EPC-00000-GE-SPC-0006 | SPC | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00000-GE-SPC-0007 | SPC | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00000-GE-SPC-0008 | SPC | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00000-HS-DBR-0001 | DBR | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-HS-HAZ-0001 | HAZ | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00000-HS-HAZ-0001 | HAZ | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00000-HS-HAZ-0001 | HAZ | ALP-EPC-00000-HS-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-HS-HAZ-0002 | HAZ | ALP-EPC-00EKA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00000-HS-HAZ-0002 | HAZ | ALP-EPC-00EKC-PR-PID-0001 | PID | IFR | 2027-05-06 | driving
ALP-EPC-00000-HS-HAZ-0002 | HAZ | ALP-IEC-10MBA-PR-PID-0001 | PID | IFR | 2027-01-11
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-EPC-00LBG-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-EPC-00LDA-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-EPC-10HAN-PR-PID-0001 | PID | IFR | 2027-05-27
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-EPC-10LAB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-EPC-10LAC-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-EPC-10LAE-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-EPC-10LAF-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-EPC-10LBA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-EPC-10LBB-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-EPC-10LBC-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-EPC-10LBD-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-EPC-20LCA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-EPC-20LCB-PR-PID-0001 | PID | IFR | 2027-06-15 | driving
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-EPC-20MAN-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-IEC-10HAA-PR-PID-0001 | PID | IFR | 2027-01-11
ALP-EPC-00000-HS-HAZ-0003 | HAZ | ALP-IEC-20MAA-PR-PID-0001 | PID | IFR | 2027-01-25
ALP-EPC-00000-HS-HAZ-0004 | HAZ | ALP-EPC-00EGA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-HS-HAZ-0004 | HAZ | ALP-EPC-00EGB-PR-PID-0001 | PID | IFR | 2027-04-06
ALP-EPC-00000-HS-HAZ-0004 | HAZ | ALP-EPC-00EGC-PR-PID-0001 | PID | IFR | 2027-02-19
ALP-EPC-00000-HS-HAZ-0004 | HAZ | ALP-EPC-10HSB-PR-PID-0001 | PID | IFR | 2027-06-11 | driving
ALP-EPC-00000-HS-HAZ-0005 | HAZ | ALP-EPC-00GBA-PR-PID-0001 | PID | IFR | 2027-03-01
ALP-EPC-00000-HS-HAZ-0005 | HAZ | ALP-EPC-00GCA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-HS-HAZ-0005 | HAZ | ALP-EPC-00GHA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-HS-HAZ-0005 | HAZ | ALP-EPC-00GKA-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-HS-HAZ-0005 | HAZ | ALP-EPC-00GMA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00000-HS-HAZ-0005 | HAZ | ALP-EPC-00GNA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00000-HS-HAZ-0005 | HAZ | ALP-EPC-00GUA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-HS-HAZ-0005 | HAZ | ALP-EPC-00QCA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-HS-HAZ-0006 | HAZ | ALP-EPC-00PGA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00000-HS-HAZ-0006 | HAZ | ALP-EPC-00QEA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-HS-HAZ-0006 | HAZ | ALP-EPC-00QHA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-HS-HAZ-0006 | HAZ | ALP-EPC-00QJA-PR-PID-0001 | PID | IFR | 2027-05-10 | driving
ALP-EPC-00000-HS-HAZ-0006 | HAZ | ALP-EPC-00QJB-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-HS-HAZ-0006 | HAZ | ALP-EPC-00SGA-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00000-HS-HAZ-0006 | HAZ | ALP-EPC-00SGC-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00000-HS-HAZ-0007 | HAZ | ALP-EPC-00000-HS-HAZ-0002 | HAZ | IFR | 2027-06-03
ALP-EPC-00000-HS-HAZ-0007 | HAZ | ALP-EPC-00000-HS-HAZ-0003 | HAZ | IFR | 2027-07-13
ALP-EPC-00000-HS-HAZ-0007 | HAZ | ALP-EPC-00000-HS-HAZ-0004 | HAZ | IFR | 2027-07-09
ALP-EPC-00000-HS-HAZ-0007 | HAZ | ALP-EPC-00000-HS-HAZ-0005 | HAZ | IFR | 2027-07-16 | driving
ALP-EPC-00000-HS-HAZ-0007 | HAZ | ALP-EPC-00000-HS-HAZ-0006 | HAZ | IFR | 2027-06-07
ALP-EPC-00000-HS-HAZ-0008 | HAZ | ALP-EPC-00000-HS-HAZ-0002 | HAZ | IFR | 2027-06-03
ALP-EPC-00000-HS-HAZ-0008 | HAZ | ALP-EPC-00000-HS-HAZ-0004 | HAZ | IFR | 2027-07-09
ALP-EPC-00000-HS-HAZ-0008 | HAZ | ALP-EPC-00UEG-PI-LAY-0001 | LAY | IFR | 2026-12-18
ALP-EPC-00000-HS-HAZ-0008 | HAZ | ALP-EPC-00UEK-PI-LAY-0001 | LAY | IFR | 2026-12-23
ALP-EPC-00000-HS-HAZ-0008 | HAZ | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-00000-HS-HAZ-0009 | HAZ | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00000-HS-HAZ-0009 | HAZ | ALP-EPC-00000-HS-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00000-HS-HAZ-0010 | HAZ | ALP-EPC-00000-HS-HAZ-0002 | HAZ | IFR | 2027-06-03
ALP-EPC-00000-HS-HAZ-0010 | HAZ | ALP-EPC-00000-HS-HAZ-0004 | HAZ | IFR | 2027-07-09
ALP-EPC-00000-HS-PLN-0001 | PLN | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16 | driving
ALP-EPC-00000-HS-PLN-0002 | PLN | ALP-EPC-00000-HS-PLN-0001 | PLN | IFR | 2026-12-14
ALP-EPC-00000-HS-PLN-0003 | PLN | ALP-EPC-00000-HS-RPT-0001 | RPT | IFR | 2026-12-14
ALP-EPC-00000-HS-PLN-0004 | PLN | ALP-EPC-00000-HS-RPT-0001 | RPT | IFR | 2026-12-14
ALP-EPC-00000-HS-PLN-0005 | PLN | ALP-EPC-00000-HS-HAZ-0010 | HAZ | IFR | 2027-09-10 | driving
ALP-EPC-00000-HS-PLN-0006 | PLN | ALP-EPC-00000-PI-SPC-0003 | SPC | IFR | 2027-05-21
ALP-EPC-00000-HS-RPT-0001 | RPT | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-HS-RPT-0002 | RPT | ALP-EPC-00000-ME-STU-0001 | STU | IFR | 2026-12-07
ALP-EPC-00000-HS-RPT-0002 | RPT | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00000-HS-RPT-0003 | RPT | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00000-HS-RPT-0004 | RPT | ALP-EPC-00000-HS-HAZ-0002 | HAZ | IFR | 2027-06-03
ALP-EPC-00000-HS-RPT-0004 | RPT | ALP-EPC-00000-HS-HAZ-0003 | HAZ | IFR | 2027-07-13
ALP-EPC-00000-HS-RPT-0005 | RPT | ALP-EPC-00000-HS-HAZ-0008 | HAZ | IFR | 2027-08-17 | driving
ALP-EPC-00000-HS-RPT-0006 | RPT | ALP-EPC-00000-HS-HAZ-0001 | HAZ | IFR | 2027-02-17
ALP-EPC-00000-HS-STU-0001 | STU | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00000-HS-STU-0001 | STU | ALP-IEC-10MBA-HS-RPT-0001 | RPT | IFR | 2027-01-11 | driving
ALP-EPC-00000-HS-STU-0001 | STU | ALP-EPC-00000-HS-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-HS-STU-0002 | STU | ALP-EPC-00000-PR-HMB-0001 | HMB | IFR | 2026-12-14 | driving
ALP-EPC-00000-HS-STU-0003 | STU | ALP-EPC-00000-HS-HAZ-0008 | HAZ | IFR | 2027-08-17
ALP-EPC-00000-HS-STU-0003 | STU | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00000-HV-DBR-0001 | DBR | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-IC-CNR-0001 | CNR | ALP-IEC-10MBY-IC-CNR-0001 | CNR | IFR | 2027-02-08 | driving
ALP-EPC-00000-IC-DBR-0001 | DBR | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-IC-IOL-0001 | IOL | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00000-IC-IOL-0001 | IOL | ALP-IEC-10MBY-IC-IOL-0001 | IOL | IFR | 2027-02-22
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00EGA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00EGB-PR-PID-0001 | PID | IFR | 2027-04-06
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00EGC-PR-PID-0001 | PID | IFR | 2027-02-19
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00EKA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00EKC-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00GBA-PR-PID-0001 | PID | IFR | 2027-03-01
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00GCA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00GHA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00GKA-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00GMA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00GNA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00GUA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00LBG-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00LDA-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00PAA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00PAB-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00PAC-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00PAH-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00PBA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00PGA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00QCA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00QEA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00QHA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00QJA-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00QJB-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00QUA-PR-PID-0001 | PID | IFR | 2027-05-11
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00SAA-HV-PID-0001 | PID | IFR | 2027-03-02
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00SGA-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-00SGC-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-10HAN-PR-PID-0001 | PID | IFR | 2027-05-27
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-10HSB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-10LAB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-10LAC-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-10LAE-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-10LAF-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-10LBA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-10LBB-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-10LBC-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-10LBD-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-20LCA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-20LCB-PR-PID-0001 | PID | IFR | 2027-06-15 | driving
ALP-EPC-00000-IC-LST-0001 | LST | ALP-EPC-20MAN-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-IC-LST-0002 | LST | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00000-IC-LST-0003 | LST | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00000-IC-MRQ-0001 | MRQ | ALP-EPC-00000-IC-SPC-0003 | SPC | IFR | 2027-01-11 | driving
ALP-EPC-00000-IC-MRQ-0002 | MRQ | ALP-EPC-00000-IC-SPC-0004 | SPC | IFR | 2027-01-11 | driving
ALP-EPC-00000-IC-RPT-0001 | RPT | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00000-IC-RPT-0002 | RPT | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00000-IC-SPC-0001 | SPC | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00000-IC-SPC-0002 | SPC | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00000-IC-SPC-0003 | SPC | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00000-IC-SPC-0004 | SPC | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00000-IC-SPC-0005 | SPC | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00000-IC-SPC-0006 | SPC | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00000-IC-TRP-0001 | TRP | ALP-EPC-00000-IC-TST-0002 | TST | IFR | 2027-01-25
ALP-EPC-00000-IC-TST-0001 | TST | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00000-IC-TST-0002 | TST | ALP-EPC-00000-IC-RPT-0002 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00000-ME-DBR-0001 | DBR | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-ME-DBR-0001 | DBR | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00000-ME-LST-0001 | LST | ALP-EPC-00000-ME-STU-0001 | STU | IFR | 2026-12-07 | driving
ALP-EPC-00000-ME-PLN-0001 | PLN | ALP-EPC-00000-ME-STU-0001 | STU | IFR | 2026-12-07 | driving
ALP-EPC-00000-ME-RPT-0001 | RPT | ALP-EPC-00000-ME-STU-0001 | STU | IFR | 2026-12-07 | driving
ALP-EPC-00000-ME-RPT-0002 | RPT | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-ME-SPC-0001 | SPC | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-ME-SPC-0002 | SPC | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-ME-SPC-0003 | SPC | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16 | driving
ALP-EPC-00000-ME-STU-0001 | STU | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00000-ME-STU-0002 | STU | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00000-PC-PRC-0001 | PRC | ALP-EPC-00000-GE-PRC-0002 | PRC | IFR | 2026-11-13
ALP-EPC-00000-PC-SCH-0001 | SCH | ALP-EPC-00000-GE-MDL-0001 | MDL | IFR | 2027-05-17
ALP-EPC-00000-PC-SCH-0001 | SCH | ALP-EPC-00000-GE-PLN-0002 | PLN | IFR | 2027-05-31 | driving
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00EGA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00EGB-PR-PID-0001 | PID | IFR | 2027-04-06
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00EGC-PR-PID-0001 | PID | IFR | 2027-02-19
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00EKA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00EKC-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00GBA-PR-PID-0001 | PID | IFR | 2027-03-01
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00GCA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00GHA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00GKA-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00GMA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00GNA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00GUA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00LBG-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00LDA-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00PAA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00PAB-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00PAC-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00PAH-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00PBA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00PGA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00QCA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00QEA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00QHA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00QJA-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00QJB-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00QUA-PR-PID-0001 | PID | IFR | 2027-05-11
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00SAA-HV-PID-0001 | PID | IFR | 2027-03-02
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00SGA-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-00SGC-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-10HAN-PR-PID-0001 | PID | IFR | 2027-05-27
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-10HSB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-10LAB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-10LAC-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-10LAE-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-10LAF-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-10LBA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-10LBB-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-10LBC-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-10LBD-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-20LCA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-20LCB-PR-PID-0001 | PID | IFR | 2027-06-15
ALP-EPC-00000-PI-LST-0001 | LST | ALP-EPC-20MAN-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PI-M3D-0001 | M3D | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00000-PI-M3D-0002 | M3D | ALP-EPC-00UEG-PI-PPL-0001 | PPL | IFR | 2027-02-26
ALP-EPC-00000-PI-M3D-0002 | M3D | ALP-EPC-00UEK-PI-PPL-0001 | PPL | IFR | 2027-03-03
ALP-EPC-00000-PI-M3D-0002 | M3D | ALP-EPC-00UGA-PI-PPL-0001 | PPL | IFR | 2027-03-03
ALP-EPC-00000-PI-M3D-0002 | M3D | ALP-EPC-00UPC-PI-PPL-0001 | PPL | IFR | 2027-05-11 | driving
ALP-EPC-00000-PI-M3D-0002 | M3D | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-00000-PI-M3D-0002 | M3D | ALP-EPC-00UZA-PI-PPL-0001 | PPL | IFR | 2027-02-09
ALP-EPC-00000-PI-M3D-0002 | M3D | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-00000-PI-M3D-0002 | M3D | ALP-EPC-20UMB-PI-PPL-0001 | PPL | IFR | 2027-05-10
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00EGA-PI-ISO-0001 | ISO | IFR | 2027-11-17
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00EGB-PI-ISO-0001 | ISO | IFR | 2027-12-06
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00EGC-PI-ISO-0001 | ISO | IFR | 2027-09-22
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00EKA-PI-ISO-0001 | ISO | IFR | 2027-08-31
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00EKC-PI-ISO-0001 | ISO | IFR | 2027-09-17
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00GBA-PI-ISO-0001 | ISO | IFR | 2027-12-21
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00GCA-PI-ISO-0001 | ISO | IFR | 2028-01-03
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00GHA-PI-ISO-0001 | ISO | IFR | 2028-01-21
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00GKA-PI-ISO-0001 | ISO | IFR | 2027-08-19
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00GMA-PI-ISO-0001 | ISO | IFR | 2027-07-27
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00GNA-PI-ISO-0001 | ISO | IFR | 2028-01-11
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00GUA-PI-ISO-0001 | ISO | IFR | 2028-01-28
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00LBG-PI-ISO-0001 | ISO | IFR | 2027-10-26
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00LDA-PI-ISO-0001 | ISO | IFR | 2028-01-12
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00PAA-PI-ISO-0001 | ISO | IFR | 2027-08-19
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00PAB-PI-ISO-0001 | ISO | IFR | 2027-08-19
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00PAC-PI-ISO-0001 | ISO | IFR | 2027-08-19
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00PAH-PI-ISO-0001 | ISO | IFR | 2028-02-07
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00PBA-PI-ISO-0001 | ISO | IFR | 2027-08-18
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00PGA-PI-ISO-0001 | ISO | IFR | 2027-10-13
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00QCA-PI-ISO-0001 | ISO | IFR | 2027-11-23
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00QEA-PI-ISO-0001 | ISO | IFR | 2027-10-06
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00QHA-PI-ISO-0001 | ISO | IFR | 2027-11-08
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00QJA-PI-ISO-0001 | ISO | IFR | 2027-12-06
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00QJB-PI-ISO-0001 | ISO | IFR | 2028-01-14
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00QUA-PI-ISO-0001 | ISO | IFR | 2027-12-21
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00SGA-PI-ISO-0001 | ISO | IFR | 2027-10-11
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-00SGC-PI-ISO-0001 | ISO | IFR | 2027-10-14
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-10HAN-PI-ISO-0001 | ISO | IFR | 2027-12-08
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-10HSB-PI-ISO-0001 | ISO | IFR | 2027-11-30
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-10LAB-PI-ISO-0001 | ISO | IFR | 2027-10-26
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-10LAC-PI-ISO-0001 | ISO | IFR | 2027-11-17
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-10LAE-PI-ISO-0001 | ISO | IFR | 2028-01-18
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-10LAF-PI-ISO-0001 | ISO | IFR | 2028-01-18
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-10LBA-PI-ISO-0001 | ISO | IFR | 2027-12-07
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-10LBB-PI-ISO-0001 | ISO | IFR | 2027-12-09
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-10LBC-PI-ISO-0001 | ISO | IFR | 2027-12-15
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-10LBD-PI-ISO-0001 | ISO | IFR | 2027-12-30
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-20LCA-PI-ISO-0001 | ISO | IFR | 2028-03-01 | driving
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-20LCB-PI-ISO-0001 | ISO | IFR | 2028-02-28
ALP-EPC-00000-PI-M3D-0003 | M3D | ALP-EPC-20MAN-PI-ISO-0001 | ISO | IFR | 2028-02-28
ALP-EPC-00000-PI-M3D-0004 | M3D | ALP-EPC-00000-PI-M3D-0003 | M3D | IFR | 2028-03-22 | driving
ALP-EPC-00000-PI-MRQ-0001 | MRQ | ALP-EPC-00000-PI-SPC-0004 | SPC | IFR | 2026-11-30 | driving
ALP-EPC-00000-PI-MRQ-0002 | MRQ | ALP-EPC-00000-PI-SPC-0005 | SPC | IFR | 2027-01-11 | driving
ALP-EPC-00000-PI-MRQ-0003 | MRQ | ALP-EPC-00000-PI-SPC-0006 | SPC | IFR | 2026-12-15 | driving
ALP-EPC-00000-PI-MRQ-0004 | MRQ | ALP-EPC-00000-PI-SPC-0007 | SPC | IFR | 2026-11-30
ALP-EPC-00000-PI-MRQ-0004 | MRQ | ALP-EPC-00PAB-ME-DSH-0001 | DSH | IFR | 2027-02-22
ALP-EPC-00000-PI-PLT-0001 | PLT | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-PI-PLT-0001 | PLT | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00000-PI-PLT-0001 | PLT | ALP-IEC-10MBA-ME-LAY-0001 | LAY | IFR | 2026-09-28
ALP-EPC-00000-PI-RPT-0001 | RPT | ALP-EPC-00000-PI-SPC-0002 | SPC | IFR | 2026-12-14 | driving
ALP-EPC-00000-PI-RPT-0001 | RPT | ALP-EPC-00000-PR-HMB-0001 | HMB | IFR | 2026-12-14
ALP-EPC-00000-PI-SPC-0001 | SPC | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-PI-SPC-0001 | SPC | ALP-EPC-00000-PR-HMB-0001 | HMB | IFR | 2026-12-14
ALP-EPC-00000-PI-SPC-0002 | SPC | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-PI-SPC-0003 | SPC | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00000-PI-SPC-0004 | SPC | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00000-PI-SPC-0005 | SPC | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00000-PI-SPC-0005 | SPC | ALP-EPC-00000-PR-HMB-0001 | HMB | IFR | 2026-12-14 | driving
ALP-EPC-00000-PI-SPC-0005 | SPC | ALP-EPC-10LBA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00000-PI-SPC-0005 | SPC | ALP-EPC-10LBB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00000-PI-SPC-0005 | SPC | ALP-EPC-10LBC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00000-PI-SPC-0005 | SPC | ALP-EPC-10LBD-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00000-PI-SPC-0006 | SPC | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00000-PI-SPC-0007 | SPC | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00000-PI-SPC-0007 | SPC | ALP-EPC-00PAB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00000-PR-CAL-0001 | CAL | ALP-EPC-00000-PR-HMB-0001 | HMB | IFR | 2026-12-14 | driving
ALP-EPC-00000-PR-CAL-0002 | CAL | ALP-EPC-00000-PR-CAL-0001 | CAL | IFR | 2027-01-04
ALP-EPC-00000-PR-DBR-0001 | DBR | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-PR-DBR-0001 | DBR | ALP-EPC-00000-PR-HMB-0001 | HMB | IFR | 2026-12-14 | driving
ALP-EPC-00000-PR-HMB-0001 | HMB | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00000-PR-LST-0001 | LST | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00000-PR-LST-0001 | LST | ALP-EPC-00000-PR-PFD-0002 | PFD | IFR | 2027-01-11
ALP-EPC-00000-PR-LST-0001 | LST | ALP-EPC-00000-PR-HMB-0001 | HMB | IFR | 2026-12-14
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00EGA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00EGB-PR-PID-0001 | PID | IFR | 2027-04-06
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00EGC-PR-PID-0001 | PID | IFR | 2027-02-19
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00EKA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00EKC-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00GBA-PR-PID-0001 | PID | IFR | 2027-03-01
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00GCA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00GHA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00GKA-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00GMA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00GNA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00GUA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00LBG-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00LDA-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00PAA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00PAB-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00PAC-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00PAH-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00PBA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00PGA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00QCA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00QEA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00QHA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00QJA-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00QJB-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00QUA-PR-PID-0001 | PID | IFR | 2027-05-11
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00SAA-HV-PID-0001 | PID | IFR | 2027-03-02
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00SGA-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-00SGC-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-10HAN-PR-PID-0001 | PID | IFR | 2027-05-27
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-10HSB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-10LAB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-10LAC-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-10LAE-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-10LAF-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-10LBA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-10LBB-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-10LBC-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-10LBD-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-20LCA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-20LCB-PR-PID-0001 | PID | IFR | 2027-06-15 | driving
ALP-EPC-00000-PR-LST-0002 | LST | ALP-EPC-20MAN-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00000-PR-LST-0003 | LST | ALP-EPC-00000-PR-STU-0001 | STU | IFR | 2027-06-04 | driving
ALP-EPC-00000-PR-PFD-0001 | PFD | ALP-EPC-00000-PR-HMB-0001 | HMB | IFR | 2026-12-14
ALP-EPC-00000-PR-PFD-0002 | PFD | ALP-EPC-00000-PR-HMB-0001 | HMB | IFR | 2026-12-14 | driving
ALP-EPC-00000-PR-RPT-0001 | RPT | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00000-PR-RPT-0002 | RPT | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00000-PR-RPT-0003 | RPT | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00000-PR-RPT-0004 | RPT | ALP-EPC-00000-PR-STU-0002 | STU | IFR | 2026-12-07 | driving
ALP-EPC-00000-PR-STU-0001 | STU | ALP-EPC-00000-PR-HMB-0001 | HMB | IFR | 2026-12-14
ALP-EPC-00000-PR-STU-0002 | STU | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00000-PR-STU-0003 | STU | ALP-EPC-00000-PR-HMB-0001 | HMB | IFR | 2026-12-14
ALP-EPC-00000-PR-STU-0004 | STU | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00000-SS-MRQ-0001 | MRQ | ALP-EPC-00000-SS-SPC-0002 | SPC | IFR | 2026-11-02
ALP-EPC-00000-SS-SPC-0001 | SPC | ALP-EPC-00000-CV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00000-SS-SPC-0002 | SPC | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00ACA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30 | driving
ALP-EPC-00ACA-CM-MDB-0001 | MDB | ALP-EPC-00ACA-CM-CMP-0001 | CMP | IFR | 2026-12-28
ALP-EPC-00ACA-CM-OMM-0001 | OMM | ALP-EPC-00ACA-CM-CMP-0001 | CMP | IFR | 2026-12-28 | driving
ALP-EPC-00ACA-EL-DSH-0001 | DSH | ALP-EPC-00ACA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00ACA-EL-DSH-0001 | DSH | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00ACA-EL-ITP-0001 | ITP | ALP-EPC-00ACA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | ALP-EPC-00ACA-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | ALP-EPC-00ACA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00ACA-EL-SLD-0001 | SLD | ALP-EPC-00000-EL-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00ACA-EL-SLD-0001 | SLD | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00ACA-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00ACA-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-STU-0005 | STU | IFR | 2026-12-07
ALP-EPC-00ACA-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00ACA-GE-RPT-0001 | RPT | ALP-EPC-00ACA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00ACA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11 | driving
ALP-EPC-00ACA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00BBA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30 | driving
ALP-EPC-00BBA-CM-MDB-0001 | MDB | ALP-EPC-00BBA-CM-CMP-0001 | CMP | IFR | 2026-12-28
ALP-EPC-00BBA-CM-OMM-0001 | OMM | ALP-EPC-00BBA-CM-CMP-0001 | CMP | IFR | 2026-12-28 | driving
ALP-EPC-00BBA-EL-DSH-0001 | DSH | ALP-EPC-00BBA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BBA-EL-DSH-0001 | DSH | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BBA-EL-ITP-0001 | ITP | ALP-EPC-00BBA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BBA-EL-MRQ-0001 | MRQ | ALP-EPC-00BBA-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00BBA-EL-MRQ-0001 | MRQ | ALP-EPC-00BBA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BBA-EL-SLD-0001 | SLD | ALP-EPC-00000-EL-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00BBA-EL-SLD-0001 | SLD | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BBA-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BBA-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00BBA-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00BBA-EL-WIR-0001 | WIR | ALP-EPC-00BBA-EL-SLD-0001 | SLD | IFC | 2027-01-19
ALP-EPC-00BBA-EL-WIR-0001 | WIR | ALP-EPC-00000-EL-STU-0002 | STU | IFC | 2027-02-25
ALP-EPC-00BBA-GE-RPT-0001 | RPT | ALP-EPC-00BBA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00BFA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30 | driving
ALP-EPC-00BFA-CM-MDB-0001 | MDB | ALP-EPC-00BFA-CM-CMP-0001 | CMP | IFR | 2026-12-28
ALP-EPC-00BFA-CM-OMM-0001 | OMM | ALP-EPC-00BFA-CM-CMP-0001 | CMP | IFR | 2026-12-28 | driving
ALP-EPC-00BFA-EL-DSH-0001 | DSH | ALP-EPC-00BFA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BFA-EL-DSH-0001 | DSH | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BFA-EL-ITP-0001 | ITP | ALP-EPC-00BFA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | ALP-EPC-00BFA-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | ALP-EPC-00BFA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | ALP-EPC-00BMA-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | ALP-EPC-00BRA-EL-DSH-0002 | DSH | IFR | 2026-11-16
ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | ALP-EPC-00BRA-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00BFA-EL-SLD-0001 | SLD | ALP-EPC-00000-EL-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00BFA-EL-SLD-0001 | SLD | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BFA-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BFA-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00BFA-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00BFA-EL-WIR-0001 | WIR | ALP-EPC-00BFA-EL-SLD-0001 | SLD | IFC | 2027-01-25
ALP-EPC-00BFA-EL-WIR-0001 | WIR | ALP-EPC-00000-EL-LST-0001 | LST | IFC | 2026-11-30
ALP-EPC-00BFA-EL-WIR-0002 | WIR | ALP-EPC-00BFA-EL-SLD-0001 | SLD | IFC | 2027-01-25
ALP-EPC-00BFA-EL-WIR-0002 | WIR | ALP-EPC-00000-EL-LST-0001 | LST | IFC | 2026-11-30
ALP-EPC-00BFA-EL-WIR-0003 | WIR | ALP-EPC-00BFA-EL-SLD-0001 | SLD | IFC | 2027-01-25
ALP-EPC-00BFA-EL-WIR-0003 | WIR | ALP-EPC-00000-EL-LST-0001 | LST | IFC | 2026-11-30
ALP-EPC-00BFA-EL-WIR-0004 | WIR | ALP-EPC-00BFA-EL-SLD-0001 | SLD | IFC | 2027-01-25
ALP-EPC-00BFA-EL-WIR-0004 | WIR | ALP-EPC-00000-EL-LST-0001 | LST | IFC | 2026-11-30
ALP-EPC-00BFA-EL-WIR-0005 | WIR | ALP-EPC-00BFA-EL-SLD-0001 | SLD | IFC | 2027-01-25
ALP-EPC-00BFA-EL-WIR-0005 | WIR | ALP-EPC-00000-EL-LST-0001 | LST | IFC | 2026-11-30
ALP-EPC-00BFA-EL-WIR-0006 | WIR | ALP-EPC-00BFA-EL-SLD-0001 | SLD | IFC | 2027-01-25
ALP-EPC-00BFA-EL-WIR-0006 | WIR | ALP-EPC-00000-EL-LST-0001 | LST | IFC | 2026-11-30
ALP-EPC-00BFA-EL-WIR-0007 | WIR | ALP-EPC-00BFA-EL-SLD-0001 | SLD | IFC | 2027-01-25
ALP-EPC-00BFA-EL-WIR-0007 | WIR | ALP-EPC-00000-EL-LST-0001 | LST | IFC | 2026-11-30
ALP-EPC-00BFA-EL-WIR-0008 | WIR | ALP-EPC-00BFA-EL-SLD-0001 | SLD | IFC | 2027-01-25
ALP-EPC-00BFA-EL-WIR-0008 | WIR | ALP-EPC-00000-EL-LST-0001 | LST | IFC | 2026-11-30
ALP-EPC-00BFA-EL-WIR-0009 | WIR | ALP-EPC-00BFA-EL-SLD-0001 | SLD | IFC | 2027-01-25
ALP-EPC-00BFA-EL-WIR-0009 | WIR | ALP-EPC-00000-EL-LST-0001 | LST | IFC | 2026-11-30
ALP-EPC-00BFA-EL-WIR-0010 | WIR | ALP-EPC-00BFA-EL-SLD-0001 | SLD | IFC | 2027-01-25
ALP-EPC-00BFA-EL-WIR-0010 | WIR | ALP-EPC-00000-EL-LST-0001 | LST | IFC | 2026-11-30
ALP-EPC-00BFA-EL-WIR-0011 | WIR | ALP-EPC-00BFA-EL-SLD-0001 | SLD | IFC | 2027-01-25
ALP-EPC-00BFA-EL-WIR-0011 | WIR | ALP-EPC-00000-EL-LST-0001 | LST | IFC | 2026-11-30
ALP-EPC-00BFA-EL-WIR-0012 | WIR | ALP-EPC-00BFA-EL-SLD-0001 | SLD | IFC | 2027-01-25
ALP-EPC-00BFA-EL-WIR-0012 | WIR | ALP-EPC-00000-EL-LST-0001 | LST | IFC | 2026-11-30
ALP-EPC-00BFA-EL-WIR-0013 | WIR | ALP-EPC-00BFA-EL-SLD-0001 | SLD | IFC | 2027-01-25
ALP-EPC-00BFA-EL-WIR-0013 | WIR | ALP-EPC-00000-EL-LST-0001 | LST | IFC | 2026-11-30
ALP-EPC-00BFA-GE-RPT-0001 | RPT | ALP-EPC-00BFA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00BFT-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30 | driving
ALP-EPC-00BFT-CM-MDB-0001 | MDB | ALP-EPC-00BFT-CM-CMP-0001 | CMP | IFR | 2026-12-28
ALP-EPC-00BFT-CM-OMM-0001 | OMM | ALP-EPC-00BFT-CM-CMP-0001 | CMP | IFR | 2026-12-28 | driving
ALP-EPC-00BFT-EL-DSH-0001 | DSH | ALP-EPC-00BFT-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BFT-EL-DSH-0001 | DSH | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BFT-EL-ITP-0001 | ITP | ALP-EPC-00BFT-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BFT-EL-MRQ-0001 | MRQ | ALP-EPC-00BFT-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00BFT-EL-MRQ-0001 | MRQ | ALP-EPC-00BFT-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BFT-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BFT-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00BFT-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00BFT-GE-RPT-0001 | RPT | ALP-EPC-00BFT-EL-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-EPC-00BLA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30 | driving
ALP-EPC-00BLA-CM-MDB-0001 | MDB | ALP-EPC-00BLA-CM-CMP-0001 | CMP | IFR | 2026-12-28
ALP-EPC-00BLA-CM-OMM-0001 | OMM | ALP-EPC-00BLA-CM-CMP-0001 | CMP | IFR | 2026-12-28
ALP-EPC-00BLA-EL-SLD-0001 | SLD | ALP-EPC-00000-EL-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00BLA-EL-SLD-0001 | SLD | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BLA-GE-RPT-0001 | RPT | ALP-EPC-00000-EL-MRQ-0002 | MRQ | IFR | 2027-01-18
ALP-EPC-00BLA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00BMA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30 | driving
ALP-EPC-00BMA-CM-MDB-0001 | MDB | ALP-EPC-00BMA-CM-CMP-0001 | CMP | IFR | 2026-12-28
ALP-EPC-00BMA-CM-OMM-0001 | OMM | ALP-EPC-00BMA-CM-CMP-0001 | CMP | IFR | 2026-12-28
ALP-EPC-00BMA-EL-DSH-0001 | DSH | ALP-EPC-00BFA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BMA-EL-DSH-0001 | DSH | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BMA-EL-SLD-0001 | SLD | ALP-EPC-00000-EL-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00BMA-EL-SLD-0001 | SLD | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BMA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00BRA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00BRA-CM-MDB-0001 | MDB | ALP-EPC-00BRA-CM-CMP-0001 | CMP | IFR | 2027-01-07
ALP-EPC-00BRA-CM-OMM-0001 | OMM | ALP-EPC-00BRA-CM-CMP-0001 | CMP | IFR | 2027-01-07 | driving
ALP-EPC-00BRA-EL-DSH-0001 | DSH | ALP-EPC-00BRA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BRA-EL-DSH-0001 | DSH | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BRA-EL-DSH-0001 | DSH | ALP-EPC-00BFA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BRA-EL-DSH-0002 | DSH | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BRA-EL-DSH-0002 | DSH | ALP-EPC-00BFA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BRA-EL-DSH-0002 | DSH | ALP-EPC-00BRA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BRA-EL-ITP-0001 | ITP | ALP-EPC-00BRA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | ALP-EPC-00BRA-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | ALP-EPC-00BRA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | ALP-EPC-00BTA-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | ALP-EPC-00BRA-EL-DSH-0002 | DSH | IFR | 2026-11-16 | driving
ALP-EPC-00BRA-EL-SLD-0001 | SLD | ALP-EPC-00000-EL-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00BRA-EL-SLD-0001 | SLD | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BRA-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BRA-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00BRA-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00BRA-GE-RPT-0001 | RPT | ALP-EPC-00BRA-EL-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-EPC-00BRA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00BTA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00BTA-CM-MDB-0001 | MDB | ALP-EPC-00BTA-CM-CMP-0001 | CMP | IFR | 2027-01-19
ALP-EPC-00BTA-CM-OMM-0001 | OMM | ALP-EPC-00BTA-CM-CMP-0001 | CMP | IFR | 2027-01-19 | driving
ALP-EPC-00BTA-EL-DSH-0001 | DSH | ALP-EPC-00BRA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00BTA-EL-DSH-0001 | DSH | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00BTA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00BXA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00BXA-CM-MDB-0001 | MDB | ALP-EPC-00BXA-CM-CMP-0001 | CMP | IFR | 2027-01-25
ALP-EPC-00BXA-GE-ITP-0001 | ITP | ALP-EPC-00BXA-GE-SPC-0001 | SPC | IFR | 2027-02-11
ALP-EPC-00BXA-GE-MRQ-0001 | MRQ | ALP-EPC-00BXA-GE-SPC-0001 | SPC | IFR | 2027-02-11 | driving
ALP-EPC-00BXA-GE-RPT-0001 | RPT | ALP-EPC-00BXA-GE-MRQ-0001 | MRQ | IFR | 2027-02-18
ALP-EPC-00BXA-GE-SPC-0001 | SPC | ALP-EPC-00000-EL-CAL-0005 | CAL | IFR | 2027-01-04
ALP-EPC-00BXA-GE-SPC-0001 | SPC | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CJA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00CJA-CM-MDB-0001 | MDB | ALP-EPC-00CJA-CM-CMP-0001 | CMP | IFR | 2027-02-05
ALP-EPC-00CJA-CM-OMM-0001 | OMM | ALP-EPC-00CJA-CM-CMP-0001 | CMP | IFR | 2027-02-05
ALP-EPC-00CJA-GE-RPT-0001 | RPT | ALP-EPC-00CJA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00CJA-IC-BLK-0001 | BLK | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CJA-IC-BLK-0001 | BLK | ALP-IEC-10MBY-IC-BLK-0001 | BLK | IFR | 2027-01-11 | driving
ALP-EPC-00CJA-IC-DSH-0001 | DSH | ALP-EPC-00CJA-IC-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00CJA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CJA-IC-ITP-0001 | ITP | ALP-EPC-00CJA-IC-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00CJA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00CJA-IC-MRQ-0001 | MRQ | ALP-EPC-00CJA-IC-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00CJA-IC-MRQ-0001 | MRQ | ALP-EPC-00CJA-IC-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00CJA-IC-SPC-0001 | SPC | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-00CJA-IC-SPC-0001 | SPC | ALP-EPC-00CJA-IC-BLK-0001 | BLK | IFR | 2027-02-01
ALP-EPC-00CJA-IC-SPC-0001 | SPC | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CJG-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00CJG-CM-MDB-0001 | MDB | ALP-EPC-00CJG-CM-CMP-0001 | CMP | IFR | 2027-02-16
ALP-EPC-00CJG-CM-OMM-0001 | OMM | ALP-EPC-00CJG-CM-CMP-0001 | CMP | IFR | 2027-02-16 | driving
ALP-EPC-00CJG-GE-ITP-0001 | ITP | ALP-EPC-00CJG-GE-SPC-0001 | SPC | IFR | 2027-02-22 | driving
ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | ALP-EPC-00CJG-GE-SPC-0001 | SPC | IFR | 2027-02-22
ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | ALP-EPC-00CJG-IC-DSH-0001 | DSH | IFR | 2027-03-08 | driving
ALP-EPC-00CJG-GE-RPT-0001 | RPT | ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-EPC-00CJG-GE-SPC-0001 | SPC | ALP-EPC-00CJG-IC-BLK-0001 | BLK | IFR | 2027-01-25 | driving
ALP-EPC-00CJG-GE-SPC-0001 | SPC | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CJG-IC-BLK-0001 | BLK | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CJG-IC-BLK-0001 | BLK | ALP-EPC-00000-IC-RPT-0002 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00CJG-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CJG-IC-DSH-0001 | DSH | ALP-EPC-00CJG-GE-SPC-0001 | SPC | IFR | 2027-02-22 | driving
ALP-EPC-00CKA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00CKA-CM-MDB-0001 | MDB | ALP-EPC-00CKA-CM-CMP-0001 | CMP | IFR | 2027-02-22
ALP-EPC-00CKA-CM-OMM-0001 | OMM | ALP-EPC-00CKA-CM-CMP-0001 | CMP | IFR | 2027-02-22 | driving
ALP-EPC-00CKA-GE-ITP-0001 | ITP | ALP-EPC-00CKA-GE-SPC-0001 | SPC | IFR | 2027-02-22 | driving
ALP-EPC-00CKA-GE-MRQ-0001 | MRQ | ALP-EPC-00CKA-GE-SPC-0001 | SPC | IFR | 2027-02-22
ALP-EPC-00CKA-GE-MRQ-0001 | MRQ | ALP-EPC-00CKA-IC-DSH-0001 | DSH | IFR | 2027-03-08 | driving
ALP-EPC-00CKA-GE-RPT-0001 | RPT | ALP-EPC-00CKA-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-EPC-00CKA-GE-SPC-0001 | SPC | ALP-EPC-00CKA-IC-BLK-0001 | BLK | IFR | 2027-01-25 | driving
ALP-EPC-00CKA-GE-SPC-0001 | SPC | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CKA-IC-BLK-0001 | BLK | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CKA-IC-BLK-0001 | BLK | ALP-EPC-00000-IC-RPT-0002 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00CKA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CKA-IC-DSH-0001 | DSH | ALP-EPC-00CKA-GE-SPC-0001 | SPC | IFR | 2027-02-22 | driving
ALP-EPC-00CKA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00CQA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00CQA-CM-MDB-0001 | MDB | ALP-EPC-00CQA-CM-CMP-0001 | CMP | IFR | 2027-02-22
ALP-EPC-00CQA-CM-OMM-0001 | OMM | ALP-EPC-00CQA-CM-CMP-0001 | CMP | IFR | 2027-02-22 | driving
ALP-EPC-00CQA-GE-RPT-0001 | RPT | ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00CQA-IC-BLK-0001 | BLK | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CQA-IC-BLK-0001 | BLK | ALP-EPC-00000-IC-RPT-0002 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00CQA-IC-DSH-0001 | DSH | ALP-EPC-00CQA-IC-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00CQA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CQA-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11 | driving
ALP-EPC-00CQA-IC-ITP-0001 | ITP | ALP-EPC-00CQA-IC-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00CQA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | ALP-EPC-00CQA-IC-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | ALP-EPC-00CQA-IC-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00CQA-IC-SPC-0001 | SPC | ALP-EPC-00000-HS-RPT-0001 | RPT | IFR | 2026-12-14
ALP-EPC-00CQA-IC-SPC-0001 | SPC | ALP-EPC-00CQA-IC-BLK-0001 | BLK | IFR | 2027-01-25
ALP-EPC-00CQA-IC-SPC-0001 | SPC | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CQA-IC-TRP-0001 | TRP | ALP-EPC-00CQA-IC-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00CYA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00CYA-CM-MDB-0001 | MDB | ALP-EPC-00CYA-CM-CMP-0001 | CMP | IFR | 2027-02-22
ALP-EPC-00CYA-CM-OMM-0001 | OMM | ALP-EPC-00CYA-CM-CMP-0001 | CMP | IFR | 2027-02-22 | driving
ALP-EPC-00CYA-GE-ITP-0001 | ITP | ALP-EPC-00CYA-GE-SPC-0001 | SPC | IFR | 2027-02-25
ALP-EPC-00CYA-GE-MRQ-0001 | MRQ | ALP-EPC-00CYA-GE-SPC-0001 | SPC | IFR | 2027-02-25
ALP-EPC-00CYA-GE-MRQ-0001 | MRQ | ALP-EPC-00CYA-IC-DSH-0001 | DSH | IFR | 2027-03-11 | driving
ALP-EPC-00CYA-GE-RPT-0001 | RPT | ALP-EPC-00CYA-GE-MRQ-0001 | MRQ | IFR | 2027-03-18
ALP-EPC-00CYA-GE-SPC-0001 | SPC | ALP-EPC-00CYA-IC-BLK-0001 | BLK | IFR | 2027-01-25
ALP-EPC-00CYA-GE-SPC-0001 | SPC | ALP-EPC-00000-IC-RPT-0002 | RPT | IFR | 2027-01-04
ALP-EPC-00CYA-GE-SPC-0001 | SPC | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CYA-IC-BLK-0001 | BLK | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CYA-IC-BLK-0001 | BLK | ALP-EPC-00000-IC-RPT-0002 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00CYA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00CYA-IC-DSH-0001 | DSH | ALP-EPC-00CYA-GE-SPC-0001 | SPC | IFR | 2027-02-25 | driving
ALP-EPC-00CYA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00EGA-CM-CMP-0001 | CMP | ALP-EPC-00EGA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00EGA-CM-CMP-0001 | CMP | ALP-EPC-00EGA-IC-CNR-0001 | CNR | IFR | 2027-04-22 | driving
ALP-EPC-00EGA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00EGA-CM-MDB-0001 | MDB | ALP-EPC-00EGA-CM-CMP-0001 | CMP | IFR | 2027-05-20
ALP-EPC-00EGA-CM-OMM-0001 | OMM | ALP-EPC-00EGA-CM-CMP-0001 | CMP | IFR | 2027-05-20 | driving
ALP-EPC-00EGA-GE-RPT-0001 | RPT | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00EGA-IC-CEM-0001 | CEM | ALP-EPC-00EGA-IC-CNR-0001 | CNR | IFR | 2027-04-22
ALP-EPC-00EGA-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00EGA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00EGA-IC-CNR-0001 | CNR | ALP-EPC-00EGA-PR-PID-0001 | PID | IFR | 2027-04-01 | driving
ALP-EPC-00EGA-IC-DSH-0001 | DSH | ALP-EPC-00EGA-PR-PID-0001 | PID | IFR | 2027-04-01 | driving
ALP-EPC-00EGA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00EGA-IC-DSH-0002 | DSH | ALP-EPC-00EGA-PR-PID-0001 | PID | IFR | 2027-04-01 | driving
ALP-EPC-00EGA-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00EGA-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00EGA-IC-HMI-0001 | HMI | ALP-EPC-00EGA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00EGA-IC-HMI-0001 | HMI | ALP-EPC-00EGA-IC-CNR-0001 | CNR | IFR | 2027-04-22 | driving
ALP-EPC-00EGA-IC-LOG-0001 | LOG | ALP-EPC-00EGA-IC-CNR-0001 | CNR | IFR | 2027-04-22 | driving
ALP-EPC-00EGA-IC-LOG-0001 | LOG | ALP-EPC-00EGA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00EGA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00EGA-ME-CAL-0001 | CAL | ALP-EPC-00EGA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00EGA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00EGA-ME-DSH-0001 | DSH | ALP-EPC-00EGA-ME-CAL-0001 | CAL | IFR | 2027-02-04
ALP-EPC-00EGA-ME-DSH-0001 | DSH | ALP-EPC-00EGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EGA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00EGA-ME-DSH-0002 | DSH | ALP-EPC-00EGA-ME-CAL-0001 | CAL | IFR | 2027-02-04
ALP-EPC-00EGA-ME-DSH-0002 | DSH | ALP-EPC-00EGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EGA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08 | driving
ALP-EPC-00EGA-ME-DSH-0003 | DSH | ALP-EPC-00EGA-ME-CAL-0001 | CAL | IFR | 2027-02-04
ALP-EPC-00EGA-ME-DSH-0003 | DSH | ALP-EPC-00EGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EGA-ME-DSH-0003 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08 | driving
ALP-EPC-00EGA-ME-DSH-0004 | DSH | ALP-EPC-00EGA-ME-CAL-0001 | CAL | IFR | 2027-02-04
ALP-EPC-00EGA-ME-DSH-0004 | DSH | ALP-EPC-00EGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EGA-ME-DSH-0004 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08 | driving
ALP-EPC-00EGA-ME-ITP-0001 | ITP | ALP-EPC-00EGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | ALP-EPC-00EGA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | ALP-EPC-00EGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | ALP-EPC-00EGC-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | ALP-EPC-00EGA-ME-DSH-0002 | DSH | IFR | 2027-02-22
ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | ALP-EPC-00EGA-ME-DSH-0003 | DSH | IFR | 2027-02-24
ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | ALP-EPC-00EGA-ME-DSH-0004 | DSH | IFR | 2027-02-22
ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | ALP-EPC-00EGC-ME-DSH-0002 | DSH | IFR | 2027-02-24
ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | ALP-EPC-00EGC-ME-DSH-0003 | DSH | IFR | 2027-02-24
ALP-EPC-00EGA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00EGA-ME-SPC-0001 | SPC | ALP-EPC-00EGA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00EGA-ME-SPC-0001 | SPC | ALP-EPC-00EGC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00EGA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00EGA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00EGA-PI-ISO-0001 | ISO | ALP-EPC-00EGA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00EGA-PI-ISO-0001 | ISO | ALP-EPC-00UEG-PI-PPL-0001 | PPL | IFR | 2027-02-26
ALP-EPC-00EGA-PI-SUP-0001 | SUP | ALP-EPC-00EGA-PI-ISO-0001 | ISO | IFC | 2027-11-24
ALP-EPC-00EGA-PR-DSH-0001 | DSH | ALP-EPC-00EGA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00EGA-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00EGA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EGA-PR-PID-0001 | PID | ALP-EPC-00EGA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00EGA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00EGA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00EGA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00EGB-CM-CMP-0001 | CMP | ALP-EPC-00EGB-PR-PID-0001 | PID | IFR | 2027-04-06
ALP-EPC-00EGB-CM-CMP-0001 | CMP | ALP-EPC-00EGB-IC-CNR-0001 | CNR | IFR | 2027-04-27 | driving
ALP-EPC-00EGB-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00EGB-CM-MDB-0001 | MDB | ALP-EPC-00EGB-CM-CMP-0001 | CMP | IFR | 2027-05-25
ALP-EPC-00EGB-CM-OMM-0001 | OMM | ALP-EPC-00EGB-CM-CMP-0001 | CMP | IFR | 2027-05-25 | driving
ALP-EPC-00EGB-GE-RPT-0001 | RPT | ALP-EPC-00EGB-ME-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-EPC-00EGB-IC-CEM-0001 | CEM | ALP-EPC-00EGB-IC-CNR-0001 | CNR | IFR | 2027-04-27
ALP-EPC-00EGB-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00EGB-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00EGB-IC-CNR-0001 | CNR | ALP-EPC-00EGB-PR-PID-0001 | PID | IFR | 2027-04-06 | driving
ALP-EPC-00EGB-IC-DSH-0001 | DSH | ALP-EPC-00EGB-PR-PID-0001 | PID | IFR | 2027-04-06 | driving
ALP-EPC-00EGB-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00EGB-IC-HMI-0001 | HMI | ALP-EPC-00EGB-PR-PID-0001 | PID | IFR | 2027-04-06
ALP-EPC-00EGB-IC-HMI-0001 | HMI | ALP-EPC-00EGB-IC-CNR-0001 | CNR | IFR | 2027-04-27 | driving
ALP-EPC-00EGB-IC-LOG-0001 | LOG | ALP-EPC-00EGB-IC-CNR-0001 | CNR | IFR | 2027-04-27 | driving
ALP-EPC-00EGB-IC-LOG-0001 | LOG | ALP-EPC-00EGB-PR-PID-0001 | PID | IFR | 2027-04-06
ALP-EPC-00EGB-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00EGB-ME-CAL-0001 | CAL | ALP-EPC-00EGB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00EGB-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00EGB-ME-DSH-0001 | DSH | ALP-EPC-00EGB-ME-CAL-0001 | CAL | IFR | 2027-03-25
ALP-EPC-00EGB-ME-DSH-0001 | DSH | ALP-EPC-00EGB-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EGB-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00EGB-ME-MRQ-0001 | MRQ | ALP-EPC-00EGB-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00EGB-ME-MRQ-0001 | MRQ | ALP-EPC-00EGB-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EGB-ME-MRQ-0001 | MRQ | ALP-EPC-00SGA-ME-DSH-0002 | DSH | IFR | 2026-11-02
ALP-EPC-00EGB-ME-MRQ-0001 | MRQ | ALP-EPC-00SGA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00EGB-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00EGB-ME-SPC-0001 | SPC | ALP-EPC-00EGB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00EGB-ME-SPC-0001 | SPC | ALP-EPC-00SGA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00EGB-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00EGB-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00EGB-PI-ISO-0001 | ISO | ALP-EPC-00EGB-PR-PID-0001 | PID | IFR | 2027-04-06
ALP-EPC-00EGB-PI-ISO-0001 | ISO | ALP-EPC-00UEG-PI-PPL-0001 | PPL | IFR | 2027-02-26
ALP-EPC-00EGB-PI-SUP-0001 | SUP | ALP-EPC-00EGB-PI-ISO-0001 | ISO | IFC | 2027-12-13 | driving
ALP-EPC-00EGB-PR-DSH-0001 | DSH | ALP-EPC-00EGB-PR-PID-0001 | PID | IFR | 2027-04-06
ALP-EPC-00EGB-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00EGB-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EGB-PR-PID-0001 | PID | ALP-EPC-00EGB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00EGB-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00EGB-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00EGB-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00EGC-CM-CMP-0001 | CMP | ALP-EPC-00EGC-PR-PID-0001 | PID | IFR | 2027-02-19
ALP-EPC-00EGC-CM-CMP-0001 | CMP | ALP-EPC-00EGC-IC-CNR-0001 | CNR | IFR | 2027-03-15 | driving
ALP-EPC-00EGC-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00EGC-CM-MDB-0001 | MDB | ALP-EPC-00EGC-CM-CMP-0001 | CMP | IFR | 2027-04-12
ALP-EPC-00EGC-CM-OMM-0001 | OMM | ALP-EPC-00EGC-CM-CMP-0001 | CMP | IFR | 2027-04-12 | driving
ALP-EPC-00EGC-IC-CEM-0001 | CEM | ALP-EPC-00EGC-IC-CNR-0001 | CNR | IFR | 2027-03-15
ALP-EPC-00EGC-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00EGC-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00EGC-IC-CNR-0001 | CNR | ALP-EPC-00EGC-PR-PID-0001 | PID | IFR | 2027-02-19 | driving
ALP-EPC-00EGC-IC-DSH-0001 | DSH | ALP-EPC-00EGC-PR-PID-0001 | PID | IFR | 2027-02-19 | driving
ALP-EPC-00EGC-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00EGC-IC-DSH-0002 | DSH | ALP-EPC-00EGC-PR-PID-0001 | PID | IFR | 2027-02-19 | driving
ALP-EPC-00EGC-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00EGC-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00EGC-IC-HMI-0001 | HMI | ALP-EPC-00EGC-PR-PID-0001 | PID | IFR | 2027-02-19
ALP-EPC-00EGC-IC-HMI-0001 | HMI | ALP-EPC-00EGC-IC-CNR-0001 | CNR | IFR | 2027-03-15 | driving
ALP-EPC-00EGC-IC-LOG-0001 | LOG | ALP-EPC-00EGC-IC-CNR-0001 | CNR | IFR | 2027-03-15 | driving
ALP-EPC-00EGC-IC-LOG-0001 | LOG | ALP-EPC-00EGC-PR-PID-0001 | PID | IFR | 2027-02-19
ALP-EPC-00EGC-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00EGC-ME-CAL-0001 | CAL | ALP-EPC-00EGC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00EGC-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00EGC-ME-DSH-0001 | DSH | ALP-EPC-00EGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EGC-ME-DSH-0001 | DSH | ALP-EPC-00EGC-ME-CAL-0001 | CAL | IFR | 2027-02-09
ALP-EPC-00EGC-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00EGC-ME-DSH-0002 | DSH | ALP-EPC-00EGC-ME-CAL-0001 | CAL | IFR | 2027-02-09 | driving
ALP-EPC-00EGC-ME-DSH-0002 | DSH | ALP-EPC-00EGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EGC-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00EGC-ME-DSH-0003 | DSH | ALP-EPC-00EGC-ME-CAL-0001 | CAL | IFR | 2027-02-09 | driving
ALP-EPC-00EGC-ME-DSH-0003 | DSH | ALP-EPC-00EGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EGC-ME-DSH-0003 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00EGC-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00EGC-PI-ISO-0001 | ISO | ALP-EPC-00EGC-PR-PID-0001 | PID | IFR | 2027-02-19
ALP-EPC-00EGC-PI-ISO-0001 | ISO | ALP-EPC-00UEG-PI-PPL-0001 | PPL | IFR | 2027-02-26
ALP-EPC-00EGC-PI-ISO-0001 | ISO | ALP-EPC-00EGC-PI-STR-0001 | STR | IFR | 2027-07-23
ALP-EPC-00EGC-PI-STR-0001 | STR | ALP-EPC-00UEG-PI-PPL-0001 | PPL | IFR | 2027-02-26
ALP-EPC-00EGC-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00EGC-PI-SUP-0001 | SUP | ALP-EPC-00EGC-PI-ISO-0001 | ISO | IFC | 2027-09-29
ALP-EPC-00EGC-PI-SUP-0001 | SUP | ALP-EPC-00EGC-PI-STR-0001 | STR | IFC | 2027-08-13
ALP-EPC-00EGC-PR-DSH-0001 | DSH | ALP-EPC-00EGC-PR-PID-0001 | PID | IFR | 2027-02-19
ALP-EPC-00EGC-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00EGC-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EGC-PR-PID-0001 | PID | ALP-EPC-00EGC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00EGC-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00EGC-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00EGC-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00EKA-CM-CMP-0001 | CMP | ALP-EPC-00EKA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00EKA-CM-CMP-0001 | CMP | ALP-EPC-00EKA-IC-CNR-0001 | CNR | IFR | 2027-03-16 | driving
ALP-EPC-00EKA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00EKA-CM-MDB-0001 | MDB | ALP-EPC-00EKA-CM-CMP-0001 | CMP | IFR | 2027-04-13
ALP-EPC-00EKA-CM-OMM-0001 | OMM | ALP-EPC-00EKA-CM-CMP-0001 | CMP | IFR | 2027-04-13 | driving
ALP-EPC-00EKA-GE-RPT-0001 | RPT | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00EKA-IC-CEM-0001 | CEM | ALP-EPC-00EKA-IC-CNR-0001 | CNR | IFR | 2027-03-16
ALP-EPC-00EKA-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00EKA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00EKA-IC-CNR-0001 | CNR | ALP-EPC-00EKA-PR-PID-0001 | PID | IFR | 2027-02-22 | driving
ALP-EPC-00EKA-IC-DSH-0001 | DSH | ALP-EPC-00EKA-PR-PID-0001 | PID | IFR | 2027-02-22 | driving
ALP-EPC-00EKA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00EKA-IC-DSH-0002 | DSH | ALP-EPC-00EKA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00EKA-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00EKA-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00EKA-IC-HMI-0001 | HMI | ALP-EPC-00EKA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00EKA-IC-HMI-0001 | HMI | ALP-EPC-00EKA-IC-CNR-0001 | CNR | IFR | 2027-03-16 | driving
ALP-EPC-00EKA-IC-LOG-0001 | LOG | ALP-EPC-00EKA-IC-CNR-0001 | CNR | IFR | 2027-03-16 | driving
ALP-EPC-00EKA-IC-LOG-0001 | LOG | ALP-EPC-00EKA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00EKA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00EKA-ME-CAL-0001 | CAL | ALP-EPC-00EKA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00EKA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00EKA-ME-DSH-0001 | DSH | ALP-EPC-00EKA-ME-CAL-0001 | CAL | IFR | 2027-02-10
ALP-EPC-00EKA-ME-DSH-0001 | DSH | ALP-EPC-00EKA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EKA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00EKA-ME-DSH-0002 | DSH | ALP-EPC-00EKA-ME-CAL-0001 | CAL | IFR | 2027-02-10 | driving
ALP-EPC-00EKA-ME-DSH-0002 | DSH | ALP-EPC-00EKA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EKA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00EKA-ME-DSH-0003 | DSH | ALP-EPC-00EKA-ME-CAL-0001 | CAL | IFR | 2027-02-10 | driving
ALP-EPC-00EKA-ME-DSH-0003 | DSH | ALP-EPC-00EKA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EKA-ME-DSH-0003 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00EKA-ME-DSH-0004 | DSH | ALP-EPC-00EKA-ME-CAL-0001 | CAL | IFR | 2027-02-10 | driving
ALP-EPC-00EKA-ME-DSH-0004 | DSH | ALP-EPC-00EKA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EKA-ME-DSH-0004 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00EKA-ME-ITP-0001 | ITP | ALP-EPC-00EKA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | ALP-EPC-00EKA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | ALP-EPC-00EKA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | ALP-EPC-00EKA-ME-DSH-0002 | DSH | IFR | 2027-02-24
ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | ALP-EPC-00EKA-ME-DSH-0003 | DSH | IFR | 2027-02-24
ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | ALP-EPC-00EKA-ME-DSH-0004 | DSH | IFR | 2027-02-24
ALP-EPC-00EKA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00EKA-ME-SPC-0001 | SPC | ALP-EPC-00EKA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00EKA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00EKA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00EKA-PI-ISO-0001 | ISO | ALP-EPC-00EKA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00EKA-PI-ISO-0001 | ISO | ALP-EPC-00UEK-PI-PPL-0001 | PPL | IFR | 2027-03-03
ALP-EPC-00EKA-PI-ISO-0001 | ISO | ALP-EPC-00EKA-PI-STR-0001 | STR | IFR | 2027-07-06 | driving
ALP-EPC-00EKA-PI-STR-0001 | STR | ALP-EPC-00UEK-PI-PPL-0001 | PPL | IFR | 2027-03-03
ALP-EPC-00EKA-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00EKA-PI-SUP-0001 | SUP | ALP-EPC-00EKA-PI-ISO-0001 | ISO | IFC | 2027-09-07
ALP-EPC-00EKA-PI-SUP-0001 | SUP | ALP-EPC-00EKA-PI-STR-0001 | STR | IFC | 2027-07-27
ALP-EPC-00EKA-PR-DSH-0001 | DSH | ALP-EPC-00EKA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00EKA-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00EKA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EKA-PR-PID-0001 | PID | ALP-EPC-00EKA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00EKA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00EKA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00EKA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00EKC-CM-CMP-0001 | CMP | ALP-EPC-00EKC-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00EKC-CM-CMP-0001 | CMP | ALP-EPC-00EKC-IC-CNR-0001 | CNR | IFR | 2027-05-27 | driving
ALP-EPC-00EKC-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00EKC-CM-MDB-0001 | MDB | ALP-EPC-00EKC-CM-CMP-0001 | CMP | IFR | 2027-06-24
ALP-EPC-00EKC-CM-OMM-0001 | OMM | ALP-EPC-00EKC-CM-CMP-0001 | CMP | IFR | 2027-06-24 | driving
ALP-EPC-00EKC-IC-CEM-0001 | CEM | ALP-EPC-00EKC-IC-CNR-0001 | CNR | IFR | 2027-05-27
ALP-EPC-00EKC-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00EKC-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00EKC-IC-CNR-0001 | CNR | ALP-EPC-00EKC-PR-PID-0001 | PID | IFR | 2027-05-06 | driving
ALP-EPC-00EKC-IC-DSH-0001 | DSH | ALP-EPC-00EKC-PR-PID-0001 | PID | IFR | 2027-05-06 | driving
ALP-EPC-00EKC-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00EKC-IC-DSH-0002 | DSH | ALP-EPC-00EKC-PR-PID-0001 | PID | IFR | 2027-05-06 | driving
ALP-EPC-00EKC-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00EKC-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00EKC-IC-HMI-0001 | HMI | ALP-EPC-00EKC-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00EKC-IC-HMI-0001 | HMI | ALP-EPC-00EKC-IC-CNR-0001 | CNR | IFR | 2027-05-27 | driving
ALP-EPC-00EKC-IC-LOG-0001 | LOG | ALP-EPC-00EKC-IC-CNR-0001 | CNR | IFR | 2027-05-27 | driving
ALP-EPC-00EKC-IC-LOG-0001 | LOG | ALP-EPC-00EKC-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00EKC-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00EKC-ME-CAL-0001 | CAL | ALP-EPC-00EKC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00EKC-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00EKC-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00EKC-PI-ISO-0001 | ISO | ALP-EPC-00EKC-PI-STR-0001 | STR | IFR | 2027-07-23 | driving
ALP-EPC-00EKC-PI-ISO-0001 | ISO | ALP-EPC-00EKC-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00EKC-PI-ISO-0001 | ISO | ALP-EPC-00UEK-PI-PPL-0001 | PPL | IFR | 2027-03-03
ALP-EPC-00EKC-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00EKC-PI-STR-0001 | STR | ALP-EPC-00UEK-PI-PPL-0001 | PPL | IFR | 2027-03-03
ALP-EPC-00EKC-PI-STR-0001 | STR | ALP-IEC-00000-PI-LST-0001 | LST | IFR | 2026-12-28
ALP-EPC-00EKC-PI-SUP-0001 | SUP | ALP-EPC-00EKC-PI-ISO-0001 | ISO | IFC | 2027-09-24
ALP-EPC-00EKC-PI-SUP-0001 | SUP | ALP-EPC-00EKC-PI-STR-0001 | STR | IFC | 2027-08-13
ALP-EPC-00EKC-PR-DSH-0001 | DSH | ALP-EPC-00EKC-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00EKC-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00EKC-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00EKC-PR-PID-0001 | PID | ALP-EPC-00EKC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00EKC-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00EKC-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00EKC-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00GBA-CM-CMP-0001 | CMP | ALP-EPC-00GBA-PR-PID-0001 | PID | IFR | 2027-03-01
ALP-EPC-00GBA-CM-CMP-0001 | CMP | ALP-EPC-00GBA-IC-CNR-0001 | CNR | IFR | 2027-03-23 | driving
ALP-EPC-00GBA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00GBA-CM-MDB-0001 | MDB | ALP-EPC-00GBA-CM-CMP-0001 | CMP | IFR | 2027-04-20
ALP-EPC-00GBA-CM-OMM-0001 | OMM | ALP-EPC-00GBA-CM-CMP-0001 | CMP | IFR | 2027-04-20 | driving
ALP-EPC-00GBA-GE-RPT-0001 | RPT | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00GBA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00GBA-IC-CNR-0001 | CNR | ALP-EPC-00GBA-PR-PID-0001 | PID | IFR | 2027-03-01 | driving
ALP-EPC-00GBA-IC-DSH-0001 | DSH | ALP-EPC-00GBA-PR-PID-0001 | PID | IFR | 2027-03-01 | driving
ALP-EPC-00GBA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00GBA-IC-DSH-0002 | DSH | ALP-EPC-00GBA-PR-PID-0001 | PID | IFR | 2027-03-01 | driving
ALP-EPC-00GBA-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00GBA-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GBA-IC-HMI-0001 | HMI | ALP-EPC-00GBA-PR-PID-0001 | PID | IFR | 2027-03-01
ALP-EPC-00GBA-IC-HMI-0001 | HMI | ALP-EPC-00GBA-IC-CNR-0001 | CNR | IFR | 2027-03-23 | driving
ALP-EPC-00GBA-ME-CAL-0001 | CAL | ALP-EPC-00GBA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GBA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00GBA-ME-DSH-0001 | DSH | ALP-EPC-00GBA-ME-CAL-0001 | CAL | IFR | 2027-02-08
ALP-EPC-00GBA-ME-DSH-0001 | DSH | ALP-EPC-00LDA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GBA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GBA-ME-DSH-0002 | DSH | ALP-EPC-00GBA-ME-CAL-0001 | CAL | IFR | 2027-02-08 | driving
ALP-EPC-00GBA-ME-DSH-0002 | DSH | ALP-EPC-00LDA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GBA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GBA-ME-DSH-0003 | DSH | ALP-EPC-00GBA-ME-CAL-0001 | CAL | IFR | 2027-02-08 | driving
ALP-EPC-00GBA-ME-DSH-0003 | DSH | ALP-EPC-00LDA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GBA-ME-DSH-0003 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GBA-ME-DSH-0004 | DSH | ALP-EPC-00GBA-ME-CAL-0001 | CAL | IFR | 2027-02-08 | driving
ALP-EPC-00GBA-ME-DSH-0004 | DSH | ALP-EPC-00LDA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GBA-ME-DSH-0004 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GBA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00GBA-PI-ISO-0001 | ISO | ALP-EPC-00GBA-PR-PID-0001 | PID | IFR | 2027-03-01
ALP-EPC-00GBA-PI-ISO-0001 | ISO | ALP-EPC-00UGA-PI-PPL-0001 | PPL | IFR | 2027-03-03
ALP-EPC-00GBA-PI-SUP-0001 | SUP | ALP-EPC-00GBA-PI-ISO-0001 | ISO | IFC | 2027-12-28 | driving
ALP-EPC-00GBA-PR-DSH-0001 | DSH | ALP-EPC-00GBA-PR-PID-0001 | PID | IFR | 2027-03-01
ALP-EPC-00GBA-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GBA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GBA-PR-PID-0001 | PID | ALP-EPC-00GBA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GBA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GBA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00GBA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00GCA-CM-CMP-0001 | CMP | ALP-EPC-00GCA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00GCA-CM-CMP-0001 | CMP | ALP-EPC-00GCA-IC-CNR-0001 | CNR | IFR | 2027-05-27 | driving
ALP-EPC-00GCA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00GCA-CM-MDB-0001 | MDB | ALP-EPC-00GCA-CM-CMP-0001 | CMP | IFR | 2027-06-24
ALP-EPC-00GCA-CM-OMM-0001 | OMM | ALP-EPC-00GCA-CM-CMP-0001 | CMP | IFR | 2027-06-24 | driving
ALP-EPC-00GCA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00GCA-IC-CNR-0001 | CNR | ALP-EPC-00GCA-PR-PID-0001 | PID | IFR | 2027-05-06 | driving
ALP-EPC-00GCA-IC-DSH-0001 | DSH | ALP-EPC-00GCA-PR-PID-0001 | PID | IFR | 2027-05-06 | driving
ALP-EPC-00GCA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00GCA-IC-DSH-0002 | DSH | ALP-EPC-00GCA-PR-PID-0001 | PID | IFR | 2027-05-06 | driving
ALP-EPC-00GCA-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00GCA-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GCA-IC-HMI-0001 | HMI | ALP-EPC-00GCA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00GCA-IC-HMI-0001 | HMI | ALP-EPC-00GCA-IC-CNR-0001 | CNR | IFR | 2027-05-27 | driving
ALP-EPC-00GCA-ME-CAL-0001 | CAL | ALP-EPC-00GCA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GCA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00GCA-ME-DSH-0001 | DSH | ALP-EPC-00GCA-ME-CAL-0001 | CAL | IFR | 2027-02-04
ALP-EPC-00GCA-ME-DSH-0001 | DSH | ALP-EPC-00LDA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GCA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GCA-ME-DSH-0002 | DSH | ALP-EPC-00GCA-ME-CAL-0001 | CAL | IFR | 2027-02-04
ALP-EPC-00GCA-ME-DSH-0002 | DSH | ALP-EPC-00LDA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GCA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08 | driving
ALP-EPC-00GCA-ME-DSH-0003 | DSH | ALP-EPC-00GCA-ME-CAL-0001 | CAL | IFR | 2027-02-04
ALP-EPC-00GCA-ME-DSH-0003 | DSH | ALP-EPC-00LDA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GCA-ME-DSH-0003 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08 | driving
ALP-EPC-00GCA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00GCA-PI-ISO-0001 | ISO | ALP-EPC-00GCA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00GCA-PI-ISO-0001 | ISO | ALP-EPC-00UGA-PI-PPL-0001 | PPL | IFR | 2027-03-03
ALP-EPC-00GCA-PI-SUP-0001 | SUP | ALP-EPC-00GCA-PI-ISO-0001 | ISO | IFC | 2028-01-10 | driving
ALP-EPC-00GCA-PR-DSH-0001 | DSH | ALP-EPC-00GCA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00GCA-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GCA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GCA-PR-PID-0001 | PID | ALP-EPC-00GCA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GCA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GCA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00GCA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00GHA-CM-CMP-0001 | CMP | ALP-EPC-00GHA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00GHA-CM-CMP-0001 | CMP | ALP-EPC-00GHA-IC-CNR-0001 | CNR | IFR | 2027-05-27 | driving
ALP-EPC-00GHA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00GHA-CM-MDB-0001 | MDB | ALP-EPC-00GHA-CM-CMP-0001 | CMP | IFR | 2027-06-24
ALP-EPC-00GHA-CM-OMM-0001 | OMM | ALP-EPC-00GHA-CM-CMP-0001 | CMP | IFR | 2027-06-24 | driving
ALP-EPC-00GHA-GE-RPT-0001 | RPT | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00GHA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00GHA-IC-CNR-0001 | CNR | ALP-EPC-00GHA-PR-PID-0001 | PID | IFR | 2027-05-06 | driving
ALP-EPC-00GHA-IC-DSH-0001 | DSH | ALP-EPC-00GHA-PR-PID-0001 | PID | IFR | 2027-05-06 | driving
ALP-EPC-00GHA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00GHA-IC-DSH-0002 | DSH | ALP-EPC-00GHA-PR-PID-0001 | PID | IFR | 2027-05-06 | driving
ALP-EPC-00GHA-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00GHA-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GHA-IC-HMI-0001 | HMI | ALP-EPC-00GHA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00GHA-IC-HMI-0001 | HMI | ALP-EPC-00GHA-IC-CNR-0001 | CNR | IFR | 2027-05-27 | driving
ALP-EPC-00GHA-IC-LOG-0001 | LOG | ALP-EPC-00GHA-IC-CNR-0001 | CNR | IFR | 2027-05-27 | driving
ALP-EPC-00GHA-IC-LOG-0001 | LOG | ALP-EPC-00GHA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00GHA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00GHA-ME-CAL-0001 | CAL | ALP-EPC-00GHA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GHA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GHA-ME-DSH-0001 | DSH | ALP-EPC-00GHA-ME-CAL-0001 | CAL | IFR | 2027-03-12
ALP-EPC-00GHA-ME-DSH-0001 | DSH | ALP-EPC-00GHA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GHA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GHA-ME-DSH-0002 | DSH | ALP-EPC-00GHA-ME-CAL-0001 | CAL | IFR | 2027-03-12
ALP-EPC-00GHA-ME-DSH-0002 | DSH | ALP-EPC-00GHA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GHA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GHA-ME-ITP-0001 | ITP | ALP-EPC-00GHA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | ALP-EPC-00GHA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | ALP-EPC-00GHA-ME-DSH-0002 | DSH | IFR | 2026-11-02
ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | ALP-EPC-00GHA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | ALP-EPC-00GKA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | ALP-EPC-00GKA-ME-DSH-0002 | DSH | IFR | 2027-03-25
ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | ALP-EPC-00GKA-ME-DSH-0003 | DSH | IFR | 2027-03-26
ALP-EPC-00GHA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00GHA-ME-SPC-0001 | SPC | ALP-EPC-00GHA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GHA-ME-SPC-0001 | SPC | ALP-EPC-00GKA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GHA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GHA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00GHA-PI-ISO-0001 | ISO | ALP-EPC-00GHA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00GHA-PI-ISO-0001 | ISO | ALP-EPC-00UGA-PI-PPL-0001 | PPL | IFR | 2027-03-03
ALP-EPC-00GHA-PI-SUP-0001 | SUP | ALP-EPC-00GHA-PI-ISO-0001 | ISO | IFC | 2028-01-28 | driving
ALP-EPC-00GHA-PR-DSH-0001 | DSH | ALP-EPC-00GHA-PR-PID-0001 | PID | IFR | 2027-05-06
ALP-EPC-00GHA-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GHA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GHA-PR-PID-0001 | PID | ALP-EPC-00GHA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GHA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GHA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00GHA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00GKA-CM-CMP-0001 | CMP | ALP-EPC-00GKA-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00GKA-CM-CMP-0001 | CMP | ALP-EPC-00GKA-IC-CNR-0001 | CNR | IFR | 2027-07-02 | driving
ALP-EPC-00GKA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00GKA-CM-MDB-0001 | MDB | ALP-EPC-00GKA-CM-CMP-0001 | CMP | IFR | 2027-07-30
ALP-EPC-00GKA-CM-OMM-0001 | OMM | ALP-EPC-00GKA-CM-CMP-0001 | CMP | IFR | 2027-07-30 | driving
ALP-EPC-00GKA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00GKA-IC-CNR-0001 | CNR | ALP-EPC-00GKA-PR-PID-0001 | PID | IFR | 2027-06-11 | driving
ALP-EPC-00GKA-IC-DSH-0001 | DSH | ALP-EPC-00GKA-PR-PID-0001 | PID | IFR | 2027-06-11 | driving
ALP-EPC-00GKA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00GKA-IC-HMI-0001 | HMI | ALP-EPC-00GKA-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00GKA-IC-HMI-0001 | HMI | ALP-EPC-00GKA-IC-CNR-0001 | CNR | IFR | 2027-07-02 | driving
ALP-EPC-00GKA-IC-LOG-0001 | LOG | ALP-EPC-00GKA-IC-CNR-0001 | CNR | IFR | 2027-07-02
ALP-EPC-00GKA-IC-LOG-0001 | LOG | ALP-EPC-00GKA-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00GKA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00GKA-ME-CAL-0001 | CAL | ALP-EPC-00GKA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GKA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GKA-ME-DSH-0001 | DSH | ALP-EPC-00GHA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GKA-ME-DSH-0001 | DSH | ALP-EPC-00GKA-ME-CAL-0001 | CAL | IFR | 2027-03-11
ALP-EPC-00GKA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GKA-ME-DSH-0002 | DSH | ALP-EPC-00GKA-ME-CAL-0001 | CAL | IFR | 2027-03-11 | driving
ALP-EPC-00GKA-ME-DSH-0002 | DSH | ALP-EPC-00GHA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GKA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GKA-ME-DSH-0003 | DSH | ALP-EPC-00GKA-ME-CAL-0001 | CAL | IFR | 2027-03-11 | driving
ALP-EPC-00GKA-ME-DSH-0003 | DSH | ALP-EPC-00GHA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GKA-ME-DSH-0003 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GKA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00GKA-PI-ISO-0001 | ISO | ALP-EPC-00GKA-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-00GKA-PI-ISO-0001 | ISO | ALP-EPC-00UZA-PI-PPL-0001 | PPL | IFR | 2027-02-09
ALP-EPC-00GKA-PI-PPL-0001 | PPL | ALP-EPC-00GKA-PR-PID-0001 | PID | IFR | 2027-06-11 | driving
ALP-EPC-00GKA-PI-PPL-0001 | PPL | ALP-EPC-00UZC-CV-CVL-0001 | CVL | IFR | 2027-03-08
ALP-EPC-00GKA-PI-SUP-0001 | SUP | ALP-EPC-00GKA-PI-ISO-0001 | ISO | IFC | 2027-08-26 | driving
ALP-EPC-00GKA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GKA-PR-PID-0001 | PID | ALP-EPC-00GKA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GKA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GKA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00GKA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00GMA-CM-CMP-0001 | CMP | ALP-EPC-00GMA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00GMA-CM-CMP-0001 | CMP | ALP-EPC-00GMA-IC-CNR-0001 | CNR | IFR | 2027-04-21 | driving
ALP-EPC-00GMA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00GMA-CM-MDB-0001 | MDB | ALP-EPC-00GMA-CM-CMP-0001 | CMP | IFR | 2027-05-19
ALP-EPC-00GMA-CM-OMM-0001 | OMM | ALP-EPC-00GMA-CM-CMP-0001 | CMP | IFR | 2027-05-19
ALP-EPC-00GMA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00GMA-IC-CNR-0001 | CNR | ALP-EPC-00GMA-PR-PID-0001 | PID | IFR | 2027-03-31 | driving
ALP-EPC-00GMA-IC-DSH-0001 | DSH | ALP-EPC-00GMA-PR-PID-0001 | PID | IFR | 2027-03-31 | driving
ALP-EPC-00GMA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00GMA-IC-HMI-0001 | HMI | ALP-EPC-00GMA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00GMA-IC-HMI-0001 | HMI | ALP-EPC-00GMA-IC-CNR-0001 | CNR | IFR | 2027-04-21 | driving
ALP-EPC-00GMA-IC-LOG-0001 | LOG | ALP-EPC-00GMA-IC-CNR-0001 | CNR | IFR | 2027-04-21 | driving
ALP-EPC-00GMA-IC-LOG-0001 | LOG | ALP-EPC-00GMA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00GMA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00GMA-ME-CAL-0001 | CAL | ALP-EPC-00GMA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GMA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00GMA-ME-DSH-0004 | DSH | ALP-EPC-00GMA-ME-CAL-0001 | CAL | IFR | 2027-02-05
ALP-EPC-00GMA-ME-DSH-0004 | DSH | ALP-EPC-00GNA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GMA-ME-DSH-0004 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GMA-ME-DSH-0005 | DSH | ALP-EPC-00GMA-ME-CAL-0001 | CAL | IFR | 2027-02-05
ALP-EPC-00GMA-ME-DSH-0005 | DSH | ALP-EPC-00GNA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GMA-ME-DSH-0005 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GMA-ME-DSH-0006 | DSH | ALP-EPC-00GMA-ME-CAL-0001 | CAL | IFR | 2027-02-05
ALP-EPC-00GMA-ME-DSH-0006 | DSH | ALP-EPC-00GNA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GMA-ME-DSH-0006 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GMA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01 | driving
ALP-EPC-00GMA-PI-ISO-0001 | ISO | ALP-EPC-00GMA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00GMA-PI-ISO-0001 | ISO | ALP-EPC-00UZA-PI-PPL-0001 | PPL | IFR | 2027-02-09
ALP-EPC-00GMA-PI-PPL-0001 | PPL | ALP-EPC-00GMA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00GMA-PI-PPL-0001 | PPL | ALP-EPC-00UZC-CV-CVL-0001 | CVL | IFR | 2027-03-08
ALP-EPC-00GMA-PI-SUP-0001 | SUP | ALP-EPC-00GMA-PI-ISO-0001 | ISO | IFC | 2027-08-03 | driving
ALP-EPC-00GMA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GMA-PR-PID-0001 | PID | ALP-EPC-00GMA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GMA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GMA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00GMA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00GNA-CM-CMP-0001 | CMP | ALP-EPC-00GNA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00GNA-CM-CMP-0001 | CMP | ALP-EPC-00GNA-IC-CNR-0001 | CNR | IFR | 2027-04-21 | driving
ALP-EPC-00GNA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00GNA-CM-MDB-0001 | MDB | ALP-EPC-00GNA-CM-CMP-0001 | CMP | IFR | 2027-05-19
ALP-EPC-00GNA-CM-OMM-0001 | OMM | ALP-EPC-00GNA-CM-CMP-0001 | CMP | IFR | 2027-05-19
ALP-EPC-00GNA-GE-RPT-0001 | RPT | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00GNA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00GNA-IC-CNR-0001 | CNR | ALP-EPC-00GNA-PR-PID-0001 | PID | IFR | 2027-03-31 | driving
ALP-EPC-00GNA-IC-DSH-0001 | DSH | ALP-EPC-00GNA-PR-PID-0001 | PID | IFR | 2027-03-31 | driving
ALP-EPC-00GNA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00GNA-IC-DSH-0002 | DSH | ALP-EPC-00GNA-PR-PID-0001 | PID | IFR | 2027-03-31 | driving
ALP-EPC-00GNA-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00GNA-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GNA-IC-HMI-0001 | HMI | ALP-EPC-00GNA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00GNA-IC-HMI-0001 | HMI | ALP-EPC-00GNA-IC-CNR-0001 | CNR | IFR | 2027-04-21 | driving
ALP-EPC-00GNA-ME-CAL-0001 | CAL | ALP-EPC-00GNA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GNA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00GNA-ME-DSH-0001 | DSH | ALP-EPC-00GNA-ME-CAL-0001 | CAL | IFR | 2027-02-05
ALP-EPC-00GNA-ME-DSH-0001 | DSH | ALP-EPC-00GNA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GNA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GNA-ME-DSH-0002 | DSH | ALP-EPC-00GNA-ME-CAL-0001 | CAL | IFR | 2027-02-05
ALP-EPC-00GNA-ME-DSH-0002 | DSH | ALP-EPC-00GNA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GNA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GNA-ME-DSH-0003 | DSH | ALP-EPC-00GNA-ME-CAL-0001 | CAL | IFR | 2027-02-05
ALP-EPC-00GNA-ME-DSH-0003 | DSH | ALP-EPC-00GNA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GNA-ME-DSH-0003 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GNA-ME-ITP-0001 | ITP | ALP-EPC-00GNA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | ALP-EPC-00GNA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | ALP-EPC-00GNA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | ALP-EPC-00GUA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | ALP-EPC-00GNA-ME-DSH-0002 | DSH | IFR | 2027-03-10
ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | ALP-EPC-00GNA-ME-DSH-0003 | DSH | IFR | 2027-03-10
ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | ALP-EPC-00GUA-ME-DSH-0002 | DSH | IFR | 2027-03-08
ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | ALP-EPC-00GMA-ME-DSH-0004 | DSH | IFR | 2027-03-05
ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | ALP-EPC-00GMA-ME-DSH-0005 | DSH | IFR | 2027-03-03
ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | ALP-EPC-00GMA-ME-DSH-0006 | DSH | IFR | 2027-03-08
ALP-EPC-00GNA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00GNA-ME-SPC-0001 | SPC | ALP-EPC-00GNA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GNA-ME-SPC-0001 | SPC | ALP-EPC-00GUA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GNA-ME-SPC-0001 | SPC | ALP-EPC-00GMA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GNA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GNA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00GNA-PI-ISO-0001 | ISO | ALP-EPC-00GNA-PR-PID-0001 | PID | IFR | 2027-03-31
ALP-EPC-00GNA-PI-ISO-0001 | ISO | ALP-EPC-00UGA-PI-PPL-0001 | PPL | IFR | 2027-03-03
ALP-EPC-00GNA-PI-SUP-0001 | SUP | ALP-EPC-00GNA-PI-ISO-0001 | ISO | IFC | 2028-01-18 | driving
ALP-EPC-00GNA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GNA-PR-PID-0001 | PID | ALP-EPC-00GNA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GNA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GNA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00GNA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00GUA-CM-CMP-0001 | CMP | ALP-EPC-00GUA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00GUA-CM-CMP-0001 | CMP | ALP-EPC-00GUA-IC-CNR-0001 | CNR | IFR | 2027-07-05 | driving
ALP-EPC-00GUA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00GUA-CM-MDB-0001 | MDB | ALP-EPC-00GUA-CM-CMP-0001 | CMP | IFR | 2027-08-02
ALP-EPC-00GUA-CM-OMM-0001 | OMM | ALP-EPC-00GUA-CM-CMP-0001 | CMP | IFR | 2027-08-02 | driving
ALP-EPC-00GUA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00GUA-IC-CNR-0001 | CNR | ALP-EPC-00GUA-PR-PID-0001 | PID | IFR | 2027-06-14 | driving
ALP-EPC-00GUA-IC-DSH-0001 | DSH | ALP-EPC-00GUA-PR-PID-0001 | PID | IFR | 2027-06-14 | driving
ALP-EPC-00GUA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00GUA-IC-HMI-0001 | HMI | ALP-EPC-00GUA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00GUA-IC-HMI-0001 | HMI | ALP-EPC-00GUA-IC-CNR-0001 | CNR | IFR | 2027-07-05 | driving
ALP-EPC-00GUA-ME-CAL-0001 | CAL | ALP-EPC-00GUA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GUA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00GUA-ME-DSH-0001 | DSH | ALP-EPC-00GNA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GUA-ME-DSH-0001 | DSH | ALP-EPC-00GUA-ME-CAL-0001 | CAL | IFR | 2027-02-02
ALP-EPC-00GUA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GUA-ME-DSH-0002 | DSH | ALP-EPC-00GUA-ME-CAL-0001 | CAL | IFR | 2027-02-02
ALP-EPC-00GUA-ME-DSH-0002 | DSH | ALP-EPC-00GNA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GUA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00GUA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00GUA-PI-ISO-0001 | ISO | ALP-EPC-00GUA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-00GUA-PI-ISO-0001 | ISO | ALP-EPC-00UGA-PI-PPL-0001 | PPL | IFR | 2027-03-03
ALP-EPC-00GUA-PI-SUP-0001 | SUP | ALP-EPC-00GUA-PI-ISO-0001 | ISO | IFC | 2028-02-04 | driving
ALP-EPC-00GUA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00GUA-PR-PID-0001 | PID | ALP-EPC-00GUA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00GUA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00GUA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00GUA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00LBG-CM-CMP-0001 | CMP | ALP-EPC-00LBG-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00LBG-CM-CMP-0001 | CMP | ALP-EPC-00LBG-IC-CNR-0001 | CNR | IFR | 2027-05-28
ALP-EPC-00LBG-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00LBG-CM-MDB-0001 | MDB | ALP-EPC-00LBG-CM-CMP-0001 | CMP | IFR | 2027-08-30
ALP-EPC-00LBG-CM-OMM-0001 | OMM | ALP-EPC-00LBG-CM-CMP-0001 | CMP | IFR | 2027-08-30
ALP-EPC-00LBG-IC-CEM-0001 | CEM | ALP-EPC-00LBG-IC-CNR-0001 | CNR | IFR | 2027-05-28
ALP-EPC-00LBG-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00LBG-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00LBG-IC-CNR-0001 | CNR | ALP-EPC-00LBG-PR-PID-0001 | PID | IFR | 2027-05-07 | driving
ALP-EPC-00LBG-IC-DSH-0001 | DSH | ALP-EPC-00LBG-PR-PID-0001 | PID | IFR | 2027-05-07 | driving
ALP-EPC-00LBG-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00LBG-IC-DSH-0002 | DSH | ALP-EPC-00LBG-PR-PID-0001 | PID | IFR | 2027-05-07 | driving
ALP-EPC-00LBG-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00LBG-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00LBG-IC-HMI-0001 | HMI | ALP-EPC-00LBG-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00LBG-IC-HMI-0001 | HMI | ALP-EPC-00LBG-IC-CNR-0001 | CNR | IFR | 2027-05-28 | driving
ALP-EPC-00LBG-IC-LOG-0001 | LOG | ALP-EPC-00LBG-IC-CNR-0001 | CNR | IFR | 2027-05-28
ALP-EPC-00LBG-IC-LOG-0001 | LOG | ALP-EPC-00LBG-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00LBG-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00LBG-ME-CAL-0001 | CAL | ALP-EPC-00LBG-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00LBG-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00LBG-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00LBG-PI-ISO-0001 | ISO | ALP-EPC-00LBG-PI-STR-0001 | STR | IFR | 2027-08-18
ALP-EPC-00LBG-PI-ISO-0001 | ISO | ALP-EPC-00LBG-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00LBG-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-00LBG-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-00LBG-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19
ALP-EPC-00LBG-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00LBG-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-00LBG-PI-STR-0001 | STR | ALP-IEC-00000-PI-LST-0001 | LST | IFR | 2026-12-28
ALP-EPC-00LBG-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-00LBG-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19 | driving
ALP-EPC-00LBG-PI-SUP-0001 | SUP | ALP-EPC-00LBG-PI-ISO-0001 | ISO | IFC | 2027-11-02
ALP-EPC-00LBG-PI-SUP-0001 | SUP | ALP-EPC-00LBG-PI-STR-0001 | STR | IFC | 2027-09-08
ALP-EPC-00LBG-PR-DSH-0001 | DSH | ALP-EPC-00LBG-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00LBG-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00LBG-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00LBG-PR-PID-0001 | PID | ALP-EPC-00LBG-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00LBG-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00LBG-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00LBG-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00LDA-CM-CMP-0001 | CMP | ALP-EPC-00LDA-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00LDA-CM-CMP-0001 | CMP | ALP-EPC-00LDA-IC-CNR-0001 | CNR | IFR | 2027-05-28 | driving
ALP-EPC-00LDA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00LDA-CM-MDB-0001 | MDB | ALP-EPC-00LDA-CM-CMP-0001 | CMP | IFR | 2027-06-25
ALP-EPC-00LDA-CM-OMM-0001 | OMM | ALP-EPC-00LDA-CM-CMP-0001 | CMP | IFR | 2027-06-25 | driving
ALP-EPC-00LDA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00LDA-IC-CNR-0001 | CNR | ALP-EPC-00LDA-PR-PID-0001 | PID | IFR | 2027-05-07 | driving
ALP-EPC-00LDA-IC-DSH-0001 | DSH | ALP-EPC-00LDA-PR-PID-0001 | PID | IFR | 2027-05-07 | driving
ALP-EPC-00LDA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00LDA-IC-DSH-0002 | DSH | ALP-EPC-00LDA-PR-PID-0001 | PID | IFR | 2027-05-07 | driving
ALP-EPC-00LDA-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00LDA-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00LDA-IC-HMI-0001 | HMI | ALP-EPC-00LDA-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00LDA-IC-HMI-0001 | HMI | ALP-EPC-00LDA-IC-CNR-0001 | CNR | IFR | 2027-05-28
ALP-EPC-00LDA-ME-CAL-0001 | CAL | ALP-EPC-00LDA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00LDA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00LDA-ME-DSH-0001 | DSH | ALP-EPC-00LDA-ME-CAL-0001 | CAL | IFR | 2027-02-04
ALP-EPC-00LDA-ME-DSH-0001 | DSH | ALP-EPC-00LDA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00LDA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00LDA-ME-DSH-0002 | DSH | ALP-EPC-00LDA-ME-CAL-0001 | CAL | IFR | 2027-02-04
ALP-EPC-00LDA-ME-DSH-0002 | DSH | ALP-EPC-00LDA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00LDA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08 | driving
ALP-EPC-00LDA-ME-ITP-0001 | ITP | ALP-EPC-00LDA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | ALP-EPC-00GBA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | ALP-EPC-00GCA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | ALP-EPC-00LDA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | ALP-EPC-00LDA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | ALP-EPC-00GBA-ME-DSH-0002 | DSH | IFR | 2027-02-24
ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | ALP-EPC-00GBA-ME-DSH-0003 | DSH | IFR | 2027-02-24
ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | ALP-EPC-00GBA-ME-DSH-0004 | DSH | IFR | 2027-02-22
ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | ALP-EPC-00GCA-ME-DSH-0002 | DSH | IFR | 2027-02-24
ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | ALP-EPC-00GCA-ME-DSH-0003 | DSH | IFR | 2027-02-22
ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | ALP-EPC-00LDA-ME-DSH-0002 | DSH | IFR | 2027-02-22
ALP-EPC-00LDA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00LDA-ME-SPC-0001 | SPC | ALP-EPC-00LDA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00LDA-ME-SPC-0001 | SPC | ALP-EPC-00GBA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00LDA-ME-SPC-0001 | SPC | ALP-EPC-00GCA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00LDA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00LDA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00LDA-PI-ISO-0001 | ISO | ALP-EPC-00LDA-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00LDA-PI-ISO-0001 | ISO | ALP-EPC-00UGA-PI-PPL-0001 | PPL | IFR | 2027-03-03
ALP-EPC-00LDA-PI-SUP-0001 | SUP | ALP-EPC-00LDA-PI-ISO-0001 | ISO | IFC | 2028-01-19 | driving
ALP-EPC-00LDA-PR-DSH-0001 | DSH | ALP-EPC-00LDA-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00LDA-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00LDA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00LDA-PR-PID-0001 | PID | ALP-EPC-00LDA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00LDA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00LDA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00LDA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00PAA-CM-CMP-0001 | CMP | ALP-EPC-00PAA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00PAA-CM-CMP-0001 | CMP | ALP-EPC-00PAA-IC-CNR-0001 | CNR | IFR | 2027-04-22 | driving
ALP-EPC-00PAA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00PAA-CM-MDB-0001 | MDB | ALP-EPC-00PAA-CM-CMP-0001 | CMP | IFR | 2027-05-20
ALP-EPC-00PAA-CM-OMM-0001 | OMM | ALP-EPC-00PAA-CM-CMP-0001 | CMP | IFR | 2027-05-20
ALP-EPC-00PAA-GE-RPT-0001 | RPT | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00PAA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00PAA-IC-CNR-0001 | CNR | ALP-EPC-00PAA-PR-PID-0001 | PID | IFR | 2027-04-01 | driving
ALP-EPC-00PAA-IC-DSH-0001 | DSH | ALP-EPC-00PAA-PR-PID-0001 | PID | IFR | 2027-04-01 | driving
ALP-EPC-00PAA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00PAA-IC-HMI-0001 | HMI | ALP-EPC-00PAA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00PAA-IC-HMI-0001 | HMI | ALP-EPC-00PAA-IC-CNR-0001 | CNR | IFR | 2027-04-22
ALP-EPC-00PAA-IC-LOG-0001 | LOG | ALP-EPC-00PAA-IC-CNR-0001 | CNR | IFR | 2027-04-22
ALP-EPC-00PAA-IC-LOG-0001 | LOG | ALP-EPC-00PAA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00PAA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00PAA-ME-CAL-0001 | CAL | ALP-EPC-00PAA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PAA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00PAA-ME-DSH-0001 | DSH | ALP-EPC-00PAA-ME-CAL-0001 | CAL | IFR | 2027-02-08
ALP-EPC-00PAA-ME-DSH-0001 | DSH | ALP-EPC-00PAA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PAA-ME-DSH-0002 | DSH | ALP-EPC-00PAA-ME-CAL-0001 | CAL | IFR | 2027-02-08
ALP-EPC-00PAA-ME-DSH-0002 | DSH | ALP-EPC-00PAA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PAA-ME-DSH-0003 | DSH | ALP-EPC-00PAA-ME-CAL-0001 | CAL | IFR | 2027-02-08
ALP-EPC-00PAA-ME-DSH-0003 | DSH | ALP-EPC-00PAA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAA-ME-DSH-0003 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PAA-ME-ITP-0001 | ITP | ALP-EPC-00PAA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | ALP-EPC-00PAA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | ALP-EPC-00PAA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | ALP-EPC-00PAA-ME-DSH-0002 | DSH | IFR | 2027-03-10
ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | ALP-EPC-00PAA-ME-DSH-0003 | DSH | IFR | 2027-03-10
ALP-EPC-00PAA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00PAA-ME-SPC-0001 | SPC | ALP-EPC-00PAA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PAA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PAA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00PAA-PI-ISO-0001 | ISO | ALP-EPC-00PAA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00PAA-PI-ISO-0001 | ISO | ALP-EPC-00UPC-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-00PAA-PI-SUP-0001 | SUP | ALP-EPC-00PAA-PI-ISO-0001 | ISO | IFC | 2027-08-26 | driving
ALP-EPC-00PAA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAA-PR-PID-0001 | PID | ALP-EPC-00PAA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PAA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00PAA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00PAA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00PAA-PR-STU-0001 | STU | ALP-EPC-00PAA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PAB-CM-CMP-0001 | CMP | ALP-EPC-00PAB-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00PAB-CM-CMP-0001 | CMP | ALP-EPC-00PAB-IC-CNR-0001 | CNR | IFR | 2027-05-28 | driving
ALP-EPC-00PAB-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00PAB-CM-MDB-0001 | MDB | ALP-EPC-00PAB-CM-CMP-0001 | CMP | IFR | 2027-06-25
ALP-EPC-00PAB-CM-OMM-0001 | OMM | ALP-EPC-00PAB-CM-CMP-0001 | CMP | IFR | 2027-06-25 | driving
ALP-EPC-00PAB-GE-RPT-0001 | RPT | ALP-EPC-00000-PI-MRQ-0004 | MRQ | IFR | 2026-11-02
ALP-EPC-00PAB-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00PAB-IC-CNR-0001 | CNR | ALP-EPC-00PAB-PR-PID-0001 | PID | IFR | 2027-05-07 | driving
ALP-EPC-00PAB-IC-DSH-0001 | DSH | ALP-EPC-00PAB-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00PAB-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00PAB-IC-HMI-0001 | HMI | ALP-EPC-00PAB-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00PAB-IC-HMI-0001 | HMI | ALP-EPC-00PAB-IC-CNR-0001 | CNR | IFR | 2027-05-28
ALP-EPC-00PAB-IC-LOG-0001 | LOG | ALP-EPC-00PAB-IC-CNR-0001 | CNR | IFR | 2027-05-28
ALP-EPC-00PAB-IC-LOG-0001 | LOG | ALP-EPC-00PAB-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00PAB-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00PAB-ME-CAL-0001 | CAL | ALP-EPC-00PAB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PAB-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00PAB-ME-DSH-0001 | DSH | ALP-EPC-00PAB-ME-CAL-0001 | CAL | IFR | 2027-02-02
ALP-EPC-00PAB-ME-DSH-0001 | DSH | ALP-EPC-00000-PI-SPC-0007 | SPC | IFR | 2026-11-30
ALP-EPC-00PAB-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08 | driving
ALP-EPC-00PAB-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00PAB-PI-ISO-0001 | ISO | ALP-EPC-00PAB-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00PAB-PI-ISO-0001 | ISO | ALP-EPC-00UPC-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-00PAB-PI-ISO-0001 | ISO | ALP-EPC-00PAB-PI-STR-0001 | STR | IFR | 2027-06-09
ALP-EPC-00PAB-PI-PPL-0001 | PPL | ALP-EPC-00PAB-PR-PID-0001 | PID | IFR | 2027-05-07
ALP-EPC-00PAB-PI-PPL-0001 | PPL | ALP-EPC-00UZC-CV-CVL-0001 | CVL | IFR | 2027-03-08
ALP-EPC-00PAB-PI-STR-0001 | STR | ALP-EPC-00UPC-PI-PPL-0001 | PPL | IFR | 2027-05-11 | driving
ALP-EPC-00PAB-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00PAB-PI-SUP-0001 | SUP | ALP-EPC-00PAB-PI-ISO-0001 | ISO | IFC | 2027-08-26 | driving
ALP-EPC-00PAB-PI-SUP-0001 | SUP | ALP-EPC-00PAB-PI-STR-0001 | STR | IFC | 2027-06-30
ALP-EPC-00PAB-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAB-PR-PID-0001 | PID | ALP-EPC-00PAB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PAB-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00PAB-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00PAB-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00PAB-PR-STU-0001 | STU | ALP-EPC-00PAB-ME-CAL-0001 | CAL | IFR | 2027-02-02
ALP-EPC-00PAB-PR-STU-0001 | STU | ALP-EPC-00PAC-ME-CAL-0001 | CAL | IFR | 2027-02-02
ALP-EPC-00PAC-CM-CMP-0001 | CMP | ALP-EPC-00PAC-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00PAC-CM-CMP-0001 | CMP | ALP-EPC-00PAC-IC-CNR-0001 | CNR | IFR | 2027-05-31 | driving
ALP-EPC-00PAC-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00PAC-CM-MDB-0001 | MDB | ALP-EPC-00PAC-CM-CMP-0001 | CMP | IFR | 2027-06-28
ALP-EPC-00PAC-CM-OMM-0001 | OMM | ALP-EPC-00PAC-CM-CMP-0001 | CMP | IFR | 2027-06-28 | driving
ALP-EPC-00PAC-GE-RPT-0001 | RPT | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00PAC-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00PAC-IC-CNR-0001 | CNR | ALP-EPC-00PAC-PR-PID-0001 | PID | IFR | 2027-05-10 | driving
ALP-EPC-00PAC-IC-DSH-0001 | DSH | ALP-EPC-00PAC-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00PAC-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00PAC-IC-HMI-0001 | HMI | ALP-EPC-00PAC-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00PAC-IC-HMI-0001 | HMI | ALP-EPC-00PAC-IC-CNR-0001 | CNR | IFR | 2027-05-31
ALP-EPC-00PAC-IC-LOG-0001 | LOG | ALP-EPC-00PAC-IC-CNR-0001 | CNR | IFR | 2027-05-31
ALP-EPC-00PAC-IC-LOG-0001 | LOG | ALP-EPC-00PAC-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00PAC-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00PAC-ME-CAL-0001 | CAL | ALP-EPC-00PAC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PAC-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00PAC-ME-DSH-0001 | DSH | ALP-EPC-00PAC-ME-CAL-0001 | CAL | IFR | 2027-02-02
ALP-EPC-00PAC-ME-DSH-0001 | DSH | ALP-EPC-00PAC-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAC-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PAC-ME-ITP-0001 | ITP | ALP-EPC-00PAC-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | ALP-EPC-00PAC-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | ALP-EPC-00PAC-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAC-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00PAC-ME-SPC-0001 | SPC | ALP-EPC-00PAC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PAC-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PAC-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00PAC-PI-ISO-0001 | ISO | ALP-EPC-00PAC-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00PAC-PI-ISO-0001 | ISO | ALP-EPC-00UPC-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-00PAC-PI-SUP-0001 | SUP | ALP-EPC-00PAC-PI-ISO-0001 | ISO | IFC | 2027-08-26 | driving
ALP-EPC-00PAC-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAC-PR-PID-0001 | PID | ALP-EPC-00PAC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PAC-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00PAC-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00PAC-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00PAH-CM-CMP-0001 | CMP | ALP-EPC-00PAH-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00PAH-CM-CMP-0001 | CMP | ALP-EPC-00PAH-IC-CNR-0001 | CNR | IFR | 2027-05-31 | driving
ALP-EPC-00PAH-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00PAH-CM-MDB-0001 | MDB | ALP-EPC-00PAH-CM-CMP-0001 | CMP | IFR | 2027-06-28
ALP-EPC-00PAH-CM-OMM-0001 | OMM | ALP-EPC-00PAH-CM-CMP-0001 | CMP | IFR | 2027-06-28 | driving
ALP-EPC-00PAH-GE-RPT-0001 | RPT | ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00PAH-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00PAH-IC-CNR-0001 | CNR | ALP-EPC-00PAH-PR-PID-0001 | PID | IFR | 2027-05-10 | driving
ALP-EPC-00PAH-IC-DSH-0001 | DSH | ALP-EPC-00PAH-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00PAH-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00PAH-IC-HMI-0001 | HMI | ALP-EPC-00PAH-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00PAH-IC-HMI-0001 | HMI | ALP-EPC-00PAH-IC-CNR-0001 | CNR | IFR | 2027-05-31
ALP-EPC-00PAH-IC-LOG-0001 | LOG | ALP-EPC-00PAH-IC-CNR-0001 | CNR | IFR | 2027-05-31
ALP-EPC-00PAH-IC-LOG-0001 | LOG | ALP-EPC-00PAH-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00PAH-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00PAH-ME-CAL-0001 | CAL | ALP-EPC-00PAH-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PAH-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00PAH-ME-DSH-0001 | DSH | ALP-EPC-00PAH-ME-CAL-0001 | CAL | IFR | 2027-03-16
ALP-EPC-00PAH-ME-DSH-0001 | DSH | ALP-EPC-00PAH-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAH-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PAH-ME-DSH-0002 | DSH | ALP-EPC-00PAH-ME-CAL-0001 | CAL | IFR | 2027-03-16 | driving
ALP-EPC-00PAH-ME-DSH-0002 | DSH | ALP-EPC-00PAH-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAH-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PAH-ME-DSH-0003 | DSH | ALP-EPC-00PAH-ME-CAL-0001 | CAL | IFR | 2027-03-16 | driving
ALP-EPC-00PAH-ME-DSH-0003 | DSH | ALP-EPC-00PAH-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAH-ME-DSH-0003 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PAH-ME-ITP-0001 | ITP | ALP-EPC-00PAH-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | ALP-EPC-00PAH-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | ALP-EPC-00PAH-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | ALP-EPC-00PAH-ME-DSH-0002 | DSH | IFR | 2027-03-30
ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | ALP-EPC-00PAH-ME-DSH-0003 | DSH | IFR | 2027-03-30
ALP-EPC-00PAH-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00PAH-ME-SPC-0001 | SPC | ALP-EPC-00PAH-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PAH-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PAH-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00PAH-PI-ISO-0001 | ISO | ALP-EPC-00PAH-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00PAH-PI-ISO-0001 | ISO | ALP-EPC-20UMB-PI-PPL-0001 | PPL | IFR | 2027-05-10
ALP-EPC-00PAH-PI-SUP-0001 | SUP | ALP-EPC-00PAH-PI-ISO-0001 | ISO | IFC | 2028-02-14 | driving
ALP-EPC-00PAH-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PAH-PR-PID-0001 | PID | ALP-EPC-00PAH-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PAH-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00PAH-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00PAH-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00PBA-CM-CMP-0001 | CMP | ALP-EPC-00PBA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00PBA-CM-CMP-0001 | CMP | ALP-EPC-00PBA-IC-CNR-0001 | CNR | IFR | 2027-04-22 | driving
ALP-EPC-00PBA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00PBA-CM-MDB-0001 | MDB | ALP-EPC-00PBA-CM-CMP-0001 | CMP | IFR | 2027-05-20
ALP-EPC-00PBA-CM-OMM-0001 | OMM | ALP-EPC-00PBA-CM-CMP-0001 | CMP | IFR | 2027-05-20
ALP-EPC-00PBA-GE-RPT-0001 | RPT | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00PBA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00PBA-IC-CNR-0001 | CNR | ALP-EPC-00PBA-PR-PID-0001 | PID | IFR | 2027-04-01 | driving
ALP-EPC-00PBA-IC-DSH-0001 | DSH | ALP-EPC-00PBA-PR-PID-0001 | PID | IFR | 2027-04-01 | driving
ALP-EPC-00PBA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00PBA-IC-DSH-0002 | DSH | ALP-EPC-00PBA-PR-PID-0001 | PID | IFR | 2027-04-01 | driving
ALP-EPC-00PBA-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00PBA-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00PBA-IC-HMI-0001 | HMI | ALP-EPC-00PBA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00PBA-IC-HMI-0001 | HMI | ALP-EPC-00PBA-IC-CNR-0001 | CNR | IFR | 2027-04-22
ALP-EPC-00PBA-ME-CAL-0001 | CAL | ALP-EPC-00PBA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PBA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00PBA-ME-DSH-0001 | DSH | ALP-EPC-00PBA-ME-CAL-0001 | CAL | IFR | 2027-02-04
ALP-EPC-00PBA-ME-DSH-0001 | DSH | ALP-EPC-00PBA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PBA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PBA-ME-DSH-0002 | DSH | ALP-EPC-00PBA-ME-CAL-0001 | CAL | IFR | 2027-02-04
ALP-EPC-00PBA-ME-DSH-0002 | DSH | ALP-EPC-00PBA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PBA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PBA-ME-DSH-0003 | DSH | ALP-EPC-00PBA-ME-CAL-0001 | CAL | IFR | 2027-02-04
ALP-EPC-00PBA-ME-DSH-0003 | DSH | ALP-EPC-00PBA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PBA-ME-DSH-0003 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PBA-ME-DSH-0004 | DSH | ALP-EPC-00PBA-ME-CAL-0001 | CAL | IFR | 2027-02-04
ALP-EPC-00PBA-ME-DSH-0004 | DSH | ALP-EPC-00PBA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PBA-ME-DSH-0004 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PBA-ME-DSH-0005 | DSH | ALP-EPC-00PBA-ME-CAL-0001 | CAL | IFR | 2027-02-04
ALP-EPC-00PBA-ME-DSH-0005 | DSH | ALP-EPC-00PBA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PBA-ME-DSH-0005 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PBA-ME-ITP-0001 | ITP | ALP-EPC-00PBA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | ALP-EPC-00PBA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | ALP-EPC-00PBA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | ALP-EPC-00PBA-ME-DSH-0002 | DSH | IFR | 2027-03-10
ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | ALP-EPC-00PBA-ME-DSH-0003 | DSH | IFR | 2027-03-10
ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | ALP-EPC-00PBA-ME-DSH-0004 | DSH | IFR | 2027-03-12
ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | ALP-EPC-00PBA-ME-DSH-0005 | DSH | IFR | 2027-03-10
ALP-EPC-00PBA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00PBA-ME-SPC-0001 | SPC | ALP-EPC-00PBA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PBA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PBA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00PBA-PI-ISO-0001 | ISO | ALP-EPC-00PBA-PR-PID-0001 | PID | IFR | 2027-04-01
ALP-EPC-00PBA-PI-ISO-0001 | ISO | ALP-EPC-00UPC-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-00PBA-PI-SUP-0001 | SUP | ALP-EPC-00PBA-PI-ISO-0001 | ISO | IFC | 2027-08-25 | driving
ALP-EPC-00PBA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PBA-PR-PID-0001 | PID | ALP-EPC-00PBA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PBA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00PBA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00PBA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00PGA-CM-CMP-0001 | CMP | ALP-EPC-00PGA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00PGA-CM-CMP-0001 | CMP | ALP-EPC-00PGA-IC-CNR-0001 | CNR | IFR | 2027-03-16 | driving
ALP-EPC-00PGA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00PGA-CM-MDB-0001 | MDB | ALP-EPC-00PGA-CM-CMP-0001 | CMP | IFR | 2027-04-13
ALP-EPC-00PGA-CM-OMM-0001 | OMM | ALP-EPC-00PGA-CM-CMP-0001 | CMP | IFR | 2027-04-13 | driving
ALP-EPC-00PGA-GE-RPT-0001 | RPT | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00PGA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00PGA-IC-CNR-0001 | CNR | ALP-EPC-00PGA-PR-PID-0001 | PID | IFR | 2027-02-22 | driving
ALP-EPC-00PGA-IC-DSH-0001 | DSH | ALP-EPC-00PGA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00PGA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00PGA-IC-DSH-0002 | DSH | ALP-EPC-00PGA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00PGA-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00PGA-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00PGA-IC-HMI-0001 | HMI | ALP-EPC-00PGA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00PGA-IC-HMI-0001 | HMI | ALP-EPC-00PGA-IC-CNR-0001 | CNR | IFR | 2027-03-16 | driving
ALP-EPC-00PGA-IC-LOG-0001 | LOG | ALP-EPC-00PGA-IC-CNR-0001 | CNR | IFR | 2027-03-16
ALP-EPC-00PGA-IC-LOG-0001 | LOG | ALP-EPC-00PGA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00PGA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00PGA-ME-CAL-0001 | CAL | ALP-EPC-00PGA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PGA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00PGA-ME-DSH-0001 | DSH | ALP-EPC-00PGA-ME-CAL-0001 | CAL | IFR | 2027-02-12
ALP-EPC-00PGA-ME-DSH-0001 | DSH | ALP-EPC-00PGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PGA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PGA-ME-DSH-0002 | DSH | ALP-EPC-00PGA-ME-CAL-0001 | CAL | IFR | 2027-02-12
ALP-EPC-00PGA-ME-DSH-0002 | DSH | ALP-EPC-00PGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PGA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PGA-ME-DSH-0003 | DSH | ALP-EPC-00PGA-ME-CAL-0001 | CAL | IFR | 2027-02-12
ALP-EPC-00PGA-ME-DSH-0003 | DSH | ALP-EPC-00PGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PGA-ME-DSH-0003 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PGA-ME-DSH-0004 | DSH | ALP-EPC-00PGA-ME-CAL-0001 | CAL | IFR | 2027-02-12
ALP-EPC-00PGA-ME-DSH-0004 | DSH | ALP-EPC-00PGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PGA-ME-DSH-0004 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PGA-ME-ITP-0001 | ITP | ALP-EPC-00PGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | ALP-EPC-00PGA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | ALP-EPC-00PGA-ME-DSH-0002 | DSH | IFR | 2026-11-02
ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | ALP-EPC-00PGA-ME-DSH-0003 | DSH | IFR | 2026-11-02
ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | ALP-EPC-00PGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | ALP-EPC-00PGA-ME-DSH-0004 | DSH | IFR | 2027-03-08
ALP-EPC-00PGA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00PGA-ME-SPC-0001 | SPC | ALP-EPC-00PGA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PGA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00PGA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00PGA-PI-ISO-0001 | ISO | ALP-EPC-00PGA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00PGA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-00PGA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-00PGA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19
ALP-EPC-00PGA-PI-ISO-0001 | ISO | ALP-EPC-00PGA-PI-STR-0001 | STR | IFR | 2027-08-17
ALP-EPC-00PGA-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-00PGA-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-00PGA-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19 | driving
ALP-EPC-00PGA-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00PGA-PI-SUP-0001 | SUP | ALP-EPC-00PGA-PI-ISO-0001 | ISO | IFC | 2027-10-20
ALP-EPC-00PGA-PI-SUP-0001 | SUP | ALP-EPC-00PGA-PI-STR-0001 | STR | IFC | 2027-09-07
ALP-EPC-00PGA-PR-DSH-0001 | DSH | ALP-EPC-00PGA-PR-PID-0001 | PID | IFR | 2027-02-22
ALP-EPC-00PGA-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00PGA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00PGA-PR-PID-0001 | PID | ALP-EPC-00PGA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00PGA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00PGA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00PGA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00QCA-CM-CMP-0001 | CMP | ALP-EPC-00QCA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QCA-CM-CMP-0001 | CMP | ALP-EPC-00QCA-IC-CNR-0001 | CNR | IFR | 2027-04-23 | driving
ALP-EPC-00QCA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00QCA-CM-MDB-0001 | MDB | ALP-EPC-00QCA-CM-CMP-0001 | CMP | IFR | 2027-05-21
ALP-EPC-00QCA-CM-OMM-0001 | OMM | ALP-EPC-00QCA-CM-CMP-0001 | CMP | IFR | 2027-05-21
ALP-EPC-00QCA-GE-RPT-0001 | RPT | ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | IFR | 2027-04-13
ALP-EPC-00QCA-IC-CEM-0001 | CEM | ALP-EPC-00QCA-IC-CNR-0001 | CNR | IFR | 2027-04-23
ALP-EPC-00QCA-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00QCA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00QCA-IC-CNR-0001 | CNR | ALP-EPC-00QCA-PR-PID-0001 | PID | IFR | 2027-04-02 | driving
ALP-EPC-00QCA-IC-DSH-0001 | DSH | ALP-EPC-00QCA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QCA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00QCA-IC-HMI-0001 | HMI | ALP-EPC-00QCA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QCA-IC-HMI-0001 | HMI | ALP-EPC-00QCA-IC-CNR-0001 | CNR | IFR | 2027-04-23
ALP-EPC-00QCA-IC-LOG-0001 | LOG | ALP-EPC-00QCA-IC-CNR-0001 | CNR | IFR | 2027-04-23
ALP-EPC-00QCA-IC-LOG-0001 | LOG | ALP-EPC-00QCA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QCA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00QCA-ME-CAL-0001 | CAL | ALP-EPC-00QCA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QCA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QCA-ME-DSH-0001 | DSH | ALP-EPC-00QCA-ME-CAL-0001 | CAL | IFR | 2027-03-19
ALP-EPC-00QCA-ME-DSH-0001 | DSH | ALP-EPC-00QCA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QCA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QCA-ME-DSH-0002 | DSH | ALP-EPC-00QCA-ME-CAL-0001 | CAL | IFR | 2027-03-19 | driving
ALP-EPC-00QCA-ME-DSH-0002 | DSH | ALP-EPC-00QCA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QCA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QCA-ME-DSH-0003 | DSH | ALP-EPC-00QCA-ME-CAL-0001 | CAL | IFR | 2027-03-19 | driving
ALP-EPC-00QCA-ME-DSH-0003 | DSH | ALP-EPC-00QCA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QCA-ME-DSH-0003 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QCA-ME-ITP-0001 | ITP | ALP-EPC-00QCA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | ALP-EPC-00QCA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | ALP-EPC-00QCA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | ALP-EPC-00QCA-ME-DSH-0002 | DSH | IFR | 2027-04-06 | driving
ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | ALP-EPC-00QCA-ME-DSH-0003 | DSH | IFR | 2027-04-05
ALP-EPC-00QCA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00QCA-ME-SPC-0001 | SPC | ALP-EPC-00QCA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QCA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QCA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00QCA-PI-ISO-0001 | ISO | ALP-EPC-00QCA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QCA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-00QCA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-00QCA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19
ALP-EPC-00QCA-PI-SUP-0001 | SUP | ALP-EPC-00QCA-PI-ISO-0001 | ISO | IFC | 2027-11-30
ALP-EPC-00QCA-PR-DSH-0001 | DSH | ALP-EPC-00QCA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QCA-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QCA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QCA-PR-PID-0001 | PID | ALP-EPC-00QCA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QCA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QCA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00QCA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00QEA-CM-CMP-0001 | CMP | ALP-EPC-00QEA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QEA-CM-CMP-0001 | CMP | ALP-EPC-00QEA-IC-CNR-0001 | CNR | IFR | 2027-04-23 | driving
ALP-EPC-00QEA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00QEA-CM-MDB-0001 | MDB | ALP-EPC-00QEA-CM-CMP-0001 | CMP | IFR | 2027-05-21
ALP-EPC-00QEA-CM-OMM-0001 | OMM | ALP-EPC-00QEA-CM-CMP-0001 | CMP | IFR | 2027-05-21
ALP-EPC-00QEA-GE-RPT-0001 | RPT | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00QEA-IC-CEM-0001 | CEM | ALP-EPC-00QEA-IC-CNR-0001 | CNR | IFR | 2027-04-23
ALP-EPC-00QEA-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00QEA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00QEA-IC-CNR-0001 | CNR | ALP-EPC-00QEA-PR-PID-0001 | PID | IFR | 2027-04-02 | driving
ALP-EPC-00QEA-IC-DSH-0001 | DSH | ALP-EPC-00QEA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QEA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00QEA-IC-DSH-0002 | DSH | ALP-EPC-00QEA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QEA-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00QEA-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QEA-IC-HMI-0001 | HMI | ALP-EPC-00QEA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QEA-IC-HMI-0001 | HMI | ALP-EPC-00QEA-IC-CNR-0001 | CNR | IFR | 2027-04-23
ALP-EPC-00QEA-ME-CAL-0001 | CAL | ALP-EPC-00QEA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QEA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QEA-ME-DSH-0001 | DSH | ALP-EPC-00QEA-ME-CAL-0001 | CAL | IFR | 2027-02-18
ALP-EPC-00QEA-ME-DSH-0001 | DSH | ALP-EPC-00QEA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QEA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QEA-ME-DSH-0002 | DSH | ALP-EPC-00QEA-ME-CAL-0001 | CAL | IFR | 2027-02-18
ALP-EPC-00QEA-ME-DSH-0002 | DSH | ALP-EPC-00QEA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QEA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QEA-ME-DSH-0003 | DSH | ALP-EPC-00QEA-ME-CAL-0001 | CAL | IFR | 2027-02-18
ALP-EPC-00QEA-ME-DSH-0003 | DSH | ALP-EPC-00QEA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QEA-ME-DSH-0003 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QEA-ME-ITP-0001 | ITP | ALP-EPC-00QEA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | ALP-EPC-00QEA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | ALP-EPC-00QEA-ME-DSH-0002 | DSH | IFR | 2026-11-02
ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | ALP-EPC-00QEA-ME-DSH-0003 | DSH | IFR | 2026-11-02
ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | ALP-EPC-00QEA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QEA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00QEA-ME-SPC-0001 | SPC | ALP-EPC-00QEA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QEA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QEA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00QEA-PI-ISO-0001 | ISO | ALP-EPC-00QEA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QEA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-00QEA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-00QEA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19
ALP-EPC-00QEA-PI-SUP-0001 | SUP | ALP-EPC-00QEA-PI-ISO-0001 | ISO | IFC | 2027-10-13
ALP-EPC-00QEA-PR-DSH-0001 | DSH | ALP-EPC-00QEA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QEA-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QEA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QEA-PR-PID-0001 | PID | ALP-EPC-00QEA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QEA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QEA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00QEA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00QHA-CM-CMP-0001 | CMP | ALP-EPC-00QHA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QHA-CM-CMP-0001 | CMP | ALP-EPC-00QHA-IC-CNR-0001 | CNR | IFR | 2027-04-26 | driving
ALP-EPC-00QHA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00QHA-CM-MDB-0001 | MDB | ALP-EPC-00QHA-CM-CMP-0001 | CMP | IFR | 2027-05-24
ALP-EPC-00QHA-CM-OMM-0001 | OMM | ALP-EPC-00QHA-CM-CMP-0001 | CMP | IFR | 2027-05-24
ALP-EPC-00QHA-GE-RPT-0001 | RPT | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00QHA-IC-CEM-0001 | CEM | ALP-EPC-00QHA-IC-CNR-0001 | CNR | IFR | 2027-04-26
ALP-EPC-00QHA-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00QHA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00QHA-IC-CNR-0001 | CNR | ALP-EPC-00QHA-PR-PID-0001 | PID | IFR | 2027-04-02 | driving
ALP-EPC-00QHA-IC-DSH-0001 | DSH | ALP-EPC-00QHA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QHA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00QHA-IC-DSH-0002 | DSH | ALP-EPC-00QHA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QHA-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00QHA-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QHA-IC-HMI-0001 | HMI | ALP-EPC-00QHA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QHA-IC-HMI-0001 | HMI | ALP-EPC-00QHA-IC-CNR-0001 | CNR | IFR | 2027-04-26
ALP-EPC-00QHA-ME-CAL-0001 | CAL | ALP-EPC-00QHA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QHA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00QHA-ME-DSH-0001 | DSH | ALP-EPC-00QHA-ME-CAL-0001 | CAL | IFR | 2027-02-05
ALP-EPC-00QHA-ME-DSH-0001 | DSH | ALP-EPC-00QHA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QHA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QHA-ME-DSH-0002 | DSH | ALP-EPC-00QHA-ME-CAL-0001 | CAL | IFR | 2027-02-05
ALP-EPC-00QHA-ME-DSH-0002 | DSH | ALP-EPC-00QHA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QHA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08 | driving
ALP-EPC-00QHA-ME-DSH-0003 | DSH | ALP-EPC-00QHA-ME-CAL-0001 | CAL | IFR | 2027-02-05
ALP-EPC-00QHA-ME-DSH-0003 | DSH | ALP-EPC-00QHA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QHA-ME-DSH-0003 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08 | driving
ALP-EPC-00QHA-ME-DSH-0004 | DSH | ALP-EPC-00QHA-ME-CAL-0001 | CAL | IFR | 2027-02-05
ALP-EPC-00QHA-ME-DSH-0004 | DSH | ALP-EPC-00QHA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QHA-ME-DSH-0004 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08 | driving
ALP-EPC-00QHA-ME-ITP-0001 | ITP | ALP-EPC-00QHA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | ALP-EPC-00QHA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | ALP-EPC-00QHA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | ALP-EPC-00QHA-ME-DSH-0002 | DSH | IFR | 2027-02-22
ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | ALP-EPC-00QHA-ME-DSH-0003 | DSH | IFR | 2027-02-22
ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | ALP-EPC-00QHA-ME-DSH-0004 | DSH | IFR | 2027-02-22
ALP-EPC-00QHA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00QHA-ME-SPC-0001 | SPC | ALP-EPC-00QHA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QHA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QHA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00QHA-PI-ISO-0001 | ISO | ALP-EPC-00QHA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QHA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-00QHA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-00QHA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19
ALP-EPC-00QHA-PI-ISO-0001 | ISO | ALP-EPC-00QHA-PI-STR-0001 | STR | IFR | 2027-08-17
ALP-EPC-00QHA-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-00QHA-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-00QHA-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19 | driving
ALP-EPC-00QHA-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00QHA-PI-SUP-0001 | SUP | ALP-EPC-00QHA-PI-ISO-0001 | ISO | IFC | 2027-11-15
ALP-EPC-00QHA-PI-SUP-0001 | SUP | ALP-EPC-00QHA-PI-STR-0001 | STR | IFC | 2027-09-07
ALP-EPC-00QHA-PR-DSH-0001 | DSH | ALP-EPC-00QHA-PR-PID-0001 | PID | IFR | 2027-04-02
ALP-EPC-00QHA-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QHA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QHA-PR-PID-0001 | PID | ALP-EPC-00QHA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QHA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QHA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00QHA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00QJA-CM-CMP-0001 | CMP | ALP-EPC-00QJA-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00QJA-CM-CMP-0001 | CMP | ALP-EPC-00QJA-IC-CNR-0001 | CNR | IFR | 2027-05-31 | driving
ALP-EPC-00QJA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00QJA-CM-MDB-0001 | MDB | ALP-EPC-00QJA-CM-CMP-0001 | CMP | IFR | 2027-06-28
ALP-EPC-00QJA-CM-OMM-0001 | OMM | ALP-EPC-00QJA-CM-CMP-0001 | CMP | IFR | 2027-06-28
ALP-EPC-00QJA-GE-RPT-0001 | RPT | ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | IFR | 2027-04-12
ALP-EPC-00QJA-IC-CEM-0001 | CEM | ALP-EPC-00QJA-IC-CNR-0001 | CNR | IFR | 2027-05-31
ALP-EPC-00QJA-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00QJA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00QJA-IC-CNR-0001 | CNR | ALP-EPC-00QJA-PR-PID-0001 | PID | IFR | 2027-05-10 | driving
ALP-EPC-00QJA-IC-DSH-0001 | DSH | ALP-EPC-00QJA-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00QJA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00QJA-IC-DSH-0002 | DSH | ALP-EPC-00QJA-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00QJA-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00QJA-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QJA-IC-HMI-0001 | HMI | ALP-EPC-00QJA-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00QJA-IC-HMI-0001 | HMI | ALP-EPC-00QJA-IC-CNR-0001 | CNR | IFR | 2027-05-31
ALP-EPC-00QJA-IC-LOG-0001 | LOG | ALP-EPC-00QJA-IC-CNR-0001 | CNR | IFR | 2027-05-31
ALP-EPC-00QJA-IC-LOG-0001 | LOG | ALP-EPC-00QJA-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00QJA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00QJA-ME-CAL-0001 | CAL | ALP-EPC-00QJA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QJA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QJA-ME-DSH-0001 | DSH | ALP-EPC-00QJA-ME-CAL-0001 | CAL | IFR | 2027-03-22
ALP-EPC-00QJA-ME-DSH-0001 | DSH | ALP-EPC-00QJA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QJA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QJA-ME-DSH-0002 | DSH | ALP-EPC-00QJA-ME-CAL-0001 | CAL | IFR | 2027-03-22 | driving
ALP-EPC-00QJA-ME-DSH-0002 | DSH | ALP-EPC-00QJA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QJA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QJA-ME-ITP-0001 | ITP | ALP-EPC-00QJA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | ALP-EPC-00QJA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | ALP-EPC-00QJA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | ALP-EPC-00QJB-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | ALP-EPC-00QJA-ME-DSH-0002 | DSH | IFR | 2027-04-05 | driving
ALP-EPC-00QJA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00QJA-ME-SPC-0001 | SPC | ALP-EPC-00QJA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QJA-ME-SPC-0001 | SPC | ALP-EPC-00QJB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QJA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QJA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00QJA-PI-ISO-0001 | ISO | ALP-EPC-00QJA-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00QJA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-00QJA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-00QJA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19
ALP-EPC-00QJA-PI-SUP-0001 | SUP | ALP-EPC-00QJA-PI-ISO-0001 | ISO | IFC | 2027-12-13 | driving
ALP-EPC-00QJA-PR-DSH-0001 | DSH | ALP-EPC-00QJA-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00QJA-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QJA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QJA-PR-PID-0001 | PID | ALP-EPC-00QJA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QJA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QJA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00QJA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00QJB-CM-CMP-0001 | CMP | ALP-EPC-00QJB-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00QJB-CM-CMP-0001 | CMP | ALP-EPC-00QJB-IC-CNR-0001 | CNR | IFR | 2027-05-31 | driving
ALP-EPC-00QJB-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00QJB-CM-MDB-0001 | MDB | ALP-EPC-00QJB-CM-CMP-0001 | CMP | IFR | 2027-06-28
ALP-EPC-00QJB-CM-OMM-0001 | OMM | ALP-EPC-00QJB-CM-CMP-0001 | CMP | IFR | 2027-06-28
ALP-EPC-00QJB-IC-CEM-0001 | CEM | ALP-EPC-00QJB-IC-CNR-0001 | CNR | IFR | 2027-05-31
ALP-EPC-00QJB-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00QJB-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00QJB-IC-CNR-0001 | CNR | ALP-EPC-00QJB-PR-PID-0001 | PID | IFR | 2027-05-10 | driving
ALP-EPC-00QJB-IC-DSH-0001 | DSH | ALP-EPC-00QJB-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00QJB-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00QJB-IC-DSH-0002 | DSH | ALP-EPC-00QJB-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00QJB-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00QJB-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QJB-IC-HMI-0001 | HMI | ALP-EPC-00QJB-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00QJB-IC-HMI-0001 | HMI | ALP-EPC-00QJB-IC-CNR-0001 | CNR | IFR | 2027-05-31
ALP-EPC-00QJB-IC-LOG-0001 | LOG | ALP-EPC-00QJB-IC-CNR-0001 | CNR | IFR | 2027-05-31
ALP-EPC-00QJB-IC-LOG-0001 | LOG | ALP-EPC-00QJB-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00QJB-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00QJB-ME-CAL-0001 | CAL | ALP-EPC-00QJB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QJB-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QJB-ME-DSH-0001 | DSH | ALP-EPC-00QJA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QJB-ME-DSH-0001 | DSH | ALP-EPC-00QJB-ME-CAL-0001 | CAL | IFR | 2027-03-24
ALP-EPC-00QJB-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QJB-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00QJB-PI-ISO-0001 | ISO | ALP-EPC-00QJB-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00QJB-PI-ISO-0001 | ISO | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-00QJB-PI-SUP-0001 | SUP | ALP-EPC-00QJB-PI-ISO-0001 | ISO | IFC | 2028-01-21 | driving
ALP-EPC-00QJB-PR-DSH-0001 | DSH | ALP-EPC-00QJB-PR-PID-0001 | PID | IFR | 2027-05-10
ALP-EPC-00QJB-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QJB-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QJB-PR-PID-0001 | PID | ALP-EPC-00QJB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QJB-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QJB-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00QJB-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00QUA-CM-CMP-0001 | CMP | ALP-EPC-00QUA-PR-PID-0001 | PID | IFR | 2027-05-11
ALP-EPC-00QUA-CM-CMP-0001 | CMP | ALP-EPC-00QUA-IC-CNR-0001 | CNR | IFR | 2027-06-02 | driving
ALP-EPC-00QUA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00QUA-CM-MDB-0001 | MDB | ALP-EPC-00QUA-CM-CMP-0001 | CMP | IFR | 2027-06-30
ALP-EPC-00QUA-CM-OMM-0001 | OMM | ALP-EPC-00QUA-CM-CMP-0001 | CMP | IFR | 2027-06-30
ALP-EPC-00QUA-GE-RPT-0001 | RPT | ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00QUA-IC-CEM-0001 | CEM | ALP-EPC-00QUA-IC-CNR-0001 | CNR | IFR | 2027-06-02
ALP-EPC-00QUA-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00QUA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00QUA-IC-CNR-0001 | CNR | ALP-EPC-00QUA-PR-PID-0001 | PID | IFR | 2027-05-11 | driving
ALP-EPC-00QUA-IC-DSH-0001 | DSH | ALP-EPC-00QUA-PR-PID-0001 | PID | IFR | 2027-05-11
ALP-EPC-00QUA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00QUA-IC-HMI-0001 | HMI | ALP-EPC-00QUA-PR-PID-0001 | PID | IFR | 2027-05-11
ALP-EPC-00QUA-IC-HMI-0001 | HMI | ALP-EPC-00QUA-IC-CNR-0001 | CNR | IFR | 2027-06-02
ALP-EPC-00QUA-IC-ITP-0001 | ITP | ALP-EPC-00QUA-IC-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QUA-IC-LOG-0001 | LOG | ALP-EPC-00QUA-IC-CNR-0001 | CNR | IFR | 2027-06-02
ALP-EPC-00QUA-IC-LOG-0001 | LOG | ALP-EPC-00QUA-PR-PID-0001 | PID | IFR | 2027-05-11
ALP-EPC-00QUA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | ALP-EPC-00QUA-IC-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | ALP-EPC-00QUA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | ALP-EPC-00QUA-ME-DSH-0002 | DSH | IFR | 2027-04-06
ALP-EPC-00QUA-IC-SPC-0001 | SPC | ALP-EPC-00QUA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QUA-IC-SPC-0001 | SPC | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00QUA-ME-CAL-0001 | CAL | ALP-EPC-00QUA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QUA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QUA-ME-DSH-0001 | DSH | ALP-EPC-00QUA-IC-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QUA-ME-DSH-0001 | DSH | ALP-EPC-00QUA-ME-CAL-0001 | CAL | IFR | 2027-03-23
ALP-EPC-00QUA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QUA-ME-DSH-0002 | DSH | ALP-EPC-00QUA-ME-CAL-0001 | CAL | IFR | 2027-03-23 | driving
ALP-EPC-00QUA-ME-DSH-0002 | DSH | ALP-EPC-00QUA-IC-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QUA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00QUA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00QUA-PI-ISO-0001 | ISO | ALP-EPC-00QUA-PR-PID-0001 | PID | IFR | 2027-05-11
ALP-EPC-00QUA-PI-ISO-0001 | ISO | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-00QUA-PI-SUP-0001 | SUP | ALP-EPC-00QUA-PI-ISO-0001 | ISO | IFC | 2027-12-28 | driving
ALP-EPC-00QUA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00QUA-PR-PID-0001 | PID | ALP-EPC-00QUA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00QUA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00QUA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00QUA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00SAA-CM-CMP-0001 | CMP | ALP-EPC-00SAA-HV-PID-0001 | PID | IFR | 2027-03-02
ALP-EPC-00SAA-CM-CMP-0001 | CMP | ALP-EPC-00SAA-IC-CNR-0001 | CNR | IFR | 2027-03-24 | driving
ALP-EPC-00SAA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00SAA-CM-MDB-0001 | MDB | ALP-EPC-00SAA-CM-CMP-0001 | CMP | IFR | 2027-04-21
ALP-EPC-00SAA-CM-OMM-0001 | OMM | ALP-EPC-00SAA-CM-CMP-0001 | CMP | IFR | 2027-04-21
ALP-EPC-00SAA-GE-RPT-0001 | RPT | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00SAA-HV-CAL-0001 | CAL | ALP-EPC-00SAA-HV-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00SAA-HV-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00SAA-HV-DSH-0001 | DSH | ALP-EPC-00SAA-HV-CAL-0001 | CAL | IFR | 2027-02-08
ALP-EPC-00SAA-HV-DSH-0001 | DSH | ALP-EPC-00SAA-HV-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SAA-HV-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00SAA-HV-ITP-0001 | ITP | ALP-EPC-00SAA-HV-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | ALP-EPC-00SAA-HV-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | ALP-EPC-00SAA-HV-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | ALP-EPC-00SAA-ME-DSH-0001 | DSH | IFR | 2027-02-23
ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | ALP-EPC-00SAA-ME-DSH-0002 | DSH | IFR | 2027-03-04
ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | ALP-EPC-00SAA-ME-DSH-0003 | DSH | IFR | 2027-02-24
ALP-EPC-00SAA-HV-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SAA-HV-PID-0001 | PID | ALP-EPC-00SAA-HV-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00SAA-HV-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00SAA-HV-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00SAA-HV-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00SAA-HV-SPC-0001 | SPC | ALP-EPC-00SAA-HV-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00SAA-HV-SPC-0001 | SPC | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00SAA-IC-CNR-0001 | CNR | ALP-EPC-00SAA-HV-PID-0001 | PID | IFR | 2027-03-02 | driving
ALP-EPC-00SAA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00SAA-IC-DSH-0001 | DSH | ALP-EPC-00SAA-HV-PID-0001 | PID | IFR | 2027-03-02
ALP-EPC-00SAA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00SAA-IC-DSH-0002 | DSH | ALP-EPC-00SAA-HV-PID-0001 | PID | IFR | 2027-03-02
ALP-EPC-00SAA-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-00SAA-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00SAA-IC-HMI-0001 | HMI | ALP-EPC-00SAA-HV-PID-0001 | PID | IFR | 2027-03-02
ALP-EPC-00SAA-IC-HMI-0001 | HMI | ALP-EPC-00SAA-IC-CNR-0001 | CNR | IFR | 2027-03-24
ALP-EPC-00SAA-IC-LOG-0001 | LOG | ALP-EPC-00SAA-IC-CNR-0001 | CNR | IFR | 2027-03-24
ALP-EPC-00SAA-IC-LOG-0001 | LOG | ALP-EPC-00SAA-HV-PID-0001 | PID | IFR | 2027-03-02
ALP-EPC-00SAA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00SAA-IC-LOG-0002 | LOG | ALP-EPC-00SAA-IC-CNR-0001 | CNR | IFR | 2027-03-24
ALP-EPC-00SAA-IC-LOG-0002 | LOG | ALP-EPC-00SAA-HV-PID-0001 | PID | IFR | 2027-03-02
ALP-EPC-00SAA-IC-LOG-0002 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00SAA-ME-DSH-0001 | DSH | ALP-EPC-00SAA-HV-CAL-0001 | CAL | IFR | 2027-02-08 | driving
ALP-EPC-00SAA-ME-DSH-0001 | DSH | ALP-EPC-00SAA-HV-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SAA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00SAA-ME-DSH-0002 | DSH | ALP-EPC-00SAA-HV-CAL-0001 | CAL | IFR | 2027-02-08 | driving
ALP-EPC-00SAA-ME-DSH-0002 | DSH | ALP-EPC-00SAA-HV-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SAA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00SAA-ME-DSH-0003 | DSH | ALP-EPC-00SAA-HV-CAL-0001 | CAL | IFR | 2027-02-08
ALP-EPC-00SAA-ME-DSH-0003 | DSH | ALP-EPC-00SAA-HV-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SAA-ME-DSH-0003 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00SAA-PI-ISO-0001 | ISO | ALP-EPC-00UBA-PI-PPL-0001 | PPL | IFR | 2027-07-06 | driving
ALP-EPC-00SAA-PI-ISO-0001 | ISO | ALP-EPC-00SAA-HV-PID-0001 | PID | IFR | 2027-03-02
ALP-EPC-00SAA-PI-SUP-0001 | SUP | ALP-EPC-00SAA-PI-ISO-0001 | ISO | IFC | 2027-09-07 | driving
ALP-EPC-00SAA-PR-DSH-0001 | DSH | ALP-EPC-00SAA-HV-PID-0001 | PID | IFR | 2027-03-02
ALP-EPC-00SAA-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00SGA-CM-CMP-0001 | CMP | ALP-EPC-00SGA-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00SGA-CM-CMP-0001 | CMP | ALP-EPC-00SGA-IC-CNR-0001 | CNR | IFR | 2027-03-17 | driving
ALP-EPC-00SGA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00SGA-CM-MDB-0001 | MDB | ALP-EPC-00SGA-CM-CMP-0001 | CMP | IFR | 2027-04-14
ALP-EPC-00SGA-CM-OMM-0001 | OMM | ALP-EPC-00SGA-CM-CMP-0001 | CMP | IFR | 2027-04-14
ALP-EPC-00SGA-GE-RPT-0001 | RPT | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00SGA-IC-CEM-0001 | CEM | ALP-EPC-00SGA-IC-CNR-0001 | CNR | IFR | 2027-03-17
ALP-EPC-00SGA-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00SGA-IC-CNR-0001 | CNR | ALP-EPC-00SGA-PR-PID-0001 | PID | IFR | 2027-02-23 | driving
ALP-EPC-00SGA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00SGA-IC-DSH-0001 | DSH | ALP-EPC-00SGA-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00SGA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00SGA-IC-HMI-0001 | HMI | ALP-EPC-00SGA-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00SGA-IC-HMI-0001 | HMI | ALP-EPC-00SGA-IC-CNR-0001 | CNR | IFR | 2027-03-17
ALP-EPC-00SGA-IC-LOG-0001 | LOG | ALP-EPC-00SGA-IC-CNR-0001 | CNR | IFR | 2027-03-17
ALP-EPC-00SGA-IC-LOG-0001 | LOG | ALP-EPC-00SGA-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00SGA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00SGA-ME-CAL-0001 | CAL | ALP-EPC-00SGA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00SGA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00SGA-ME-DSH-0001 | DSH | ALP-EPC-00SGA-ME-CAL-0001 | CAL | IFR | 2027-02-11
ALP-EPC-00SGA-ME-DSH-0001 | DSH | ALP-EPC-00SGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SGA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00SGA-ME-DSH-0001 | DSH | ALP-EPC-00EGB-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SGA-ME-DSH-0002 | DSH | ALP-EPC-00SGA-ME-CAL-0001 | CAL | IFR | 2027-02-11
ALP-EPC-00SGA-ME-DSH-0002 | DSH | ALP-EPC-00SGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SGA-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00SGA-ME-DSH-0002 | DSH | ALP-EPC-00EGB-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SGA-ME-ITP-0001 | ITP | ALP-EPC-00SGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | ALP-EPC-00SGA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | ALP-EPC-00SGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | ALP-EPC-00SGA-ME-DSH-0002 | DSH | IFR | 2026-11-02
ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | ALP-EPC-00SGC-ME-DSH-0001 | DSH | IFR | 2027-03-08
ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | ALP-EPC-00SGC-ME-DSH-0002 | DSH | IFR | 2027-03-03
ALP-EPC-00SGA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00SGA-ME-SPC-0001 | SPC | ALP-EPC-00SGA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00SGA-ME-SPC-0001 | SPC | ALP-EPC-00SGC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00SGA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00SGA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00SGA-PI-ISO-0001 | ISO | ALP-EPC-00SGA-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00SGA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-00SGA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-00SGA-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19
ALP-EPC-00SGA-PI-ISO-0001 | ISO | ALP-EPC-00SGA-PI-STR-0001 | STR | IFR | 2027-08-16 | driving
ALP-EPC-00SGA-PI-PPL-0001 | PPL | ALP-EPC-00SGA-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00SGA-PI-PPL-0001 | PPL | ALP-EPC-00UZC-CV-CVL-0001 | CVL | IFR | 2027-03-08
ALP-EPC-00SGA-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-00SGA-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-00SGA-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19 | driving
ALP-EPC-00SGA-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00SGA-PI-SUP-0001 | SUP | ALP-EPC-00SGA-PI-ISO-0001 | ISO | IFC | 2027-10-18
ALP-EPC-00SGA-PI-SUP-0001 | SUP | ALP-EPC-00SGA-PI-STR-0001 | STR | IFC | 2027-09-06
ALP-EPC-00SGA-PR-CAL-0001 | CAL | ALP-EPC-00SGA-ME-CAL-0001 | CAL | IFR | 2027-02-11
ALP-EPC-00SGA-PR-DSH-0001 | DSH | ALP-EPC-00SGA-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00SGA-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-00SGA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SGA-PR-PID-0001 | PID | ALP-EPC-00SGA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00SGA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00SGA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00SGA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00SGC-CM-CMP-0001 | CMP | ALP-EPC-00SGC-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00SGC-CM-CMP-0001 | CMP | ALP-EPC-00SGC-IC-CNR-0001 | CNR | IFR | 2027-03-17 | driving
ALP-EPC-00SGC-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00SGC-CM-MDB-0001 | MDB | ALP-EPC-00SGC-CM-CMP-0001 | CMP | IFR | 2027-04-14
ALP-EPC-00SGC-CM-OMM-0001 | OMM | ALP-EPC-00SGC-CM-CMP-0001 | CMP | IFR | 2027-04-14
ALP-EPC-00SGC-IC-CEM-0001 | CEM | ALP-EPC-00SGC-IC-CNR-0001 | CNR | IFR | 2027-03-17
ALP-EPC-00SGC-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-00SGC-IC-CNR-0001 | CNR | ALP-EPC-00SGC-PR-PID-0001 | PID | IFR | 2027-02-23 | driving
ALP-EPC-00SGC-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00SGC-IC-DSH-0001 | DSH | ALP-EPC-00SGC-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00SGC-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00SGC-IC-HMI-0001 | HMI | ALP-EPC-00SGC-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00SGC-IC-HMI-0001 | HMI | ALP-EPC-00SGC-IC-CNR-0001 | CNR | IFR | 2027-03-17
ALP-EPC-00SGC-IC-LOG-0001 | LOG | ALP-EPC-00SGC-IC-CNR-0001 | CNR | IFR | 2027-03-17
ALP-EPC-00SGC-IC-LOG-0001 | LOG | ALP-EPC-00SGC-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00SGC-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00SGC-ME-CAL-0001 | CAL | ALP-EPC-00SGC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00SGC-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00SGC-ME-DSH-0001 | DSH | ALP-EPC-00SGC-ME-CAL-0001 | CAL | IFR | 2027-02-10
ALP-EPC-00SGC-ME-DSH-0001 | DSH | ALP-EPC-00SGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SGC-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00SGC-ME-DSH-0002 | DSH | ALP-EPC-00SGC-ME-CAL-0001 | CAL | IFR | 2027-02-10
ALP-EPC-00SGC-ME-DSH-0002 | DSH | ALP-EPC-00SGA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SGC-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00SGC-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-00SGC-PI-ISO-0001 | ISO | ALP-EPC-00SGC-PR-PID-0001 | PID | IFR | 2027-02-23
ALP-EPC-00SGC-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-00SGC-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-00SGC-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19
ALP-EPC-00SGC-PI-SUP-0001 | SUP | ALP-EPC-00SGC-PI-ISO-0001 | ISO | IFC | 2027-10-21
ALP-EPC-00SGC-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SGC-PR-PID-0001 | PID | ALP-EPC-00SGC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00SGC-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-00SGC-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-00SGC-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-00SGY-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00SGY-CM-MDB-0001 | MDB | ALP-EPC-00SGY-CM-CMP-0001 | CMP | IFR | 2027-03-05
ALP-EPC-00SGY-CM-OMM-0001 | OMM | ALP-EPC-00SGY-CM-CMP-0001 | CMP | IFR | 2027-03-05 | driving
ALP-EPC-00SGY-GE-ITP-0001 | ITP | ALP-EPC-00SGY-GE-SPC-0001 | SPC | IFR | 2027-03-02
ALP-EPC-00SGY-GE-MRQ-0001 | MRQ | ALP-EPC-00SGY-GE-SPC-0001 | SPC | IFR | 2027-03-02
ALP-EPC-00SGY-GE-MRQ-0001 | MRQ | ALP-EPC-00SGY-IC-DSH-0001 | DSH | IFR | 2027-03-16 | driving
ALP-EPC-00SGY-GE-RPT-0001 | RPT | ALP-EPC-00SGY-GE-MRQ-0001 | MRQ | IFR | 2027-03-23
ALP-EPC-00SGY-GE-SPC-0001 | SPC | ALP-EPC-00SGY-IC-BLK-0001 | BLK | IFR | 2027-01-25
ALP-EPC-00SGY-GE-SPC-0001 | SPC | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00SGY-GE-SPC-0001 | SPC | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00SGY-IC-BLK-0001 | BLK | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00SGY-IC-BLK-0001 | BLK | ALP-EPC-00000-IC-RPT-0002 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00SGY-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00SGY-IC-DSH-0001 | DSH | ALP-EPC-00SGY-GE-SPC-0001 | SPC | IFR | 2027-03-02 | driving
ALP-EPC-00SGY-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00SMA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00SMA-CM-MDB-0001 | MDB | ALP-EPC-00SMA-CM-CMP-0001 | CMP | IFR | 2027-03-08
ALP-EPC-00SMA-GE-RPT-0001 | RPT | ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00SMA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00SMA-ME-DSH-0001 | DSH | ALP-EPC-00SMA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SMA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00SMA-ME-ITP-0001 | ITP | ALP-EPC-00SMA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | ALP-EPC-00SMA-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | ALP-EPC-00SMA-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00SMA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-00SMA-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00UAC-CV-ARC-0001 | ARC | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00UAC-CV-ARC-0001 | ARC | ALP-EPC-00UAC-PI-LAY-0001 | LAY | IFR | 2026-12-01
ALP-EPC-00UAC-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18 | driving
ALP-EPC-00UAC-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UAC-CV-EFD-0001 | EFD | ALP-EPC-00UAC-CV-FND-0001 | FND | IFR | 2027-02-18 | driving
ALP-EPC-00UAC-CV-EFD-0001 | EFD | ALP-E01-00ACA-CV-CAL-0001 | CAL | IFR | 2027-01-26
ALP-EPC-00UAC-CV-FND-0001 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18 | driving
ALP-EPC-00UAC-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UAC-CV-FND-0001 | FND | ALP-EPC-00UAC-PI-LAY-0001 | LAY | IFR | 2026-12-01
ALP-EPC-00UAC-CV-RBR-0001 | RBR | ALP-EPC-00UAC-CV-FND-0001 | FND | IFR | 2027-02-18 | driving
ALP-EPC-00UAC-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-CAL-0001 | CAL | IFR | 2027-01-14
ALP-EPC-00UAC-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UAC-EL-CBL-0001 | CBL | ALP-EPC-00UAC-EL-ELY-0001 | ELY | IFR | 2027-05-07
ALP-EPC-00UAC-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UAC-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UAC-EL-ELY-0001 | ELY | ALP-EPC-00UAC-PI-LAY-0001 | LAY | IFR | 2026-12-01
ALP-EPC-00UAC-EL-ELY-0002 | ELY | ALP-EPC-00UAC-EL-ELY-0001 | ELY | IFR | 2027-05-07
ALP-EPC-00UAC-EL-ELY-0003 | ELY | ALP-EPC-00UAC-CV-FND-0001 | FND | IFR | 2027-02-18
ALP-EPC-00UAC-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UAC-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UAC-HS-GAD-0001 | GAD | ALP-EPC-00UAC-CV-ARC-0001 | ARC | IFR | 2027-01-20 | driving
ALP-EPC-00UAC-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UAC-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UAC-HV-GAD-0001 | GAD | ALP-EPC-00UAC-CV-ARC-0001 | ARC | IFR | 2027-01-20
ALP-EPC-00UAC-HV-GAD-0001 | GAD | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UAC-IC-ELY-0001 | ELY | ALP-EPC-00UAC-CV-ARC-0001 | ARC | IFR | 2027-01-20 | driving
ALP-EPC-00UAC-IC-ELY-0001 | ELY | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UAC-IC-ELY-0002 | ELY | ALP-EPC-00UAC-PI-LAY-0001 | LAY | IFR | 2026-12-01
ALP-EPC-00UAC-IC-ELY-0002 | ELY | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UAC-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UAC-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00UAC-IC-LOP-0001 | LOP | ALP-EPC-00UAC-IC-ELY-0002 | ELY | IFR | 2027-08-03 | driving
ALP-EPC-00UAC-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-00UAC-IC-LOP-0002 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27 | driving
ALP-EPC-00UAC-IC-LOP-0002 | LOP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06
ALP-EPC-00UAC-PI-LAY-0001 | LAY | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UAC-SS-STL-0001 | STL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UAC-SS-STL-0001 | STL | ALP-EPC-00UAC-CV-ARC-0001 | ARC | IFR | 2027-01-20
ALP-EPC-00UAC-SS-STL-0001 | STL | ALP-EPC-00UAC-CV-CAL-0001 | CAL | IFR | 2027-02-08 | driving
ALP-EPC-00UAC-SS-STL-0002 | STL | ALP-EPC-00UAC-CV-CAL-0001 | CAL | IFR | 2027-02-08 | driving
ALP-EPC-00UAC-SS-STL-0002 | STL | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00UAC-SS-STL-0002 | STL | ALP-EPC-00UAC-PI-LAY-0001 | LAY | IFR | 2026-12-01
ALP-EPC-00UBA-CV-ARC-0001 | ARC | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00UBA-CV-ARC-0001 | ARC | ALP-EPC-00UBA-PI-LAY-0001 | LAY | IFR | 2026-12-09
ALP-EPC-00UBA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UBA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UBA-CV-EFD-0001 | EFD | ALP-EPC-00UBA-CV-FND-0001 | FND | IFR | 2027-02-18
ALP-EPC-00UBA-CV-EFD-0001 | EFD | ALP-E06-00XJA-CV-CAL-0001 | CAL | IFR | 2027-02-22 | driving
ALP-EPC-00UBA-CV-FND-0001 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18 | driving
ALP-EPC-00UBA-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UBA-CV-FND-0001 | FND | ALP-EPC-00UBA-PI-LAY-0001 | LAY | IFR | 2026-12-09
ALP-EPC-00UBA-CV-RBR-0001 | RBR | ALP-EPC-00UBA-CV-FND-0001 | FND | IFR | 2027-02-18 | driving
ALP-EPC-00UBA-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-CAL-0001 | CAL | IFR | 2027-01-14
ALP-EPC-00UBA-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UBA-EL-CBL-0001 | CBL | ALP-EPC-00UBA-EL-ELY-0001 | ELY | IFR | 2027-03-16
ALP-EPC-00UBA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UBA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08 | driving
ALP-EPC-00UBA-EL-ELY-0001 | ELY | ALP-EPC-00UBA-PI-LAY-0001 | LAY | IFR | 2026-12-09
ALP-EPC-00UBA-EL-ELY-0002 | ELY | ALP-EPC-00UBA-EL-ELY-0001 | ELY | IFR | 2027-03-16
ALP-EPC-00UBA-EL-ELY-0002 | ELY | ALP-EPC-00UBA-PI-PPL-0001 | PPL | IFR | 2027-07-06 | driving
ALP-EPC-00UBA-EL-ELY-0003 | ELY | ALP-EPC-00UBA-CV-FND-0001 | FND | IFR | 2027-02-18 | driving
ALP-EPC-00UBA-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UBA-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UBA-HS-GAD-0001 | GAD | ALP-EPC-00UBA-CV-ARC-0001 | ARC | IFR | 2027-01-26 | driving
ALP-EPC-00UBA-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UBA-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UBA-HV-GAD-0001 | GAD | ALP-EPC-00SAA-HV-CAL-0001 | CAL | IFR | 2027-02-08
ALP-EPC-00UBA-HV-GAD-0001 | GAD | ALP-EPC-00UBA-PI-LAY-0001 | LAY | IFR | 2026-12-09
ALP-EPC-00UBA-HV-GAD-0002 | GAD | ALP-EPC-00UBA-CV-ARC-0001 | ARC | IFR | 2027-01-26
ALP-EPC-00UBA-HV-GAD-0002 | GAD | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UBA-IC-ELY-0001 | ELY | ALP-EPC-00UBA-CV-ARC-0001 | ARC | IFR | 2027-01-26 | driving
ALP-EPC-00UBA-IC-ELY-0001 | ELY | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UBA-IC-ELY-0002 | ELY | ALP-EPC-00UBA-PI-LAY-0001 | LAY | IFR | 2026-12-09
ALP-EPC-00UBA-IC-ELY-0002 | ELY | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UBA-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UBA-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00UBA-IC-LOP-0001 | LOP | ALP-EPC-00UBA-IC-ELY-0002 | ELY | IFR | 2027-08-09 | driving
ALP-EPC-00UBA-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-00UBA-IC-LOP-0002 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27 | driving
ALP-EPC-00UBA-IC-LOP-0002 | LOP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06
ALP-EPC-00UBA-PI-LAY-0001 | LAY | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UBA-PI-PPL-0001 | PPL | ALP-EPC-00UBA-PI-LAY-0001 | LAY | IFR | 2026-12-09
ALP-EPC-00UBA-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-SPC-0002 | SPC | IFR | 2026-12-14
ALP-EPC-00UBA-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-M3D-0001 | M3D | IFR | 2026-12-14
ALP-EPC-00UBA-SS-STL-0001 | STL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UBA-SS-STL-0001 | STL | ALP-EPC-00UBA-CV-ARC-0001 | ARC | IFR | 2027-01-26
ALP-EPC-00UBA-SS-STL-0001 | STL | ALP-EPC-00UBA-CV-CAL-0001 | CAL | IFR | 2027-02-24 | driving
ALP-EPC-00UBA-SS-STL-0002 | STL | ALP-EPC-00UBA-CV-CAL-0001 | CAL | IFR | 2027-02-24 | driving
ALP-EPC-00UBA-SS-STL-0002 | STL | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00UBA-SS-STL-0002 | STL | ALP-EPC-00UBA-PI-LAY-0001 | LAY | IFR | 2026-12-09
ALP-EPC-00UBF-CV-CAL-0001 | CAL | ALP-IEC-10MBA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-00UBF-CV-CAL-0001 | CAL | ALP-IEC-10HAA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-00UBF-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UBF-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UBF-CV-EFD-0001 | EFD | ALP-EPC-00UBF-CV-FND-0001 | FND | IFR | 2027-04-06 | driving
ALP-EPC-00UBF-CV-EFD-0001 | EFD | ALP-E02-10BBT-CV-CAL-0001 | CAL | IFR | 2027-03-23
ALP-EPC-00UBF-CV-EFD-0001 | EFD | ALP-IEC-10BAT-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-00UBF-CV-EFD-0001 | EFD | ALP-IEC-10MBA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-00UBF-CV-EFD-0001 | EFD | ALP-IEC-10HAA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-00UBF-CV-FND-0001 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UBF-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UBF-CV-FND-0001 | FND | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-00UBF-CV-FND-0001 | FND | ALP-IEC-10BAT-EL-GAD-0001 | GAD | IFR | 2026-09-28
ALP-EPC-00UBF-CV-FND-0001 | FND | ALP-EPC-00UBF-CV-FND-0002 | FND | IFR | 2027-03-02 | driving
ALP-EPC-00UBF-CV-FND-0001 | FND | ALP-IEC-10MBA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-00UBF-CV-FND-0001 | FND | ALP-IEC-10HAA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-00UBF-CV-FND-0002 | FND | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-00UBF-CV-FND-0002 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UBF-CV-FND-0002 | FND | ALP-EPC-00000-CV-SPC-0002 | SPC | IFR | 2027-02-01 | driving
ALP-EPC-00UBF-CV-RBR-0001 | RBR | ALP-EPC-00UBF-CV-FND-0001 | FND | IFR | 2027-04-06 | driving
ALP-EPC-00UBF-EL-ELY-0001 | ELY | ALP-EPC-00UBF-CV-FND-0001 | FND | IFR | 2027-04-06
ALP-EPC-00UBF-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UBF-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UBF-SS-STL-0001 | STL | ALP-EPC-00UBF-CV-CAL-0001 | CAL | IFR | 2027-04-13 | driving
ALP-EPC-00UBF-SS-STL-0001 | STL | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00UBF-SS-STL-0001 | STL | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-00UCA-CV-ARC-0001 | ARC | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UCA-CV-ARC-0001 | ARC | ALP-EPC-00UCA-PI-LAY-0001 | LAY | IFR | 2026-12-15 | driving
ALP-EPC-00UCA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UCA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UCA-CV-FND-0001 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18 | driving
ALP-EPC-00UCA-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UCA-CV-FND-0001 | FND | ALP-EPC-00UCA-PI-LAY-0001 | LAY | IFR | 2026-12-15
ALP-EPC-00UCA-CV-RBR-0001 | RBR | ALP-EPC-00UCA-CV-FND-0001 | FND | IFR | 2027-02-17 | driving
ALP-EPC-00UCA-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-CAL-0001 | CAL | IFR | 2027-01-14
ALP-EPC-00UCA-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UCA-EL-CBL-0001 | CBL | ALP-EPC-00UCA-EL-ELY-0001 | ELY | IFR | 2027-03-15
ALP-EPC-00UCA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UCA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08 | driving
ALP-EPC-00UCA-EL-ELY-0001 | ELY | ALP-EPC-00UCA-PI-LAY-0001 | LAY | IFR | 2026-12-15
ALP-EPC-00UCA-EL-ELY-0002 | ELY | ALP-EPC-00UCA-EL-ELY-0001 | ELY | IFR | 2027-03-15
ALP-EPC-00UCA-EL-ELY-0002 | ELY | ALP-EPC-00UCA-PI-PPL-0001 | PPL | IFR | 2027-07-07 | driving
ALP-EPC-00UCA-EL-ELY-0003 | ELY | ALP-EPC-00UCA-CV-FND-0001 | FND | IFR | 2027-02-17
ALP-EPC-00UCA-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UCA-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UCA-HS-GAD-0001 | GAD | ALP-EPC-00UCA-CV-ARC-0001 | ARC | IFR | 2027-02-02 | driving
ALP-EPC-00UCA-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UCA-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UCA-HV-GAD-0001 | GAD | ALP-EPC-00SAA-HV-CAL-0001 | CAL | IFR | 2027-02-08
ALP-EPC-00UCA-HV-GAD-0001 | GAD | ALP-EPC-00UCA-PI-LAY-0001 | LAY | IFR | 2026-12-15
ALP-EPC-00UCA-HV-GAD-0002 | GAD | ALP-EPC-00UCA-CV-ARC-0001 | ARC | IFR | 2027-02-02 | driving
ALP-EPC-00UCA-HV-GAD-0002 | GAD | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UCA-IC-ELY-0001 | ELY | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UCA-IC-ELY-0001 | ELY | ALP-EPC-00UCA-PI-LAY-0001 | LAY | IFR | 2026-12-15
ALP-EPC-00UCA-IC-ELY-0002 | ELY | ALP-EPC-00UCA-CV-ARC-0001 | ARC | IFR | 2027-02-02 | driving
ALP-EPC-00UCA-IC-ELY-0002 | ELY | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UCA-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UCA-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00UCA-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27 | driving
ALP-EPC-00UCA-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06
ALP-EPC-00UCA-IC-LOP-0002 | LOP | ALP-EPC-00UCA-IC-ELY-0001 | ELY | IFR | 2027-08-06 | driving
ALP-EPC-00UCA-IC-LOP-0002 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-00UCA-PI-LAY-0001 | LAY | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UCA-PI-PPL-0001 | PPL | ALP-EPC-00UCA-PI-LAY-0001 | LAY | IFR | 2026-12-15
ALP-EPC-00UCA-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-SPC-0002 | SPC | IFR | 2026-12-14
ALP-EPC-00UCA-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-M3D-0001 | M3D | IFR | 2026-12-14
ALP-EPC-00UCA-SS-STL-0001 | STL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UCA-SS-STL-0001 | STL | ALP-EPC-00UCA-CV-ARC-0001 | ARC | IFR | 2027-02-02
ALP-EPC-00UCA-SS-STL-0001 | STL | ALP-EPC-00UCA-CV-CAL-0001 | CAL | IFR | 2027-04-06 | driving
ALP-EPC-00UCA-SS-STL-0002 | STL | ALP-EPC-00UCA-CV-CAL-0001 | CAL | IFR | 2027-04-06 | driving
ALP-EPC-00UCA-SS-STL-0002 | STL | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00UCA-SS-STL-0002 | STL | ALP-EPC-00UCA-PI-LAY-0001 | LAY | IFR | 2026-12-15
ALP-EPC-00UEG-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UEG-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UEG-CV-EFD-0001 | EFD | ALP-EPC-00UEG-CV-FND-0001 | FND | IFR | 2027-04-21
ALP-EPC-00UEG-CV-EFD-0001 | EFD | ALP-M16-00EGA-CV-CAL-0001 | CAL | IFR | 2027-02-22
ALP-EPC-00UEG-CV-FND-0001 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UEG-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UEG-CV-FND-0001 | FND | ALP-EPC-00UEG-PI-LAY-0001 | LAY | IFR | 2026-12-18
ALP-EPC-00UEG-CV-RBR-0001 | RBR | ALP-EPC-00UEG-CV-FND-0001 | FND | IFR | 2027-04-21 | driving
ALP-EPC-00UEG-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-CAL-0001 | CAL | IFR | 2027-01-14
ALP-EPC-00UEG-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UEG-EL-CBL-0001 | CBL | ALP-EPC-00UEG-EL-ELY-0001 | ELY | IFR | 2027-07-30
ALP-EPC-00UEG-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UEG-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UEG-EL-ELY-0001 | ELY | ALP-EPC-00UEG-PI-LAY-0001 | LAY | IFR | 2026-12-18
ALP-EPC-00UEG-EL-ELY-0002 | ELY | ALP-EPC-00UEG-EL-ELY-0001 | ELY | IFR | 2027-07-30
ALP-EPC-00UEG-EL-ELY-0002 | ELY | ALP-EPC-00UEG-PI-PPL-0001 | PPL | IFR | 2027-02-26
ALP-EPC-00UEG-EL-ELY-0003 | ELY | ALP-EPC-00UEG-CV-FND-0001 | FND | IFR | 2027-04-21
ALP-EPC-00UEG-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UEG-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UEG-IC-ELY-0001 | ELY | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UEG-IC-ELY-0001 | ELY | ALP-EPC-00UEG-PI-LAY-0001 | LAY | IFR | 2026-12-18
ALP-EPC-00UEG-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UEG-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00UEG-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27 | driving
ALP-EPC-00UEG-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06
ALP-EPC-00UEG-IC-LOP-0002 | LOP | ALP-EPC-00UEG-IC-ELY-0001 | ELY | IFR | 2027-08-06 | driving
ALP-EPC-00UEG-IC-LOP-0002 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-00UEG-PI-LAY-0001 | LAY | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UEG-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-M3D-0001 | M3D | IFR | 2026-12-14
ALP-EPC-00UEG-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-SPC-0002 | SPC | IFR | 2026-12-14
ALP-EPC-00UEG-PI-PPL-0001 | PPL | ALP-EPC-00UEG-PI-LAY-0001 | LAY | IFR | 2026-12-18 | driving
ALP-EPC-00UEG-SS-STL-0001 | STL | ALP-EPC-00UEG-CV-CAL-0001 | CAL | IFR | 2027-02-16 | driving
ALP-EPC-00UEG-SS-STL-0001 | STL | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00UEG-SS-STL-0001 | STL | ALP-EPC-00UEG-PI-LAY-0001 | LAY | IFR | 2026-12-18
ALP-EPC-00UEK-CV-ARC-0001 | ARC | ALP-EPC-00UEK-PI-LAY-0001 | LAY | IFR | 2026-12-23
ALP-EPC-00UEK-CV-ARC-0001 | ARC | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UEK-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UEK-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UEK-CV-EFD-0001 | EFD | ALP-EPC-00UEK-CV-FND-0001 | FND | IFR | 2027-06-17 | driving
ALP-EPC-00UEK-CV-EFD-0001 | EFD | ALP-M15-00EKA-CV-CAL-0001 | CAL | IFR | 2027-02-25
ALP-EPC-00UEK-CV-FND-0001 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UEK-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UEK-CV-FND-0001 | FND | ALP-EPC-00UEK-PI-LAY-0001 | LAY | IFR | 2026-12-23
ALP-EPC-00UEK-CV-RBR-0001 | RBR | ALP-EPC-00UEK-CV-FND-0001 | FND | IFR | 2027-06-17 | driving
ALP-EPC-00UEK-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-CAL-0001 | CAL | IFR | 2027-01-14
ALP-EPC-00UEK-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UEK-EL-CBL-0001 | CBL | ALP-EPC-00UEK-EL-ELY-0001 | ELY | IFR | 2027-04-13
ALP-EPC-00UEK-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UEK-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UEK-EL-ELY-0001 | ELY | ALP-EPC-00UEK-PI-LAY-0001 | LAY | IFR | 2026-12-23
ALP-EPC-00UEK-EL-ELY-0002 | ELY | ALP-EPC-00UEK-EL-ELY-0001 | ELY | IFR | 2027-04-13
ALP-EPC-00UEK-EL-ELY-0002 | ELY | ALP-EPC-00UEK-PI-PPL-0001 | PPL | IFR | 2027-03-03
ALP-EPC-00UEK-EL-ELY-0003 | ELY | ALP-EPC-00UEK-CV-FND-0001 | FND | IFR | 2027-06-17
ALP-EPC-00UEK-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UEK-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UEK-HS-GAD-0001 | GAD | ALP-EPC-00UEK-CV-ARC-0001 | ARC | IFR | 2027-04-30 | driving
ALP-EPC-00UEK-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UEK-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UEK-HV-GAD-0001 | GAD | ALP-EPC-00UEK-CV-ARC-0001 | ARC | IFR | 2027-04-30 | driving
ALP-EPC-00UEK-HV-GAD-0001 | GAD | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UEK-IC-ELY-0001 | ELY | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UEK-IC-ELY-0001 | ELY | ALP-EPC-00UEK-PI-LAY-0001 | LAY | IFR | 2026-12-23
ALP-EPC-00UEK-IC-ELY-0002 | ELY | ALP-EPC-00UEK-CV-ARC-0001 | ARC | IFR | 2027-04-30 | driving
ALP-EPC-00UEK-IC-ELY-0002 | ELY | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UEK-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UEK-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00UEK-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27 | driving
ALP-EPC-00UEK-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06
ALP-EPC-00UEK-IC-LOP-0002 | LOP | ALP-EPC-00UEK-IC-ELY-0001 | ELY | IFR | 2027-08-06 | driving
ALP-EPC-00UEK-IC-LOP-0002 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-00UEK-PI-LAY-0001 | LAY | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UEK-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-M3D-0001 | M3D | IFR | 2026-12-14
ALP-EPC-00UEK-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-SPC-0002 | SPC | IFR | 2026-12-14
ALP-EPC-00UEK-PI-PPL-0001 | PPL | ALP-EPC-00UEK-PI-LAY-0001 | LAY | IFR | 2026-12-23 | driving
ALP-EPC-00UEK-SS-STL-0001 | STL | ALP-EPC-00UEK-CV-CAL-0001 | CAL | IFR | 2027-04-12 | driving
ALP-EPC-00UEK-SS-STL-0001 | STL | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00UEK-SS-STL-0001 | STL | ALP-EPC-00UEK-PI-LAY-0001 | LAY | IFR | 2026-12-23
ALP-EPC-00UGA-CV-ARC-0001 | ARC | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00UGA-CV-ARC-0001 | ARC | ALP-EPC-00UGA-PI-LAY-0001 | LAY | IFR | 2026-12-11
ALP-EPC-00UGA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UGA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UGA-CV-EFD-0001 | EFD | ALP-EPC-00UGA-CV-FND-0001 | FND | IFR | 2027-02-24
ALP-EPC-00UGA-CV-EFD-0001 | EFD | ALP-M12-00GBA-CV-CAL-0001 | CAL | IFR | 2027-03-11
ALP-EPC-00UGA-CV-EFD-0001 | EFD | ALP-M13-00GHA-CV-CAL-0001 | CAL | IFR | 2027-02-11
ALP-EPC-00UGA-CV-EFD-0001 | EFD | ALP-M14-00GNA-CV-CAL-0001 | CAL | IFR | 2027-03-01
ALP-EPC-00UGA-CV-FND-0001 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18 | driving
ALP-EPC-00UGA-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UGA-CV-FND-0001 | FND | ALP-EPC-00UGA-PI-LAY-0001 | LAY | IFR | 2026-12-11
ALP-EPC-00UGA-CV-RBR-0001 | RBR | ALP-EPC-00UGA-CV-FND-0001 | FND | IFR | 2027-02-24 | driving
ALP-EPC-00UGA-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-CAL-0001 | CAL | IFR | 2027-01-14
ALP-EPC-00UGA-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UGA-EL-CBL-0001 | CBL | ALP-EPC-00UGA-EL-ELY-0001 | ELY | IFR | 2027-09-09
ALP-EPC-00UGA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UGA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UGA-EL-ELY-0001 | ELY | ALP-EPC-00UGA-PI-LAY-0001 | LAY | IFR | 2026-12-11
ALP-EPC-00UGA-EL-ELY-0002 | ELY | ALP-EPC-00UGA-EL-ELY-0001 | ELY | IFR | 2027-09-09 | driving
ALP-EPC-00UGA-EL-ELY-0002 | ELY | ALP-EPC-00UGA-PI-PPL-0001 | PPL | IFR | 2027-03-03
ALP-EPC-00UGA-EL-ELY-0003 | ELY | ALP-EPC-00UGA-CV-FND-0001 | FND | IFR | 2027-02-24
ALP-EPC-00UGA-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UGA-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UGA-HS-GAD-0001 | GAD | ALP-EPC-00UGA-CV-ARC-0001 | ARC | IFR | 2027-01-22 | driving
ALP-EPC-00UGA-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UGA-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UGA-HV-GAD-0001 | GAD | ALP-EPC-00UGA-CV-ARC-0001 | ARC | IFR | 2027-01-22
ALP-EPC-00UGA-HV-GAD-0001 | GAD | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UGA-IC-ELY-0001 | ELY | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UGA-IC-ELY-0001 | ELY | ALP-EPC-00UGA-PI-LAY-0001 | LAY | IFR | 2026-12-11
ALP-EPC-00UGA-IC-ELY-0002 | ELY | ALP-EPC-00UGA-CV-ARC-0001 | ARC | IFR | 2027-01-22 | driving
ALP-EPC-00UGA-IC-ELY-0002 | ELY | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UGA-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UGA-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00UGA-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-00UGA-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06
ALP-EPC-00UGA-IC-LOP-0002 | LOP | ALP-EPC-00UGA-IC-ELY-0001 | ELY | IFR | 2027-08-10 | driving
ALP-EPC-00UGA-IC-LOP-0002 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-00UGA-PI-LAY-0001 | LAY | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UGA-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-M3D-0001 | M3D | IFR | 2026-12-14
ALP-EPC-00UGA-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-SPC-0002 | SPC | IFR | 2026-12-14
ALP-EPC-00UGA-PI-PPL-0001 | PPL | ALP-EPC-00UGA-PI-LAY-0001 | LAY | IFR | 2026-12-11
ALP-EPC-00UGA-SS-STL-0001 | STL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UGA-SS-STL-0001 | STL | ALP-EPC-00UGA-CV-ARC-0001 | ARC | IFR | 2027-01-22
ALP-EPC-00UGA-SS-STL-0001 | STL | ALP-EPC-00UGA-CV-CAL-0001 | CAL | IFR | 2027-02-22 | driving
ALP-EPC-00UGA-SS-STL-0002 | STL | ALP-EPC-00UGA-CV-CAL-0001 | CAL | IFR | 2027-02-22 | driving
ALP-EPC-00UGA-SS-STL-0002 | STL | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00UGA-SS-STL-0002 | STL | ALP-EPC-00UGA-PI-LAY-0001 | LAY | IFR | 2026-12-11
ALP-EPC-00UPA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UPA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UPA-CV-CAL-0002 | CAL | ALP-EPC-00000-PR-STU-0003 | STU | IFR | 2027-06-02 | driving
ALP-EPC-00UPA-CV-CAL-0002 | CAL | ALP-EPC-00PAA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00UPA-CV-CVL-0001 | CVL | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UPA-CV-CVL-0001 | CVL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UPA-CV-CVL-0001 | CVL | ALP-EPC-00UPA-CV-CAL-0002 | CAL | IFR | 2027-06-23 | driving
ALP-EPC-00UPA-CV-MOS-0001 | MOS | ALP-EPC-00UPA-CV-CVL-0001 | CVL | IFR | 2027-08-17 | driving
ALP-EPC-00UPA-CV-RBR-0001 | RBR | ALP-EPC-00UPA-CV-CVL-0001 | CVL | IFR | 2027-08-17 | driving
ALP-EPC-00UPA-CV-RPT-0001 | RPT | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UPA-EL-ELY-0001 | ELY | ALP-EPC-00UPA-CV-CVL-0001 | CVL | IFR | 2027-08-17 | driving
ALP-EPC-00UPA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UPA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UPA-EL-ELY-0002 | ELY | ALP-EPC-00UPA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-00UPA-EL-ELY-0002 | ELY | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UPA-EL-ELY-0002 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08 | driving
ALP-EPC-00UPA-GE-RPT-0001 | RPT | ALP-EPC-00000-CV-MRQ-0003 | MRQ | IFR | 2026-11-02
ALP-EPC-00UPA-PI-LAY-0001 | LAY | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UPC-CV-ARC-0001 | ARC | ALP-EPC-00UPC-PI-LAY-0001 | LAY | IFR | 2026-12-02
ALP-EPC-00UPC-CV-ARC-0001 | ARC | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-00UPC-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18 | driving
ALP-EPC-00UPC-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UPC-CV-EFD-0001 | EFD | ALP-EPC-00UPC-CV-FND-0001 | FND | IFR | 2027-04-08 | driving
ALP-EPC-00UPC-CV-EFD-0001 | EFD | ALP-M03-00PAC-CV-CAL-0001 | CAL | IFR | 2027-02-25
ALP-EPC-00UPC-CV-EFD-0001 | EFD | ALP-M04-00PAA-CV-CAL-0001 | CAL | IFR | 2027-03-11
ALP-EPC-00UPC-CV-EFD-0001 | EFD | ALP-M05-00PBA-CV-CAL-0001 | CAL | IFR | 2027-03-12
ALP-EPC-00UPC-CV-FND-0001 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UPC-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UPC-CV-FND-0001 | FND | ALP-EPC-00UPC-PI-LAY-0001 | LAY | IFR | 2026-12-02
ALP-EPC-00UPC-CV-FND-0001 | FND | ALP-EPC-00UPC-CV-FND-0002 | FND | IFR | 2027-03-02 | driving
ALP-EPC-00UPC-CV-FND-0002 | FND | ALP-EPC-00UPC-PI-LAY-0001 | LAY | IFR | 2026-12-02
ALP-EPC-00UPC-CV-FND-0002 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UPC-CV-FND-0002 | FND | ALP-EPC-00000-CV-SPC-0002 | SPC | IFR | 2027-02-01 | driving
ALP-EPC-00UPC-CV-RBR-0001 | RBR | ALP-EPC-00UPC-CV-FND-0001 | FND | IFR | 2027-04-08 | driving
ALP-EPC-00UPC-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-CAL-0001 | CAL | IFR | 2027-01-14
ALP-EPC-00UPC-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UPC-EL-CBL-0001 | CBL | ALP-EPC-00UPC-EL-ELY-0001 | ELY | IFR | 2027-08-13
ALP-EPC-00UPC-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UPC-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UPC-EL-ELY-0001 | ELY | ALP-EPC-00UPC-PI-LAY-0001 | LAY | IFR | 2026-12-02
ALP-EPC-00UPC-EL-ELY-0002 | ELY | ALP-EPC-00UPC-EL-ELY-0001 | ELY | IFR | 2027-08-13
ALP-EPC-00UPC-EL-ELY-0002 | ELY | ALP-EPC-00UPC-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-00UPC-EL-ELY-0003 | ELY | ALP-EPC-00UPC-CV-FND-0001 | FND | IFR | 2027-04-08
ALP-EPC-00UPC-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UPC-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UPC-HS-GAD-0001 | GAD | ALP-EPC-00UPC-CV-ARC-0001 | ARC | IFR | 2027-01-14 | driving
ALP-EPC-00UPC-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UPC-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UPC-HV-GAD-0001 | GAD | ALP-EPC-00UPC-CV-ARC-0001 | ARC | IFR | 2027-01-14
ALP-EPC-00UPC-HV-GAD-0001 | GAD | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UPC-IC-ELY-0001 | ELY | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UPC-IC-ELY-0001 | ELY | ALP-EPC-00UPC-PI-LAY-0001 | LAY | IFR | 2026-12-02
ALP-EPC-00UPC-IC-ELY-0002 | ELY | ALP-EPC-00UPC-CV-ARC-0001 | ARC | IFR | 2027-01-14 | driving
ALP-EPC-00UPC-IC-ELY-0002 | ELY | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UPC-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UPC-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00UPC-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27 | driving
ALP-EPC-00UPC-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06
ALP-EPC-00UPC-IC-LOP-0002 | LOP | ALP-EPC-00UPC-IC-ELY-0001 | ELY | IFR | 2027-08-06 | driving
ALP-EPC-00UPC-IC-LOP-0002 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-00UPC-PI-LAY-0001 | LAY | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UPC-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-M3D-0001 | M3D | IFR | 2026-12-14
ALP-EPC-00UPC-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-SPC-0002 | SPC | IFR | 2026-12-14
ALP-EPC-00UPC-PI-PPL-0001 | PPL | ALP-EPC-00UPC-PI-LAY-0001 | LAY | IFR | 2026-12-02
ALP-EPC-00UPC-SS-STL-0001 | STL | ALP-EPC-00UPC-CV-CAL-0001 | CAL | IFR | 2027-02-09 | driving
ALP-EPC-00UPC-SS-STL-0001 | STL | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00UPC-SS-STL-0001 | STL | ALP-EPC-00UPC-PI-LAY-0001 | LAY | IFR | 2026-12-02
ALP-EPC-00UQA-CV-ARC-0001 | ARC | ALP-EPC-00UQA-PI-LAY-0001 | LAY | IFR | 2026-12-21 | driving
ALP-EPC-00UQA-CV-ARC-0001 | ARC | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UQA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UQA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UQA-CV-EFD-0001 | EFD | ALP-EPC-00UQA-CV-FND-0001 | FND | IFR | 2027-03-16
ALP-EPC-00UQA-CV-EFD-0001 | EFD | ALP-M01-10LAC-CV-CAL-0001 | CAL | IFR | 2027-02-25
ALP-EPC-00UQA-CV-EFD-0001 | EFD | ALP-M07-00PGA-CV-CAL-0001 | CAL | IFR | 2027-03-11
ALP-EPC-00UQA-CV-EFD-0001 | EFD | ALP-M08-00QEA-CV-CAL-0001 | CAL | IFR | 2027-03-17
ALP-EPC-00UQA-CV-EFD-0001 | EFD | ALP-M09-00QHA-CV-CAL-0001 | CAL | IFR | 2027-02-25
ALP-EPC-00UQA-CV-EFD-0001 | EFD | ALP-M18-10HSB-CV-CAL-0001 | CAL | IFR | 2027-03-22
ALP-EPC-00UQA-CV-EFD-0001 | EFD | ALP-M20-00SGA-CV-CAL-0001 | CAL | IFR | 2027-03-03
ALP-EPC-00UQA-CV-FND-0001 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UQA-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UQA-CV-FND-0001 | FND | ALP-EPC-00UQA-PI-LAY-0001 | LAY | IFR | 2026-12-21
ALP-EPC-00UQA-CV-RBR-0001 | RBR | ALP-EPC-00UQA-CV-FND-0001 | FND | IFR | 2027-03-16
ALP-EPC-00UQA-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-CAL-0001 | CAL | IFR | 2027-01-14
ALP-EPC-00UQA-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UQA-EL-CBL-0001 | CBL | ALP-EPC-00UQA-EL-ELY-0001 | ELY | IFR | 2027-05-12
ALP-EPC-00UQA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UQA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UQA-EL-ELY-0001 | ELY | ALP-EPC-00UQA-PI-LAY-0001 | LAY | IFR | 2026-12-21
ALP-EPC-00UQA-EL-ELY-0002 | ELY | ALP-EPC-00UQA-EL-ELY-0001 | ELY | IFR | 2027-05-12
ALP-EPC-00UQA-EL-ELY-0002 | ELY | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-00UQA-EL-ELY-0002 | ELY | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-00UQA-EL-ELY-0002 | ELY | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19
ALP-EPC-00UQA-EL-ELY-0003 | ELY | ALP-EPC-00UQA-CV-FND-0001 | FND | IFR | 2027-03-16
ALP-EPC-00UQA-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UQA-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UQA-HS-GAD-0001 | GAD | ALP-EPC-00UQA-CV-ARC-0001 | ARC | IFR | 2027-01-25 | driving
ALP-EPC-00UQA-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UQA-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UQA-HV-GAD-0001 | GAD | ALP-EPC-00UQA-CV-ARC-0001 | ARC | IFR | 2027-01-25
ALP-EPC-00UQA-HV-GAD-0001 | GAD | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UQA-IC-ELY-0001 | ELY | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UQA-IC-ELY-0001 | ELY | ALP-EPC-00UQA-PI-LAY-0001 | LAY | IFR | 2026-12-21
ALP-EPC-00UQA-IC-ELY-0002 | ELY | ALP-EPC-00UQA-CV-ARC-0001 | ARC | IFR | 2027-01-25 | driving
ALP-EPC-00UQA-IC-ELY-0002 | ELY | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UQA-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06
ALP-EPC-00UQA-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00UQA-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27 | driving
ALP-EPC-00UQA-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06
ALP-EPC-00UQA-IC-LOP-0002 | LOP | ALP-EPC-00UQA-IC-ELY-0001 | ELY | IFR | 2027-08-20 | driving
ALP-EPC-00UQA-IC-LOP-0002 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-00UQA-IC-LOP-0003 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27 | driving
ALP-EPC-00UQA-IC-LOP-0003 | LOP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06
ALP-EPC-00UQA-PI-LAY-0001 | LAY | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UQA-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-M3D-0001 | M3D | IFR | 2026-12-14
ALP-EPC-00UQA-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-SPC-0002 | SPC | IFR | 2026-12-14
ALP-EPC-00UQA-PI-PPL-0001 | PPL | ALP-EPC-00UQA-PI-LAY-0001 | LAY | IFR | 2026-12-21
ALP-EPC-00UQA-PI-PPL-0002 | PPL | ALP-EPC-00UQA-PI-LAY-0001 | LAY | IFR | 2026-12-21
ALP-EPC-00UQA-PI-PPL-0002 | PPL | ALP-EPC-00000-PI-SPC-0002 | SPC | IFR | 2026-12-14
ALP-EPC-00UQA-PI-PPL-0002 | PPL | ALP-EPC-00000-PI-M3D-0001 | M3D | IFR | 2026-12-14
ALP-EPC-00UQA-PI-PPL-0003 | PPL | ALP-EPC-00UQA-PI-LAY-0001 | LAY | IFR | 2026-12-21
ALP-EPC-00UQA-PI-PPL-0003 | PPL | ALP-EPC-00000-PI-SPC-0002 | SPC | IFR | 2026-12-14
ALP-EPC-00UQA-PI-PPL-0003 | PPL | ALP-EPC-00000-PI-M3D-0001 | M3D | IFR | 2026-12-14
ALP-EPC-00UQA-SS-STL-0001 | STL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UQA-SS-STL-0001 | STL | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00UQA-SS-STL-0001 | STL | ALP-EPC-00UQA-PI-LAY-0001 | LAY | IFR | 2026-12-21
ALP-EPC-00UQA-SS-STL-0001 | STL | ALP-EPC-00UQA-CV-CAL-0001 | CAL | IFR | 2027-03-30 | driving
ALP-EPC-00USA-CV-ARC-0001 | ARC | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00USA-CV-ARC-0001 | ARC | ALP-EPC-00UCA-PI-LAY-0001 | LAY | IFR | 2026-12-15 | driving
ALP-EPC-00USA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00USA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00USA-CV-FND-0001 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18 | driving
ALP-EPC-00USA-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00USA-CV-FND-0001 | FND | ALP-EPC-00UCA-PI-LAY-0001 | LAY | IFR | 2026-12-15
ALP-EPC-00USA-CV-RBR-0001 | RBR | ALP-EPC-00USA-CV-FND-0001 | FND | IFR | 2027-02-17 | driving
ALP-EPC-00USA-EL-ELY-0001 | ELY | ALP-EPC-00USA-CV-FND-0001 | FND | IFR | 2027-02-17
ALP-EPC-00USA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00USA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00USA-HS-GAD-0001 | GAD | ALP-EPC-00USA-CV-ARC-0001 | ARC | IFR | 2027-01-25 | driving
ALP-EPC-00USA-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00USA-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00USA-HV-GAD-0001 | GAD | ALP-EPC-00USA-CV-ARC-0001 | ARC | IFR | 2027-01-25
ALP-EPC-00USA-HV-GAD-0001 | GAD | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00USA-IC-ELY-0001 | ELY | ALP-EPC-00USA-CV-ARC-0001 | ARC | IFR | 2027-01-25 | driving
ALP-EPC-00USA-IC-ELY-0001 | ELY | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00USA-SS-STL-0001 | STL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00USA-SS-STL-0001 | STL | ALP-EPC-00USA-CV-ARC-0001 | ARC | IFR | 2027-01-25
ALP-EPC-00USA-SS-STL-0001 | STL | ALP-EPC-00USA-CV-CAL-0001 | CAL | IFR | 2027-04-05 | driving
ALP-EPC-00USA-SS-STL-0002 | STL | ALP-EPC-00USA-CV-CAL-0001 | CAL | IFR | 2027-04-05 | driving
ALP-EPC-00USA-SS-STL-0002 | STL | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00USA-SS-STL-0002 | STL | ALP-EPC-00UCA-PI-LAY-0001 | LAY | IFR | 2026-12-15
ALP-EPC-00UYA-CV-ARC-0001 | ARC | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UYA-CV-ARC-0001 | ARC | ALP-EPC-00UCA-PI-LAY-0001 | LAY | IFR | 2026-12-15 | driving
ALP-EPC-00UYA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UYA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UYA-CV-FND-0001 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18 | driving
ALP-EPC-00UYA-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UYA-CV-FND-0001 | FND | ALP-EPC-00UCA-PI-LAY-0001 | LAY | IFR | 2026-12-15
ALP-EPC-00UYA-CV-RBR-0001 | RBR | ALP-EPC-00UYA-CV-FND-0001 | FND | IFR | 2027-02-17 | driving
ALP-EPC-00UYA-EL-ELY-0001 | ELY | ALP-EPC-00UYA-CV-FND-0001 | FND | IFR | 2027-02-17
ALP-EPC-00UYA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UYA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UYA-HS-GAD-0001 | GAD | ALP-EPC-00UYA-CV-ARC-0001 | ARC | IFR | 2027-02-02 | driving
ALP-EPC-00UYA-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UYA-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UYA-HV-GAD-0001 | GAD | ALP-EPC-00UYA-CV-ARC-0001 | ARC | IFR | 2027-02-02
ALP-EPC-00UYA-HV-GAD-0001 | GAD | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00UYA-IC-ELY-0001 | ELY | ALP-EPC-00UYA-CV-ARC-0001 | ARC | IFR | 2027-02-02 | driving
ALP-EPC-00UYA-IC-ELY-0001 | ELY | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-00UYA-SS-STL-0001 | STL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UYA-SS-STL-0001 | STL | ALP-EPC-00UYA-CV-ARC-0001 | ARC | IFR | 2027-02-02
ALP-EPC-00UYA-SS-STL-0001 | STL | ALP-EPC-00UYA-CV-CAL-0001 | CAL | IFR | 2027-04-07 | driving
ALP-EPC-00UYA-SS-STL-0002 | STL | ALP-EPC-00UYA-CV-CAL-0001 | CAL | IFR | 2027-04-07 | driving
ALP-EPC-00UYA-SS-STL-0002 | STL | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00UYA-SS-STL-0002 | STL | ALP-EPC-00UCA-PI-LAY-0001 | LAY | IFR | 2026-12-15
ALP-EPC-00UZA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UZA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UZA-CV-CVL-0001 | CVL | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UZA-CV-CVL-0002 | CVL | ALP-EPC-00000-ME-STU-0001 | STU | IFR | 2026-12-07
ALP-EPC-00UZA-CV-CVL-0002 | CVL | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UZA-CV-CVL-0002 | CVL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UZA-CV-CVL-0002 | CVL | ALP-EPC-00GKA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00UZA-CV-CVL-0002 | CVL | ALP-EPC-00GMA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00UZA-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-CAL-0001 | CAL | IFR | 2027-01-14
ALP-EPC-00UZA-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UZA-EL-CBL-0001 | CBL | ALP-EPC-00UZA-EL-ELY-0001 | ELY | IFR | 2027-03-11 | driving
ALP-EPC-00UZA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00UZA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08 | driving
ALP-EPC-00UZA-EL-ELY-0001 | ELY | ALP-EPC-00UZA-PI-LAY-0001 | LAY | IFR | 2026-12-01
ALP-EPC-00UZA-EL-ELY-0002 | ELY | ALP-EPC-00UZA-EL-ELY-0001 | ELY | IFR | 2027-03-11 | driving
ALP-EPC-00UZA-EL-ELY-0002 | ELY | ALP-EPC-00UZA-PI-PPL-0001 | PPL | IFR | 2027-02-09
ALP-EPC-00UZA-EL-ELY-0003 | ELY | ALP-EPC-00UZA-CV-CVL-0002 | CVL | IFR | 2027-03-03 | driving
ALP-EPC-00UZA-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UZA-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UZA-IC-ELY-0001 | ELY | ALP-EPC-00UZA-PI-LAY-0001 | LAY | IFR | 2026-12-01
ALP-EPC-00UZA-IC-ELY-0001 | ELY | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UZA-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-00UZA-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00UZA-IC-LOP-0001 | LOP | ALP-EPC-00UZA-IC-ELY-0001 | ELY | IFR | 2027-08-03 | driving
ALP-EPC-00UZA-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-00UZA-IC-LOP-0002 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27 | driving
ALP-EPC-00UZA-IC-LOP-0002 | LOP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06
ALP-EPC-00UZA-PI-LAY-0001 | LAY | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UZA-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-M3D-0001 | M3D | IFR | 2026-12-14 | driving
ALP-EPC-00UZA-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-SPC-0002 | SPC | IFR | 2026-12-14
ALP-EPC-00UZA-PI-PPL-0001 | PPL | ALP-EPC-00UZA-PI-LAY-0001 | LAY | IFR | 2026-12-01
ALP-EPC-00UZB-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UZB-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UZB-CV-CVL-0001 | CVL | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UZB-CV-CVL-0001 | CVL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04 | driving
ALP-EPC-00UZB-CV-CVL-0001 | CVL | ALP-EPC-00GKA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00UZB-CV-CVL-0001 | CVL | ALP-EPC-00GMA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00UZB-EL-ELY-0001 | ELY | ALP-EPC-00UZB-CV-CVL-0001 | CVL | IFR | 2027-02-08 | driving
ALP-EPC-00UZB-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UZB-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UZC-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UZC-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UZC-CV-CVL-0001 | CVL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UZC-CV-CVL-0001 | CVL | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UZC-CV-CVL-0001 | CVL | ALP-EPC-00GKA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00UZC-CV-CVL-0001 | CVL | ALP-EPC-00GMA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00UZC-CV-RBR-0001 | RBR | ALP-EPC-00UZC-CV-CVL-0001 | CVL | IFR | 2027-03-08
ALP-EPC-00UZC-EL-ELY-0001 | ELY | ALP-EPC-00UZC-CV-CVL-0001 | CVL | IFR | 2027-03-08 | driving
ALP-EPC-00UZC-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UZC-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UZD-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18 | driving
ALP-EPC-00UZD-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UZD-CV-FND-0001 | FND | ALP-EPC-00UZA-PI-LAY-0001 | LAY | IFR | 2026-12-01
ALP-EPC-00UZD-CV-FND-0001 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UZD-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UZD-CV-RBR-0001 | RBR | ALP-EPC-00UZD-CV-FND-0001 | FND | IFR | 2027-04-16
ALP-EPC-00UZD-EL-ELY-0001 | ELY | ALP-EPC-00UZD-CV-FND-0001 | FND | IFR | 2027-04-16 | driving
ALP-EPC-00UZD-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UZD-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UZD-SS-STL-0001 | STL | ALP-EPC-00UZD-CV-CAL-0001 | CAL | IFR | 2027-02-10 | driving
ALP-EPC-00UZD-SS-STL-0001 | STL | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00UZD-SS-STL-0001 | STL | ALP-EPC-00UZA-PI-LAY-0001 | LAY | IFR | 2026-12-01
ALP-EPC-00UZE-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UZE-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UZE-CV-CVL-0001 | CVL | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-00UZE-CV-CVL-0001 | CVL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UZE-CV-CVL-0001 | CVL | ALP-EPC-00GKA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00UZE-CV-CVL-0001 | CVL | ALP-EPC-00GMA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-00UZE-CV-RBR-0001 | RBR | ALP-EPC-00UZE-CV-CVL-0001 | CVL | IFR | 2027-03-18
ALP-EPC-00UZE-EL-ELY-0001 | ELY | ALP-EPC-00UZE-CV-CVL-0001 | CVL | IFR | 2027-03-18 | driving
ALP-EPC-00UZE-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UZE-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UZF-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UZF-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UZF-CV-FND-0001 | FND | ALP-EPC-00UZF-CV-FND-0002 | FND | IFR | 2027-05-31 | driving
ALP-EPC-00UZF-CV-FND-0001 | FND | ALP-EPC-00UPA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-00UZF-CV-FND-0001 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-00UZF-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UZF-CV-FND-0002 | FND | ALP-EPC-00UPA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-00UZF-CV-FND-0002 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UZF-CV-FND-0002 | FND | ALP-EPC-00000-CV-SPC-0002 | SPC | IFR | 2027-02-01
ALP-EPC-00UZF-CV-RBR-0001 | RBR | ALP-EPC-00UZF-CV-FND-0001 | FND | IFR | 2027-07-07 | driving
ALP-EPC-00UZF-CV-RPT-0001 | RPT | ALP-EPC-00000-ME-STU-0001 | STU | IFR | 2026-12-07
ALP-EPC-00UZF-CV-RPT-0001 | RPT | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00UZF-EL-ELY-0001 | ELY | ALP-EPC-00UZF-CV-FND-0001 | FND | IFR | 2027-07-07 | driving
ALP-EPC-00UZF-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-00UZF-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-00UZF-GE-MRQ-0001 | MRQ | ALP-EPC-00UZF-GE-SPC-0001 | SPC | IFR | 2027-07-06 | driving
ALP-EPC-00UZF-GE-RPT-0001 | RPT | ALP-EPC-00UZF-GE-MRQ-0001 | MRQ | IFR | 2027-07-13
ALP-EPC-00UZF-GE-SPC-0001 | SPC | ALP-EPC-00000-ME-STU-0001 | STU | IFR | 2026-12-07
ALP-EPC-00UZF-GE-SPC-0001 | SPC | ALP-EPC-00000-ME-PLN-0001 | PLN | IFR | 2027-01-04
ALP-EPC-00UZF-GE-SPC-0001 | SPC | ALP-EPC-00UZF-CV-RPT-0001 | RPT | IFR | 2027-06-08 | driving
ALP-EPC-00UZF-GE-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-00UZF-SS-STL-0001 | STL | ALP-EPC-00UZF-CV-CAL-0001 | CAL | IFR | 2027-06-09 | driving
ALP-EPC-00UZF-SS-STL-0001 | STL | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00UZF-SS-STL-0001 | STL | ALP-EPC-00UPA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-00XJA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-00XJA-CM-MDB-0001 | MDB | ALP-EPC-00XJA-CM-CMP-0001 | CMP | IFR | 2027-01-25
ALP-EPC-00XJA-CM-OMM-0001 | OMM | ALP-EPC-00XJA-CM-CMP-0001 | CMP | IFR | 2027-01-25 | driving
ALP-EPC-00XJA-EL-DSH-0001 | DSH | ALP-EPC-00XJA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00XJA-EL-DSH-0001 | DSH | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00XJA-EL-ITP-0001 | ITP | ALP-EPC-00XJA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | ALP-EPC-00XJA-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | ALP-EPC-00XJA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | ALP-EPC-00XJA-ME-DSH-0001 | DSH | IFR | 2027-02-22
ALP-EPC-00XJA-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-00XJA-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-00XJA-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-00XJA-GE-RPT-0001 | RPT | ALP-EPC-00XJA-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-00XJA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-00XJA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-00XJA-ME-DSH-0001 | DSH | ALP-EPC-00XJA-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-00XJA-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08 | driving
ALP-EPC-10BBT-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-10BBT-CM-MDB-0001 | MDB | ALP-EPC-10BBT-CM-CMP-0001 | CMP | IFR | 2027-01-25
ALP-EPC-10BBT-CM-OMM-0001 | OMM | ALP-EPC-10BBT-CM-CMP-0001 | CMP | IFR | 2027-01-25 | driving
ALP-EPC-10BBT-EL-DSH-0001 | DSH | ALP-EPC-10BBT-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10BBT-EL-DSH-0001 | DSH | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-10BBT-EL-ITP-0001 | ITP | ALP-EPC-10BBT-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | ALP-EPC-10BBT-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | ALP-EPC-10BBT-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | ALP-EPC-20BBT-EL-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-10BBT-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-10BBT-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-LST-0001 | LST | IFR | 2026-11-02
ALP-EPC-10BBT-EL-SPC-0001 | SPC | ALP-EPC-00000-EL-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-10BBT-GE-RPT-0001 | RPT | ALP-EPC-10BBT-EL-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-10BBT-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-10BBT-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10HAN-CM-CMP-0001 | CMP | ALP-EPC-10HAN-PR-PID-0001 | PID | IFR | 2027-05-27
ALP-EPC-10HAN-CM-CMP-0001 | CMP | ALP-EPC-10HAN-IC-CNR-0001 | CNR | IFR | 2027-06-17
ALP-EPC-10HAN-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-10HAN-CM-MDB-0001 | MDB | ALP-EPC-10HAN-CM-CMP-0001 | CMP | IFR | 2027-09-02
ALP-EPC-10HAN-CM-OMM-0001 | OMM | ALP-EPC-10HAN-CM-CMP-0001 | CMP | IFR | 2027-09-02
ALP-EPC-10HAN-GE-RPT-0001 | RPT | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-10HAN-IC-CEM-0001 | CEM | ALP-EPC-10HAN-IC-CNR-0001 | CNR | IFR | 2027-06-17
ALP-EPC-10HAN-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-10HAN-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-10HAN-IC-CNR-0001 | CNR | ALP-EPC-10HAN-PR-PID-0001 | PID | IFR | 2027-05-27 | driving
ALP-EPC-10HAN-IC-DSH-0001 | DSH | ALP-EPC-10HAN-PR-PID-0001 | PID | IFR | 2027-05-27
ALP-EPC-10HAN-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-10HAN-IC-DSH-0002 | DSH | ALP-EPC-10HAN-PR-PID-0001 | PID | IFR | 2027-05-27
ALP-EPC-10HAN-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-10HAN-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10HAN-IC-HMI-0001 | HMI | ALP-EPC-10HAN-PR-PID-0001 | PID | IFR | 2027-05-27
ALP-EPC-10HAN-IC-HMI-0001 | HMI | ALP-EPC-10HAN-IC-CNR-0001 | CNR | IFR | 2027-06-17
ALP-EPC-10HAN-IC-LOG-0001 | LOG | ALP-EPC-10HAN-IC-CNR-0001 | CNR | IFR | 2027-06-17
ALP-EPC-10HAN-IC-LOG-0001 | LOG | ALP-EPC-10HAN-PR-PID-0001 | PID | IFR | 2027-05-27
ALP-EPC-10HAN-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10HAN-ME-CAL-0001 | CAL | ALP-EPC-10HAN-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10HAN-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10HAN-ME-DSH-0001 | DSH | ALP-EPC-10HAN-ME-CAL-0001 | CAL | IFR | 2027-03-19
ALP-EPC-10HAN-ME-DSH-0001 | DSH | ALP-EPC-10HAN-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10HAN-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-10HAN-ME-DSH-0002 | DSH | ALP-EPC-10HAN-ME-CAL-0001 | CAL | IFR | 2027-03-19 | driving
ALP-EPC-10HAN-ME-DSH-0002 | DSH | ALP-EPC-10HAN-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10HAN-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-10HAN-ME-ITP-0001 | ITP | ALP-EPC-10HAN-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | ALP-EPC-10HAN-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | ALP-EPC-10HAN-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | ALP-EPC-10HAN-ME-DSH-0002 | DSH | IFR | 2027-04-02
ALP-EPC-10HAN-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-10HAN-ME-SPC-0001 | SPC | ALP-EPC-10HAN-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10HAN-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-10HAN-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-10HAN-PI-ISO-0001 | ISO | ALP-EPC-10HAN-PR-PID-0001 | PID | IFR | 2027-05-27
ALP-EPC-10HAN-PI-ISO-0001 | ISO | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-10HAN-PI-ISO-0001 | ISO | ALP-EPC-10HAN-PI-STR-0001 | STR | IFR | 2027-08-17
ALP-EPC-10HAN-PI-STR-0001 | STR | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-10HAN-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10HAN-PI-SUP-0001 | SUP | ALP-EPC-10HAN-PI-ISO-0001 | ISO | IFC | 2027-12-15 | driving
ALP-EPC-10HAN-PI-SUP-0001 | SUP | ALP-EPC-10HAN-PI-STR-0001 | STR | IFC | 2027-09-07
ALP-EPC-10HAN-PR-DSH-0001 | DSH | ALP-EPC-10HAN-PR-PID-0001 | PID | IFR | 2027-05-27
ALP-EPC-10HAN-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10HAN-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10HAN-PR-PID-0001 | PID | ALP-EPC-10HAN-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10HAN-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10HAN-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-10HAN-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-10HNE-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-10HNE-CM-MDB-0001 | MDB | ALP-EPC-10HNE-CM-CMP-0001 | CMP | IFR | 2027-03-08
ALP-EPC-10HNE-GE-RPT-0001 | RPT | ALP-EPC-10HNE-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-EPC-10HNE-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-10HNE-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10HNE-ME-DSH-0001 | DSH | ALP-EPC-10HNE-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10HNE-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-10HNE-SS-MRQ-0001 | MRQ | ALP-EPC-10HNE-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-10HNE-SS-MRQ-0001 | MRQ | ALP-EPC-10HNE-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10HNE-SS-SPC-0001 | SPC | ALP-EPC-00000-HS-STU-0002 | STU | IFR | 2027-01-18
ALP-EPC-10HNE-SS-SPC-0001 | SPC | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10HSB-CM-CMP-0001 | CMP | ALP-EPC-10HSB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10HSB-CM-CMP-0001 | CMP | ALP-EPC-10HSB-IC-CNR-0001 | CNR | IFR | 2027-07-02 | driving
ALP-EPC-10HSB-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-10HSB-CM-MDB-0001 | MDB | ALP-EPC-10HSB-CM-CMP-0001 | CMP | IFR | 2027-07-30
ALP-EPC-10HSB-CM-OMM-0001 | OMM | ALP-EPC-10HSB-CM-CMP-0001 | CMP | IFR | 2027-07-30 | driving
ALP-EPC-10HSB-GE-RPT-0001 | RPT | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-10HSB-IC-CEM-0001 | CEM | ALP-EPC-10HSB-IC-CNR-0001 | CNR | IFR | 2027-07-02
ALP-EPC-10HSB-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-10HSB-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-10HSB-IC-CNR-0001 | CNR | ALP-EPC-10HSB-PR-PID-0001 | PID | IFR | 2027-06-11 | driving
ALP-EPC-10HSB-IC-DSH-0001 | DSH | ALP-EPC-10HSB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10HSB-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-10HSB-IC-DSH-0002 | DSH | ALP-EPC-10HSB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10HSB-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-10HSB-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10HSB-IC-HMI-0001 | HMI | ALP-EPC-10HSB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10HSB-IC-HMI-0001 | HMI | ALP-EPC-10HSB-IC-CNR-0001 | CNR | IFR | 2027-07-02
ALP-EPC-10HSB-IC-LOG-0001 | LOG | ALP-EPC-10HSB-IC-CNR-0001 | CNR | IFR | 2027-07-02
ALP-EPC-10HSB-IC-LOG-0001 | LOG | ALP-EPC-10HSB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10HSB-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10HSB-ME-CAL-0001 | CAL | ALP-EPC-10HSB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10HSB-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10HSB-ME-DSH-0001 | DSH | ALP-EPC-10HSB-ME-CAL-0001 | CAL | IFR | 2027-02-26
ALP-EPC-10HSB-ME-DSH-0001 | DSH | ALP-EPC-10HSB-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10HSB-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-10HSB-ME-DSH-0002 | DSH | ALP-EPC-10HSB-ME-CAL-0001 | CAL | IFR | 2027-02-26
ALP-EPC-10HSB-ME-DSH-0002 | DSH | ALP-EPC-10HSB-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10HSB-ME-DSH-0002 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-10HSB-ME-ITP-0001 | ITP | ALP-EPC-10HSB-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | ALP-EPC-10HSB-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | ALP-EPC-10HSB-ME-DSH-0002 | DSH | IFR | 2026-11-02
ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | ALP-EPC-10HSB-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10HSB-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-10HSB-ME-SPC-0001 | SPC | ALP-EPC-10HSB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10HSB-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-10HSB-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-10HSB-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-10HSB-PI-ISO-0001 | ISO | ALP-EPC-10HSB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10HSB-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-10HSB-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19
ALP-EPC-10HSB-PI-SUP-0001 | SUP | ALP-EPC-10HSB-PI-ISO-0001 | ISO | IFC | 2027-12-07
ALP-EPC-10HSB-PR-DSH-0001 | DSH | ALP-EPC-10HSB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10HSB-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10HSB-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10HSB-PR-PID-0001 | PID | ALP-EPC-10HSB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10HSB-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10HSB-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-10HSB-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-10LAB-CM-CMP-0001 | CMP | ALP-EPC-10LAB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10LAB-CM-CMP-0001 | CMP | ALP-EPC-10LAB-IC-CNR-0001 | CNR | IFR | 2027-07-02
ALP-EPC-10LAB-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-10LAB-CM-MDB-0001 | MDB | ALP-EPC-10LAB-CM-CMP-0001 | CMP | IFR | 2027-09-03
ALP-EPC-10LAB-CM-OMM-0001 | OMM | ALP-EPC-10LAB-CM-CMP-0001 | CMP | IFR | 2027-09-03
ALP-EPC-10LAB-IC-CEM-0001 | CEM | ALP-EPC-10LAB-IC-CNR-0001 | CNR | IFR | 2027-07-02
ALP-EPC-10LAB-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-10LAB-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-10LAB-IC-CNR-0001 | CNR | ALP-EPC-10LAB-PR-PID-0001 | PID | IFR | 2027-06-11 | driving
ALP-EPC-10LAB-IC-DSH-0001 | DSH | ALP-EPC-10LAB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10LAB-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-10LAB-IC-DSH-0002 | DSH | ALP-EPC-10LAB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10LAB-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-10LAB-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LAB-IC-HMI-0001 | HMI | ALP-EPC-10LAB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10LAB-IC-HMI-0001 | HMI | ALP-EPC-10LAB-IC-CNR-0001 | CNR | IFR | 2027-07-02
ALP-EPC-10LAB-IC-LOG-0001 | LOG | ALP-EPC-10LAB-IC-CNR-0001 | CNR | IFR | 2027-07-02
ALP-EPC-10LAB-IC-LOG-0001 | LOG | ALP-EPC-10LAB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10LAB-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LAB-ME-CAL-0001 | CAL | ALP-EPC-10LAB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LAB-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LAB-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-10LAB-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-10LAB-PI-ISO-0001 | ISO | ALP-EPC-10LAB-PI-STR-0001 | STR | IFR | 2027-08-19
ALP-EPC-10LAB-PI-ISO-0001 | ISO | ALP-EPC-10LAB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10LAB-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-10LAB-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19
ALP-EPC-10LAB-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LAB-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-10LAB-PI-STR-0001 | STR | ALP-IEC-00000-PI-LST-0001 | LST | IFR | 2026-12-28
ALP-EPC-10LAB-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-10LAB-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19 | driving
ALP-EPC-10LAB-PI-SUP-0001 | SUP | ALP-EPC-10LAB-PI-ISO-0001 | ISO | IFC | 2027-11-02
ALP-EPC-10LAB-PI-SUP-0001 | SUP | ALP-EPC-10LAB-PI-STR-0001 | STR | IFC | 2027-09-09
ALP-EPC-10LAB-PR-DSH-0001 | DSH | ALP-EPC-10LAB-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10LAB-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LAB-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10LAB-PR-PID-0001 | PID | ALP-EPC-10LAB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LAB-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LAB-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-10LAB-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-10LAC-CM-CMP-0001 | CMP | ALP-EPC-10LAC-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10LAC-CM-CMP-0001 | CMP | ALP-EPC-10LAC-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LAC-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-10LAC-CM-MDB-0001 | MDB | ALP-EPC-10LAC-CM-CMP-0001 | CMP | IFR | 2027-09-06
ALP-EPC-10LAC-CM-OMM-0001 | OMM | ALP-EPC-10LAC-CM-CMP-0001 | CMP | IFR | 2027-09-06
ALP-EPC-10LAC-GE-RPT-0001 | RPT | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-10LAC-IC-CEM-0001 | CEM | ALP-EPC-10LAC-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LAC-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-10LAC-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-10LAC-IC-CNR-0001 | CNR | ALP-EPC-10LAC-PR-PID-0001 | PID | IFR | 2027-06-11 | driving
ALP-EPC-10LAC-IC-DSH-0001 | DSH | ALP-EPC-10LAC-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10LAC-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-10LAC-IC-DSH-0002 | DSH | ALP-EPC-10LAC-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10LAC-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-10LAC-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LAC-IC-HMI-0001 | HMI | ALP-EPC-10LAC-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10LAC-IC-HMI-0001 | HMI | ALP-EPC-10LAC-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LAC-IC-LOG-0001 | LOG | ALP-EPC-10LAC-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LAC-IC-LOG-0001 | LOG | ALP-EPC-10LAC-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10LAC-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LAC-ME-CAL-0001 | CAL | ALP-EPC-10LAC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LAC-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11 | driving
ALP-EPC-10LAC-ME-DSH-0001 | DSH | ALP-EPC-10LAC-ME-CAL-0001 | CAL | IFR | 2027-02-03
ALP-EPC-10LAC-ME-DSH-0001 | DSH | ALP-EPC-10LAC-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10LAC-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-10LAC-ME-ITP-0001 | ITP | ALP-EPC-10LAC-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | ALP-EPC-10LAC-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | ALP-EPC-10LAC-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10LAC-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-10LAC-ME-SPC-0001 | SPC | ALP-EPC-10LAC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LAC-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-10LAC-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-10LAC-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-10LAC-PI-ISO-0001 | ISO | ALP-EPC-10LAC-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10LAC-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-10LAC-PI-ISO-0001 | ISO | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19
ALP-EPC-10LAC-PI-ISO-0001 | ISO | ALP-EPC-10LAC-PI-STR-0001 | STR | IFR | 2027-08-17
ALP-EPC-10LAC-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0001 | PPL | IFR | 2027-04-15
ALP-EPC-10LAC-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0002 | PPL | IFR | 2027-06-25
ALP-EPC-10LAC-PI-STR-0001 | STR | ALP-EPC-00UQA-PI-PPL-0003 | PPL | IFR | 2027-07-19 | driving
ALP-EPC-10LAC-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LAC-PI-SUP-0001 | SUP | ALP-EPC-10LAC-PI-ISO-0001 | ISO | IFC | 2027-11-24
ALP-EPC-10LAC-PI-SUP-0001 | SUP | ALP-EPC-10LAC-PI-STR-0001 | STR | IFC | 2027-09-07
ALP-EPC-10LAC-PR-DSH-0001 | DSH | ALP-EPC-10LAC-PR-PID-0001 | PID | IFR | 2027-06-11
ALP-EPC-10LAC-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LAC-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10LAC-PR-PID-0001 | PID | ALP-EPC-10LAC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LAC-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LAC-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-10LAC-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-10LAE-CM-CMP-0001 | CMP | ALP-EPC-10LAE-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LAE-CM-CMP-0001 | CMP | ALP-EPC-10LAE-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LAE-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-10LAE-CM-MDB-0001 | MDB | ALP-EPC-10LAE-CM-CMP-0001 | CMP | IFR | 2027-09-07
ALP-EPC-10LAE-CM-OMM-0001 | OMM | ALP-EPC-10LAE-CM-CMP-0001 | CMP | IFR | 2027-09-07
ALP-EPC-10LAE-IC-CEM-0001 | CEM | ALP-EPC-10LAE-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LAE-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-10LAE-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-10LAE-IC-CNR-0001 | CNR | ALP-EPC-10LAE-PR-PID-0001 | PID | IFR | 2027-06-14 | driving
ALP-EPC-10LAE-IC-DSH-0001 | DSH | ALP-EPC-10LAE-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LAE-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-10LAE-IC-DSH-0002 | DSH | ALP-EPC-10LAE-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LAE-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-10LAE-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LAE-IC-HMI-0001 | HMI | ALP-EPC-10LAE-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LAE-IC-HMI-0001 | HMI | ALP-EPC-10LAE-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LAE-IC-LOG-0001 | LOG | ALP-EPC-10LAE-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LAE-IC-LOG-0001 | LOG | ALP-EPC-10LAE-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LAE-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LAE-ME-CAL-0001 | CAL | ALP-EPC-10LAE-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LAE-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LAE-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-10LAE-PI-ISO-0001 | ISO | ALP-EPC-10LAE-PI-STR-0001 | STR | IFR | 2027-11-02
ALP-EPC-10LAE-PI-ISO-0001 | ISO | ALP-EPC-10LAE-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LAE-PI-ISO-0001 | ISO | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-10LAE-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LAE-PI-STR-0001 | STR | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-10LAE-PI-STR-0001 | STR | ALP-IEC-00000-PI-LST-0001 | LST | IFR | 2026-12-28
ALP-EPC-10LAE-PI-SUP-0001 | SUP | ALP-EPC-10LAE-PI-ISO-0001 | ISO | IFC | 2028-01-25 | driving
ALP-EPC-10LAE-PI-SUP-0001 | SUP | ALP-EPC-10LAE-PI-STR-0001 | STR | IFC | 2027-11-23
ALP-EPC-10LAE-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10LAE-PR-PID-0001 | PID | ALP-EPC-10LAE-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LAE-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LAE-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-10LAE-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-10LAF-CM-CMP-0001 | CMP | ALP-EPC-10LAF-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LAF-CM-CMP-0001 | CMP | ALP-EPC-10LAF-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LAF-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-10LAF-CM-MDB-0001 | MDB | ALP-EPC-10LAF-CM-CMP-0001 | CMP | IFR | 2027-09-13
ALP-EPC-10LAF-CM-OMM-0001 | OMM | ALP-EPC-10LAF-CM-CMP-0001 | CMP | IFR | 2027-09-13 | driving
ALP-EPC-10LAF-IC-CEM-0001 | CEM | ALP-EPC-10LAF-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LAF-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-10LAF-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-10LAF-IC-CNR-0001 | CNR | ALP-EPC-10LAF-PR-PID-0001 | PID | IFR | 2027-06-14 | driving
ALP-EPC-10LAF-IC-DSH-0001 | DSH | ALP-EPC-10LAF-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LAF-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-10LAF-IC-DSH-0002 | DSH | ALP-EPC-10LAF-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LAF-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-10LAF-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LAF-IC-HMI-0001 | HMI | ALP-EPC-10LAF-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LAF-IC-HMI-0001 | HMI | ALP-EPC-10LAF-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LAF-IC-LOG-0001 | LOG | ALP-EPC-10LAF-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LAF-IC-LOG-0001 | LOG | ALP-EPC-10LAF-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LAF-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LAF-ME-CAL-0001 | CAL | ALP-EPC-10LAF-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LAF-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LAF-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-10LAF-PI-ISO-0001 | ISO | ALP-EPC-10LAF-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LAF-PI-ISO-0001 | ISO | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-10LAF-PI-ISO-0001 | ISO | ALP-EPC-10LAF-PI-STR-0001 | STR | IFR | 2027-11-08
ALP-EPC-10LAF-PI-STR-0001 | STR | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-10LAF-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LAF-PI-SUP-0001 | SUP | ALP-EPC-10LAF-PI-ISO-0001 | ISO | IFC | 2028-01-25 | driving
ALP-EPC-10LAF-PI-SUP-0001 | SUP | ALP-EPC-10LAF-PI-STR-0001 | STR | IFC | 2027-11-29
ALP-EPC-10LAF-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10LAF-PR-PID-0001 | PID | ALP-EPC-10LAF-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LAF-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LAF-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-10LAF-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-10LBA-CM-CMP-0001 | CMP | ALP-EPC-10LBA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBA-CM-CMP-0001 | CMP | ALP-EPC-10LBA-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-10LBA-CM-MDB-0001 | MDB | ALP-EPC-10LBA-CM-CMP-0001 | CMP | IFR | 2027-09-17
ALP-EPC-10LBA-CM-OMM-0001 | OMM | ALP-EPC-10LBA-CM-CMP-0001 | CMP | IFR | 2027-09-17 | driving
ALP-EPC-10LBA-GE-RPT-0001 | RPT | ALP-EPC-00000-PI-MRQ-0002 | MRQ | IFR | 2027-01-18
ALP-EPC-10LBA-IC-CEM-0001 | CEM | ALP-EPC-10LBA-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBA-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-10LBA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-10LBA-IC-CNR-0001 | CNR | ALP-EPC-10LBA-PR-PID-0001 | PID | IFR | 2027-06-14 | driving
ALP-EPC-10LBA-IC-DSH-0001 | DSH | ALP-EPC-10LBA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-10LBA-IC-HMI-0001 | HMI | ALP-EPC-10LBA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBA-IC-HMI-0001 | HMI | ALP-EPC-10LBA-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBA-IC-LOG-0001 | LOG | ALP-EPC-10LBA-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBA-IC-LOG-0001 | LOG | ALP-EPC-10LBA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LBA-ME-CAL-0001 | CAL | ALP-EPC-10LBA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LBA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LBA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-10LBA-PI-ISO-0001 | ISO | ALP-EPC-10LBA-PI-STR-0001 | STR | IFR | 2027-08-02
ALP-EPC-10LBA-PI-ISO-0001 | ISO | ALP-EPC-10LBA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBA-PI-ISO-0001 | ISO | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-10LBA-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LBA-PI-STR-0001 | STR | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-10LBA-PI-STR-0001 | STR | ALP-IEC-00000-PI-LST-0001 | LST | IFR | 2026-12-28
ALP-EPC-10LBA-PI-SUP-0001 | SUP | ALP-EPC-10LBA-PI-ISO-0001 | ISO | IFC | 2027-12-14 | driving
ALP-EPC-10LBA-PI-SUP-0001 | SUP | ALP-EPC-10LBA-PI-STR-0001 | STR | IFC | 2027-08-23
ALP-EPC-10LBA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10LBA-PR-PID-0001 | PID | ALP-EPC-10LBA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LBA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LBA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-10LBA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-10LBB-CM-CMP-0001 | CMP | ALP-EPC-10LBB-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBB-CM-CMP-0001 | CMP | ALP-EPC-10LBB-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBB-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-10LBB-CM-MDB-0001 | MDB | ALP-EPC-10LBB-CM-CMP-0001 | CMP | IFR | 2027-09-24
ALP-EPC-10LBB-CM-OMM-0001 | OMM | ALP-EPC-10LBB-CM-CMP-0001 | CMP | IFR | 2027-09-24 | driving
ALP-EPC-10LBB-IC-CEM-0001 | CEM | ALP-EPC-10LBB-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBB-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-10LBB-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-10LBB-IC-CNR-0001 | CNR | ALP-EPC-10LBB-PR-PID-0001 | PID | IFR | 2027-06-14 | driving
ALP-EPC-10LBB-IC-DSH-0001 | DSH | ALP-EPC-10LBB-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBB-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-10LBB-IC-HMI-0001 | HMI | ALP-EPC-10LBB-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBB-IC-HMI-0001 | HMI | ALP-EPC-10LBB-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBB-IC-LOG-0001 | LOG | ALP-EPC-10LBB-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBB-IC-LOG-0001 | LOG | ALP-EPC-10LBB-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBB-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LBB-ME-CAL-0001 | CAL | ALP-EPC-10LBB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LBB-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LBB-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-10LBB-PI-ISO-0001 | ISO | ALP-EPC-10LBB-PI-STR-0001 | STR | IFR | 2027-08-06
ALP-EPC-10LBB-PI-ISO-0001 | ISO | ALP-EPC-10LBB-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBB-PI-ISO-0001 | ISO | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-10LBB-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LBB-PI-STR-0001 | STR | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-10LBB-PI-STR-0001 | STR | ALP-IEC-00000-PI-LST-0001 | LST | IFR | 2026-12-28
ALP-EPC-10LBB-PI-SUP-0001 | SUP | ALP-EPC-10LBB-PI-ISO-0001 | ISO | IFC | 2027-12-16
ALP-EPC-10LBB-PI-SUP-0001 | SUP | ALP-EPC-10LBB-PI-STR-0001 | STR | IFC | 2027-08-27
ALP-EPC-10LBB-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10LBB-PR-PID-0001 | PID | ALP-EPC-10LBB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LBB-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LBB-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-10LBB-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-10LBC-CM-CMP-0001 | CMP | ALP-EPC-10LBC-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBC-CM-CMP-0001 | CMP | ALP-EPC-10LBC-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBC-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-10LBC-CM-MDB-0001 | MDB | ALP-EPC-10LBC-CM-CMP-0001 | CMP | IFR | 2027-09-24
ALP-EPC-10LBC-CM-OMM-0001 | OMM | ALP-EPC-10LBC-CM-CMP-0001 | CMP | IFR | 2027-09-24 | driving
ALP-EPC-10LBC-IC-CEM-0001 | CEM | ALP-EPC-10LBC-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBC-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-10LBC-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-10LBC-IC-CNR-0001 | CNR | ALP-EPC-10LBC-PR-PID-0001 | PID | IFR | 2027-06-14 | driving
ALP-EPC-10LBC-IC-DSH-0001 | DSH | ALP-EPC-10LBC-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBC-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-10LBC-IC-HMI-0001 | HMI | ALP-EPC-10LBC-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBC-IC-HMI-0001 | HMI | ALP-EPC-10LBC-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBC-IC-LOG-0001 | LOG | ALP-EPC-10LBC-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBC-IC-LOG-0001 | LOG | ALP-EPC-10LBC-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBC-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LBC-ME-CAL-0001 | CAL | ALP-EPC-10LBC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LBC-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LBC-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-10LBC-PI-ISO-0001 | ISO | ALP-EPC-10LBC-PI-STR-0001 | STR | IFR | 2027-08-16
ALP-EPC-10LBC-PI-ISO-0001 | ISO | ALP-EPC-10LBC-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBC-PI-ISO-0001 | ISO | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-10LBC-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LBC-PI-STR-0001 | STR | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-10LBC-PI-STR-0001 | STR | ALP-IEC-00000-PI-LST-0001 | LST | IFR | 2026-12-28
ALP-EPC-10LBC-PI-SUP-0001 | SUP | ALP-EPC-10LBC-PI-ISO-0001 | ISO | IFC | 2027-12-22 | driving
ALP-EPC-10LBC-PI-SUP-0001 | SUP | ALP-EPC-10LBC-PI-STR-0001 | STR | IFC | 2027-09-06
ALP-EPC-10LBC-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10LBC-PR-PID-0001 | PID | ALP-EPC-10LBC-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LBC-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LBC-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-10LBC-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-10LBD-CM-CMP-0001 | CMP | ALP-EPC-10LBD-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBD-CM-CMP-0001 | CMP | ALP-EPC-10LBD-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBD-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-10LBD-CM-MDB-0001 | MDB | ALP-EPC-10LBD-CM-CMP-0001 | CMP | IFR | 2027-09-27
ALP-EPC-10LBD-CM-OMM-0001 | OMM | ALP-EPC-10LBD-CM-CMP-0001 | CMP | IFR | 2027-09-27 | driving
ALP-EPC-10LBD-IC-CEM-0001 | CEM | ALP-EPC-10LBD-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBD-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-10LBD-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-10LBD-IC-CNR-0001 | CNR | ALP-EPC-10LBD-PR-PID-0001 | PID | IFR | 2027-06-14 | driving
ALP-EPC-10LBD-IC-DSH-0001 | DSH | ALP-EPC-10LBD-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBD-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-10LBD-IC-HMI-0001 | HMI | ALP-EPC-10LBD-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBD-IC-HMI-0001 | HMI | ALP-EPC-10LBD-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBD-IC-LOG-0001 | LOG | ALP-EPC-10LBD-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-10LBD-IC-LOG-0001 | LOG | ALP-EPC-10LBD-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBD-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LBD-ME-CAL-0001 | CAL | ALP-EPC-10LBD-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LBD-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LBD-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-10LBD-PI-ISO-0001 | ISO | ALP-EPC-10LBD-PI-STR-0001 | STR | IFR | 2027-08-18
ALP-EPC-10LBD-PI-ISO-0001 | ISO | ALP-EPC-10LBD-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-10LBD-PI-ISO-0001 | ISO | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-10LBD-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10LBD-PI-STR-0001 | STR | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-10LBD-PI-STR-0001 | STR | ALP-IEC-00000-PI-LST-0001 | LST | IFR | 2026-12-28
ALP-EPC-10LBD-PI-SUP-0001 | SUP | ALP-EPC-10LBD-PI-ISO-0001 | ISO | IFC | 2028-01-06 | driving
ALP-EPC-10LBD-PI-SUP-0001 | SUP | ALP-EPC-10LBD-PI-STR-0001 | STR | IFC | 2027-09-08
ALP-EPC-10LBD-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10LBD-PR-PID-0001 | PID | ALP-EPC-10LBD-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-10LBD-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-10LBD-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-10LBD-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-10UHA-CV-CAL-0001 | CAL | ALP-IEC-10MBA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UHA-CV-CAL-0001 | CAL | ALP-IEC-10HAA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UHA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-10UHA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10UHA-CV-EFD-0001 | EFD | ALP-EPC-10UHA-CV-FND-0001 | FND | IFR | 2027-04-12 | driving
ALP-EPC-10UHA-CV-EFD-0001 | EFD | ALP-M19-10HAN-CV-CAL-0001 | CAL | IFR | 2027-03-05
ALP-EPC-10UHA-CV-EFD-0001 | EFD | ALP-IEC-10MBA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UHA-CV-EFD-0001 | EFD | ALP-IEC-10HAA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UHA-CV-FND-0001 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-10UHA-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10UHA-CV-FND-0001 | FND | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-10UHA-CV-FND-0001 | FND | ALP-IEC-10HAA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UHA-CV-FND-0001 | FND | ALP-EPC-10UHA-CV-FND-0002 | FND | IFR | 2027-03-04 | driving
ALP-EPC-10UHA-CV-FND-0001 | FND | ALP-IEC-10MBA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UHA-CV-FND-0002 | FND | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-10UHA-CV-FND-0002 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10UHA-CV-FND-0002 | FND | ALP-EPC-00000-CV-SPC-0002 | SPC | IFR | 2027-02-01 | driving
ALP-EPC-10UHA-CV-RBR-0001 | RBR | ALP-EPC-10UHA-CV-FND-0001 | FND | IFR | 2027-04-12 | driving
ALP-EPC-10UHA-EL-ELY-0001 | ELY | ALP-EPC-10UHA-CV-FND-0001 | FND | IFR | 2027-04-12
ALP-EPC-10UHA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-10UHA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-10UHN-CV-CAL-0001 | CAL | ALP-IEC-10MBA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UHN-CV-CAL-0001 | CAL | ALP-IEC-10HAA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UHN-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-10UHN-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10UHN-CV-EFD-0001 | EFD | ALP-EPC-10UHN-CV-FND-0001 | FND | IFR | 2027-03-31
ALP-EPC-10UHN-CV-EFD-0001 | EFD | ALP-IEC-10MBA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UHN-CV-EFD-0001 | EFD | ALP-IEC-10HAA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UHN-CV-EFD-0001 | EFD | ALP-S02-10HNE-CV-CAL-0001 | CAL | IFR | 2027-03-01
ALP-EPC-10UHN-CV-FND-0001 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-10UHN-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10UHN-CV-FND-0001 | FND | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-10UHN-CV-FND-0001 | FND | ALP-EPC-10UHN-CV-FND-0002 | FND | IFR | 2027-03-02 | driving
ALP-EPC-10UHN-CV-FND-0001 | FND | ALP-IEC-10MBA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UHN-CV-FND-0001 | FND | ALP-IEC-10HAA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UHN-CV-FND-0002 | FND | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-10UHN-CV-FND-0002 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10UHN-CV-FND-0002 | FND | ALP-EPC-00000-CV-SPC-0002 | SPC | IFR | 2027-02-01 | driving
ALP-EPC-10UHN-CV-RBR-0001 | RBR | ALP-EPC-10UHN-CV-FND-0001 | FND | IFR | 2027-03-31 | driving
ALP-EPC-10UHN-EL-ELY-0001 | ELY | ALP-EPC-10UHN-CV-FND-0001 | FND | IFR | 2027-03-31
ALP-EPC-10UHN-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-10UHN-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-10UMA-CV-ARC-0001 | ARC | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24 | driving
ALP-EPC-10UMA-CV-ARC-0001 | ARC | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-10UMA-CV-CAL-0001 | CAL | ALP-IEC-10MBA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UMA-CV-CAL-0001 | CAL | ALP-IEC-10HAA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UMA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-10UMA-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10UMA-CV-EFD-0001 | EFD | ALP-EPC-10UMA-CV-FND-0002 | FND | IFR | 2027-04-20 | driving
ALP-EPC-10UMA-CV-EFD-0001 | EFD | ALP-IEC-10MKA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UMA-CV-EFD-0001 | EFD | ALP-M21-00SMA-CV-CAL-0001 | CAL | IFR | 2027-02-22
ALP-EPC-10UMA-CV-EFD-0001 | EFD | ALP-IEC-10MBA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UMA-CV-EFD-0001 | EFD | ALP-IEC-10HAA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UMA-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10UMA-CV-FND-0001 | FND | ALP-EPC-00000-CV-SPC-0002 | SPC | IFR | 2027-02-01 | driving
ALP-EPC-10UMA-CV-FND-0001 | FND | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-10UMA-CV-FND-0001 | FND | ALP-IEC-10MBA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UMA-CV-FND-0002 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-10UMA-CV-FND-0002 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-10UMA-CV-FND-0002 | FND | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-10UMA-CV-FND-0002 | FND | ALP-IEC-10MBA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UMA-CV-FND-0002 | FND | ALP-EPC-10UMA-CV-FND-0001 | FND | IFR | 2027-03-08 | driving
ALP-EPC-10UMA-CV-FND-0002 | FND | ALP-IEC-10HAA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-10UMA-CV-RBR-0001 | RBR | ALP-EPC-10UMA-CV-FND-0002 | FND | IFR | 2027-04-20 | driving
ALP-EPC-10UMA-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-CAL-0001 | CAL | IFR | 2027-01-14
ALP-EPC-10UMA-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-10UMA-EL-CBL-0001 | CBL | ALP-EPC-10UMA-EL-ELY-0001 | ELY | IFR | 2027-04-06
ALP-EPC-10UMA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-10UMA-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-10UMA-EL-ELY-0001 | ELY | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-10UMA-EL-ELY-0002 | ELY | ALP-EPC-10UMA-EL-ELY-0001 | ELY | IFR | 2027-04-06
ALP-EPC-10UMA-EL-ELY-0002 | ELY | ALP-EPC-10UMA-PI-PPL-0001 | PPL | IFR | 2027-05-11
ALP-EPC-10UMA-EL-ELY-0003 | ELY | ALP-EPC-10UMA-CV-FND-0002 | FND | IFR | 2027-04-20
ALP-EPC-10UMA-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-10UMA-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-10UMA-HS-GAD-0001 | GAD | ALP-EPC-10UMA-CV-ARC-0001 | ARC | IFR | 2027-02-01 | driving
ALP-EPC-10UMA-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-10UMA-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-10UMA-HV-GAD-0001 | GAD | ALP-EPC-00SAA-HV-CAL-0001 | CAL | IFR | 2027-02-08
ALP-EPC-10UMA-HV-GAD-0001 | GAD | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-10UMA-HV-GAD-0002 | GAD | ALP-EPC-10UMA-CV-ARC-0001 | ARC | IFR | 2027-02-01
ALP-EPC-10UMA-HV-GAD-0002 | GAD | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-10UMA-IC-ELY-0001 | ELY | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-10UMA-IC-ELY-0001 | ELY | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-10UMA-IC-ELY-0002 | ELY | ALP-EPC-10UMA-CV-ARC-0001 | ARC | IFR | 2027-02-01 | driving
ALP-EPC-10UMA-IC-ELY-0002 | ELY | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-10UMA-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06
ALP-EPC-10UMA-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-10UMA-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27 | driving
ALP-EPC-10UMA-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06
ALP-EPC-10UMA-IC-LOP-0001 | LOP | ALP-IEC-10MBY-IC-CBL-0001 | CBL | IFR | 2027-05-31
ALP-EPC-10UMA-IC-LOP-0001 | LOP | ALP-IEC-10MBY-IC-IOL-0001 | IOL | IFR | 2027-02-22
ALP-EPC-10UMA-IC-LOP-0002 | LOP | ALP-EPC-10UMA-IC-ELY-0001 | ELY | IFR | 2027-08-17 | driving
ALP-EPC-10UMA-IC-LOP-0002 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-10UMA-IC-LOP-0003 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27 | driving
ALP-EPC-10UMA-IC-LOP-0003 | LOP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06
ALP-EPC-10UMA-PI-LAY-0001 | LAY | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-10UMA-PI-LAY-0001 | LAY | ALP-IEC-10HAA-ME-GAD-0001 | GAD | IFR | 2026-09-28
ALP-EPC-10UMA-PI-LAY-0001 | LAY | ALP-IEC-10MBA-ME-GAD-0001 | GAD | IFR | 2026-09-28
ALP-EPC-10UMA-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-M3D-0001 | M3D | IFR | 2026-12-14
ALP-EPC-10UMA-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-SPC-0002 | SPC | IFR | 2026-12-14
ALP-EPC-10UMA-PI-PPL-0001 | PPL | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-10UMA-SS-STL-0001 | STL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-10UMA-SS-STL-0001 | STL | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-10UMA-SS-STL-0001 | STL | ALP-EPC-10UMA-PI-LAY-0001 | LAY | IFR | 2026-12-24
ALP-EPC-10UMA-SS-STL-0001 | STL | ALP-EPC-10UMA-CV-CAL-0001 | CAL | IFR | 2027-04-07 | driving
ALP-EPC-20BBT-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-20BBT-CM-MDB-0001 | MDB | ALP-EPC-20BBT-CM-CMP-0001 | CMP | IFR | 2027-01-25
ALP-EPC-20BBT-CM-OMM-0001 | OMM | ALP-EPC-20BBT-CM-CMP-0001 | CMP | IFR | 2027-01-25 | driving
ALP-EPC-20BBT-EL-DSH-0001 | DSH | ALP-EPC-10BBT-EL-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-20BBT-EL-DSH-0001 | DSH | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-20BBT-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-20BBT-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-20LCA-CM-CMP-0001 | CMP | ALP-EPC-20LCA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-20LCA-CM-CMP-0001 | CMP | ALP-EPC-20LCA-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-20LCA-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-20LCA-CM-MDB-0001 | MDB | ALP-EPC-20LCA-CM-CMP-0001 | CMP | IFR | 2027-09-30
ALP-EPC-20LCA-CM-OMM-0001 | OMM | ALP-EPC-20LCA-CM-CMP-0001 | CMP | IFR | 2027-09-30 | driving
ALP-EPC-20LCA-IC-CEM-0001 | CEM | ALP-EPC-20LCA-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-20LCA-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-20LCA-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-20LCA-IC-CNR-0001 | CNR | ALP-EPC-20LCA-PR-PID-0001 | PID | IFR | 2027-06-14 | driving
ALP-EPC-20LCA-IC-DSH-0001 | DSH | ALP-EPC-20LCA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-20LCA-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-20LCA-IC-DSH-0002 | DSH | ALP-EPC-20LCA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-20LCA-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-20LCA-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-20LCA-IC-HMI-0001 | HMI | ALP-EPC-20LCA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-20LCA-IC-HMI-0001 | HMI | ALP-EPC-20LCA-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-20LCA-IC-LOG-0001 | LOG | ALP-EPC-20LCA-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-20LCA-IC-LOG-0001 | LOG | ALP-EPC-20LCA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-20LCA-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-20LCA-ME-CAL-0001 | CAL | ALP-EPC-20LCA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-20LCA-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-20LCA-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-20LCA-PI-ISO-0001 | ISO | ALP-EPC-20LCA-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-20LCA-PI-ISO-0001 | ISO | ALP-EPC-20UMB-PI-PPL-0001 | PPL | IFR | 2027-05-10
ALP-EPC-20LCA-PI-ISO-0001 | ISO | ALP-EPC-20LCA-PI-STR-0001 | STR | IFR | 2028-01-05 | driving
ALP-EPC-20LCA-PI-STR-0001 | STR | ALP-EPC-20UMB-PI-PPL-0001 | PPL | IFR | 2027-05-10
ALP-EPC-20LCA-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-20LCA-PI-SUP-0001 | SUP | ALP-EPC-20LCA-PI-ISO-0001 | ISO | IFC | 2028-03-08 | driving
ALP-EPC-20LCA-PI-SUP-0001 | SUP | ALP-EPC-20LCA-PI-STR-0001 | STR | IFC | 2028-01-26
ALP-EPC-20LCA-PR-DSH-0001 | DSH | ALP-EPC-20LCA-PR-PID-0001 | PID | IFR | 2027-06-14 | driving
ALP-EPC-20LCA-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-20LCA-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-20LCA-PR-PID-0001 | PID | ALP-EPC-20LCA-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-20LCA-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-20LCA-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-20LCA-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-20LCB-CM-CMP-0001 | CMP | ALP-EPC-20LCB-PR-PID-0001 | PID | IFR | 2027-06-15
ALP-EPC-20LCB-CM-CMP-0001 | CMP | ALP-EPC-20LCB-IC-CNR-0001 | CNR | IFR | 2027-07-06
ALP-EPC-20LCB-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-20LCB-CM-MDB-0001 | MDB | ALP-EPC-20LCB-CM-CMP-0001 | CMP | IFR | 2027-10-01
ALP-EPC-20LCB-CM-OMM-0001 | OMM | ALP-EPC-20LCB-CM-CMP-0001 | CMP | IFR | 2027-10-01 | driving
ALP-EPC-20LCB-GE-RPT-0001 | RPT | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-EPC-20LCB-IC-CEM-0001 | CEM | ALP-EPC-20LCB-IC-CNR-0001 | CNR | IFR | 2027-07-06
ALP-EPC-20LCB-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-20LCB-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-20LCB-IC-CNR-0001 | CNR | ALP-EPC-20LCB-PR-PID-0001 | PID | IFR | 2027-06-15 | driving
ALP-EPC-20LCB-IC-DSH-0001 | DSH | ALP-EPC-20LCB-PR-PID-0001 | PID | IFR | 2027-06-15
ALP-EPC-20LCB-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-20LCB-IC-DSH-0002 | DSH | ALP-EPC-20LCB-PR-PID-0001 | PID | IFR | 2027-06-15
ALP-EPC-20LCB-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-20LCB-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-20LCB-IC-HMI-0001 | HMI | ALP-EPC-20LCB-PR-PID-0001 | PID | IFR | 2027-06-15
ALP-EPC-20LCB-IC-HMI-0001 | HMI | ALP-EPC-20LCB-IC-CNR-0001 | CNR | IFR | 2027-07-06
ALP-EPC-20LCB-IC-LOG-0001 | LOG | ALP-EPC-20LCB-IC-CNR-0001 | CNR | IFR | 2027-07-06
ALP-EPC-20LCB-IC-LOG-0001 | LOG | ALP-EPC-20LCB-PR-PID-0001 | PID | IFR | 2027-06-15
ALP-EPC-20LCB-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-20LCB-ME-CAL-0001 | CAL | ALP-EPC-20LCB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-20LCB-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-20LCB-ME-DSH-0001 | DSH | ALP-EPC-20LCB-ME-CAL-0001 | CAL | IFR | 2027-03-04
ALP-EPC-20LCB-ME-DSH-0001 | DSH | ALP-EPC-20LCB-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-20LCB-ME-DSH-0001 | DSH | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-20LCB-ME-ITP-0001 | ITP | ALP-EPC-20LCB-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | ALP-EPC-20LCB-ME-DSH-0001 | DSH | IFR | 2026-11-02
ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | ALP-EPC-20LCB-ME-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-20LCB-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-SPC-0001 | SPC | IFR | 2026-12-14
ALP-EPC-20LCB-ME-SPC-0001 | SPC | ALP-EPC-20LCB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-20LCB-ME-SPC-0001 | SPC | ALP-EPC-00000-ME-DBR-0001 | DBR | IFR | 2027-02-08
ALP-EPC-20LCB-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-20LCB-PI-ISO-0001 | ISO | ALP-EPC-20LCB-PR-PID-0001 | PID | IFR | 2027-06-15
ALP-EPC-20LCB-PI-ISO-0001 | ISO | ALP-EPC-20UMB-PI-PPL-0001 | PPL | IFR | 2027-05-10
ALP-EPC-20LCB-PI-ISO-0001 | ISO | ALP-EPC-20LCB-PI-STR-0001 | STR | IFR | 2028-01-03 | driving
ALP-EPC-20LCB-PI-STR-0001 | STR | ALP-EPC-20UMB-PI-PPL-0001 | PPL | IFR | 2027-05-10
ALP-EPC-20LCB-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-20LCB-PI-SUP-0001 | SUP | ALP-EPC-20LCB-PI-ISO-0001 | ISO | IFC | 2028-03-06 | driving
ALP-EPC-20LCB-PI-SUP-0001 | SUP | ALP-EPC-20LCB-PI-STR-0001 | STR | IFC | 2028-01-24
ALP-EPC-20LCB-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-20LCB-PR-PID-0001 | PID | ALP-EPC-20LCB-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-20LCB-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-20LCB-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-20LCB-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-20MAN-CM-CMP-0001 | CMP | ALP-EPC-20MAN-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-20MAN-CM-CMP-0001 | CMP | ALP-EPC-20MAN-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-20MAN-CM-CMP-0001 | CMP | ALP-EPC-00000-CM-PLN-0001 | PLN | IFR | 2026-11-30
ALP-EPC-20MAN-CM-MDB-0001 | MDB | ALP-EPC-20MAN-CM-CMP-0001 | CMP | IFR | 2027-10-04
ALP-EPC-20MAN-CM-OMM-0001 | OMM | ALP-EPC-20MAN-CM-CMP-0001 | CMP | IFR | 2027-10-04 | driving
ALP-EPC-20MAN-IC-CEM-0001 | CEM | ALP-EPC-20MAN-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-20MAN-IC-CEM-0001 | CEM | ALP-EPC-00000-HS-HAZ-0007 | HAZ | IFR | 2027-08-13
ALP-EPC-20MAN-IC-CNR-0001 | CNR | ALP-EPC-00000-IC-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-20MAN-IC-CNR-0001 | CNR | ALP-EPC-20MAN-PR-PID-0001 | PID | IFR | 2027-06-14 | driving
ALP-EPC-20MAN-IC-DSH-0001 | DSH | ALP-EPC-20MAN-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-20MAN-IC-DSH-0001 | DSH | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-20MAN-IC-DSH-0002 | DSH | ALP-EPC-20MAN-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-20MAN-IC-DSH-0002 | DSH | ALP-EPC-00000-IC-SPC-0002 | SPC | IFR | 2027-01-11
ALP-EPC-20MAN-IC-DSH-0002 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-20MAN-IC-HMI-0001 | HMI | ALP-EPC-20MAN-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-20MAN-IC-HMI-0001 | HMI | ALP-EPC-20MAN-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-20MAN-IC-LOG-0001 | LOG | ALP-EPC-20MAN-IC-CNR-0001 | CNR | IFR | 2027-07-05
ALP-EPC-20MAN-IC-LOG-0001 | LOG | ALP-EPC-20MAN-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-20MAN-IC-LOG-0001 | LOG | ALP-EPC-00000-IC-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-20MAN-ME-CAL-0001 | CAL | ALP-EPC-20MAN-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-20MAN-ME-CAL-0001 | CAL | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-20MAN-PI-ISO-0001 | ISO | ALP-EPC-00000-PI-M3D-0002 | M3D | IFR | 2027-06-01
ALP-EPC-20MAN-PI-ISO-0001 | ISO | ALP-EPC-20MAN-PI-STR-0001 | STR | IFR | 2028-01-03 | driving
ALP-EPC-20MAN-PI-ISO-0001 | ISO | ALP-EPC-20MAN-PR-PID-0001 | PID | IFR | 2027-06-14
ALP-EPC-20MAN-PI-ISO-0001 | ISO | ALP-EPC-20UMB-PI-PPL-0001 | PPL | IFR | 2027-05-10
ALP-EPC-20MAN-PI-STR-0001 | STR | ALP-EPC-00000-PI-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-20MAN-PI-STR-0001 | STR | ALP-EPC-20UMB-PI-PPL-0001 | PPL | IFR | 2027-05-10
ALP-EPC-20MAN-PI-STR-0001 | STR | ALP-IEC-00000-PI-LST-0001 | LST | IFR | 2026-12-28
ALP-EPC-20MAN-PI-SUP-0001 | SUP | ALP-EPC-20MAN-PI-ISO-0001 | ISO | IFC | 2028-03-06 | driving
ALP-EPC-20MAN-PI-SUP-0001 | SUP | ALP-EPC-20MAN-PI-STR-0001 | STR | IFC | 2028-01-24
ALP-EPC-20MAN-PR-DSH-0001 | DSH | ALP-EPC-20MAN-PR-PID-0001 | PID | IFR | 2027-06-14 | driving
ALP-EPC-20MAN-PR-DSH-0001 | DSH | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-20MAN-PR-PID-0001 | PID | ALP-EPC-00000-PI-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-20MAN-PR-PID-0001 | PID | ALP-EPC-20MAN-PR-SDS-0001 | SDS | IFR | 2026-11-02
ALP-EPC-20MAN-PR-PID-0001 | PID | ALP-EPC-00000-PR-DBR-0001 | DBR | IFR | 2027-01-11
ALP-EPC-20MAN-PR-SDS-0001 | SDS | ALP-EPC-00000-GE-DBR-0001 | DBR | IFR | 2026-11-16
ALP-EPC-20MAN-PR-SDS-0001 | SDS | ALP-EPC-00000-PR-PFD-0001 | PFD | IFR | 2026-11-02
ALP-EPC-20UMB-CV-ARC-0001 | ARC | ALP-EPC-20UMB-PI-LAY-0001 | LAY | IFR | 2026-12-10
ALP-EPC-20UMB-CV-ARC-0001 | ARC | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14 | driving
ALP-EPC-20UMB-CV-CAL-0001 | CAL | ALP-IEC-20MAA-CV-CAL-0001 | CAL | IFR | 2026-12-28
ALP-EPC-20UMB-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-20UMB-CV-CAL-0001 | CAL | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-20UMB-CV-EFD-0001 | EFD | ALP-EPC-20UMB-CV-FND-0002 | FND | IFR | 2027-04-20
ALP-EPC-20UMB-CV-EFD-0001 | EFD | ALP-M02-20LCB-CV-CAL-0001 | CAL | IFR | 2027-03-29
ALP-EPC-20UMB-CV-EFD-0001 | EFD | ALP-IEC-20MAA-CV-CAL-0001 | CAL | IFR | 2026-12-28
ALP-EPC-20UMB-CV-EFD-0001 | EFD | ALP-IEC-10MKA-CV-CAL-0001 | CAL | IFR | 2026-12-14
ALP-EPC-20UMB-CV-EFD-0001 | EFD | ALP-M21-00SMA-CV-CAL-0001 | CAL | IFR | 2027-02-22
ALP-EPC-20UMB-CV-FND-0001 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-20UMB-CV-FND-0001 | FND | ALP-EPC-00000-CV-SPC-0002 | SPC | IFR | 2027-02-01 | driving
ALP-EPC-20UMB-CV-FND-0001 | FND | ALP-EPC-20UMB-PI-LAY-0001 | LAY | IFR | 2026-12-10
ALP-EPC-20UMB-CV-FND-0001 | FND | ALP-IEC-20MAA-CV-CAL-0001 | CAL | IFR | 2026-12-28
ALP-EPC-20UMB-CV-FND-0002 | FND | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-20UMB-CV-FND-0002 | FND | ALP-EPC-00000-CV-RPT-0001 | RPT | IFR | 2027-01-04
ALP-EPC-20UMB-CV-FND-0002 | FND | ALP-EPC-20UMB-PI-LAY-0001 | LAY | IFR | 2026-12-10
ALP-EPC-20UMB-CV-FND-0002 | FND | ALP-IEC-20MAA-CV-CAL-0001 | CAL | IFR | 2026-12-28
ALP-EPC-20UMB-CV-FND-0002 | FND | ALP-EPC-20UMB-CV-FND-0001 | FND | IFR | 2027-03-08 | driving
ALP-EPC-20UMB-CV-RBR-0001 | RBR | ALP-EPC-20UMB-CV-FND-0002 | FND | IFR | 2027-04-20 | driving
ALP-EPC-20UMB-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-CAL-0001 | CAL | IFR | 2027-01-14
ALP-EPC-20UMB-EL-CBL-0001 | CBL | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-20UMB-EL-CBL-0001 | CBL | ALP-EPC-20UMB-EL-ELY-0001 | ELY | IFR | 2027-09-17 | driving
ALP-EPC-20UMB-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-SLD-0001 | SLD | IFR | 2026-11-02
ALP-EPC-20UMB-EL-ELY-0001 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-20UMB-EL-ELY-0001 | ELY | ALP-EPC-20UMB-PI-LAY-0001 | LAY | IFR | 2026-12-10
ALP-EPC-20UMB-EL-ELY-0002 | ELY | ALP-EPC-20UMB-EL-ELY-0001 | ELY | IFR | 2027-09-17 | driving
ALP-EPC-20UMB-EL-ELY-0002 | ELY | ALP-EPC-20UMB-PI-PPL-0001 | PPL | IFR | 2027-05-10
ALP-EPC-20UMB-EL-ELY-0003 | ELY | ALP-EPC-20UMB-CV-FND-0002 | FND | IFR | 2027-04-20
ALP-EPC-20UMB-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0003 | STU | IFR | 2027-02-08
ALP-EPC-20UMB-EL-ELY-0003 | ELY | ALP-EPC-00000-EL-STU-0004 | STU | IFR | 2026-12-15
ALP-EPC-20UMB-HS-GAD-0001 | GAD | ALP-EPC-20UMB-CV-ARC-0001 | ARC | IFR | 2027-01-20 | driving
ALP-EPC-20UMB-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-20UMB-HS-GAD-0001 | GAD | ALP-EPC-00000-HS-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-20UMB-HV-GAD-0001 | GAD | ALP-EPC-20UMB-CV-ARC-0001 | ARC | IFR | 2027-01-20
ALP-EPC-20UMB-HV-GAD-0001 | GAD | ALP-EPC-00000-HV-DBR-0001 | DBR | IFR | 2026-12-14
ALP-EPC-20UMB-IC-ELY-0001 | ELY | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-20UMB-IC-ELY-0001 | ELY | ALP-EPC-20UMB-PI-LAY-0001 | LAY | IFR | 2026-12-10
ALP-EPC-20UMB-IC-ELY-0002 | ELY | ALP-EPC-20UMB-CV-ARC-0001 | ARC | IFR | 2027-01-20 | driving
ALP-EPC-20UMB-IC-ELY-0002 | ELY | ALP-EPC-00000-HS-HAZ-0009 | HAZ | IFR | 2027-01-11
ALP-EPC-20UMB-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06 | driving
ALP-EPC-20UMB-IC-HUP-0001 | HUP | ALP-EPC-00000-IC-SPC-0001 | SPC | IFR | 2027-01-11
ALP-EPC-20UMB-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-20UMB-IC-LOP-0001 | LOP | ALP-EPC-00000-IC-LST-0001 | LST | IFR | 2027-07-06
ALP-EPC-20UMB-IC-LOP-0001 | LOP | ALP-IEC-10MBY-IC-CBL-0001 | CBL | IFR | 2027-05-31
ALP-EPC-20UMB-IC-LOP-0001 | LOP | ALP-IEC-10MBY-IC-IOL-0001 | IOL | IFR | 2027-02-22
ALP-EPC-20UMB-IC-LOP-0002 | LOP | ALP-EPC-20UMB-IC-ELY-0001 | ELY | IFR | 2027-08-06
ALP-EPC-20UMB-IC-LOP-0002 | LOP | ALP-EPC-00000-IC-IOL-0001 | IOL | IFR | 2027-07-27
ALP-EPC-20UMB-PI-LAY-0001 | LAY | ALP-EPC-00000-PI-PLT-0001 | PLT | IFR | 2026-11-02
ALP-EPC-20UMB-PI-LAY-0001 | LAY | ALP-IEC-20MAA-ME-GAD-0001 | GAD | IFR | 2026-09-28
ALP-EPC-20UMB-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-M3D-0001 | M3D | IFR | 2026-12-14
ALP-EPC-20UMB-PI-PPL-0001 | PPL | ALP-EPC-00000-PI-SPC-0002 | SPC | IFR | 2026-12-14
ALP-EPC-20UMB-PI-PPL-0001 | PPL | ALP-EPC-20UMB-PI-LAY-0001 | LAY | IFR | 2026-12-10
ALP-EPC-20UMB-SS-STL-0001 | STL | ALP-EPC-00000-CV-CAL-0001 | CAL | IFR | 2027-01-18
ALP-EPC-20UMB-SS-STL-0001 | STL | ALP-EPC-00000-SS-SPC-0001 | SPC | IFR | 2026-11-02
ALP-EPC-20UMB-SS-STL-0001 | STL | ALP-EPC-20UMB-PI-LAY-0001 | LAY | IFR | 2026-12-10
ALP-EPC-20UMB-SS-STL-0001 | STL | ALP-EPC-20UMB-CV-CAL-0001 | CAL | IFR | 2027-04-08 | driving
ALP-H01-00SAA-EL-WIR-0001 | WIR | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-H01-00SAA-EL-WIR-0002 | WIR | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-H01-00SAA-IC-DSH-0001 | DSH | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-H01-00SAA-IC-IOL-0001 | IOL | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-H01-00SAA-ME-CAL-0001 | CAL | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-H01-00SAA-ME-DSH-0001 | DSH | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-H01-00SAA-ME-GAD-0001 | GAD | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-H01-00SAA-ME-ITP-0001 | ITP | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-H01-00SAA-ME-LST-0001 | LST | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-H01-00SAA-ME-MDB-0001 | MDB | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-H01-00SAA-ME-OMM-0001 | OMM | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-H01-00SAA-ME-PRC-0001 | PRC | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-H01-00SAA-ME-TRP-0001 | TRP | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-H01-00SAA-ME-TST-0001 | TST | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-H01-00SAA-PR-PID-0001 | PID | ALP-EPC-00SAA-HV-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I01-00CJA-EL-WIR-0001 | WIR | ALP-EPC-00CJA-IC-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-I01-00CJA-IC-IOL-0001 | IOL | ALP-EPC-00CJA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I01-00CJA-ME-CAL-0001 | CAL | ALP-EPC-00CJA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I01-00CJA-ME-DSH-0001 | DSH | ALP-EPC-00CJA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I01-00CJA-ME-GAD-0001 | GAD | ALP-EPC-00CJA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I01-00CJA-ME-ITP-0001 | ITP | ALP-EPC-00CJA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I01-00CJA-ME-LST-0001 | LST | ALP-EPC-00CJA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I01-00CJA-ME-MDB-0001 | MDB | ALP-EPC-00CJA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I01-00CJA-ME-OMM-0001 | OMM | ALP-EPC-00CJA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I01-00CJA-ME-PRC-0001 | PRC | ALP-EPC-00CJA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I01-00CJA-ME-TRP-0001 | TRP | ALP-EPC-00CJA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I01-00CJA-ME-TST-0001 | TST | ALP-EPC-00CJA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I02-00CQA-EL-WIR-0001 | WIR | ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-I02-00CQA-IC-DSH-0001 | DSH | ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I02-00CQA-IC-IOL-0001 | IOL | ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I02-00CQA-ME-CAL-0001 | CAL | ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I02-00CQA-ME-DSH-0001 | DSH | ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I02-00CQA-ME-GAD-0001 | GAD | ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I02-00CQA-ME-ITP-0001 | ITP | ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I02-00CQA-ME-LST-0001 | LST | ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I02-00CQA-ME-MDB-0001 | MDB | ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I02-00CQA-ME-OMM-0001 | OMM | ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I02-00CQA-ME-PRC-0001 | PRC | ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I02-00CQA-ME-TRP-0001 | TRP | ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I02-00CQA-ME-TST-0001 | TST | ALP-EPC-00CQA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I03-00QUA-EL-WIR-0001 | WIR | ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-I03-00QUA-IC-DSH-0001 | DSH | ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I03-00QUA-IC-IOL-0001 | IOL | ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I03-00QUA-ME-CAL-0001 | CAL | ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I03-00QUA-ME-DSH-0001 | DSH | ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I03-00QUA-ME-GAD-0001 | GAD | ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I03-00QUA-ME-ITP-0001 | ITP | ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I03-00QUA-ME-LST-0001 | LST | ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I03-00QUA-ME-MDB-0001 | MDB | ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I03-00QUA-ME-OMM-0001 | OMM | ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I03-00QUA-ME-PRC-0001 | PRC | ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I03-00QUA-ME-TRP-0001 | TRP | ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I03-00QUA-ME-TST-0001 | TST | ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I03-00QUA-PR-PID-0001 | PID | ALP-EPC-00QUA-IC-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-I04-00000-ME-DSH-0001 | DSH | ALP-EPC-00000-IC-MRQ-0001 | MRQ | IFR | 2027-01-18
ALP-I04-00000-ME-ITP-0001 | ITP | ALP-EPC-00000-IC-MRQ-0001 | MRQ | IFR | 2027-01-18
ALP-I04-00000-ME-MDB-0001 | MDB | ALP-EPC-00000-IC-MRQ-0001 | MRQ | IFR | 2027-01-18
ALP-I05-00000-ME-DSH-0001 | DSH | ALP-EPC-00000-IC-MRQ-0002 | MRQ | IFR | 2027-01-18
ALP-I05-00000-ME-ITP-0001 | ITP | ALP-EPC-00000-IC-MRQ-0002 | MRQ | IFR | 2027-01-18
ALP-I05-00000-ME-MDB-0001 | MDB | ALP-EPC-00000-IC-MRQ-0002 | MRQ | IFR | 2027-01-18
ALP-I06-00SGY-EL-WIR-0001 | WIR | ALP-EPC-00SGY-GE-MRQ-0001 | MRQ | IFC | 2027-03-26
ALP-I06-00SGY-IC-IOL-0001 | IOL | ALP-EPC-00SGY-GE-MRQ-0001 | MRQ | IFR | 2027-03-23
ALP-I06-00SGY-ME-CAL-0001 | CAL | ALP-EPC-00SGY-GE-MRQ-0001 | MRQ | IFR | 2027-03-23
ALP-I06-00SGY-ME-DSH-0001 | DSH | ALP-EPC-00SGY-GE-MRQ-0001 | MRQ | IFR | 2027-03-23
ALP-I06-00SGY-ME-GAD-0001 | GAD | ALP-EPC-00SGY-GE-MRQ-0001 | MRQ | IFR | 2027-03-23
ALP-I06-00SGY-ME-ITP-0001 | ITP | ALP-EPC-00SGY-GE-MRQ-0001 | MRQ | IFR | 2027-03-23
ALP-I06-00SGY-ME-LST-0001 | LST | ALP-EPC-00SGY-GE-MRQ-0001 | MRQ | IFR | 2027-03-23
ALP-I06-00SGY-ME-MDB-0001 | MDB | ALP-EPC-00SGY-GE-MRQ-0001 | MRQ | IFR | 2027-03-23
ALP-I06-00SGY-ME-OMM-0001 | OMM | ALP-EPC-00SGY-GE-MRQ-0001 | MRQ | IFR | 2027-03-23
ALP-I06-00SGY-ME-PRC-0001 | PRC | ALP-EPC-00SGY-GE-MRQ-0001 | MRQ | IFR | 2027-03-23
ALP-I06-00SGY-ME-TRP-0001 | TRP | ALP-EPC-00SGY-GE-MRQ-0001 | MRQ | IFR | 2027-03-23
ALP-I06-00SGY-ME-TST-0001 | TST | ALP-EPC-00SGY-GE-MRQ-0001 | MRQ | IFR | 2027-03-23
ALP-I07-00CYA-EL-WIR-0001 | WIR | ALP-EPC-00CYA-GE-MRQ-0001 | MRQ | IFC | 2027-03-23
ALP-I07-00CYA-IC-IOL-0001 | IOL | ALP-EPC-00CYA-GE-MRQ-0001 | MRQ | IFR | 2027-03-18
ALP-I07-00CYA-ME-CAL-0001 | CAL | ALP-EPC-00CYA-GE-MRQ-0001 | MRQ | IFR | 2027-03-18
ALP-I07-00CYA-ME-DSH-0001 | DSH | ALP-EPC-00CYA-GE-MRQ-0001 | MRQ | IFR | 2027-03-18
ALP-I07-00CYA-ME-GAD-0001 | GAD | ALP-EPC-00CYA-GE-MRQ-0001 | MRQ | IFR | 2027-03-18
ALP-I07-00CYA-ME-ITP-0001 | ITP | ALP-EPC-00CYA-GE-MRQ-0001 | MRQ | IFR | 2027-03-18
ALP-I07-00CYA-ME-LST-0001 | LST | ALP-EPC-00CYA-GE-MRQ-0001 | MRQ | IFR | 2027-03-18
ALP-I07-00CYA-ME-MDB-0001 | MDB | ALP-EPC-00CYA-GE-MRQ-0001 | MRQ | IFR | 2027-03-18
ALP-I07-00CYA-ME-OMM-0001 | OMM | ALP-EPC-00CYA-GE-MRQ-0001 | MRQ | IFR | 2027-03-18
ALP-I07-00CYA-ME-PRC-0001 | PRC | ALP-EPC-00CYA-GE-MRQ-0001 | MRQ | IFR | 2027-03-18
ALP-I07-00CYA-ME-TRP-0001 | TRP | ALP-EPC-00CYA-GE-MRQ-0001 | MRQ | IFR | 2027-03-18
ALP-I07-00CYA-ME-TST-0001 | TST | ALP-EPC-00CYA-GE-MRQ-0001 | MRQ | IFR | 2027-03-18
ALP-I08-00CJG-EL-WIR-0001 | WIR | ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | IFC | 2027-03-18
ALP-I08-00CJG-IC-IOL-0001 | IOL | ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I08-00CJG-IC-LOG-0001 | LOG | ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I08-00CJG-ME-CAL-0001 | CAL | ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I08-00CJG-ME-DSH-0001 | DSH | ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I08-00CJG-ME-GAD-0001 | GAD | ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I08-00CJG-ME-ITP-0001 | ITP | ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I08-00CJG-ME-LST-0001 | LST | ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I08-00CJG-ME-MDB-0001 | MDB | ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I08-00CJG-ME-OMM-0001 | OMM | ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I08-00CJG-ME-PRC-0001 | PRC | ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I08-00CJG-ME-TRP-0001 | TRP | ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I08-00CJG-ME-TST-0001 | TST | ALP-EPC-00CJG-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I09-00CKA-EL-WIR-0001 | WIR | ALP-EPC-00CKA-GE-MRQ-0001 | MRQ | IFC | 2027-03-18
ALP-I09-00CKA-IC-IOL-0001 | IOL | ALP-EPC-00CKA-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I09-00CKA-ME-CAL-0001 | CAL | ALP-EPC-00CKA-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I09-00CKA-ME-DSH-0001 | DSH | ALP-EPC-00CKA-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I09-00CKA-ME-GAD-0001 | GAD | ALP-EPC-00CKA-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I09-00CKA-ME-ITP-0001 | ITP | ALP-EPC-00CKA-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I09-00CKA-ME-LST-0001 | LST | ALP-EPC-00CKA-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I09-00CKA-ME-MDB-0001 | MDB | ALP-EPC-00CKA-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I09-00CKA-ME-OMM-0001 | OMM | ALP-EPC-00CKA-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I09-00CKA-ME-PRC-0001 | PRC | ALP-EPC-00CKA-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I09-00CKA-ME-TRP-0001 | TRP | ALP-EPC-00CKA-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I09-00CKA-ME-TST-0001 | TST | ALP-EPC-00CKA-GE-MRQ-0001 | MRQ | IFR | 2027-03-15
ALP-I10-00000-ME-DSH-0001 | DSH | ALP-EPC-00000-GE-MRQ-0003 | MRQ | IFR | 2027-04-21
ALP-I10-00000-ME-ITP-0001 | ITP | ALP-EPC-00000-GE-MRQ-0003 | MRQ | IFR | 2027-04-21
ALP-I10-00000-ME-MDB-0001 | MDB | ALP-EPC-00000-GE-MRQ-0003 | MRQ | IFR | 2027-04-21
ALP-M01-10LAC-CV-CAL-0001 | CAL | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M01-10LAC-EL-WIR-0001 | WIR | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M01-10LAC-IC-DSH-0001 | DSH | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M01-10LAC-IC-IOL-0001 | IOL | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M01-10LAC-ME-CAL-0001 | CAL | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M01-10LAC-ME-DSH-0001 | DSH | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M01-10LAC-ME-GAD-0001 | GAD | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M01-10LAC-ME-ITP-0001 | ITP | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M01-10LAC-ME-LST-0001 | LST | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M01-10LAC-ME-MDB-0001 | MDB | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M01-10LAC-ME-OMM-0001 | OMM | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M01-10LAC-ME-PRC-0001 | PRC | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M01-10LAC-ME-TRP-0001 | TRP | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M01-10LAC-ME-TST-0001 | TST | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M01-10LAC-PR-PID-0001 | PID | ALP-EPC-10LAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M02-20LCB-CV-CAL-0001 | CAL | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M02-20LCB-EL-WIR-0001 | WIR | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M02-20LCB-IC-DSH-0001 | DSH | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M02-20LCB-IC-IOL-0001 | IOL | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M02-20LCB-ME-CAL-0001 | CAL | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M02-20LCB-ME-DSH-0001 | DSH | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M02-20LCB-ME-GAD-0001 | GAD | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M02-20LCB-ME-ITP-0001 | ITP | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M02-20LCB-ME-LST-0001 | LST | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M02-20LCB-ME-MDB-0001 | MDB | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M02-20LCB-ME-OMM-0001 | OMM | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M02-20LCB-ME-PRC-0001 | PRC | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M02-20LCB-ME-TRP-0001 | TRP | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M02-20LCB-ME-TST-0001 | TST | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M02-20LCB-PR-PID-0001 | PID | ALP-EPC-20LCB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M03-00PAC-CV-CAL-0001 | CAL | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M03-00PAC-EL-WIR-0001 | WIR | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M03-00PAC-IC-DSH-0001 | DSH | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M03-00PAC-IC-IOL-0001 | IOL | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M03-00PAC-ME-CAL-0001 | CAL | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M03-00PAC-ME-DSH-0001 | DSH | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M03-00PAC-ME-GAD-0001 | GAD | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M03-00PAC-ME-ITP-0001 | ITP | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M03-00PAC-ME-LST-0001 | LST | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M03-00PAC-ME-MDB-0001 | MDB | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M03-00PAC-ME-OMM-0001 | OMM | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M03-00PAC-ME-PRC-0001 | PRC | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M03-00PAC-ME-TRP-0001 | TRP | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M03-00PAC-ME-TST-0001 | TST | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M03-00PAC-PR-PID-0001 | PID | ALP-EPC-00PAC-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M04-00PAA-CV-CAL-0001 | CAL | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M04-00PAA-EL-WIR-0001 | WIR | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M04-00PAA-IC-DSH-0001 | DSH | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M04-00PAA-IC-IOL-0001 | IOL | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M04-00PAA-ME-CAL-0001 | CAL | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M04-00PAA-ME-DSH-0001 | DSH | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M04-00PAA-ME-GAD-0001 | GAD | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M04-00PAA-ME-ITP-0001 | ITP | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M04-00PAA-ME-LST-0001 | LST | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M04-00PAA-ME-MDB-0001 | MDB | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M04-00PAA-ME-OMM-0001 | OMM | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M04-00PAA-ME-PRC-0001 | PRC | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M04-00PAA-ME-TRP-0001 | TRP | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M04-00PAA-ME-TST-0001 | TST | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M04-00PAA-PR-PID-0001 | PID | ALP-EPC-00PAA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M05-00PBA-CV-CAL-0001 | CAL | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M05-00PBA-EL-WIR-0001 | WIR | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M05-00PBA-IC-DSH-0001 | DSH | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M05-00PBA-IC-IOL-0001 | IOL | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M05-00PBA-IC-LOG-0001 | LOG | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M05-00PBA-ME-CAL-0001 | CAL | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M05-00PBA-ME-DSH-0001 | DSH | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M05-00PBA-ME-GAD-0001 | GAD | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M05-00PBA-ME-ITP-0001 | ITP | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M05-00PBA-ME-LST-0001 | LST | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M05-00PBA-ME-MDB-0001 | MDB | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M05-00PBA-ME-OMM-0001 | OMM | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M05-00PBA-ME-PRC-0001 | PRC | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M05-00PBA-ME-TRP-0001 | TRP | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M05-00PBA-ME-TST-0001 | TST | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M05-00PBA-PR-PID-0001 | PID | ALP-EPC-00PBA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M06-00PAH-EL-WIR-0001 | WIR | ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M06-00PAH-IC-DSH-0001 | DSH | ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M06-00PAH-IC-IOL-0001 | IOL | ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M06-00PAH-ME-CAL-0001 | CAL | ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M06-00PAH-ME-DSH-0001 | DSH | ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M06-00PAH-ME-GAD-0001 | GAD | ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M06-00PAH-ME-ITP-0001 | ITP | ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M06-00PAH-ME-LST-0001 | LST | ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M06-00PAH-ME-MDB-0001 | MDB | ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M06-00PAH-ME-OMM-0001 | OMM | ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M06-00PAH-ME-PRC-0001 | PRC | ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M06-00PAH-ME-TRP-0001 | TRP | ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M06-00PAH-ME-TST-0001 | TST | ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M06-00PAH-PR-PID-0001 | PID | ALP-EPC-00PAH-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M07-00PGA-CV-CAL-0001 | CAL | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M07-00PGA-EL-WIR-0001 | WIR | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M07-00PGA-IC-DSH-0001 | DSH | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M07-00PGA-IC-IOL-0001 | IOL | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M07-00PGA-ME-CAL-0001 | CAL | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M07-00PGA-ME-DSH-0001 | DSH | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M07-00PGA-ME-GAD-0001 | GAD | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M07-00PGA-ME-ITP-0001 | ITP | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M07-00PGA-ME-LST-0001 | LST | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M07-00PGA-ME-MDB-0001 | MDB | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M07-00PGA-ME-OMM-0001 | OMM | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M07-00PGA-ME-PRC-0001 | PRC | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M07-00PGA-ME-TRP-0001 | TRP | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M07-00PGA-ME-TST-0001 | TST | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M07-00PGA-PR-PID-0001 | PID | ALP-EPC-00PGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M08-00QEA-CV-CAL-0001 | CAL | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M08-00QEA-EL-WIR-0001 | WIR | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M08-00QEA-IC-DSH-0001 | DSH | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M08-00QEA-IC-IOL-0001 | IOL | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M08-00QEA-IC-LOG-0001 | LOG | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M08-00QEA-ME-CAL-0001 | CAL | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M08-00QEA-ME-DSH-0001 | DSH | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M08-00QEA-ME-GAD-0001 | GAD | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M08-00QEA-ME-ITP-0001 | ITP | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M08-00QEA-ME-LST-0001 | LST | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M08-00QEA-ME-MDB-0001 | MDB | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M08-00QEA-ME-OMM-0001 | OMM | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M08-00QEA-ME-PRC-0001 | PRC | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M08-00QEA-ME-TRP-0001 | TRP | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M08-00QEA-ME-TST-0001 | TST | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M08-00QEA-PR-PID-0001 | PID | ALP-EPC-00QEA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M09-00QHA-CV-CAL-0001 | CAL | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M09-00QHA-EL-WIR-0001 | WIR | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M09-00QHA-IC-DSH-0001 | DSH | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M09-00QHA-IC-IOL-0001 | IOL | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M09-00QHA-IC-LOG-0001 | LOG | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M09-00QHA-ME-CAL-0001 | CAL | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M09-00QHA-ME-DSH-0001 | DSH | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M09-00QHA-ME-GAD-0001 | GAD | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M09-00QHA-ME-ITP-0001 | ITP | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M09-00QHA-ME-LST-0001 | LST | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M09-00QHA-ME-MDB-0001 | MDB | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M09-00QHA-ME-OMM-0001 | OMM | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M09-00QHA-ME-PRC-0001 | PRC | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M09-00QHA-ME-TRP-0001 | TRP | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M09-00QHA-ME-TST-0001 | TST | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M09-00QHA-PR-PID-0001 | PID | ALP-EPC-00QHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M10-00QJA-EL-WIR-0001 | WIR | ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | IFC | 2027-04-15
ALP-M10-00QJA-IC-DSH-0001 | DSH | ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | IFR | 2027-04-12
ALP-M10-00QJA-IC-IOL-0001 | IOL | ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | IFR | 2027-04-12
ALP-M10-00QJA-ME-CAL-0001 | CAL | ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | IFR | 2027-04-12
ALP-M10-00QJA-ME-DSH-0001 | DSH | ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | IFR | 2027-04-12
ALP-M10-00QJA-ME-GAD-0001 | GAD | ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | IFR | 2027-04-12
ALP-M10-00QJA-ME-ITP-0001 | ITP | ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | IFR | 2027-04-12
ALP-M10-00QJA-ME-LST-0001 | LST | ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | IFR | 2027-04-12
ALP-M10-00QJA-ME-MDB-0001 | MDB | ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | IFR | 2027-04-12
ALP-M10-00QJA-ME-OMM-0001 | OMM | ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | IFR | 2027-04-12
ALP-M10-00QJA-ME-PRC-0001 | PRC | ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | IFR | 2027-04-12
ALP-M10-00QJA-ME-TRP-0001 | TRP | ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | IFR | 2027-04-12
ALP-M10-00QJA-ME-TST-0001 | TST | ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | IFR | 2027-04-12
ALP-M10-00QJA-PR-PID-0001 | PID | ALP-EPC-00QJA-ME-MRQ-0001 | MRQ | IFR | 2027-04-12
ALP-M11-00QCA-EL-WIR-0001 | WIR | ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | IFC | 2027-04-16
ALP-M11-00QCA-IC-DSH-0001 | DSH | ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | IFR | 2027-04-13
ALP-M11-00QCA-IC-IOL-0001 | IOL | ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | IFR | 2027-04-13
ALP-M11-00QCA-ME-CAL-0001 | CAL | ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | IFR | 2027-04-13
ALP-M11-00QCA-ME-DSH-0001 | DSH | ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | IFR | 2027-04-13
ALP-M11-00QCA-ME-GAD-0001 | GAD | ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | IFR | 2027-04-13
ALP-M11-00QCA-ME-ITP-0001 | ITP | ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | IFR | 2027-04-13
ALP-M11-00QCA-ME-LST-0001 | LST | ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | IFR | 2027-04-13
ALP-M11-00QCA-ME-MDB-0001 | MDB | ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | IFR | 2027-04-13
ALP-M11-00QCA-ME-OMM-0001 | OMM | ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | IFR | 2027-04-13
ALP-M11-00QCA-ME-PRC-0001 | PRC | ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | IFR | 2027-04-13
ALP-M11-00QCA-ME-TRP-0001 | TRP | ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | IFR | 2027-04-13
ALP-M11-00QCA-ME-TST-0001 | TST | ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | IFR | 2027-04-13
ALP-M11-00QCA-PR-PID-0001 | PID | ALP-EPC-00QCA-ME-MRQ-0001 | MRQ | IFR | 2027-04-13
ALP-M12-00GBA-CV-CAL-0001 | CAL | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M12-00GBA-EL-WIR-0001 | WIR | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M12-00GBA-IC-DSH-0001 | DSH | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M12-00GBA-IC-IOL-0001 | IOL | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M12-00GBA-IC-LOG-0001 | LOG | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M12-00GBA-ME-CAL-0001 | CAL | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M12-00GBA-ME-DSH-0001 | DSH | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M12-00GBA-ME-GAD-0001 | GAD | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M12-00GBA-ME-ITP-0001 | ITP | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M12-00GBA-ME-LST-0001 | LST | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M12-00GBA-ME-MDB-0001 | MDB | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M12-00GBA-ME-OMM-0001 | OMM | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M12-00GBA-ME-PRC-0001 | PRC | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M12-00GBA-ME-TRP-0001 | TRP | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M12-00GBA-ME-TST-0001 | TST | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M12-00GBA-PR-PID-0001 | PID | ALP-EPC-00LDA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M13-00GHA-CV-CAL-0001 | CAL | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M13-00GHA-EL-WIR-0001 | WIR | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M13-00GHA-IC-DSH-0001 | DSH | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M13-00GHA-IC-IOL-0001 | IOL | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M13-00GHA-ME-CAL-0001 | CAL | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M13-00GHA-ME-DSH-0001 | DSH | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M13-00GHA-ME-GAD-0001 | GAD | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M13-00GHA-ME-ITP-0001 | ITP | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M13-00GHA-ME-LST-0001 | LST | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M13-00GHA-ME-MDB-0001 | MDB | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M13-00GHA-ME-OMM-0001 | OMM | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M13-00GHA-ME-PRC-0001 | PRC | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M13-00GHA-ME-TRP-0001 | TRP | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M13-00GHA-ME-TST-0001 | TST | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M13-00GHA-PR-PID-0001 | PID | ALP-EPC-00GHA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M14-00GNA-CV-CAL-0001 | CAL | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M14-00GNA-EL-WIR-0001 | WIR | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M14-00GNA-IC-DSH-0001 | DSH | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M14-00GNA-IC-IOL-0001 | IOL | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M14-00GNA-IC-LOG-0001 | LOG | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M14-00GNA-ME-CAL-0001 | CAL | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M14-00GNA-ME-DSH-0001 | DSH | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M14-00GNA-ME-GAD-0001 | GAD | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M14-00GNA-ME-ITP-0001 | ITP | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M14-00GNA-ME-LST-0001 | LST | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M14-00GNA-ME-MDB-0001 | MDB | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M14-00GNA-ME-OMM-0001 | OMM | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M14-00GNA-ME-PRC-0001 | PRC | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M14-00GNA-ME-TRP-0001 | TRP | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M14-00GNA-ME-TST-0001 | TST | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M14-00GNA-PR-PID-0001 | PID | ALP-EPC-00GNA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M15-00EKA-CV-CAL-0001 | CAL | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M15-00EKA-EL-WIR-0001 | WIR | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M15-00EKA-IC-DSH-0001 | DSH | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M15-00EKA-IC-IOL-0001 | IOL | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M15-00EKA-ME-CAL-0001 | CAL | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M15-00EKA-ME-DSH-0001 | DSH | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M15-00EKA-ME-GAD-0001 | GAD | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M15-00EKA-ME-ITP-0001 | ITP | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M15-00EKA-ME-LST-0001 | LST | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M15-00EKA-ME-MDB-0001 | MDB | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M15-00EKA-ME-OMM-0001 | OMM | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M15-00EKA-ME-PRC-0001 | PRC | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M15-00EKA-ME-TRP-0001 | TRP | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M15-00EKA-ME-TST-0001 | TST | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M15-00EKA-PR-PID-0001 | PID | ALP-EPC-00EKA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M16-00EGA-CV-CAL-0001 | CAL | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M16-00EGA-EL-WIR-0001 | WIR | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M16-00EGA-IC-DSH-0001 | DSH | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M16-00EGA-IC-IOL-0001 | IOL | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M16-00EGA-ME-CAL-0001 | CAL | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M16-00EGA-ME-DSH-0001 | DSH | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M16-00EGA-ME-GAD-0001 | GAD | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M16-00EGA-ME-ITP-0001 | ITP | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M16-00EGA-ME-LST-0001 | LST | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M16-00EGA-ME-MDB-0001 | MDB | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M16-00EGA-ME-OMM-0001 | OMM | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M16-00EGA-ME-PRC-0001 | PRC | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M16-00EGA-ME-TRP-0001 | TRP | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M16-00EGA-ME-TST-0001 | TST | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M16-00EGA-PR-PID-0001 | PID | ALP-EPC-00EGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M17-00EGB-GE-ITP-0001 | ITP | ALP-EPC-00EGB-ME-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-M17-00EGB-GE-MOS-0001 | MOS | ALP-EPC-00EGB-ME-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-M17-00EGB-GE-MOS-0002 | MOS | ALP-EPC-00EGB-ME-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-M17-00EGB-GE-MOS-0003 | MOS | ALP-EPC-00EGB-ME-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-M17-00EGB-GE-MOS-0004 | MOS | ALP-EPC-00EGB-ME-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-M17-00EGB-GE-MOS-0005 | MOS | ALP-EPC-00EGB-ME-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-M17-00EGB-GE-MOS-0006 | MOS | ALP-EPC-00EGB-ME-MRQ-0001 | MRQ | IFR | 2026-11-23
ALP-M18-10HSB-CV-CAL-0001 | CAL | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M18-10HSB-EL-WIR-0001 | WIR | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M18-10HSB-IC-DSH-0001 | DSH | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M18-10HSB-IC-IOL-0001 | IOL | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M18-10HSB-ME-CAL-0001 | CAL | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M18-10HSB-ME-DSH-0001 | DSH | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M18-10HSB-ME-GAD-0001 | GAD | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M18-10HSB-ME-ITP-0001 | ITP | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M18-10HSB-ME-LST-0001 | LST | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M18-10HSB-ME-MDB-0001 | MDB | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M18-10HSB-ME-OMM-0001 | OMM | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M18-10HSB-ME-PRC-0001 | PRC | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M18-10HSB-ME-TRP-0001 | TRP | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M18-10HSB-ME-TST-0001 | TST | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M18-10HSB-PR-PID-0001 | PID | ALP-EPC-10HSB-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M19-10HAN-CV-CAL-0001 | CAL | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M19-10HAN-EL-WIR-0001 | WIR | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M19-10HAN-IC-DSH-0001 | DSH | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M19-10HAN-IC-IOL-0001 | IOL | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M19-10HAN-ME-CAL-0001 | CAL | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M19-10HAN-ME-DSH-0001 | DSH | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M19-10HAN-ME-GAD-0001 | GAD | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M19-10HAN-ME-ITP-0001 | ITP | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M19-10HAN-ME-LST-0001 | LST | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M19-10HAN-ME-MDB-0001 | MDB | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M19-10HAN-ME-OMM-0001 | OMM | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M19-10HAN-ME-PRC-0001 | PRC | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M19-10HAN-ME-TRP-0001 | TRP | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M19-10HAN-ME-TST-0001 | TST | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M19-10HAN-PR-PID-0001 | PID | ALP-EPC-10HAN-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M20-00SGA-CV-CAL-0001 | CAL | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M20-00SGA-EL-WIR-0001 | WIR | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M20-00SGA-IC-DSH-0001 | DSH | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M20-00SGA-IC-IOL-0001 | IOL | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M20-00SGA-ME-CAL-0001 | CAL | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M20-00SGA-ME-DSH-0001 | DSH | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M20-00SGA-ME-GAD-0001 | GAD | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M20-00SGA-ME-ITP-0001 | ITP | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M20-00SGA-ME-LST-0001 | LST | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M20-00SGA-ME-MDB-0001 | MDB | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M20-00SGA-ME-OMM-0001 | OMM | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M20-00SGA-ME-PRC-0001 | PRC | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M20-00SGA-ME-TRP-0001 | TRP | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M20-00SGA-ME-TST-0001 | TST | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M20-00SGA-PR-PID-0001 | PID | ALP-EPC-00SGA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M21-00SMA-CV-CAL-0001 | CAL | ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M21-00SMA-EL-WIR-0001 | WIR | ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | IFC | 2026-11-05
ALP-M21-00SMA-IC-IOL-0001 | IOL | ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M21-00SMA-ME-CAL-0001 | CAL | ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M21-00SMA-ME-DSH-0001 | DSH | ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M21-00SMA-ME-GAD-0001 | GAD | ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M21-00SMA-ME-ITP-0001 | ITP | ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M21-00SMA-ME-LST-0001 | LST | ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M21-00SMA-ME-MDB-0001 | MDB | ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M21-00SMA-ME-OMM-0001 | OMM | ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M21-00SMA-ME-PRC-0001 | PRC | ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M21-00SMA-ME-TRP-0001 | TRP | ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M21-00SMA-ME-TST-0001 | TST | ALP-EPC-00SMA-ME-MRQ-0001 | MRQ | IFR | 2026-11-02
ALP-M22-00000-GE-ITP-0001 | ITP | ALP-EPC-00000-GE-MRQ-0004 | MRQ | IFR | 2027-04-22
ALP-M22-00000-GE-MOS-0001 | MOS | ALP-EPC-00000-GE-MRQ-0004 | MRQ | IFR | 2027-04-22
ALP-M22-00000-GE-MOS-0002 | MOS | ALP-EPC-00000-GE-MRQ-0004 | MRQ | IFR | 2027-04-22
ALP-M22-00000-GE-MOS-0003 | MOS | ALP-EPC-00000-GE-MRQ-0004 | MRQ | IFR | 2027-04-22
ALP-M22-00000-GE-MOS-0004 | MOS | ALP-EPC-00000-GE-MRQ-0004 | MRQ | IFR | 2027-04-22
ALP-M22-00000-GE-MOS-0005 | MOS | ALP-EPC-00000-GE-MRQ-0004 | MRQ | IFR | 2027-04-22
ALP-M22-00000-GE-MOS-0006 | MOS | ALP-EPC-00000-GE-MRQ-0004 | MRQ | IFR | 2027-04-22
ALP-M23-00000-GE-ITP-0001 | ITP | ALP-EPC-00000-GE-MRQ-0005 | MRQ | IFR | 2027-06-25
ALP-M23-00000-GE-MOS-0001 | MOS | ALP-EPC-00000-GE-MRQ-0005 | MRQ | IFR | 2027-06-25
ALP-M23-00000-GE-MOS-0002 | MOS | ALP-EPC-00000-GE-MRQ-0005 | MRQ | IFR | 2027-06-25
ALP-M23-00000-GE-MOS-0003 | MOS | ALP-EPC-00000-GE-MRQ-0005 | MRQ | IFR | 2027-06-25
ALP-M23-00000-GE-MOS-0004 | MOS | ALP-EPC-00000-GE-MRQ-0005 | MRQ | IFR | 2027-06-25
ALP-M23-00000-GE-MOS-0005 | MOS | ALP-EPC-00000-GE-MRQ-0005 | MRQ | IFR | 2027-06-25
ALP-M23-00000-GE-MOS-0006 | MOS | ALP-EPC-00000-GE-MRQ-0005 | MRQ | IFR | 2027-06-25
ALP-M24-00UZF-GE-ITP-0001 | ITP | ALP-EPC-00UZF-GE-MRQ-0001 | MRQ | IFR | 2027-07-13
ALP-M24-00UZF-GE-MOS-0001 | MOS | ALP-EPC-00UZF-GE-MRQ-0001 | MRQ | IFR | 2027-07-13
ALP-M24-00UZF-GE-MOS-0002 | MOS | ALP-EPC-00UZF-GE-MRQ-0001 | MRQ | IFR | 2027-07-13
ALP-M24-00UZF-GE-MOS-0003 | MOS | ALP-EPC-00UZF-GE-MRQ-0001 | MRQ | IFR | 2027-07-13
ALP-M24-00UZF-GE-MOS-0004 | MOS | ALP-EPC-00UZF-GE-MRQ-0001 | MRQ | IFR | 2027-07-13
ALP-M24-00UZF-GE-MOS-0005 | MOS | ALP-EPC-00UZF-GE-MRQ-0001 | MRQ | IFR | 2027-07-13
ALP-M24-00UZF-GE-MOS-0006 | MOS | ALP-EPC-00UZF-GE-MRQ-0001 | MRQ | IFR | 2027-07-13
ALP-P01-00000-ME-DSH-0001 | DSH | ALP-EPC-00000-PI-MRQ-0001 | MRQ | IFR | 2026-12-07
ALP-P01-00000-ME-ITP-0001 | ITP | ALP-EPC-00000-PI-MRQ-0001 | MRQ | IFR | 2026-12-07
ALP-P01-00000-ME-MDB-0001 | MDB | ALP-EPC-00000-PI-MRQ-0001 | MRQ | IFR | 2026-12-07
ALP-P02-10LBA-ME-DSH-0001 | DSH | ALP-EPC-00000-PI-MRQ-0002 | MRQ | IFR | 2027-01-18
ALP-P02-10LBA-ME-ITP-0001 | ITP | ALP-EPC-00000-PI-MRQ-0002 | MRQ | IFR | 2027-01-18
ALP-P02-10LBA-ME-MDB-0001 | MDB | ALP-EPC-00000-PI-MRQ-0002 | MRQ | IFR | 2027-01-18
ALP-P03-00000-ME-DSH-0001 | DSH | ALP-EPC-00000-PI-MRQ-0003 | MRQ | IFR | 2026-12-22
ALP-P03-00000-ME-ITP-0001 | ITP | ALP-EPC-00000-PI-MRQ-0003 | MRQ | IFR | 2026-12-22
ALP-P03-00000-ME-MDB-0001 | MDB | ALP-EPC-00000-PI-MRQ-0003 | MRQ | IFR | 2026-12-22
ALP-P04-00PAB-ME-DSH-0001 | DSH | ALP-EPC-00000-PI-MRQ-0004 | MRQ | IFR | 2026-11-02
ALP-P04-00PAB-ME-ITP-0001 | ITP | ALP-EPC-00000-PI-MRQ-0004 | MRQ | IFR | 2026-11-02
ALP-P04-00PAB-ME-MDB-0001 | MDB | ALP-EPC-00000-PI-MRQ-0004 | MRQ | IFR | 2026-11-02
ALP-P05-00000-ME-DSH-0001 | DSH | ALP-EPC-00000-GE-MRQ-0006 | MRQ | IFR | 2027-03-25
ALP-P05-00000-ME-ITP-0001 | ITP | ALP-EPC-00000-GE-MRQ-0006 | MRQ | IFR | 2027-03-25
ALP-P05-00000-ME-MDB-0001 | MDB | ALP-EPC-00000-GE-MRQ-0006 | MRQ | IFR | 2027-03-25
ALP-P06-00000-ME-DSH-0001 | DSH | ALP-EPC-00000-GE-MRQ-0007 | MRQ | IFR | 2026-12-07
ALP-P06-00000-ME-ITP-0001 | ITP | ALP-EPC-00000-GE-MRQ-0007 | MRQ | IFR | 2026-12-07
ALP-P06-00000-ME-MDB-0001 | MDB | ALP-EPC-00000-GE-MRQ-0007 | MRQ | IFR | 2026-12-07
ALP-P07-00000-ME-DSH-0001 | DSH | ALP-EPC-00000-GE-MRQ-0008 | MRQ | IFR | 2026-12-07
ALP-P07-00000-ME-ITP-0001 | ITP | ALP-EPC-00000-GE-MRQ-0008 | MRQ | IFR | 2026-12-07
ALP-P07-00000-ME-MDB-0001 | MDB | ALP-EPC-00000-GE-MRQ-0008 | MRQ | IFR | 2026-12-07
ALP-S01-00000-GE-ITP-0001 | ITP | ALP-EPC-00000-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-S01-00000-GE-MOS-0001 | MOS | ALP-EPC-00000-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-S01-00000-GE-MOS-0002 | MOS | ALP-EPC-00000-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-S01-00000-GE-MOS-0003 | MOS | ALP-EPC-00000-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-S01-00000-GE-MOS-0004 | MOS | ALP-EPC-00000-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-S01-00000-GE-MOS-0005 | MOS | ALP-EPC-00000-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-S01-00000-GE-MOS-0006 | MOS | ALP-EPC-00000-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-S01-00UAC-SS-STL-0001 | STL | ALP-EPC-00UAC-SS-STL-0002 | STL | IFR | 2027-03-19
ALP-S01-00UBA-SS-STL-0001 | STL | ALP-EPC-00UBA-SS-STL-0002 | STL | IFR | 2027-04-02
ALP-S01-00UBF-SS-STL-0001 | STL | ALP-EPC-00UBF-SS-STL-0001 | STL | IFR | 2027-05-12
ALP-S01-00UCA-SS-STL-0001 | STL | ALP-EPC-00UCA-SS-STL-0002 | STL | IFR | 2027-05-13
ALP-S01-00UEG-SS-STL-0001 | STL | ALP-EPC-00UEG-SS-STL-0001 | STL | IFR | 2027-03-19
ALP-S01-00UEK-SS-STL-0001 | STL | ALP-EPC-00UEK-SS-STL-0001 | STL | IFR | 2027-05-13
ALP-S01-00UGA-SS-STL-0001 | STL | ALP-EPC-00UGA-SS-STL-0002 | STL | IFR | 2027-03-31
ALP-S01-00UPC-SS-STL-0001 | STL | ALP-EPC-00UPC-SS-STL-0001 | STL | IFR | 2027-03-16
ALP-S01-00UQA-SS-STL-0001 | STL | ALP-EPC-00UQA-SS-STL-0001 | STL | IFR | 2027-05-12
ALP-S01-00USA-SS-STL-0001 | STL | ALP-EPC-00USA-SS-STL-0002 | STL | IFR | 2027-05-14
ALP-S01-00UYA-SS-STL-0001 | STL | ALP-EPC-00UYA-SS-STL-0002 | STL | IFR | 2027-05-12
ALP-S01-00UZD-SS-STL-0001 | STL | ALP-EPC-00UZD-SS-STL-0001 | STL | IFR | 2027-04-07
ALP-S01-00UZD-SS-STL-0002 | STL | ALP-EPC-00UZD-SS-STL-0001 | STL | IFR | 2027-04-07
ALP-S01-00UZF-SS-STL-0001 | STL | ALP-EPC-00UZF-SS-STL-0001 | STL | IFR | 2027-07-12
ALP-S01-10UMA-SS-STL-0001 | STL | ALP-EPC-10UMA-SS-STL-0001 | STL | IFR | 2027-06-02
ALP-S01-20UMB-SS-STL-0001 | STL | ALP-EPC-20UMB-SS-STL-0001 | STL | IFR | 2027-06-03
ALP-S02-10HNE-CV-CAL-0001 | CAL | ALP-EPC-10HNE-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-S02-10HNE-GE-ITP-0001 | ITP | ALP-EPC-10HNE-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-S02-10HNE-GE-MOS-0001 | MOS | ALP-EPC-10HNE-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-S02-10HNE-GE-MOS-0002 | MOS | ALP-EPC-10HNE-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-S02-10HNE-GE-MOS-0003 | MOS | ALP-EPC-10HNE-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-S02-10HNE-GE-MOS-0004 | MOS | ALP-EPC-10HNE-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-S02-10HNE-GE-MOS-0005 | MOS | ALP-EPC-10HNE-SS-MRQ-0001 | MRQ | IFR | 2026-11-09
ALP-S02-10HNE-GE-MOS-0006 | MOS | ALP-EPC-10HNE-SS-MRQ-0001 | MRQ | IFR | 2026-11-09

## EWP
Alpilla 600 MW Combined Cycle Power Plant - Engineering work packages
engine engineering_plan v1.6.0 ¦ generated 2026-09-29T03:49:44Z by EPCE ¦ data 73eaa92ce7c1ff26 ¦ dates computed from the workflow network and the CPM (working days)
EWP | CWA | CWP | Title | Docs | IFC complete | Last document | CWP start | Needed | Float wd | Vendor data MR | Vendor data | Vendor float
EWP-01-CV-01 | CWA-01 | CWP-01-CV-01 | IFC documents for Piling - power block GT/HRSG | 4 | 2027-04-12 | ALP-EPC-10UMA-CV-FND-0001 | 2027-04-19 | 2027-03-22 | -3 | MR-CV-001 | 2027-01-28 | 37
EWP-01-CV-02 | CWA-01 | CWP-01-CV-02 | IFC documents for Foundations - power block GT/HRSG | 14 | 2027-06-22 | ALP-EPC-10UMA-CV-RBR-0001 | 2027-05-17 | 2027-04-19 | -7 | MR-CV-002 | 2027-01-07 | 72
EWP-01-EL-01 | CWA-01 | CWP-01-EL-01 | IFC documents for Electrical - power block GT/HRSG | 11 | 2027-10-28 | ALP-EPC-00UBF-EL-ELY-0001 | 2028-02-07 | 2028-01-10 | 81 | MR-EL-012 | 2027-08-02 | 115
EWP-01-HV-01 | CWA-01 | CWP-01-HV-01 | IFC documents for HVAC and fire protection - GT hall | 1 | 2027-06-11 | ALP-EPC-10UMA-HV-GAD-0001 | 2027-11-29 | 2027-11-01 | 125 | MR-ME-020 | 2027-03-25 | 157
EWP-01-IC-01 | CWA-01 | CWP-01-IC-01 | IFC documents for I&C - power block GT/HRSG | 13 | 2027-10-05 | ALP-EPC-10UMA-IC-ELY-0001 | 2028-03-06 | 2028-02-07 | 128 | MR-EL-012 | 2027-08-02 | 135
EWP-01-ME-01 | CWA-01 | CWP-01-ME-01 | IFC documents for GT, generator and HRSG erection | 14 | 2027-09-06 | ALP-IEC-10MBA-ME-PRC-0001 | 2027-11-15 | 2027-10-18 | 30 | MR-ME-024 | 2027-10-15 | 1
EWP-01-PI-01 | CWA-01 | CWP-01-PI-01 | IFC documents for Piping - power block GT/HRSG | 19 | 2028-02-29 | ALP-EPC-10LAE-PI-SUP-0001 | 2028-01-10 | 2027-12-13 | 19 | MR-ME-023 | 2027-10-13 | 43
EWP-01-SS-01 | CWA-01 | CWP-01-SS-01 | IFC documents for GT hall steel, cladding, crane, pipe racks | 5 | 2027-07-07 | ALP-EPC-10UMA-SS-STL-0001 | 2027-08-09 | 2027-07-12 | 36 | MR-SS-001 | 2027-02-25 | 97
EWP-02-CV-01 | CWA-02 | CWP-02-CV-01 | IFC documents for Piling - ST hall and condenser | 1 | 2027-04-12 | ALP-EPC-20UMB-CV-FND-0001 | 2027-04-19 | 2027-03-22 | -5 | MR-CV-001 | 2027-01-28 | 37
EWP-02-CV-02 | CWA-02 | CWP-02-CV-02 | IFC documents for Foundations - ST hall and condenser | 5 | 2027-06-25 | ALP-EPC-20UMB-CV-RBR-0001 | 2027-05-17 | 2027-04-19 | -4 | MR-CV-002 | 2027-01-07 | 72
EWP-02-EL-01 | CWA-02 | CWP-02-EL-01 | IFC documents for Electrical - ST island | 4 | 2027-11-24 | ALP-EPC-20UMB-EL-ELY-0002 | 2028-03-27 | 2028-02-28 | 90 | MR-EL-008 | 2027-05-06 | 212
EWP-02-IC-01 | CWA-02 | CWP-02-IC-01 | IFC documents for I&C - ST island | 5 | 2027-10-01 | ALP-EPC-20UMB-IC-ELY-0001 | 2028-04-24 | 2028-03-27 | 168 | MR-IC-010 | 2027-07-12 | 185
EWP-02-ME-01 | CWA-02 | CWP-02-ME-01 | IFC documents for Condenser, ST and generator erection | 5 | 2027-06-11 | ALP-M02-20LCB-ME-GAD-0001 | 2028-01-17 | 2027-12-20 | 208 | MR-ME-024 | 2027-10-15 | 46
EWP-02-PI-01 | CWA-02 | CWP-02-PI-01 | IFC documents for Piping - ST island | 11 | 2028-04-26 | ALP-EPC-20LCA-PI-SUP-0001 | 2028-02-28 | 2028-01-31 | 13 | MR-ME-022 | 2027-07-27 | 134
EWP-02-SS-01 | CWA-02 | CWP-02-SS-01 | IFC documents for ST hall steel, cladding, crane | 3 | 2027-07-08 | ALP-EPC-20UMB-SS-STL-0001 | 2027-08-09 | 2027-07-12 | 35 | MR-SS-001 | 2027-02-25 | 97
EWP-03-CV-01 | CWA-03 | CWP-03-CV-01 | IFC documents for Foundations - electrical building | 6 | 2027-05-11 | ALP-EPC-00UBA-HV-GAD-0002 | 2027-04-26 | 2027-03-29 | -10 | MR-CV-002 | 2027-01-07 | 57
EWP-03-EL-01 | CWA-03 | CWP-03-EL-01 | IFC documents for MV/LV switchgear, UPS, DC, emergency diesel | 31 | 2027-09-21 | ALP-EPC-00UBA-IC-ELY-0002 | 2027-11-22 | 2027-10-25 | 53 | MR-EL-012 | 2027-08-02 | 60
EWP-03-HV-01 | CWA-03 | CWP-03-HV-01 | IFC documents for HVAC plant and electrical building HVAC | 7 | 2027-10-20 | ALP-EPC-00SAA-PI-SUP-0001 | 2027-11-08 | 2027-10-11 | 28 | MR-HV-001 | 2027-03-25 | 142
EWP-03-SS-01 | CWA-03 | CWP-03-SS-01 | IFC documents for Electrical building | 4 | 2027-05-07 | ALP-EPC-00UBA-SS-STL-0002 | 2027-06-21 | 2027-05-24 | 56
EWP-04-CV-01 | CWA-04 | CWP-04-CV-01 | IFC documents for Foundations - GIS building and gantry | 6 | 2027-05-04 | ALP-EPC-00UAC-HV-GAD-0001 | 2027-05-03 | 2027-04-05 | -3
EWP-04-EL-01 | CWA-04 | CWP-04-EL-01 | IFC documents for GIS erection, HV connections, testing | 11 | 2027-10-07 | ALP-EPC-00UAC-EL-CBL-0001 | 2028-02-01 | 2028-01-04 | 93 | MR-EL-008 | 2027-05-06 | 173
EWP-04-SS-01 | CWA-04 | CWP-04-SS-01 | IFC documents for GIS building | 4 | 2027-04-23 | ALP-EPC-00UAC-SS-STL-0002 | 2027-06-28 | 2027-05-31 | 56
EWP-05-CV-01 | CWA-05 | CWP-05-CV-01 | IFC documents for CW pump house and onshore culverts | 9 | 2027-06-10 | ALP-EPC-00UPC-CV-RBR-0001 | 2027-04-22 | 2027-03-25 | -10 | MR-CV-002 | 2027-01-07 | 55
EWP-05-EL-01 | CWA-05 | CWP-05-EL-01 | IFC documents for Electrical - CW pump house | 4 | 2027-11-03 | ALP-EPC-00UPC-EL-ELY-0003 | 2028-02-28 | 2028-01-31 | 77 | MR-EL-008 | 2027-05-06 | 192
EWP-05-IC-01 | CWA-05 | CWP-05-IC-01 | IFC documents for I&C - CW pump house | 5 | 2027-09-14 | ALP-EPC-00UPC-IC-ELY-0001 | 2028-03-27 | 2028-02-28 | 138 | MR-IC-010 | 2027-07-12 | 165
EWP-05-ME-01 | CWA-05 | CWP-05-ME-01 | IFC documents for CW pumps, screens, electro-chlorination | 7 | 2027-05-27 | ALP-M05-00PBA-EL-WIR-0001 | 2028-01-17 | 2027-12-20 | 187 | MR-ME-005 | 2027-03-31 | 188
EWP-05-PI-01 | CWA-05 | CWP-05-PI-01 | IFC documents for CW GRP piping onshore | 10 | 2027-10-05 | ALP-EPC-00PBA-PI-SUP-0001 | 2027-10-18 | 2027-09-20 | 49 | MR-PI-004 | 2027-02-24 | 148
EWP-06-CV-01 | CWA-06 | CWP-06-CV-01 | IFC documents for Marine works | 11 | 2027-10-20 | ALP-EPC-00UPA-EL-ELY-0001 | 2027-10-01 | 2027-09-03 | -7 | MR-CV-003 | 2027-04-13 | 103
EWP-07-CV-01 | CWA-07 | CWP-07-CV-01 | IFC documents for Demolition and foundations - water treatment | 5 | 2027-06-07 | ALP-EPC-00UGA-HV-GAD-0001 | 2027-05-03 | 2027-04-05 | -12
EWP-07-EL-01 | CWA-07 | CWP-07-EL-01 | IFC documents for Electrical - water treatment | 4 | 2027-11-08 | ALP-EPC-00UGA-EL-ELY-0002 | 2028-03-20 | 2028-02-21 | 91 | MR-EL-008 | 2027-05-06 | 207
EWP-07-IC-01 | CWA-07 | CWP-07-IC-01 | IFC documents for I&C - water treatment | 5 | 2027-09-24 | ALP-EPC-00UGA-IC-ELY-0001 | 2028-04-17 | 2028-03-20 | 153 | MR-IC-004 | 2027-05-06 | 227
EWP-07-ME-01 | CWA-07 | CWP-07-ME-01 | IFC documents for Water treatment packages and tanks | 7 | 2027-06-03 | ALP-M12-00GBA-EL-WIR-0001 | 2028-01-24 | 2027-12-27 | 197 | MR-ME-012 | 2027-04-08 | 187
EWP-07-PI-01 | CWA-07 | CWP-07-PI-01 | IFC documents for Piping - water treatment | 13 | 2028-03-09 | ALP-EPC-00GHA-PI-SUP-0001 | 2028-02-21 | 2028-01-24 | 17 | MR-PI-001 | 2027-02-25 | 237
EWP-07-SS-01 | CWA-07 | CWP-07-SS-01 | IFC documents for Water treatment building | 4 | 2027-05-05 | ALP-EPC-00UGA-SS-STL-0002 | 2027-07-12 | 2027-06-14 | 58
EWP-08-CV-01 | CWA-08 | CWP-08-CV-01 | IFC documents for Foundations - BOP utilities | 5 | 2027-06-10 | ALP-EPC-00UQA-HV-GAD-0001 | 2027-06-01 | 2027-05-04 | 3
EWP-08-EL-01 | CWA-08 | CWP-08-EL-01 | IFC documents for Electrical - BOP utilities | 4 | 2027-10-25 | ALP-EPC-00UQA-EL-CBL-0001 | 2028-02-07 | 2028-01-10 | 85 | MR-EL-008 | 2027-05-06 | 177
EWP-08-IC-01 | CWA-08 | CWP-08-IC-01 | IFC documents for I&C - BOP utilities | 6 | 2027-10-08 | ALP-EPC-00UQA-IC-ELY-0001 | 2028-03-20 | 2028-02-21 | 129 | MR-IC-004 | 2027-05-06 | 207
EWP-08-ME-01 | CWA-08 | CWP-08-ME-01 | IFC documents for BOP utilities equipment | 17 | 2027-08-19 | ALP-M11-00QCA-ME-GAD-0001 | 2027-11-29 | 2027-11-01 | 108 | MR-ME-023 | 2027-10-13 | 13
EWP-08-PI-01 | CWA-08 | CWP-08-PI-01 | IFC documents for Piping - BOP utilities | 25 | 2028-01-26 | ALP-EPC-10LAB-PI-SUP-0001 | 2028-01-10 | 2027-12-13 | 28 | MR-ME-022 | 2027-07-27 | 99
EWP-08-SS-01 | CWA-08 | CWP-08-SS-01 | IFC documents for Utility building and pipe racks | 3 | 2027-06-16 | ALP-EPC-00UQA-SS-STL-0001 | 2027-07-27 | 2027-06-29 | 39 | MR-SS-001 | 2027-02-25 | 88
EWP-09-CV-01 | CWA-09 | CWP-09-CV-01 | IFC documents for Foundations - gas station | 8 | 2027-08-13 | ALP-EPC-00UEK-CV-RBR-0001 | 2027-09-01 | 2027-08-04 | 18
EWP-09-EL-01 | CWA-09 | CWP-09-EL-01 | IFC documents for Electrical - gas station | 4 | 2027-09-08 | ALP-EPC-00UEK-EL-ELY-0003 | 2028-01-24 | 2027-12-27 | 89 | MR-EL-008 | 2027-05-06 | 167
EWP-09-IC-01 | CWA-09 | CWP-09-IC-01 | IFC documents for I&C - gas station | 5 | 2027-09-15 | ALP-EPC-00UEK-IC-ELY-0001 | 2028-02-21 | 2028-01-24 | 111 | MR-IC-004 | 2027-05-06 | 187
EWP-09-ME-01 | CWA-09 | CWP-09-ME-01 | IFC documents for Gas station equipment | 3 | 2027-05-20 | ALP-M15-00EKA-EL-WIR-0001 | 2027-11-29 | 2027-11-01 | 147 | MR-ME-015 | 2027-03-25 | 157
EWP-09-PI-01 | CWA-09 | CWP-09-PI-01 | IFC documents for Piping - gas station and gas line to the GT | 5 | 2027-12-08 | ALP-EPC-00EKC-PI-SUP-0001 | 2027-12-27 | 2027-11-29 | 33 | MR-PI-001 | 2027-02-25 | 197
EWP-10-CV-01 | CWA-10 | CWP-10-CV-01 | IFC documents for Bund and tank foundations - LDO | 5 | 2027-07-08 | ALP-EPC-00UEG-CV-EFD-0001 | 2027-07-01 | 2027-06-03 | 20
EWP-10-EL-01 | CWA-10 | CWP-10-EL-01 | IFC documents for Electrical - LDO | 4 | 2027-10-12 | ALP-EPC-00UEG-EL-CBL-0001 | 2028-02-21 | 2028-01-24 | 92 | MR-EL-008 | 2027-05-06 | 187
EWP-10-IC-01 | CWA-10 | CWP-10-IC-01 | IFC documents for I&C - LDO | 4 | 2027-09-14 | ALP-EPC-00UEG-IC-ELY-0001 | 2028-03-20 | 2028-02-21 | 133 | MR-IC-004 | 2027-05-06 | 207
EWP-10-ME-01 | CWA-10 | CWP-10-ME-01 | IFC documents for LDO tanks and skids | 3 | 2027-05-07 | ALP-M16-00EGA-ME-GAD-0001 | 2027-11-01 | 2027-10-04 | 175 | MR-ME-017 | 2027-05-05 | 108
EWP-10-PI-01 | CWA-10 | CWP-10-PI-01 | IFC documents for Piping - LDO | 7 | 2028-01-24 | ALP-EPC-00EGC-PI-SUP-0001 | 2028-01-24 | 2027-12-27 | 30 | MR-PI-001 | 2027-02-25 | 217
EWP-11-CV-01 | CWA-11 | CWP-11-CV-01 | IFC documents for Foundations - control, administration, workshop | 13 | 2027-05-03 | ALP-EPC-00USA-HV-GAD-0001 | 2027-04-26 | 2027-03-29 | -1
EWP-11-EL-01 | CWA-11 | CWP-11-EL-01 | IFC documents for Electrical - buildings | 6 | 2027-09-03 | ALP-EPC-00UCA-EL-ELY-0002 | 2027-12-06 | 2027-11-08 | 62 | MR-EL-008 | 2027-05-06 | 132
EWP-11-HV-01 | CWA-11 | CWP-11-HV-01 | IFC documents for HVAC - buildings | 2 | 2027-08-04 | ALP-EPC-00UCA-PI-PPL-0001 | 2027-12-06 | 2027-11-08 | 82 | MR-HV-001 | 2027-03-25 | 162
EWP-11-IC-01 | CWA-11 | CWP-11-IC-01 | IFC documents for DCS, CCR, telecom, CCTV | 17 | 2027-10-07 | ALP-EPC-00UCA-IC-ELY-0001 | 2027-12-20 | 2027-11-22 | 76 | MR-IC-008 | 2027-07-29 | 82
EWP-11-SS-01 | CWA-11 | CWP-11-SS-01 | IFC documents for Control, administration and workshop buildings | 12 | 2027-06-18 | ALP-EPC-00USA-SS-STL-0002 | 2027-06-21 | 2027-05-24 | 35
EWP-12-CV-01 | CWA-12 | CWP-12-CV-01 | IFC documents for Mobilisation, temporary facilities, site preparation | 3 | 2027-02-22 | ALP-EPC-00UZB-CV-CVL-0001 | 2027-01-25 | 2027-01-18 | -13 | MR-CV-002 | 2027-01-07 | 7
EWP-12-CV-02 | CWA-12 | CWP-12-CV-02 | IFC documents for Roads, drainage and underground services | 10 | 2027-06-21 | ALP-EPC-00UZD-CV-FND-0001 | 2027-04-19 | 2027-03-22 | 16
EWP-12-EL-01 | CWA-12 | CWP-12-EL-01 | IFC documents for Earthing grid and site lighting | 8 | 2027-06-17 | ALP-EPC-00UZD-EL-ELY-0001 | 2027-06-14 | 2027-05-17 | 27 | MR-EL-009 | 2027-04-08 | 27
EWP-12-PI-01 | CWA-12 | CWP-12-PI-01 | IFC documents for Underground piping | 12 | 2027-10-18 | ALP-EPC-00UZA-IC-ELY-0001 | 2027-08-09 | 2027-07-12 | 4 | MR-EL-010 | 2027-06-22 | 74

## PWP (MR)
Alpilla 600 MW Combined Cycle Power Plant - Procurement work packages (material requisitions)
engine engineering_plan v1.6.0 ¦ generated 2026-09-29T03:49:44Z by EPCE ¦ data 73eaa92ce7c1ff26 ¦ dates computed from the workflow network and the CPM (working days)
MR | Title | Type | Supplier | Docs | MR issue | PO | Vendor data | On site (ROS) | Needed by CWP | Needed | Float wd | CWPs
MR-CV-001 | Piling works | subcontract |  | 10 | 2026-11-05 | 2027-01-14 | 2027-01-28 | 2027-02-11 | CWP-01-CV-01 | 2027-04-19 | 47 | CWP-01-CV-01 CWP-02-CV-01
MR-CV-002 | Civil and building works | subcontract |  | 10 | 2026-11-05 | 2026-12-24 | 2027-01-07 | 2027-01-07 | CWP-12-CV-01 | 2027-01-25 | 12 | CWP-12-CV-01 CWP-01-CV-02 CWP-02-CV-02 CWP-03-CV-01 CWP-05-CV-01
MR-CV-003 | Marine works | subcontract |  | 10 | 2026-11-05 | 2027-03-02 | 2027-04-13 | 2027-07-20 | CWP-06-CV-01 | 2027-10-01 | 53 | CWP-06-CV-01
MR-EL-001 | 380 kV GIS | equipment |  | 19 |  | 2026-12-15 | 2027-03-09 | 2028-01-25 | CWP-04-EL-01 | 2028-02-01 | 5 | CWP-04-EL-01
MR-EL-002 | Unit auxiliary transformers | equipment |  | 20 | 2026-11-05 | 2027-02-09 | 2027-04-20 | 2027-12-14 | CWP-01-EL-01 | 2028-02-07 | 39 | CWP-01-EL-01 CWP-02-EL-01
MR-EL-003 | MV switchgear 10.5 kV | equipment |  | 16 | 2026-11-05 | 2027-01-14 | 2027-03-11 | 2027-10-21 | CWP-03-EL-01 | 2027-11-22 | 22 | CWP-03-EL-01
MR-EL-004 | LV transformers | equipment |  | 16 | 2026-11-12 | 2027-02-19 | 2027-04-02 | 2027-09-03 | CWP-03-EL-01 | 2027-11-22 | 56 | CWP-03-EL-01
MR-EL-005 | LV switchboards and MCCs | equipment |  | 19 | 2026-11-05 | 2027-01-28 | 2027-03-25 | 2027-09-23 | CWP-03-EL-01 | 2027-11-22 | 42 | CWP-03-EL-01
MR-EL-006 | Emergency diesel generator | equipment |  | 20 | 2026-11-05 | 2027-01-14 | 2027-03-11 | 2027-10-21 | CWP-03-EL-01 | 2027-11-22 | 22 | CWP-03-EL-01
MR-EL-007 | UPS, batteries and DC systems | equipment |  | 18 | 2026-11-26 | 2027-03-02 | 2027-04-13 | 2027-09-14 | CWP-03-EL-01 | 2027-11-22 | 49 | CWP-03-EL-01
MR-EL-008 | Power and control cables | bulk |  | 6 | 2027-02-18 | 2027-04-08 | 2027-05-06 | 2027-09-09 | CWP-03-EL-01 | 2027-11-22 | 52 | CWP-01-EL-01 CWP-02-EL-01 CWP-03-EL-01 CWP-05-EL-01 CWP-07-EL-01 CWP-08-EL-01 CWP-09-EL-01 CWP-10-EL-01 CWP-11-EL-01 CWP-04-EL-01
MR-EL-009 | Cable trays, earthing and lighting materials | bulk |  | 6 | 2027-01-21 | 2027-03-11 | 2027-04-08 | 2027-07-15 | CWP-12-EL-01 | 2027-06-14 | -23 | CWP-12-EL-01 CWP-01-EL-01 CWP-02-EL-01
MR-EL-010 | Cathodic protection (marine structures, buried piping and tanks) | equipment |  | 13 | 2027-02-23 | 2027-04-27 | 2027-06-22 | 2027-09-07 | CWP-12-PI-01 | 2027-11-01 | 39 | CWP-06-CV-01 CWP-12-PI-01
MR-EL-011 | Construction power supply (RMU, temporary distribution) | equipment |  | 14 |  | 2026-11-16 | 2026-12-07 | 2027-01-18 | CWP-12-CV-01 | 2027-01-25 | 5 | CWP-12-CV-01
MR-EL-012 | Electrical and I&C installation (subcontract) | subcontract |  | 10 | 2027-04-19 | 2027-07-05 | 2027-08-02 | 2027-07-05 | CWP-03-EL-01 | 2027-11-22 | 100 | CWP-03-EL-01 CWP-01-EL-01 CWP-01-IC-01
MR-EL-101 | Generators, excitation, GCB and busducts (IEC) | iec_supply | IEC | 16 |  | 2026-11-02 | 2027-01-25 | 2027-11-08 | CWP-01-ME-01 | 2027-11-15 | 5 | CWP-01-ME-01 CWP-02-ME-01
MR-EL-102 | Generator step-up transformers (IEC) | iec_supply | IEC | 15 |  | 2026-11-02 | 2027-01-11 | 2027-11-29 | CWP-01-EL-01 | 2028-02-07 | 50 | CWP-01-EL-01 CWP-02-EL-01
MR-HV-001 | HVAC plant and equipment | equipment |  | 23 | 2026-11-05 | 2027-01-28 | 2027-03-25 | 2027-09-23 | CWP-03-HV-01 | 2027-11-08 | 32 | CWP-03-HV-01 CWP-11-HV-01 CWP-01-HV-01
MR-IC-001 | Plant DCS | equipment |  | 17 | 2026-11-05 | 2027-01-21 | 2027-04-01 | 2027-11-25 | CWP-11-IC-01 | 2027-12-20 | 17 | CWP-11-IC-01
MR-IC-002 | Continuous emission monitoring system | equipment |  | 18 | 2026-11-05 | 2027-03-15 | 2027-05-10 | 2027-11-08 | CWP-01-IC-01 | 2028-03-06 | 85 | CWP-01-IC-01
MR-IC-003 | Steam/water analysis system | equipment |  | 20 | 2026-11-05 | 2027-03-15 | 2027-05-10 | 2027-11-08 | CWP-01-IC-01 | 2028-03-06 | 85 | CWP-01-IC-01
MR-IC-004 | Field instruments | bulk |  | 54 | 2027-01-21 | 2027-03-25 | 2027-05-06 | 2027-10-21 | CWP-09-IC-01 | 2028-02-21 | 87 | CWP-01-IC-01 CWP-02-IC-01 CWP-05-IC-01 CWP-07-IC-01 CWP-08-IC-01 CWP-09-IC-01 CWP-10-IC-01
MR-IC-005 | Control valves | bulk |  | 32 | 2027-01-21 | 2027-03-25 | 2027-05-06 | 2027-11-18 | CWP-01-PI-01 | 2028-01-10 | 37 | CWP-01-PI-01 CWP-02-PI-01 CWP-08-PI-01
MR-IC-006 | Fire detection and alarm system | equipment |  | 28 | 2027-03-26 | 2027-05-28 | 2027-07-23 | 2027-10-29 | CWP-11-IC-01 | 2027-12-20 | 36 | CWP-11-IC-01
MR-IC-007 | Telecom, CCTV, access control and perimeter security | equipment |  | 17 | 2027-03-23 | 2027-05-25 | 2027-07-20 | 2027-10-26 | CWP-11-IC-01 | 2027-12-20 | 39 | CWP-11-IC-01
MR-IC-008 | BOP safety instrumented system (IEC 61511) | equipment |  | 18 | 2027-03-18 | 2027-05-20 | 2027-07-29 | 2027-12-02 | CWP-11-IC-01 | 2027-12-20 | 12 | CWP-11-IC-01
MR-IC-009 | Operator training simulator, historian and performance monitoring | equipment |  | 17 | 2027-03-18 | 2027-06-03 | 2027-08-26 | 2028-03-23 | CWP-11-IC-01 | 2028-04-10 | 12 | CWP-11-IC-01
MR-IC-010 | Instrument installation materials (tubing, fittings, junction boxes, supports) | bulk |  | 17 | 2027-04-26 | 2027-06-14 | 2027-07-12 | 2027-09-20 | CWP-01-IC-01 | 2028-03-06 | 120 | CWP-01-IC-01 CWP-02-IC-01 CWP-05-IC-01
MR-IC-101 | Turbine control system (IEC) | iec_supply | IEC | 19 |  | 2026-11-02 | 2027-01-25 | 2027-08-23 | CWP-01-IC-01 | 2028-03-06 | 140 | CWP-01-IC-01 CWP-02-IC-01
MR-ME-001 | Boiler feed pumps | equipment |  | 20 | 2026-11-05 | 2027-01-14 | 2027-03-11 | 2027-11-18 | CWP-08-ME-01 | 2027-11-29 | 7 | CWP-08-ME-01
MR-ME-002 | Condensate extraction pumps | equipment |  | 20 | 2026-11-05 | 2027-02-18 | 2027-04-15 | 2027-11-25 | CWP-02-ME-01 | 2028-01-17 | 37 | CWP-02-ME-01
MR-ME-003 | CW pumps | equipment |  | 20 | 2026-11-05 | 2027-01-14 | 2027-03-25 | 2027-12-30 | CWP-05-ME-01 | 2028-01-17 | 12 | CWP-05-ME-01
MR-ME-004 | Travelling band screens and trash rakes | equipment |  | 22 | 2026-11-05 | 2027-02-02 | 2027-03-30 | 2027-11-09 | CWP-05-ME-01 | 2028-01-17 | 49 | CWP-05-ME-01
MR-ME-005 | Electro-chlorination package | equipment |  | 25 | 2026-11-05 | 2027-02-03 | 2027-03-31 | 2027-11-10 | CWP-05-ME-01 | 2028-01-17 | 48 | CWP-05-ME-01
MR-ME-006 | Condenser tube cleaning system | equipment |  | 21 | 2026-11-05 | 2027-03-12 | 2027-05-07 | 2027-11-05 | CWP-02-PI-01 | 2028-02-28 | 81 | CWP-02-PI-01
MR-ME-007 | Closed cooling water heat exchangers, pumps, tank | equipment |  | 23 | 2026-11-05 | 2027-02-09 | 2027-04-06 | 2027-10-05 | CWP-08-ME-01 | 2027-11-29 | 39 | CWP-08-ME-01
MR-ME-008 | Air compressors and dryers | equipment |  | 23 | 2026-11-05 | 2027-02-15 | 2027-04-12 | 2027-10-11 | CWP-08-ME-01 | 2027-11-29 | 35 | CWP-08-ME-01
MR-ME-009 | Auxiliary boiler | equipment |  | 24 | 2026-11-05 | 2027-01-14 | 2027-03-25 | 2027-11-18 | CWP-08-ME-01 | 2027-11-29 | 7 | CWP-08-ME-01
MR-ME-010 | Nitrogen, hydrogen and CO2 supply | equipment |  | 21 | 2027-04-15 | 2027-06-03 | 2027-07-15 | 2027-11-04 | CWP-08-ME-01 | 2027-11-29 | 17 | CWP-08-ME-01
MR-ME-011 | Chemical dosing skid | equipment |  | 21 | 2027-04-16 | 2027-05-28 | 2027-07-09 | 2027-12-10 | CWP-08-ME-01 | 2027-11-29 | -9 | CWP-08-ME-01
MR-ME-012 | Water treatment package (SWRO, demin, condensate polishing) | equipment |  | 29 | 2026-11-05 | 2027-01-28 | 2027-04-08 | 2028-01-13 | CWP-07-ME-01 | 2028-01-24 | 7 | CWP-07-ME-01
MR-ME-013 | Shop-built tanks and demin forwarding pumps | equipment |  | 24 | 2026-11-05 | 2027-01-14 | 2027-02-25 | 2027-07-29 | CWP-08-ME-01 | 2027-11-29 | 87 | CWP-07-ME-01 CWP-08-ME-01
MR-ME-014 | Waste water and sanitary treatment packages | equipment |  | 28 | 2026-11-05 | 2027-01-28 | 2027-03-25 | 2027-09-23 | CWP-07-ME-01 | 2028-01-24 | 87 | CWP-07-ME-01
MR-ME-015 | Gas receiving and metering station | equipment |  | 23 | 2026-11-05 | 2027-01-14 | 2027-03-25 | 2027-11-18 | CWP-09-ME-01 | 2027-11-29 | 7 | CWP-09-ME-01
MR-ME-016 | LDO unloading and forwarding / treatment skids | equipment |  | 26 | 2026-11-05 | 2027-01-14 | 2027-03-11 | 2027-10-21 | CWP-10-ME-01 | 2027-11-01 | 7 | CWP-10-ME-01
MR-ME-017 | Field-erected storage tanks (API 650): LDO storage and fire water | subcontract |  | 12 | 2026-11-26 | 2027-03-24 | 2027-05-05 | 2027-06-30 | CWP-10-ME-01 | 2027-11-01 | 88 | CWP-08-ME-01 CWP-10-ME-01
MR-ME-018 | Aqueous ammonia storage and forwarding | equipment |  | 21 | 2026-11-05 | 2027-02-18 | 2027-04-15 | 2027-10-14 | CWP-08-ME-01 | 2027-11-29 | 32 | CWP-08-ME-01
MR-ME-019 | HRSG blowdown and drain tanks | equipment |  | 21 | 2026-11-05 | 2027-02-05 | 2027-03-19 | 2027-08-20 | CWP-01-ME-01 | 2027-11-15 | 61 | CWP-01-ME-01
MR-ME-020 | Fire pumps and fire protection systems | equipment |  | 22 | 2026-11-05 | 2027-01-28 | 2027-03-25 | 2027-10-07 | CWP-01-HV-01 | 2027-11-29 | 37 | CWP-08-ME-01 CWP-01-HV-01
MR-ME-021 | EOT cranes | equipment |  | 18 | 2026-11-05 | 2027-01-14 | 2027-03-11 | 2027-10-21 | CWP-01-ME-01 | 2027-11-15 | 17 | CWP-01-ME-01 CWP-02-ME-01
MR-ME-022 | Painting and insulation (subcontract) | subcontract |  | 10 | 2027-04-27 | 2027-06-29 | 2027-07-27 | 2027-06-29 | CWP-01-PI-01 | 2028-01-10 | 139 | CWP-01-PI-01 CWP-02-PI-01 CWP-08-PI-01
MR-ME-023 | Mechanical and piping erection (subcontract) | subcontract |  | 10 | 2027-06-30 | 2027-09-15 | 2027-10-13 | 2027-09-15 | CWP-01-ME-01 | 2027-11-15 | 43 | CWP-01-ME-01 CWP-02-ME-01 CWP-08-ME-01 CWP-01-PI-01
MR-ME-024 | Heavy transport, barge landing and marine logistics (subcontract) | subcontract |  | 10 | 2027-07-16 | 2027-09-17 | 2027-10-15 | 2027-09-17 | CWP-01-ME-01 | 2027-11-15 | 41 | CWP-01-ME-01 CWP-02-ME-01
MR-ME-101 | Gas turbine package incl. auxiliaries (IEC) | iec_supply | IEC | 19 |  | 2026-11-02 | 2027-01-25 | 2027-11-15 | CWP-01-ME-01 | 2027-11-15 | 0 | CWP-01-ME-01
MR-ME-102 | HRSG incl. SCR (IEC) | iec_supply | IEC | 17 |  | 2026-11-02 | 2027-01-25 | 2027-11-15 | CWP-01-ME-01 | 2027-11-15 | 0 | CWP-01-ME-01
MR-ME-103 | Steam turbine and condenser (IEC) | iec_supply | IEC | 18 |  | 2026-11-02 | 2027-02-08 | 2028-01-10 | CWP-02-ME-01 | 2028-01-17 | 5 | CWP-02-ME-01
MR-PI-001 | Piping bulk materials (carbon steel, stainless) | bulk |  | 6 | 2026-12-10 | 2027-01-28 | 2027-02-25 | 2027-07-15 | CWP-12-PI-01 | 2027-08-09 | 17 | CWP-12-PI-01 CWP-01-PI-01 CWP-02-PI-01 CWP-07-PI-01 CWP-08-PI-01 CWP-09-PI-01 CWP-10-PI-01
MR-PI-002 | Alloy piping P91 / P22 (main steam, reheat) | bulk |  | 6 | 2027-01-21 | 2027-03-25 | 2027-05-06 | 2028-02-10 | CWP-01-PI-01 | 2028-01-10 | -23 | CWP-01-PI-01 CWP-02-PI-01
MR-PI-003 | Valves (manual and check) | bulk |  | 6 | 2026-12-25 | 2027-03-08 | 2027-04-19 | 2027-10-04 | CWP-01-PI-01 | 2028-01-10 | 70 | CWP-01-PI-01 CWP-02-PI-01 CWP-08-PI-01
MR-PI-004 | GRP CW pipes and fittings | bulk |  | 7 | 2026-11-05 | 2027-01-13 | 2027-02-24 | 2027-09-08 | CWP-05-PI-01 | 2027-10-18 | 28 | CWP-05-PI-01
MR-PI-005 | Pipe supports, spring hangers and snubbers | bulk |  | 48 | 2027-03-30 | 2027-05-25 | 2027-07-06 | 2027-10-05 | CWP-01-PI-01 | 2028-01-10 | 69 | CWP-01-PI-01 CWP-02-PI-01 CWP-08-PI-01
MR-PI-006 | Piping specialty items (strainers, steam traps, expansion joints, sight glasses) | bulk |  | 6 | 2026-12-10 | 2027-04-05 | 2027-05-17 | 2027-08-16 | CWP-01-PI-01 | 2028-01-10 | 105 | CWP-01-PI-01 CWP-02-PI-01 CWP-08-PI-01
MR-PI-007 | Safety and relief valves | bulk |  | 30 | 2026-12-10 | 2027-04-01 | 2027-05-27 | 2027-09-09 | CWP-01-PI-01 | 2028-01-10 | 87 | CWP-01-PI-01 CWP-02-PI-01 CWP-08-PI-01
MR-SS-001 | Structural steel supply and fabrication | subcontract |  | 26 | 2026-11-12 | 2027-01-28 | 2027-02-25 | 2027-06-03 | CWP-08-SS-01 | 2027-07-27 | 38 | CWP-01-SS-01 CWP-02-SS-01 CWP-08-SS-01
MR-SS-002 | Stack 65 m with silencer | subcontract |  | 12 | 2026-11-12 | 2027-01-28 | 2027-03-25 | 2027-09-23 | CWP-01-ME-01 | 2027-11-15 | 37 | CWP-01-ME-01

## CWP
Alpilla 600 MW Combined Cycle Power Plant - Construction work packages (CPM dates)
engine engineering_plan v1.6.0 ¦ generated 2026-09-29T03:49:44Z by EPCE ¦ data 73eaa92ce7c1ff26 ¦ dates computed from the workflow network and the CPM (working days)
CWP | CWA | Discipline | Title | Contractor | Start | Finish | Total float wd | EWP | PWP (MR)
CWP-01-CV-01 | CWA-01 | civil | Piling - power block GT/HRSG | Piling contractor | 2027-04-19 | 2027-07-09 | 40 | EWP-01-CV-01 | MR-CV-001
CWP-01-CV-02 | CWA-01 | civil | Foundations - power block GT/HRSG | Civil contractor | 2027-05-17 | 2027-11-12 | 40 | EWP-01-CV-02 | MR-CV-002
CWP-01-EL-01 | CWA-01 | electrical | Electrical - power block GT/HRSG | Electrical contractor | 2028-02-07 | 2028-08-04 | 237 | EWP-01-EL-01 | MR-EL-002, MR-EL-008, MR-EL-009, MR-EL-012, MR-EL-102
CWP-01-HV-01 | CWA-01 | hvac | HVAC and fire protection - GT hall | HVAC contractor | 2027-11-29 | 2028-03-17 | 337 | EWP-01-HV-01 | MR-HV-001, MR-ME-020
CWP-01-IC-01 | CWA-01 | i_and_c | I&C - power block GT/HRSG | I&C contractor | 2028-03-06 | 2028-08-18 | 10 | EWP-01-IC-01 | MR-EL-012, MR-IC-002, MR-IC-003, MR-IC-004, MR-IC-010, MR-IC-101
CWP-01-ME-01 | CWA-01 | mechanical | GT, generator and HRSG erection | Mechanical contractor | 2027-11-15 | 2028-07-07 | 10 | EWP-01-ME-01 | MR-EL-101, MR-ME-019, MR-ME-021, MR-ME-023, MR-ME-024, MR-ME-101, MR-ME-102, MR-SS-002
CWP-01-PI-01 | CWA-01 | piping | Piping - power block GT/HRSG | Mechanical contractor | 2028-01-10 | 2028-08-04 | 10 | EWP-01-PI-01 | MR-IC-005, MR-ME-022, MR-ME-023, MR-PI-001, MR-PI-002, MR-PI-003, MR-PI-005, MR-PI-006, MR-PI-007
CWP-01-SS-01 | CWA-01 | structural | GT hall steel, cladding, crane, pipe racks | Steel contractor | 2027-08-09 | 2028-01-07 | 40 | EWP-01-SS-01 | MR-SS-001
CWP-02-CV-01 | CWA-02 | civil | Piling - ST hall and condenser | Piling contractor | 2027-04-19 | 2027-06-25 | 66 | EWP-02-CV-01 | MR-CV-001
CWP-02-CV-02 | CWA-02 | civil | Foundations - ST hall and condenser | Civil contractor | 2027-05-17 | 2027-11-26 | 66 | EWP-02-CV-02 | MR-CV-002
CWP-02-EL-01 | CWA-02 | electrical | Electrical - ST island | Electrical contractor | 2028-03-27 | 2028-08-25 | 222 | EWP-02-EL-01 | MR-EL-002, MR-EL-008, MR-EL-009, MR-EL-102
CWP-02-IC-01 | CWA-02 | i_and_c | I&C - ST island | I&C contractor | 2028-04-24 | 2028-09-22 | 31 | EWP-02-IC-01 | MR-IC-004, MR-IC-010, MR-IC-101
CWP-02-ME-01 | CWA-02 | mechanical | Condenser, ST and generator erection | Mechanical contractor | 2028-01-17 | 2028-08-11 | 31 | EWP-02-ME-01 | MR-EL-101, MR-ME-002, MR-ME-021, MR-ME-023, MR-ME-024, MR-ME-103
CWP-02-PI-01 | CWA-02 | piping | Piping - ST island | Mechanical contractor | 2028-02-28 | 2028-09-22 | 31 | EWP-02-PI-01 | MR-IC-005, MR-ME-006, MR-ME-022, MR-PI-001, MR-PI-002, MR-PI-003, MR-PI-005, MR-PI-006, MR-PI-007
CWP-02-SS-01 | CWA-02 | structural | ST hall steel, cladding, crane | Steel contractor | 2027-08-09 | 2028-01-07 | 86 | EWP-02-SS-01 | MR-SS-001
CWP-03-CV-01 | CWA-03 | civil | Foundations - electrical building | Civil contractor | 2027-04-26 | 2027-07-30 | 82 | EWP-03-CV-01 | MR-CV-002
CWP-03-EL-01 | CWA-03 | electrical | MV/LV switchgear, UPS, DC, emergency diesel | Electrical contractor | 2027-11-22 | 2028-03-24 | 82 | EWP-03-EL-01 | MR-EL-003, MR-EL-004, MR-EL-005, MR-EL-006, MR-EL-007, MR-EL-008, MR-EL-012
CWP-03-HV-01 | CWA-03 | hvac | HVAC plant and electrical building HVAC | HVAC contractor | 2027-11-08 | 2028-02-11 | 362 | EWP-03-HV-01 | MR-HV-001
CWP-03-SS-01 | CWA-03 | structural | Electrical building | Building contractor | 2027-06-21 | 2028-01-14 | 82 | EWP-03-SS-01
CWP-04-CV-01 | CWA-04 | civil | Foundations - GIS building and gantry | Civil contractor | 2027-05-03 | 2027-07-23 | 97 | EWP-04-CV-01
CWP-04-EL-01 | CWA-04 | electrical | GIS erection, HV connections, testing | GIS supplier / electrical contractor | 2028-02-01 | 2028-06-19 | 21 | EWP-04-EL-01 | MR-EL-001, MR-EL-008
CWP-04-SS-01 | CWA-04 | structural | GIS building | Building contractor | 2027-06-28 | 2027-11-12 | 97 | EWP-04-SS-01
CWP-05-CV-01 | CWA-05 | civil | CW pump house and onshore culverts | Civil contractor | 2027-04-22 | 2027-11-17 | 127 | EWP-05-CV-01 | MR-CV-002
CWP-05-EL-01 | CWA-05 | electrical | Electrical - CW pump house | Electrical contractor | 2028-02-28 | 2028-06-02 | 55 | EWP-05-EL-01 | MR-EL-008
CWP-05-IC-01 | CWA-05 | i_and_c | I&C - CW pump house | I&C contractor | 2028-03-27 | 2028-06-16 | 55 | EWP-05-IC-01 | MR-IC-004, MR-IC-010
CWP-05-ME-01 | CWA-05 | mechanical | CW pumps, screens, electro-chlorination | Mechanical contractor | 2028-01-17 | 2028-05-05 | 55 | EWP-05-ME-01 | MR-ME-003, MR-ME-004, MR-ME-005
CWP-05-PI-01 | CWA-05 | piping | CW GRP piping onshore | Mechanical contractor | 2027-10-18 | 2028-03-31 | 327 | EWP-05-PI-01 | MR-PI-004
CWP-06-CV-01 | CWA-06 | civil | Marine works | Marine contractor | 2027-10-01 | 2028-03-30 | 21 | EWP-06-CV-01 | MR-CV-003, MR-EL-010
CWP-07-CV-01 | CWA-07 | civil | Demolition and foundations - water treatment | Civil contractor | 2027-05-03 | 2027-10-01 | 110 | EWP-07-CV-01
CWP-07-EL-01 | CWA-07 | electrical | Electrical - water treatment | Electrical contractor | 2028-03-20 | 2028-07-07 | 30 | EWP-07-EL-01 | MR-EL-008
CWP-07-IC-01 | CWA-07 | i_and_c | I&C - water treatment | I&C contractor | 2028-04-17 | 2028-07-21 | 30 | EWP-07-IC-01 | MR-IC-004
CWP-07-ME-01 | CWA-07 | mechanical | Water treatment packages and tanks | Mechanical contractor | 2028-01-24 | 2028-06-09 | 30 | EWP-07-ME-01 | MR-ME-012, MR-ME-013, MR-ME-014
CWP-07-PI-01 | CWA-07 | piping | Piping - water treatment | Mechanical contractor | 2028-02-21 | 2028-07-07 | 257 | EWP-07-PI-01 | MR-PI-001
CWP-07-SS-01 | CWA-07 | structural | Water treatment building | Building contractor | 2027-07-12 | 2027-11-26 | 110 | EWP-07-SS-01
CWP-08-CV-01 | CWA-08 | civil | Foundations - BOP utilities | Civil contractor | 2027-06-01 | 2027-10-18 | 59 | EWP-08-CV-01
CWP-08-EL-01 | CWA-08 | electrical | Electrical - BOP utilities | Electrical contractor | 2028-02-07 | 2028-06-23 | 30 | EWP-08-EL-01 | MR-EL-008
CWP-08-IC-01 | CWA-08 | i_and_c | I&C - BOP utilities | I&C contractor | 2028-03-20 | 2028-07-21 | 30 | EWP-08-IC-01 | MR-IC-004
CWP-08-ME-01 | CWA-08 | mechanical | BOP utilities equipment | Mechanical contractor | 2027-11-29 | 2028-05-12 | 30 | EWP-08-ME-01 | MR-ME-001, MR-ME-007, MR-ME-008, MR-ME-009, MR-ME-010, MR-ME-011, MR-ME-013, MR-ME-017, MR-ME-018, MR-ME-020, MR-ME-023
CWP-08-PI-01 | CWA-08 | piping | Piping - BOP utilities | Mechanical contractor | 2028-01-10 | 2028-06-23 | 267 | EWP-08-PI-01 | MR-IC-005, MR-ME-022, MR-PI-001, MR-PI-003, MR-PI-005, MR-PI-006, MR-PI-007
CWP-08-SS-01 | CWA-08 | structural | Utility building and pipe racks | Steel contractor | 2027-07-27 | 2027-12-13 | 59 | EWP-08-SS-01 | MR-SS-001
CWP-09-CV-01 | CWA-09 | civil | Foundations - gas station | Civil contractor | 2027-09-01 | 2027-11-23 | 113 | EWP-09-CV-01
CWP-09-EL-01 | CWA-09 | electrical | Electrical - gas station | Electrical contractor | 2028-01-24 | 2028-03-31 | 90 | EWP-09-EL-01 | MR-EL-008
CWP-09-IC-01 | CWA-09 | i_and_c | I&C - gas station | I&C contractor | 2028-02-21 | 2028-04-28 | 90 | EWP-09-IC-01 | MR-IC-004
CWP-09-ME-01 | CWA-09 | mechanical | Gas station equipment | Mechanical contractor | 2027-11-29 | 2028-02-18 | 90 | EWP-09-ME-01 | MR-ME-015
CWP-09-PI-01 | CWA-09 | piping | Piping - gas station and gas line to the GT | Mechanical contractor | 2027-12-27 | 2028-04-14 | 317 | EWP-09-PI-01 | MR-PI-001
CWP-10-CV-01 | CWA-10 | civil | Bund and tank foundations - LDO | Civil contractor | 2027-07-01 | 2027-11-03 | 153 | EWP-10-CV-01
CWP-10-EL-01 | CWA-10 | electrical | Electrical - LDO | Electrical contractor | 2028-02-21 | 2028-05-12 | 126 | EWP-10-EL-01 | MR-EL-008
CWP-10-IC-01 | CWA-10 | i_and_c | I&C - LDO | I&C contractor | 2028-03-20 | 2028-06-09 | 126 | EWP-10-IC-01 | MR-IC-004
CWP-10-ME-01 | CWA-10 | mechanical | LDO tanks and skids | Tank contractor | 2027-11-01 | 2028-05-12 | 126 | EWP-10-ME-01 | MR-ME-016, MR-ME-017
CWP-10-PI-01 | CWA-10 | piping | Piping - LDO | Mechanical contractor | 2028-01-24 | 2028-06-09 | 277 | EWP-10-PI-01 | MR-PI-001
CWP-11-CV-01 | CWA-11 | civil | Foundations - control, administration, workshop | Civil contractor | 2027-04-26 | 2027-08-13 | 85 | EWP-11-CV-01
CWP-11-EL-01 | CWA-11 | electrical | Electrical - buildings | Electrical contractor | 2027-12-06 | 2028-03-24 | 332 | EWP-11-EL-01 | MR-EL-008
CWP-11-HV-01 | CWA-11 | hvac | HVAC - buildings | HVAC contractor | 2027-12-06 | 2028-03-10 | 342 | EWP-11-HV-01 | MR-HV-001
CWP-11-IC-01 | CWA-11 | i_and_c | DCS, CCR, telecom, CCTV | DCS supplier / I&C contractor | 2027-12-20 | 2028-05-05 | 85 | EWP-11-IC-01 | MR-IC-001, MR-IC-006, MR-IC-007, MR-IC-008, MR-IC-009
CWP-11-SS-01 | CWA-11 | structural | Control, administration and workshop buildings | Building contractor | 2027-06-21 | 2028-02-25 | 85 | EWP-11-SS-01
CWP-12-CV-01 | CWA-12 | civil | Mobilisation, temporary facilities, site preparation | Civil contractor | 2027-01-25 | 2027-04-16 | 40 | EWP-12-CV-01 | MR-CV-002, MR-EL-011
CWP-12-CV-02 | CWA-12 | civil | Roads, drainage and underground services | Civil contractor | 2027-04-19 | 2028-06-09 | 277 | EWP-12-CV-02
CWP-12-EL-01 | CWA-12 | electrical | Earthing grid and site lighting | Electrical contractor | 2027-06-14 | 2028-05-26 | 287 | EWP-12-EL-01 | MR-EL-009
CWP-12-PI-01 | CWA-12 | piping | Underground piping | Mechanical contractor | 2027-08-09 | 2028-05-12 | 297 | EWP-12-PI-01 | MR-EL-010, MR-PI-001

## CWA
Alpilla 600 MW Combined Cycle Power Plant - Construction work areas (path of construction)
engine engineering_plan v1.6.0 ¦ generated 2026-09-29T03:49:44Z by EPCE ¦ data 73eaa92ce7c1ff26 ¦ dates computed from the workflow network and the CPM (working days)
CWA | Title | Path | Extent (plant grid m) | Structures | Description | CWPs
CWA-01 | Power block - GT and HRSG | 2 | E 85-245, N 125-215 | 10UMA 10UHA 10UHN 00UBF | GT hall, GT, generator, filter house, HRSG, stack, GT GSU bay, ammonia injection | CWP-01-CV-01, CWP-01-CV-02, CWP-01-EL-01, CWP-01-HV-01, CWP-01-IC-01, CWP-01-ME-01, CWP-01-PI-01, CWP-01-SS-01
CWA-02 | Power block - ST and condenser | 3 | E 80-175, N 55-125 | 20UMB 00UBF | ST hall, ST, generator, condenser, CEPs, ST GSU bay | CWP-02-CV-01, CWP-02-CV-02, CWP-02-EL-01, CWP-02-IC-01, CWP-02-ME-01, CWP-02-PI-01, CWP-02-SS-01
CWA-03 | Electrical building and emergency power | 4 | E 20-75, N 100-240 | 00UBA | MV/LV switchgear, UPS/DC, emergency diesel, HVAC plant rooms | CWP-03-CV-01, CWP-03-EL-01, CWP-03-HV-01, CWP-03-SS-01
CWA-04 | 380 kV GIS switchyard | 5 | E 20-80, N 240-295 | 00UAC | GIS building, line gantry (TP-E1) | CWP-04-CV-01, CWP-04-EL-01, CWP-04-SS-01
CWA-05 | CW pump house and onshore CW | 2 | E 120-180, N 0-55 | 00UPC | CW pump house, screens, electro-chlorination, onshore CW culverts and GRP pipes | CWP-05-CV-01, CWP-05-EL-01, CWP-05-IC-01, CWP-05-ME-01, CWP-05-PI-01
CWA-06 | Marine works (offshore) | 3 | E 100-300, N -720-0 | 00UPA | Intake head, intake and outfall pipelines, outfall diffuser; works window 1 October - 30 April | CWP-06-CV-01
CWA-07 | Water treatment and effluents | 4 | E 290-395, N 12-110 | 00UGA | Demolition of the old foundations, SWRO, demineralisation, condensate polishing, tanks, WWT, sanitary | CWP-07-CV-01, CWP-07-EL-01, CWP-07-IC-01, CWP-07-ME-01, CWP-07-PI-01, CWP-07-SS-01
CWA-08 | BOP utilities | 4 | E 180-290, N 55-125 | 00UQA | BFPs, CCW, compressed air, auxiliary boiler, N2, chemical dosing, ammonia storage, fire pumps | CWP-08-CV-01, CWP-08-EL-01, CWP-08-IC-01, CWP-08-ME-01, CWP-08-PI-01, CWP-08-SS-01
CWA-09 | Fuel gas station | 5 | E 300-395, N 220-295 | 00UEK | Gas receiving, filtration, fiscal metering (TP-G1) | CWP-09-CV-01, CWP-09-EL-01, CWP-09-IC-01, CWP-09-ME-01, CWP-09-PI-01
CWA-10 | LDO tank farm and unloading | 5 | E 215-300, N 220-295 | 00UEG | 4 unloading bays, 2 x 3,500 m3 tanks in bund, forwarding and treatment | CWP-10-CV-01, CWP-10-EL-01, CWP-10-IC-01, CWP-10-ME-01, CWP-10-PI-01
CWA-11 | Control, administration and workshop buildings | 4 | E 80-210, N 215-295 | 00UCA 00UYA 00USA | Control building with CCR and DCS rooms, administration, workshop and warehouse | CWP-11-CV-01, CWP-11-EL-01, CWP-11-HV-01, CWP-11-IC-01, CWP-11-SS-01
CWA-12 | Site-wide infrastructure | 1 | E 0-400, N 0-300 | 00UZA 00UZB 00UZC | Mobilisation, temporary facilities, roads, drainage, fencing, underground services, earthing grid, site lighting | CWP-12-CV-01, CWP-12-CV-02, CWP-12-EL-01, CWP-12-PI-01

## Coverage systems
Alpilla 600 MW Combined Cycle Power Plant - Coverage: documents per KKS system
engine engineering_plan v1.6.0 ¦ generated 2026-09-29T03:49:44Z by EPCE ¦ data 73eaa92ce7c1ff26 ¦ dates computed from the workflow network and the CPM (working days)
System | Title | Category | Scope | Docs | Types | Missing required
00ACA | 380 kV GIS switchyard | electrical_hv | IEPC | 25 | CAL 2, CMP 1, DSH 4, GAD 1, IOL 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PRC 1, RPT 1, SLD 1, SPC 1, TRP 1, TST 1, WIR 1
00BBA | MV switchgear 10.5 kV | electrical_mv_lv | IEPC | 21 | CAL 1, CMP 1, DSH 2, GAD 1, IOL 1, ITP 2, LST 1, MDB 2, MRQ 1, OMM 2, PRC 1, RPT 1, SLD 1, SPC 1, TRP 1, TST 1, WIR 1
00BFA | LV switchgear 0.4 kV | electrical_mv_lv | IEPC | 34 | CAL 1, CMP 1, DSH 2, GAD 1, IOL 1, ITP 2, LST 1, MDB 2, MRQ 1, OMM 2, PRC 1, RPT 1, SLD 1, SPC 1, TRP 1, TST 1, WIR 14
00BFT | LV transformers | electrical_mv_lv | IEPC | 20 | CAL 1, CMP 1, DSH 2, GAD 1, IOL 1, ITP 2, LST 1, MDB 2, MRQ 1, OMM 2, PRC 1, RPT 1, SLD 1, SPC 1, TRP 1, TST 1
00BLA | Lighting and small power | electrical_mv_lv | IEPC | 9 | CMP 1, DSH 1, ITP 1, LOG 1, MDB 2, OMM 1, RPT 1, SLD 1
00BMA | Emergency LV switchgear | electrical_mv_lv | IEPC | 6 | CMP 1, DSH 1, LOG 1, MDB 1, OMM 1, SLD 1
00BRA | UPS | electrical_mv_lv | IEPC | 23 | CAL 1, CMP 1, DSH 3, GAD 1, IOL 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PRC 1, RPT 1, SLD 1, SPC 1, TRP 1, TST 1, WIR 1
00BTA | Batteries and DC 220 V | electrical_mv_lv | IEPC | 6 | CMP 1, DSH 1, LOG 1, MDB 1, OMM 1, SLD 1
00BXA | Earthing and lightning protection | common | IEPC | 16 | CMP 1, IOL 1, ITP 2, LST 1, MDB 2, MRQ 1, OMM 1, PRC 1, RPT 1, SPC 1, STU 2, TRP 1, TST 1
00CJA | Plant DCS | i_and_c | IEPC | 22 | BLK 1, CAL 1, CMP 1, DSH 2, GAD 1, IOL 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PRC 1, RPT 1, SPC 1, TRP 1, TST 1, WIR 1
00CJG | Safety instrumented systems (BOP) | i_and_c | IEPC | 22 | BLK 1, CAL 1, CMP 1, DSH 2, GAD 1, IOL 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PRC 1, RPT 1, SPC 1, TRP 1, TST 1, WIR 1
00CKA | Historian, performance monitoring and operator training simulator | i_and_c | IEPC | 22 | BLK 1, CAL 1, CMP 1, DSH 2, GAD 1, IOL 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PRC 1, RPT 1, SPC 1, TRP 1, TST 1, WIR 1
00CQA | Continuous emission monitoring | i_and_c | IEPC | 25 | BLK 1, CAL 1, CMP 1, DSH 4, GAD 1, IOL 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PRC 1, RPT 1, SPC 1, TRP 2, TST 1, WIR 1
00CYA | Telecom, CCTV, access control, security | i_and_c | IEPC | 22 | BLK 1, CAL 1, CMP 1, DSH 2, GAD 1, IOL 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PRC 1, RPT 1, SPC 1, TRP 1, TST 1, WIR 1
00EGA | LDO unloading | fuel_gas | IEPC | 38 | CAL 3, CEM 1, CMP 1, CNR 1, DSH 9, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, SUP 1, TRP 1, TST 1, WIR 1
00EGB | LDO storage | fuel_gas | IEPC | 25 | CAL 1, CEM 1, CMP 1, CNR 1, DSH 3, HMI 1, ISO 1, ITP 1, LOG 1, MDB 1, MOS 6, MRQ 1, OMM 1, PID 1, RPT 1, SDS 1, SPC 1, SUP 1
00EGC | LDO forwarding and treatment | fuel_gas | IEPC | 19 | CAL 1, CEM 1, CMP 1, CNR 1, DSH 6, HMI 1, ISO 1, LOG 1, MDB 1, OMM 1, PID 1, SDS 1, STR 1, SUP 1
00EKA | Gas receiving, filtration and fiscal metering station | fuel_gas | IEPC | 39 | CAL 3, CEM 1, CMP 1, CNR 1, DSH 9, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, STR 1, SUP 1, TRP 1, TST 1, WIR 1
00EKC | Fuel gas distribution to GT and auxiliary boiler | fuel_gas | IEPC | 16 | CAL 1, CEM 1, CMP 1, CNR 1, DSH 3, HMI 1, ISO 1, LOG 1, MDB 1, OMM 1, PID 1, SDS 1, STR 1, SUP 1
00GBA | Seawater reverse osmosis | water_treatment | IEPC | 34 | CAL 3, CMP 1, CNR 1, DSH 9, GAD 1, HMI 1, IOL 1, ISO 1, ITP 1, LOG 1, LST 1, MDB 2, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SUP 1, TRP 1, TST 1, WIR 1
00GCA | Demineralisation | water_treatment | IEPC | 16 | CAL 1, CMP 1, CNR 1, DSH 6, HMI 1, ISO 1, MDB 1, OMM 1, PID 1, SDS 1, SUP 1
00GHA | Demineralised water storage and distribution | water_treatment | IEPC | 35 | CAL 3, CMP 1, CNR 1, DSH 7, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, SUP 1, TRP 1, TST 1, WIR 1
00GKA | Potable water | water_treatment | IEPC | 16 | CAL 1, CMP 1, CNR 1, DSH 4, HMI 1, ISO 1, LOG 1, MDB 1, OMM 1, PID 1, PPL 1, SDS 1, SUP 1
00GMA | Process drains and waste water collection | water_treatment | IEPC | 16 | CAL 1, CMP 1, CNR 1, DSH 4, HMI 1, ISO 1, LOG 1, MDB 1, OMM 1, PID 1, PPL 1, SDS 1, SUP 1
00GNA | Waste water treatment | water_treatment | IEPC | 35 | CAL 3, CMP 1, CNR 1, DSH 7, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, SUP 1, TRP 1, TST 1, WIR 1
00GQA | Storm water drainage | civil_structural | IEPC | 2 | CVL 1, MDB 1
00GUA | Sanitary waste water treatment | water_treatment | IEPC | 13 | CAL 1, CMP 1, CNR 1, DSH 3, HMI 1, ISO 1, MDB 1, OMM 1, PID 1, SDS 1, SUP 1
00LBG | Auxiliary steam | water_steam_cycle | IEPC | 16 | CAL 1, CEM 1, CMP 1, CNR 1, DSH 3, HMI 1, ISO 1, LOG 1, MDB 1, OMM 1, PID 1, SDS 1, STR 1, SUP 1
00LDA | Condensate polishing | water_treatment | IEPC | 18 | CAL 1, CMP 1, CNR 1, DSH 5, HMI 1, ISO 1, ITP 1, MDB 1, MRQ 1, OMM 1, PID 1, SDS 1, SPC 1, SUP 1
00PAA | CW intake, screens and outfall | cooling | IEPC | 35 | CAL 3, CMP 1, CNR 1, DSH 6, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, STU 1, SUP 1, TRP 1, TST 1, WIR 1
00PAB | CW piping | cooling | IEPC | 20 | CAL 1, CMP 1, CNR 1, DSH 3, HMI 1, ISO 1, ITP 1, LOG 1, MDB 2, OMM 1, PID 1, PPL 1, RPT 1, SDS 1, STR 1, STU 1, SUP 1
00PAC | CW pumps | cooling | IEPC | 32 | CAL 3, CMP 1, CNR 1, DSH 4, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, SUP 1, TRP 1, TST 1, WIR 1
00PAH | Condenser tube cleaning | cooling | IEPC | 33 | CAL 2, CMP 1, CNR 1, DSH 6, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, SUP 1, TRP 1, TST 1, WIR 1
00PBA | Electro-chlorination | cooling | IEPC | 37 | CAL 3, CMP 1, CNR 1, DSH 9, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, SUP 1, TRP 1, TST 1, WIR 1
00PGA | Closed cooling water | cooling | IEPC | 38 | CAL 3, CMP 1, CNR 1, DSH 9, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, STR 1, SUP 1, TRP 1, TST 1, WIR 1
00QCA | Chemical dosing | auxiliary_mechanical | IEPC | 35 | CAL 2, CEM 1, CMP 1, CNR 1, DSH 7, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, SUP 1, TRP 1, TST 1, WIR 1
00QEA | Compressed air | auxiliary_mechanical | IEPC | 37 | CAL 3, CEM 1, CMP 1, CNR 1, DSH 8, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, SUP 1, TRP 1, TST 1, WIR 1
00QHA | Auxiliary boiler | auxiliary_mechanical | IEPC | 39 | CAL 3, CEM 1, CMP 1, CNR 1, DSH 9, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, STR 1, SUP 1, TRP 1, TST 1, WIR 1
00QJA | Nitrogen supply | auxiliary_mechanical | IEPC | 35 | CAL 2, CEM 1, CMP 1, CNR 1, DSH 7, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, SUP 1, TRP 1, TST 1, WIR 1
00QJB | Hydrogen and CO2 supply | auxiliary_mechanical | IEPC | 16 | CAL 1, CEM 1, CMP 1, CNR 1, DSH 4, HMI 1, ISO 1, LOG 1, MDB 1, OMM 1, PID 1, SDS 1, SUP 1
00QUA | Sampling and SWAS | auxiliary_mechanical | IEPC | 33 | CAL 2, CEM 1, CMP 1, CNR 1, DSH 5, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, SUP 1, TRP 1, TST 1, WIR 1
00SAA | HVAC | hvac | IEPC | 38 | CAL 2, CMP 1, CNR 1, DSH 9, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 2, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, SUP 1, TRP 1, TST 1, WIR 2
00SGA | Fire water system | fire_protection | IEPC | 38 | CAL 4, CEM 1, CMP 1, CNR 1, DSH 6, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PPL 1, PRC 1, RPT 1, SDS 1, SPC 1, STR 1, SUP 1, TRP 1, TST 1, WIR 1
00SGC | Deluge, spray and foam systems | fire_protection | IEPC | 15 | CAL 1, CEM 1, CMP 1, CNR 1, DSH 3, HMI 1, ISO 1, LOG 1, MDB 1, OMM 1, PID 1, SDS 1, SUP 1
00SGY | Fire detection and alarm | i_and_c | IEPC | 22 | BLK 1, CAL 1, CMP 1, DSH 2, GAD 1, IOL 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PRC 1, RPT 1, SPC 1, TRP 1, TST 1, WIR 1
00SMA | Cranes and hoists | other | IEPC | 21 | CAL 2, CMP 1, DSH 2, GAD 1, IOL 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 1, PRC 1, RPT 1, SPC 1, TRP 1, TST 1, WIR 1
00UAC | GIS building | civil_structural | IEPC | 20 | ARC 1, CAL 1, CBL 1, EFD 1, ELY 5, FND 1, GAD 2, HUP 1, LAY 1, LOP 2, RBR 1, STL 3
00UBA | Electrical building | civil_structural | IEPC | 22 | ARC 1, CAL 1, CBL 1, EFD 1, ELY 5, FND 1, GAD 3, HUP 1, LAY 1, LOP 2, PPL 1, RBR 1, STL 3
00UBF | Transformer bays | civil_structural | IEPC | 8 | CAL 1, EFD 1, ELY 1, FND 2, RBR 1, STL 2
00UCA | Control building | civil_structural | IEPC | 21 | ARC 1, CAL 1, CBL 1, ELY 5, FND 1, GAD 3, HUP 1, LAY 1, LOP 2, PPL 1, RBR 1, STL 3
00UEG | LDO tank farm structures | civil_structural | IEPC | 16 | CAL 1, CBL 1, EFD 1, ELY 4, FND 1, HUP 1, LAY 1, LOP 2, PPL 1, RBR 1, STL 2
00UEK | Gas station structures | civil_structural | IEPC | 20 | ARC 1, CAL 1, CBL 1, EFD 1, ELY 5, FND 1, GAD 2, HUP 1, LAY 1, LOP 2, PPL 1, RBR 1, STL 2
00UGA | Water treatment building and basins | civil_structural | IEPC | 21 | ARC 1, CAL 1, CBL 1, EFD 1, ELY 5, FND 1, GAD 2, HUP 1, LAY 1, LOP 2, PPL 1, RBR 1, STL 3
00UPA | CW intake and outfall marine structures | civil_structural | IEPC | 17 | CAL 2, CVL 1, ELY 2, ITP 1, LAY 1, MOS 7, RBR 1, RPT 2
00UPC | CW pump house | civil_structural | IEPC | 21 | ARC 1, CAL 1, CBL 1, EFD 1, ELY 5, FND 2, GAD 2, HUP 1, LAY 1, LOP 2, PPL 1, RBR 1, STL 2
00UQA | Utility building | civil_structural | IEPC | 23 | ARC 1, CAL 1, CBL 1, EFD 1, ELY 5, FND 1, GAD 2, HUP 1, LAY 1, LOP 3, PPL 3, RBR 1, STL 2
00USA | Workshop and warehouse | civil_structural | IEPC | 11 | ARC 1, CAL 1, ELY 2, FND 1, GAD 2, RBR 1, STL 3
00UYA | Administration building | civil_structural | IEPC | 11 | ARC 1, CAL 1, ELY 2, FND 1, GAD 2, RBR 1, STL 3
00UZA | Roads and paving | civil_structural | IEPC | 13 | CAL 1, CBL 1, CVL 2, ELY 4, HUP 1, LAY 1, LOP 2, PPL 1
00UZB | Fencing and gates | civil_structural | IEPC | 3 | CAL 1, CVL 1, ELY 1
00UZC | Site drainage and culverts | civil_structural | IEPC | 4 | CAL 1, CVL 1, ELY 1, RBR 1
00UZD | Pipe racks and pipe sleepers | civil_structural | IEPC | 7 | CAL 1, ELY 1, FND 1, RBR 1, STL 3
00UZE | Cable trenches and duct banks | civil_structural | IEPC | 4 | CAL 1, CVL 1, ELY 1, RBR 1
00UZF | Temporary barge landing | civil_structural | IEPC | 18 | CAL 1, ELY 1, FND 2, ITP 1, MOS 6, MRQ 1, RBR 1, RPT 2, SPC 1, STL 2
00XJA | Emergency diesel generator | electrical_mv_lv | IEPC | 26 | CAL 2, CMP 1, DSH 5, GAD 1, IOL 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PRC 1, RPT 1, SLD 1, SPC 1, TRP 1, TST 1, WIR 1
10BAA | GT generator busduct | electrical_hv | IEC | 3 | DSH 1, MDB 1, SLD 1
10BAC | GT generator circuit breaker | electrical_hv | IEC | 3 | DSH 1, MDB 1, SLD 1
10BAT | GT generator step-up transformer | electrical_hv | IEC | 16 | CAL 2, CMP 1, DSH 2, GAD 1, IOL 1, ITP 1, LST 1, MDB 2, OMM 1, PRC 1, TRP 1, TST 1, WIR 1
10BBT | GT unit auxiliary transformer | electrical_mv_lv | IEPC | 25 | CAL 2, CMP 1, DSH 4, GAD 1, IOL 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PRC 1, RPT 1, SLD 1, SPC 1, TRP 1, TST 1, WIR 1
10HAA | HRSG pressure system | hrsg | IEC | 23 | CAL 2, CMP 1, DSH 3, GAD 1, HMB 1, IOL 1, ITP 2, LST 1, M3D 1, MDB 2, OMM 2, PID 1, PRC 2, TRP 1, TST 1, WIR 1
10HAN | HRSG blowdown and drains (EPC tanks and headers) | water_steam_cycle | IEPC | 37 | CAL 3, CEM 1, CMP 1, CNR 1, DSH 7, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, STR 1, SUP 1, TRP 1, TST 1, WIR 1
10HNA | HRSG flue gas ducting | hrsg | IEC | 3 | DSH 1, MDB 1, PID 1
10HNE | Stack 65 m with CEMS platform and silencer | hrsg | IEPC | 16 | CAL 1, CMP 1, DSH 2, ITP 1, LOG 1, MDB 1, MOS 6, MRQ 1, RPT 1, SPC 1
10HSA | SCR catalyst and ammonia injection | hrsg | IEC | 3 | DSH 1, MDB 1, PID 1
10HSB | Ammonia storage and supply | auxiliary_mechanical | IEPC | 36 | CAL 3, CEM 1, CMP 1, CNR 1, DSH 7, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, SUP 1, TRP 1, TST 1, WIR 1
10LAB | Feedwater piping | condensate_feedwater | IEPC | 16 | CAL 1, CEM 1, CMP 1, CNR 1, DSH 3, HMI 1, ISO 1, LOG 1, MDB 1, OMM 1, PID 1, SDS 1, STR 1, SUP 1
10LAC | Boiler feed pumps | condensate_feedwater | IEPC | 36 | CAL 3, CEM 1, CMP 1, CNR 1, DSH 6, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, STR 1, SUP 1, TRP 1, TST 1, WIR 1
10LAE | HP attemperation spray water | condensate_feedwater | IEPC | 15 | CAL 1, CEM 1, CMP 1, CNR 1, DSH 2, HMI 1, ISO 1, LOG 1, MDB 1, OMM 1, PID 1, SDS 1, STR 1, SUP 1
10LAF | Reheat attemperation spray water | condensate_feedwater | IEPC | 15 | CAL 1, CEM 1, CMP 1, CNR 1, DSH 2, HMI 1, ISO 1, LOG 1, MDB 1, OMM 1, PID 1, SDS 1, STR 1, SUP 1
10LBA | Main steam piping | water_steam_cycle | IEPC | 18 | CAL 1, CEM 1, CMP 1, CNR 1, DSH 2, HMI 1, ISO 1, ITP 1, LOG 1, MDB 2, OMM 1, PID 1, RPT 1, SDS 1, STR 1, SUP 1
10LBB | Hot reheat piping | water_steam_cycle | IEPC | 14 | CAL 1, CEM 1, CMP 1, CNR 1, DSH 1, HMI 1, ISO 1, LOG 1, MDB 1, OMM 1, PID 1, SDS 1, STR 1, SUP 1
10LBC | Cold reheat piping | water_steam_cycle | IEPC | 14 | CAL 1, CEM 1, CMP 1, CNR 1, DSH 1, HMI 1, ISO 1, LOG 1, MDB 1, OMM 1, PID 1, SDS 1, STR 1, SUP 1
10LBD | LP steam piping | water_steam_cycle | IEPC | 14 | CAL 1, CEM 1, CMP 1, CNR 1, DSH 1, HMI 1, ISO 1, LOG 1, MDB 1, OMM 1, PID 1, SDS 1, STR 1, SUP 1
10MBA | Gas turbine | gas_turbine | IEC | 27 | CAL 2, CMP 1, DSH 4, GAD 1, HMB 2, IOL 1, ITP 1, LAY 1, LST 2, M3D 1, MDB 2, OMM 1, PID 1, PRC 1, RPT 2, TRP 1, TST 1, WIR 2
10MBL | GT inlet air system | gas_turbine | IEC | 3 | DSH 1, MDB 1, PID 1
10MBN | GT liquid fuel and water injection | gas_turbine | IEC | 3 | DSH 1, MDB 1, PID 1
10MBP | GT fuel gas system incl. performance heater | gas_turbine | IEC | 3 | DSH 1, MDB 1, PID 1
10MBU | GT compressor washing | gas_turbine | IEC | 3 | DSH 1, MDB 1, PID 1
10MBV | GT lube oil system | gas_turbine | IEC | 3 | DSH 1, MDB 1, PID 1
10MBY | GT control and protection (TCS) | i_and_c | IEC | 23 | BLK 1, CAL 1, CBL 1, CMP 1, CNR 1, DSH 1, GAD 1, IOL 1, ITP 1, LOG 6, LST 1, MDB 2, OMM 1, PRC 1, TRP 1, TST 1, WIR 1
10MKA | GT generator | generator | IEC | 22 | CAL 3, CMP 1, DSH 2, GAD 2, IOL 1, ITP 2, LST 1, MDB 2, OMM 2, PID 1, PRC 1, RPT 1, TRP 1, TST 1, WIR 1
10MKC | GT excitation and static frequency converter | generator | IEC | 3 | DSH 1, MDB 1, SLD 1
10MKG | GT generator gas system (H2/CO2) | generator | IEC | 3 | DSH 1, MDB 1, PID 1
10UHA | HRSG foundations and structures | civil_structural | IEPC | 6 | CAL 1, EFD 1, ELY 1, FND 2, RBR 1
10UHN | Stack foundation | civil_structural | IEPC | 6 | CAL 1, EFD 1, ELY 1, FND 2, RBR 1
10UMA | Gas turbine hall | civil_structural | IEPC | 23 | ARC 1, CAL 1, CBL 1, EFD 1, ELY 5, FND 2, GAD 3, HUP 1, LAY 1, LOP 3, PPL 1, RBR 1, STL 2
20BAA | ST generator busduct | electrical_hv | IEC | 3 | DSH 1, MDB 1, SLD 1
20BAC | ST generator circuit breaker | electrical_hv | IEC | 3 | DSH 1, MDB 1, SLD 1
20BAT | ST generator step-up transformer | electrical_hv | IEC | 3 | DSH 1, GAD 1, MDB 1
20BBT | ST unit auxiliary transformer | electrical_mv_lv | IEPC | 7 | CMP 1, DSH 2, LOG 1, MDB 1, OMM 1, SLD 1
20LCA | Main condensate piping | condensate_feedwater | IEPC | 16 | CAL 1, CEM 1, CMP 1, CNR 1, DSH 3, HMI 1, ISO 1, LOG 1, MDB 1, OMM 1, PID 1, SDS 1, STR 1, SUP 1
20LCB | Condensate extraction pumps | condensate_feedwater | IEPC | 35 | CAL 3, CEM 1, CMP 1, CNR 1, DSH 5, GAD 1, HMI 1, IOL 1, ISO 1, ITP 2, LOG 1, LST 1, MDB 2, MRQ 1, OMM 2, PID 2, PRC 1, RPT 1, SDS 1, SPC 1, STR 1, SUP 1, TRP 1, TST 1, WIR 1
20MAA | HP turbine | steam_turbine | IEC | 24 | CAL 2, CMP 1, DSH 4, GAD 1, HMB 1, IOL 1, ITP 2, LST 1, M3D 1, MDB 2, OMM 2, PID 1, PRC 2, TRP 1, TST 1, WIR 1
20MAB | IP/LP turbine | steam_turbine | IEC | 3 | DSH 1, MDB 1, PID 1
20MAG | Condensing system | water_steam_cycle | IEC | 5 | CAL 1, DSH 1, GAD 1, MDB 1, PID 1
20MAJ | Condenser vacuum system | steam_turbine | IEC | 3 | DSH 1, MDB 1, PID 1
20MAN | Turbine bypass stations and piping | water_steam_cycle | IEPC | 16 | CAL 1, CEM 1, CMP 1, CNR 1, DSH 3, HMI 1, ISO 1, LOG 1, MDB 1, OMM 1, PID 1, SDS 1, STR 1, SUP 1
20MAV | ST lube oil system | steam_turbine | IEC | 3 | DSH 1, MDB 1, PID 1
20MAW | Gland steam system | steam_turbine | IEC | 3 | DSH 1, MDB 1, PID 1
20MAX | ST control fluid system | steam_turbine | IEC | 3 | DSH 1, MDB 1, PID 1
20MAY | ST control and protection | i_and_c | IEC | 5 | BLK 1, CBL 1, CNR 1, IOL 1, MDB 1
20MKA | ST generator | generator | IEC | 6 | CAL 1, DSH 1, GAD 1, MDB 1, PID 1, RPT 1
20MKC | ST excitation | generator | IEC | 3 | DSH 1, MDB 1, SLD 1
20UMB | Steam turbine hall | civil_structural | IEPC | 21 | ARC 1, CAL 1, CBL 1, EFD 1, ELY 5, FND 2, GAD 2, HUP 1, LAY 1, LOP 2, PPL 1, RBR 1, STL 2

## Coverage requirements
Alpilla 600 MW Combined Cycle Power Plant - Coverage: Employer's Requirements answered by documents
engine engineering_plan v1.6.0 ¦ generated 2026-09-29T03:49:44Z by EPCE ¦ data 73eaa92ce7c1ff26 ¦ dates computed from the workflow network and the CPM (working days)
Requirement | Title | Docs | Documents
ER-01.01 | Purpose of the Works | 1 | ALP-EPC-00000-GE-DBR-0001
ER-01.02 | Plant configuration | 215 | ALP-EPC-00000-GE-DBR-0001 ALP-EPC-00000-PR-DBR-0001 ALP-EPC-00000-PR-PFD-0002 ALP-EPC-00EGA-ME-CAL-0001 ALP-EPC-00EGA-PI-ISO-0001 ALP-EPC-00EGA-PR-PID-0001 ALP-EPC-00EGA-PR-SDS-0001 ALP-EPC-00EGB-ME-CAL-0001 ALP-EPC-00EGB-PI-ISO-0001 ALP-EPC-00EGB-PR-PID-0001 ALP-EPC-00EGB-PR-SDS-0001 ALP-EPC-00EGC-ME-CAL-0001 ALP-EPC-00EGC-PI-ISO-0001 ALP-EPC-00EGC-PI-STR-0001 ALP-EPC-00EGC-PR-PID-0001 ALP-EPC-00EGC-PR-SDS-0001 ALP-EPC-00EKA-ME-CAL-0001 ALP-EPC-00EKA-PI-ISO-0001 ALP-EPC-00EKA-PI-STR-0001 ALP-EPC-00EKA-PR-PID-0001 ALP-EPC-00EKA-PR-SDS-0001 ALP-EPC-00EKC-ME-CAL-0001 ALP-EPC-00EKC-PI-ISO-0001 ALP-EPC-00EKC-PI-STR-0001 ALP-EPC-00EKC-PR-PID-0001 ALP-EPC-00EKC-PR-SDS-0001 ALP-EPC-00GBA-ME-CAL-0001 ALP-EPC-00GBA-PI-ISO-0001 ALP-EPC-00GBA-PR-PID-0001 ALP-EPC-00GBA-PR-SDS-0001 ALP-EPC-00GCA-ME-CAL-0001 ALP-EPC-00GCA-PI-ISO-0001 ALP-EPC-00GCA-PR-PID-0001 ALP-EPC-00GCA-PR-SDS-0001 ALP-EPC-00GHA-ME-CAL-0001 ALP-EPC-00GHA-PI-ISO-0001 ALP-EPC-00GHA-PR-PID-0001 ALP-EPC-00GHA-PR-SDS-0001 ALP-EPC-00GKA-ME-CAL-0001 ALP-EPC-00GKA-PI-ISO-0001 ALP-EPC-00GKA-PR-PID-0001 ALP-EPC-00GKA-PR-SDS-0001 ALP-EPC-00GMA-ME-CAL-0001 ALP-EPC-00GMA-PI-ISO-0001 ALP-EPC-00GMA-PR-PID-0001 ALP-EPC-00GMA-PR-SDS-0001 ALP-EPC-00GNA-ME-CAL-0001 ALP-EPC-00GNA-PI-ISO-0001 ALP-EPC-00GNA-PR-PID-0001 ALP-EPC-00GNA-PR-SDS-0001 ALP-EPC-00GUA-ME-CAL-0001 ALP-EPC-00GUA-PI-ISO-0001 ALP-EPC-00GUA-PR-PID-0001 ALP-EPC-00GUA-PR-SDS-0001 ALP-EPC-00LBG-ME-CAL-0001 ALP-EPC-00LBG-PI-ISO-0001 ALP-EPC-00LBG-PI-STR-0001 ALP-EPC-00LBG-PR-PID-0001 ALP-EPC-00LBG-PR-SDS-0001 ALP-EPC-00LDA-ME-CAL-0001 ALP-EPC-00LDA-PI-ISO-0001 ALP-EPC-00LDA-PR-PID-0001 ALP-EPC-00LDA-PR-SDS-0001 ALP-EPC-00PAA-ME-CAL-0001 ALP-EPC-00PAA-PI-ISO-0001 ALP-EPC-00PAA-PR-PID-0001 ALP-EPC-00PAA-PR-SDS-0001 ALP-EPC-00PAB-ME-CAL-0001 ALP-EPC-00PAB-PI-ISO-0001 ALP-EPC-00PAB-PI-STR-0001 ALP-EPC-00PAB-PR-PID-0001 ALP-EPC-00PAB-PR-SDS-0001 ALP-EPC-00PAC-ME-CAL-0001 ALP-EPC-00PAC-PI-ISO-0001 ALP-EPC-00PAC-PR-PID-0001 ALP-EPC-00PAC-PR-SDS-0001 ALP-EPC-00PAH-ME-CAL-0001 ALP-EPC-00PAH-PI-ISO-0001 ALP-EPC-00PAH-PR-PID-0001 ALP-EPC-00PAH-PR-SDS-0001 ALP-EPC-00PBA-ME-CAL-0001 ALP-EPC-00PBA-PI-ISO-0001 ALP-EPC-00PBA-PR-PID-0001 ALP-EPC-00PBA-PR-SDS-0001 ALP-EPC-00PGA-ME-CAL-0001 ALP-EPC-00PGA-PI-ISO-0001 ALP-EPC-00PGA-PI-STR-0001 ALP-EPC-00PGA-PR-PID-0001 ALP-EPC-00PGA-PR-SDS-0001 ALP-EPC-00QCA-ME-CAL-0001 ALP-EPC-00QCA-PI-ISO-0001 ALP-EPC-00QCA-PR-PID-0001 ALP-EPC-00QCA-PR-SDS-0001 ALP-EPC-00QEA-ME-CAL-0001 ALP-EPC-00QEA-PI-ISO-0001 ALP-EPC-00QEA-PR-PID-0001 ALP-EPC-00QEA-PR-SDS-0001 ALP-EPC-00QHA-ME-CAL-0001 ALP-EPC-00QHA-PI-ISO-0001 ALP-EPC-00QHA-PI-STR-0001 ALP-EPC-00QHA-PR-PID-0001 ALP-EPC-00QHA-PR-SDS-0001 ALP-EPC-00QJA-ME-CAL-0001 ALP-EPC-00QJA-PI-ISO-0001 ALP-EPC-00QJA-PR-PID-0001 ALP-EPC-00QJA-PR-SDS-0001 ALP-EPC-00QJB-ME-CAL-0001 ALP-EPC-00QJB-PI-ISO-0001 ALP-EPC-00QJB-PR-PID-0001 ALP-EPC-00QJB-PR-SDS-0001 ALP-EPC-00QUA-ME-CAL-0001 ALP-EPC-00QUA-PI-ISO-0001 ALP-EPC-00QUA-PR-PID-0001 ALP-EPC-00QUA-PR-SDS-0001 ALP-EPC-00SAA-HV-CAL-0001 ALP-EPC-00SAA-HV-PID-0001 ALP-EPC-00SAA-HV-SDS-0001 ALP-EPC-00SAA-PI-ISO-0001 ALP-EPC-00SGA-ME-CAL-0001 ALP-EPC-00SGA-PI-ISO-0001 ALP-EPC-00SGA-PI-STR-0001 ALP-EPC-00SGA-PR-PID-0001 ALP-EPC-00SGA-PR-SDS-0001 ALP-EPC-00SGC-ME-CAL-0001 ALP-EPC-00SGC-PI-ISO-0001 ALP-EPC-00SGC-PR-PID-0001 ALP-EPC-00SGC-PR-SDS-0001 ALP-EPC-00UAC-PI-LAY-0001 ALP-EPC-00UBA-PI-LAY-0001 ALP-EPC-00UBA-PI-PPL-0001 ALP-EPC-00UCA-PI-LAY-0001 ALP-EPC-00UCA-PI-PPL-0001 ALP-EPC-00UEG-PI-LAY-0001 ALP-EPC-00UEG-PI-PPL-0001 ALP-EPC-00UEK-PI-LAY-0001 ALP-EPC-00UEK-PI-PPL-0001 ALP-EPC-00UGA-PI-LAY-0001 ALP-EPC-00UGA-PI-PPL-0001 ALP-EPC-00UPA-PI-LAY-0001 ALP-EPC-00UPC-PI-LAY-0001 ALP-EPC-00UPC-PI-PPL-0001 ALP-EPC-00UQA-PI-LAY-0001 ALP-EPC-00UQA-PI-PPL-0001 ALP-EPC-00UQA-PI-PPL-0002 ALP-EPC-00UQA-PI-PPL-0003 ALP-EPC-00UZA-PI-LAY-0001 ALP-EPC-00UZA-PI-PPL-0001 ALP-EPC-10HAN-ME-CAL-0001 ALP-EPC-10HAN-PI-ISO-0001 ALP-EPC-10HAN-PI-STR-0001 ALP-EPC-10HAN-PR-PID-0001 ALP-EPC-10HAN-PR-SDS-0001 ALP-EPC-10HSB-ME-CAL-0001 ALP-EPC-10HSB-PI-ISO-0001 ALP-EPC-10HSB-PR-PID-0001 ALP-EPC-10HSB-PR-SDS-0001 ALP-EPC-10LAB-ME-CAL-0001 ALP-EPC-10LAB-PI-ISO-0001 ALP-EPC-10LAB-PI-STR-0001 ALP-EPC-10LAB-PR-PID-0001 ALP-EPC-10LAB-PR-SDS-0001 ALP-EPC-10LAC-ME-CAL-0001 ALP-EPC-10LAC-PI-ISO-0001 ALP-EPC-10LAC-PI-STR-0001 ALP-EPC-10LAC-PR-PID-0001 ALP-EPC-10LAC-PR-SDS-0001 ALP-EPC-10LAE-ME-CAL-0001 ALP-EPC-10LAE-PI-ISO-0001 ALP-EPC-10LAE-PI-STR-0001 ALP-EPC-10LAE-PR-PID-0001 ALP-EPC-10LAE-PR-SDS-0001 ALP-EPC-10LAF-ME-CAL-0001 ALP-EPC-10LAF-PI-ISO-0001 ALP-EPC-10LAF-PI-STR-0001 ALP-EPC-10LAF-PR-PID-0001 ALP-EPC-10LAF-PR-SDS-0001 ALP-EPC-10LBA-ME-CAL-0001 ALP-EPC-10LBA-PI-ISO-0001 ALP-EPC-10LBA-PI-STR-0001 ALP-EPC-10LBA-PR-PID-0001 ALP-EPC-10LBA-PR-SDS-0001 ALP-EPC-10LBB-ME-CAL-0001 ALP-EPC-10LBB-PI-ISO-0001 ALP-EPC-10LBB-PI-STR-0001 ALP-EPC-10LBB-PR-PID-0001 ALP-EPC-10LBB-PR-SDS-0001 ALP-EPC-10LBC-ME-CAL-0001 ALP-EPC-10LBC-PI-ISO-0001 ALP-EPC-10LBC-PI-STR-0001 ALP-EPC-10LBC-PR-PID-0001 ALP-EPC-10LBC-PR-SDS-0001 ALP-EPC-10LBD-ME-CAL-0001 ALP-EPC-10LBD-PI-ISO-0001 ALP-EPC-10LBD-PI-STR-0001 ALP-EPC-10LBD-PR-PID-0001 ALP-EPC-10LBD-PR-SDS-0001 ALP-EPC-10UMA-PI-LAY-0001 ALP-EPC-10UMA-PI-PPL-0001 ALP-EPC-20LCA-ME-CAL-0001 ALP-EPC-20LCA-PI-ISO-0001 ALP-EPC-20LCA-PI-STR-0001 ALP-EPC-20LCA-PR-PID-0001 ALP-EPC-20LCA-PR-SDS-0001 ALP-EPC-20LCB-ME-CAL-0001 ALP-EPC-20LCB-PI-ISO-0001 ALP-EPC-20LCB-PI-STR-0001 ALP-EPC-20LCB-PR-PID-0001 ALP-EPC-20LCB-PR-SDS-0001 ALP-EPC-20MAN-ME-CAL-0001 ALP-EPC-20MAN-PI-ISO-0001 ALP-EPC-20MAN-PI-STR-0001 ALP-EPC-20MAN-PR-PID-0001 ALP-EPC-20MAN-PR-SDS-0001 ALP-EPC-20UMB-PI-LAY-0001 ALP-EPC-20UMB-PI-PPL-0001
ER-01.03 | Design life and operating regime | 3 | ALP-EPC-00000-GE-DBR-0001 ALP-EPC-00000-PR-RPT-0004 ALP-EPC-00000-PR-STU-0002
ER-01.04 | Turnkey completeness | 1 | ALP-EPC-00000-GE-DBR-0001
ER-01.05 | Units and language | 1 | ALP-EPC-00000-GE-DBR-0001
ER-01.06 | Plant identification system | 1 | ALP-EPC-00000-GE-PRC-0001
ER-01.07 | Codes and standards hierarchy | 1 | ALP-EPC-00000-GE-LST-0001
ER-01.08 | Proven technology | 1 | ALP-IEC-10MBA-ME-DSH-0001
ER-01.09 | Design responsibility | 1 | ALP-EPC-00000-GE-PLN-0001
ER-01.10 | Engineering database and data handover | 2 | ALP-EPC-00000-GE-PRC-0003 ALP-EPC-00000-PI-M3D-0004
ER-02.01 | Site location and area | 3 | ALP-EPC-00000-CV-RPT-0003 ALP-EPC-00000-GE-DBR-0001 ALP-EPC-00000-PR-DBR-0001
ER-02.02 | Ambient design range | 1 | ALP-EPC-00000-GE-DBR-0001
ER-02.03 | Site Reference Conditions (SRC) | 1 | ALP-EPC-00000-GE-DBR-0001
ER-02.04 | Seawater conditions | 1 | ALP-EPC-00PAA-PR-SDS-0001
ER-02.05 | Wind, snow and rain | 1 | ALP-EPC-00000-GE-DBR-0001
ER-02.06 | Seismic design | 2 | ALP-EPC-00000-CV-DBR-0001 ALP-EPC-00000-CV-STU-0001
ER-02.07 | Geotechnical conditions | 1 | ALP-EPC-00000-CV-RPT-0001
ER-02.08 | Corrosive coastal atmosphere | 4 | ALP-EPC-00000-EL-CAL-0005 ALP-EPC-00000-ME-DBR-0001 ALP-EPC-00000-ME-RPT-0002 ALP-EPC-00000-ME-SPC-0002
ER-02.09 | Flood protection | 1 | ALP-EPC-00UZC-CV-CVL-0001
ER-02.10 | Airborne salt and dust | 1 | ALP-EPC-00ACA-EL-SPC-0001
ER-02.11 | Design ambient points | 1 | ALP-EPC-00000-GE-DBR-0001
ER-02.12 | Lightning | 1 | ALP-EPC-00000-EL-STU-0004
ER-02.13 | Existing features on the Site | 1 | ALP-EPC-00UZC-CV-CVL-0001
ER-02.14 | Access and transport | 2 | ALP-EPC-00000-ME-STU-0001 ALP-EPC-00UZF-CV-RPT-0001
ER-03.01 | Fuels | 1 | ALP-EPC-00000-GE-DBR-0001
ER-03.02 | Natural gas specification | 1 | ALP-EPC-00000-PR-HMB-0001
ER-03.03 | Gas supply conditions at terminal point | 1 | ALP-EPC-00EKA-PR-SDS-0001
ER-03.04 | Gas receiving and fiscal metering station | 1 | ALP-EPC-00EKA-PR-SDS-0001
ER-03.05 | Performance fuel gas heating | 1 | ALP-IEC-10MBA-PR-PID-0001
ER-03.06 | Natural gas contaminant limits | 1 | ALP-EPC-00EKA-ME-SPC-0001
ER-03.07 | Light diesel oil specification and burner limits | 1 | ALP-EPC-00EGC-PR-SDS-0001
ER-03.08 | LDO unloading and storage | 1 | ALP-EPC-00EGB-PR-SDS-0001
ER-03.09 | LDO forwarding and treatment | 1 | ALP-EPC-00EGC-PR-SDS-0001
ER-03.10 | Fuel transfer and LDO start | 1 | ALP-EPC-00000-IC-CNR-0001
ER-03.11 | NOx control and SCR on LDO | 1 | ALP-IEC-10MBA-PR-PID-0001
ER-04.01 | Net electrical output | 1 | ALP-EPC-00000-PR-CAL-0001
ER-04.02 | Net heat rate | 1 | ALP-EPC-00000-PR-CAL-0001
ER-04.03 | Part-load efficiency | 1 | ALP-EPC-00000-PR-CAL-0001
ER-04.04 | Start-up times | 1 | ALP-IEC-10MBY-IC-CNR-0001
ER-04.05 | Load ramp rate | 2 | ALP-EPC-00000-PR-RPT-0002 ALP-IEC-10MBY-IC-CNR-0001
ER-04.06 | Minimum environmental load | 1 | ALP-EPC-00000-PR-HMB-0001
ER-04.07 | Frequency and voltage support | 1 | ALP-EPC-00000-EL-STU-0006
ER-04.08 | Reactive capability | 1 | ALP-EPC-00000-EL-STU-0006
ER-04.09 | House load and island operation | 1 | ALP-EPC-00000-IC-CNR-0001
ER-04.10 | Auxiliary power | 1 | ALP-EPC-00000-EL-LST-0001
ER-04.11 | Degradation | 2 | ALP-EPC-00000-PR-CAL-0001 ALP-EPC-00000-PR-CAL-0002
ER-04.12 | Availability target | 1 | ALP-EPC-00000-PR-STU-0002
ER-05.01 | Gas turbine type | 1 | ALP-IEC-10MBA-ME-DSH-0001
ER-05.02 | Inlet air system | 1 | ALP-IEC-10MBA-PR-PID-0001
ER-05.03 | Combustion dynamics monitoring | 1 | ALP-IEC-10MBA-ME-DSH-0001
ER-05.04 | Enclosure and ventilation | 1 | ALP-IEC-10MBA-ME-DSH-0001
ER-05.05 | Compressor washing | 1 | ALP-IEC-10MBA-PR-PID-0001
ER-05.06 | Condition monitoring and remote diagnostics | 1 | ALP-IEC-10MBY-IC-BLK-0001
ER-05.07 | Maintenance intervals | 1 | ALP-IEC-10MBA-ME-DSH-0001
ER-06.01 | HRSG type | 1 | ALP-IEC-10HAA-ME-DSH-0001
ER-06.02 | Design code | 1 | ALP-IEC-10HAA-ME-DSH-0001
ER-06.03 | SCR and CO catalyst | 1 | ALP-IEC-10HAA-PR-PID-0001
ER-06.04 | Ammonia system | 1 | ALP-EPC-10HSB-PR-SDS-0001
ER-06.05 | Cycling capability | 1 | ALP-IEC-10HAA-ME-DSH-0001
ER-06.06 | Stack | 1 | ALP-EPC-10HNE-SS-SPC-0001
ER-06.07 | Drains and blowdown | 1 | ALP-EPC-10HAN-PR-SDS-0001
ER-06.08 | Preservation | 1 | ALP-EPC-00QJA-PR-SDS-0001
ER-07.01 | Steam turbine | 1 | ALP-IEC-20MAA-ME-DSH-0001
ER-07.02 | Main steam conditions | 1 | ALP-IEC-20MAA-ME-DSH-0001
ER-07.03 | Condenser | 1 | ALP-EPC-00PAH-PR-SDS-0001
ER-07.04 | Cooling water temperature rise | 1 | ALP-IEC-20MAG-ME-DSH-0001
ER-07.05 | Vacuum system | 1 | ALP-IEC-20MAA-PR-PID-0001
ER-07.06 | Lube and control oil | 1 | ALP-IEC-20MAA-PR-PID-0001
ER-07.07 | Condenser design standard | 1 | ALP-IEC-20MAG-ME-DSH-0001
ER-07.08 | Condenser pressure | 1 | ALP-IEC-20MAG-ME-DSH-0001
ER-07.09 | Steam bypass to the condenser | 1 | ALP-EPC-20MAN-PR-SDS-0001
ER-07.10 | Condenser leak detection and protection | 1 | ALP-EPC-00QUA-PR-SDS-0001
ER-07.11 | Circulating water flow | 2 | ALP-EPC-00PAB-PR-STU-0001 ALP-EPC-00PAC-ME-CAL-0001
ER-08.01 | Once-through seawater cooling | 2 | ALP-EPC-00PAB-PR-SDS-0001 ALP-EPC-00UPA-CV-CAL-0002
ER-08.02 | Screening | 2 | ALP-EPC-00PAA-PR-SDS-0001 ALP-EPC-00PAA-PR-STU-0001
ER-08.03 | Circulating water pumps | 1 | ALP-EPC-00PAC-PR-SDS-0001
ER-08.04 | Biofouling control | 1 | ALP-EPC-00PBA-PR-SDS-0001
ER-08.05 | Thermal plume | 1 | ALP-EPC-00000-PR-STU-0003
ER-08.06 | Closed cooling water | 1 | ALP-EPC-00PGA-PR-SDS-0001
ER-08.07 | Jellyfish and mucilage | 2 | ALP-EPC-00PAA-PR-SDS-0001 ALP-EPC-00PAA-PR-STU-0001
ER-09.01 | Raw water | 1 | ALP-EPC-00GBA-PR-SDS-0001
ER-09.02 | Demineralised water | 1 | ALP-EPC-00GCA-PR-SDS-0001
ER-09.03 | Cycle chemistry | 1 | ALP-EPC-00000-PR-RPT-0001
ER-09.04 | Condensate polishing | 1 | ALP-EPC-00LDA-PR-SDS-0001
ER-09.05 | Waste water | 1 | ALP-EPC-00GNA-PR-SDS-0001
ER-09.06 | Stormwater | 1 | ALP-EPC-00UZC-CV-CVL-0001
ER-10.01 | Feed water pumps | 85 | ALP-EPC-00000-ME-DBR-0001 ALP-EPC-00EGA-ME-DSH-0001 ALP-EPC-00EGA-ME-DSH-0002 ALP-EPC-00EGA-ME-DSH-0003 ALP-EPC-00EGA-ME-DSH-0004 ALP-EPC-00EGB-ME-DSH-0001 ALP-EPC-00EGC-ME-DSH-0001 ALP-EPC-00EGC-ME-DSH-0002 ALP-EPC-00EGC-ME-DSH-0003 ALP-EPC-00EKA-ME-DSH-0001 ALP-EPC-00EKA-ME-DSH-0002 ALP-EPC-00EKA-ME-DSH-0003 ALP-EPC-00EKA-ME-DSH-0004 ALP-EPC-00GBA-ME-DSH-0001 ALP-EPC-00GBA-ME-DSH-0002 ALP-EPC-00GBA-ME-DSH-0003 ALP-EPC-00GBA-ME-DSH-0004 ALP-EPC-00GCA-ME-DSH-0001 ALP-EPC-00GCA-ME-DSH-0002 ALP-EPC-00GCA-ME-DSH-0003 ALP-EPC-00GHA-ME-DSH-0001 ALP-EPC-00GHA-ME-DSH-0002 ALP-EPC-00GKA-ME-DSH-0001 ALP-EPC-00GKA-ME-DSH-0002 ALP-EPC-00GKA-ME-DSH-0003 ALP-EPC-00GMA-ME-DSH-0004 ALP-EPC-00GMA-ME-DSH-0005 ALP-EPC-00GMA-ME-DSH-0006 ALP-EPC-00GNA-ME-DSH-0001 ALP-EPC-00GNA-ME-DSH-0002 ALP-EPC-00GNA-ME-DSH-0003 ALP-EPC-00GUA-ME-DSH-0001 ALP-EPC-00GUA-ME-DSH-0002 ALP-EPC-00LDA-ME-DSH-0001 ALP-EPC-00LDA-ME-DSH-0002 ALP-EPC-00PAA-ME-DSH-0001 ALP-EPC-00PAA-ME-DSH-0002 ALP-EPC-00PAA-ME-DSH-0003 ALP-EPC-00PAB-ME-DSH-0001 ALP-EPC-00PAC-ME-DSH-0001 ALP-EPC-00PAH-ME-DSH-0001 ALP-EPC-00PAH-ME-DSH-0002 ALP-EPC-00PAH-ME-DSH-0003 ALP-EPC-00PBA-ME-DSH-0001 ALP-EPC-00PBA-ME-DSH-0002 ALP-EPC-00PBA-ME-DSH-0003 ALP-EPC-00PBA-ME-DSH-0004 ALP-EPC-00PBA-ME-DSH-0005 ALP-EPC-00PGA-ME-DSH-0001 ALP-EPC-00PGA-ME-DSH-0002 ALP-EPC-00PGA-ME-DSH-0003 ALP-EPC-00PGA-ME-DSH-0004 ALP-EPC-00QCA-ME-DSH-0001 ALP-EPC-00QCA-ME-DSH-0002 ALP-EPC-00QCA-ME-DSH-0003 ALP-EPC-00QEA-ME-DSH-0001 ALP-EPC-00QEA-ME-DSH-0002 ALP-EPC-00QEA-ME-DSH-0003 ALP-EPC-00QHA-ME-DSH-0001 ALP-EPC-00QHA-ME-DSH-0002 ALP-EPC-00QHA-ME-DSH-0003 ALP-EPC-00QHA-ME-DSH-0004 ALP-EPC-00QJA-ME-DSH-0001 ALP-EPC-00QJA-ME-DSH-0002 ALP-EPC-00QJB-ME-DSH-0001 ALP-EPC-00QUA-ME-DSH-0001 ALP-EPC-00QUA-ME-DSH-0002 ALP-EPC-00SAA-HV-DSH-0001 ALP-EPC-00SAA-ME-DSH-0001 ALP-EPC-00SAA-ME-DSH-0002 ALP-EPC-00SAA-ME-DSH-0003 ALP-EPC-00SGA-ME-DSH-0001 ALP-EPC-00SGA-ME-DSH-0002 ALP-EPC-00SGC-ME-DSH-0001 ALP-EPC-00SGC-ME-DSH-0002 ALP-EPC-00SMA-ME-DSH-0001 ALP-EPC-00XJA-ME-DSH-0001 ALP-EPC-10HAN-ME-DSH-0001 ALP-EPC-10HAN-ME-DSH-0002 ALP-EPC-10HNE-ME-DSH-0001 ALP-EPC-10HSB-ME-DSH-0001 ALP-EPC-10HSB-ME-DSH-0002 ALP-EPC-10LAC-ME-DSH-0001 ALP-EPC-10LAC-PR-SDS-0001 ALP-EPC-20LCB-ME-DSH-0001
ER-10.02 | Condensate pumps | 1 | ALP-EPC-20LCB-PR-SDS-0001
ER-10.03 | Compressed air | 1 | ALP-EPC-00QEA-PR-SDS-0001
ER-10.04 | Auxiliary boiler | 1 | ALP-EPC-00QHA-PR-SDS-0001
ER-10.05 | Fire protection | 27 | ALP-EPC-00000-CM-TRP-0007 ALP-EPC-00000-HS-HAZ-0009 ALP-EPC-00000-HS-STU-0003 ALP-EPC-00SGA-PR-CAL-0001 ALP-EPC-00SGA-PR-SDS-0001 ALP-EPC-00UAC-HS-GAD-0001 ALP-EPC-00UAC-IC-ELY-0001 ALP-EPC-00UBA-HS-GAD-0001 ALP-EPC-00UBA-IC-ELY-0001 ALP-EPC-00UCA-HS-GAD-0001 ALP-EPC-00UCA-IC-ELY-0002 ALP-EPC-00UEK-HS-GAD-0001 ALP-EPC-00UEK-IC-ELY-0002 ALP-EPC-00UGA-HS-GAD-0001 ALP-EPC-00UGA-IC-ELY-0002 ALP-EPC-00UPC-HS-GAD-0001 ALP-EPC-00UPC-IC-ELY-0002 ALP-EPC-00UQA-HS-GAD-0001 ALP-EPC-00UQA-IC-ELY-0002 ALP-EPC-00USA-HS-GAD-0001 ALP-EPC-00USA-IC-ELY-0001 ALP-EPC-00UYA-HS-GAD-0001 ALP-EPC-00UYA-IC-ELY-0001 ALP-EPC-10UMA-HS-GAD-0001 ALP-EPC-10UMA-IC-ELY-0002 ALP-EPC-20UMB-HS-GAD-0001 ALP-EPC-20UMB-IC-ELY-0002
ER-10.06 | HVAC | 16 | ALP-EPC-00000-HV-DBR-0001 ALP-EPC-00SAA-HV-SDS-0001 ALP-EPC-00UAC-HV-GAD-0001 ALP-EPC-00UBA-HV-GAD-0001 ALP-EPC-00UBA-HV-GAD-0002 ALP-EPC-00UCA-HV-GAD-0001 ALP-EPC-00UCA-HV-GAD-0002 ALP-EPC-00UEK-HV-GAD-0001 ALP-EPC-00UGA-HV-GAD-0001 ALP-EPC-00UPC-HV-GAD-0001 ALP-EPC-00UQA-HV-GAD-0001 ALP-EPC-00USA-HV-GAD-0001 ALP-EPC-00UYA-HV-GAD-0001 ALP-EPC-10UMA-HV-GAD-0001 ALP-EPC-10UMA-HV-GAD-0002 ALP-EPC-20UMB-HV-GAD-0001
ER-10.07 | Cranes | 2 | ALP-EPC-00000-ME-STU-0002 ALP-EPC-00SMA-ME-SPC-0001
ER-10.08 | Nitrogen and hydrogen | 1 | ALP-EPC-00QJA-PR-SDS-0001
ER-11.01 | Grid connection | 1 | ALP-EPC-00ACA-EL-SPC-0001
ER-11.02 | Generators | 1 | ALP-IEC-10MKA-EL-DSH-0001
ER-11.03 | Generator step-up transformers | 1 | ALP-IEC-10BAT-EL-DSH-0001
ER-11.04 | Auxiliary power supply | 28 | ALP-EPC-00000-EL-DBR-0001 ALP-EPC-00000-EL-RPT-0001 ALP-EPC-00ACA-EL-DSH-0001 ALP-EPC-00BBA-EL-DSH-0001 ALP-EPC-00BBA-EL-SLD-0001 ALP-EPC-00BBA-EL-WIR-0001 ALP-EPC-00BFA-EL-DSH-0001 ALP-EPC-00BFA-EL-WIR-0001 ALP-EPC-00BFA-EL-WIR-0002 ALP-EPC-00BFA-EL-WIR-0003 ALP-EPC-00BFA-EL-WIR-0004 ALP-EPC-00BFA-EL-WIR-0005 ALP-EPC-00BFA-EL-WIR-0006 ALP-EPC-00BFA-EL-WIR-0007 ALP-EPC-00BFA-EL-WIR-0008 ALP-EPC-00BFA-EL-WIR-0009 ALP-EPC-00BFA-EL-WIR-0010 ALP-EPC-00BFA-EL-WIR-0011 ALP-EPC-00BFA-EL-WIR-0012 ALP-EPC-00BFA-EL-WIR-0013 ALP-EPC-00BFT-EL-DSH-0001 ALP-EPC-00BMA-EL-DSH-0001 ALP-EPC-00BRA-EL-DSH-0001 ALP-EPC-00BRA-EL-DSH-0002 ALP-EPC-00BTA-EL-DSH-0001 ALP-EPC-00XJA-EL-DSH-0001 ALP-EPC-10BBT-EL-DSH-0001 ALP-EPC-20BBT-EL-DSH-0001
ER-11.05 | Emergency power | 3 | ALP-EPC-00000-EL-CAL-0002 ALP-EPC-00000-EL-CAL-0003 ALP-EPC-00XJA-EL-SPC-0001
ER-11.06 | Protection | 2 | ALP-EPC-00000-EL-LST-0003 ALP-EPC-00000-EL-STU-0002
ER-11.07 | Earthing and lightning | 35 | ALP-EPC-00000-EL-STU-0003 ALP-EPC-00UAC-EL-ELY-0001 ALP-EPC-00UAC-EL-ELY-0003 ALP-EPC-00UBA-EL-ELY-0001 ALP-EPC-00UBA-EL-ELY-0003 ALP-EPC-00UBF-EL-ELY-0001 ALP-EPC-00UCA-EL-ELY-0001 ALP-EPC-00UCA-EL-ELY-0003 ALP-EPC-00UEG-EL-ELY-0001 ALP-EPC-00UEG-EL-ELY-0003 ALP-EPC-00UEK-EL-ELY-0001 ALP-EPC-00UEK-EL-ELY-0003 ALP-EPC-00UGA-EL-ELY-0001 ALP-EPC-00UGA-EL-ELY-0003 ALP-EPC-00UPA-EL-ELY-0001 ALP-EPC-00UPA-EL-ELY-0002 ALP-EPC-00UPC-EL-ELY-0001 ALP-EPC-00UPC-EL-ELY-0003 ALP-EPC-00UQA-EL-ELY-0001 ALP-EPC-00UQA-EL-ELY-0003 ALP-EPC-00USA-EL-ELY-0001 ALP-EPC-00UYA-EL-ELY-0001 ALP-EPC-00UZA-EL-ELY-0001 ALP-EPC-00UZA-EL-ELY-0003 ALP-EPC-00UZB-EL-ELY-0001 ALP-EPC-00UZC-EL-ELY-0001 ALP-EPC-00UZD-EL-ELY-0001 ALP-EPC-00UZE-EL-ELY-0001 ALP-EPC-00UZF-EL-ELY-0001 ALP-EPC-10UHA-EL-ELY-0001 ALP-EPC-10UHN-EL-ELY-0001 ALP-EPC-10UMA-EL-ELY-0001 ALP-EPC-10UMA-EL-ELY-0003 ALP-EPC-20UMB-EL-ELY-0001 ALP-EPC-20UMB-EL-ELY-0003
ER-11.08 | Cables | 26 | ALP-EPC-00000-EL-BLK-0001 ALP-EPC-00000-EL-BLK-0002 ALP-EPC-00000-EL-CAL-0004 ALP-EPC-00000-EL-SPC-0001 ALP-EPC-00UAC-EL-CBL-0001 ALP-EPC-00UAC-EL-ELY-0002 ALP-EPC-00UBA-EL-CBL-0001 ALP-EPC-00UBA-EL-ELY-0002 ALP-EPC-00UCA-EL-CBL-0001 ALP-EPC-00UCA-EL-ELY-0002 ALP-EPC-00UEG-EL-CBL-0001 ALP-EPC-00UEG-EL-ELY-0002 ALP-EPC-00UEK-EL-CBL-0001 ALP-EPC-00UEK-EL-ELY-0002 ALP-EPC-00UGA-EL-CBL-0001 ALP-EPC-00UGA-EL-ELY-0002 ALP-EPC-00UPC-EL-CBL-0001 ALP-EPC-00UPC-EL-ELY-0002 ALP-EPC-00UQA-EL-CBL-0001 ALP-EPC-00UQA-EL-ELY-0002 ALP-EPC-00UZA-EL-CBL-0001 ALP-EPC-00UZA-EL-ELY-0002 ALP-EPC-10UMA-EL-CBL-0001 ALP-EPC-10UMA-EL-ELY-0002 ALP-EPC-20UMB-EL-CBL-0001 ALP-EPC-20UMB-EL-ELY-0002
ER-11.09 | Metering and TSO interface | 2 | ALP-EPC-00000-EL-SPC-0003 ALP-EPC-00000-EL-TRP-0001
ER-12.01 | Distributed control system | 135 | ALP-EPC-00000-IC-DBR-0001 ALP-EPC-00000-IC-SPC-0005 ALP-EPC-00000-IC-TST-0001 ALP-EPC-00ACA-IC-DSH-0001 ALP-EPC-00CJA-IC-BLK-0001 ALP-EPC-00CJA-IC-DSH-0001 ALP-EPC-00CJG-IC-BLK-0001 ALP-EPC-00CJG-IC-DSH-0001 ALP-EPC-00CKA-IC-BLK-0001 ALP-EPC-00CKA-IC-DSH-0001 ALP-EPC-00CQA-IC-BLK-0001 ALP-EPC-00CQA-IC-DSH-0001 ALP-EPC-00CQA-IC-DSH-0002 ALP-EPC-00CYA-IC-BLK-0001 ALP-EPC-00CYA-IC-DSH-0001 ALP-EPC-00EGA-IC-DSH-0001 ALP-EPC-00EGA-IC-DSH-0002 ALP-EPC-00EGB-IC-DSH-0001 ALP-EPC-00EGC-IC-DSH-0001 ALP-EPC-00EGC-IC-DSH-0002 ALP-EPC-00EKA-IC-DSH-0001 ALP-EPC-00EKA-IC-DSH-0002 ALP-EPC-00EKC-IC-DSH-0001 ALP-EPC-00EKC-IC-DSH-0002 ALP-EPC-00GBA-IC-DSH-0001 ALP-EPC-00GBA-IC-DSH-0002 ALP-EPC-00GCA-IC-DSH-0001 ALP-EPC-00GCA-IC-DSH-0002 ALP-EPC-00GHA-IC-DSH-0001 ALP-EPC-00GHA-IC-DSH-0002 ALP-EPC-00GKA-IC-DSH-0001 ALP-EPC-00GMA-IC-DSH-0001 ALP-EPC-00GNA-IC-DSH-0001 ALP-EPC-00GNA-IC-DSH-0002 ALP-EPC-00GUA-IC-DSH-0001 ALP-EPC-00LBG-IC-DSH-0001 ALP-EPC-00LBG-IC-DSH-0002 ALP-EPC-00LDA-IC-DSH-0001 ALP-EPC-00LDA-IC-DSH-0002 ALP-EPC-00PAA-IC-DSH-0001 ALP-EPC-00PAB-IC-DSH-0001 ALP-EPC-00PAC-IC-DSH-0001 ALP-EPC-00PAH-IC-DSH-0001 ALP-EPC-00PBA-IC-DSH-0001 ALP-EPC-00PBA-IC-DSH-0002 ALP-EPC-00PGA-IC-DSH-0001 ALP-EPC-00PGA-IC-DSH-0002 ALP-EPC-00QCA-IC-DSH-0001 ALP-EPC-00QEA-IC-DSH-0001 ALP-EPC-00QEA-IC-DSH-0002 ALP-EPC-00QHA-IC-DSH-0001 ALP-EPC-00QHA-IC-DSH-0002 ALP-EPC-00QJA-IC-DSH-0001 ALP-EPC-00QJA-IC-DSH-0002 ALP-EPC-00QJB-IC-DSH-0001 ALP-EPC-00QJB-IC-DSH-0002 ALP-EPC-00QUA-IC-DSH-0001 ALP-EPC-00SAA-IC-DSH-0001 ALP-EPC-00SAA-IC-DSH-0002 ALP-EPC-00SGA-IC-DSH-0001 ALP-EPC-00SGC-IC-DSH-0001 ALP-EPC-00SGY-IC-BLK-0001 ALP-EPC-00SGY-IC-DSH-0001 ALP-EPC-00UAC-IC-ELY-0002 ALP-EPC-00UAC-IC-HUP-0001 ALP-EPC-00UAC-IC-LOP-0001 ALP-EPC-00UAC-IC-LOP-0002 ALP-EPC-00UBA-IC-ELY-0002 ALP-EPC-00UBA-IC-HUP-0001 ALP-EPC-00UBA-IC-LOP-0001 ALP-EPC-00UBA-IC-LOP-0002 ALP-EPC-00UCA-IC-ELY-0001 ALP-EPC-00UCA-IC-HUP-0001 ALP-EPC-00UCA-IC-LOP-0001 ALP-EPC-00UCA-IC-LOP-0002 ALP-EPC-00UEG-IC-ELY-0001 ALP-EPC-00UEG-IC-HUP-0001 ALP-EPC-00UEG-IC-LOP-0001 ALP-EPC-00UEG-IC-LOP-0002 ALP-EPC-00UEK-IC-ELY-0001 ALP-EPC-00UEK-IC-HUP-0001 ALP-EPC-00UEK-IC-LOP-0001 ALP-EPC-00UEK-IC-LOP-0002 ALP-EPC-00UGA-IC-ELY-0001 ALP-EPC-00UGA-IC-HUP-0001 ALP-EPC-00UGA-IC-LOP-0001 ALP-EPC-00UGA-IC-LOP-0002 ALP-EPC-00UPC-IC-ELY-0001 ALP-EPC-00UPC-IC-HUP-0001 ALP-EPC-00UPC-IC-LOP-0001 ALP-EPC-00UPC-IC-LOP-0002 ALP-EPC-00UQA-IC-ELY-0001 ALP-EPC-00UQA-IC-HUP-0001 ALP-EPC-00UQA-IC-LOP-0001 ALP-EPC-00UQA-IC-LOP-0002 ALP-EPC-00UQA-IC-LOP-0003 ALP-EPC-00UZA-IC-ELY-0001 ALP-EPC-00UZA-IC-HUP-0001 ALP-EPC-00UZA-IC-LOP-0001 ALP-EPC-00UZA-IC-LOP-0002 ALP-EPC-00XJA-IC-DSH-0001 ALP-EPC-10BBT-IC-DSH-0001 ALP-EPC-10HAN-IC-DSH-0001 ALP-EPC-10HAN-IC-DSH-0002 ALP-EPC-10HNE-IC-DSH-0001 ALP-EPC-10HSB-IC-DSH-0001 ALP-EPC-10HSB-IC-DSH-0002 ALP-EPC-10LAB-IC-DSH-0001 ALP-EPC-10LAB-IC-DSH-0002 ALP-EPC-10LAC-IC-DSH-0001 ALP-EPC-10LAC-IC-DSH-0002 ALP-EPC-10LAE-IC-DSH-0001 ALP-EPC-10LAE-IC-DSH-0002 ALP-EPC-10LAF-IC-DSH-0001 ALP-EPC-10LAF-IC-DSH-0002 ALP-EPC-10LBA-IC-DSH-0001 ALP-EPC-10LBB-IC-DSH-0001 ALP-EPC-10LBC-IC-DSH-0001 ALP-EPC-10LBD-IC-DSH-0001 ALP-EPC-10UMA-IC-ELY-0001 ALP-EPC-10UMA-IC-HUP-0001 ALP-EPC-10UMA-IC-LOP-0001 ALP-EPC-10UMA-IC-LOP-0002 ALP-EPC-10UMA-IC-LOP-0003 ALP-EPC-20BBT-IC-DSH-0001 ALP-EPC-20LCA-IC-DSH-0001 ALP-EPC-20LCA-IC-DSH-0002 ALP-EPC-20LCB-IC-DSH-0001 ALP-EPC-20LCB-IC-DSH-0002 ALP-EPC-20MAN-IC-DSH-0001 ALP-EPC-20MAN-IC-DSH-0002 ALP-EPC-20UMB-IC-ELY-0001 ALP-EPC-20UMB-IC-HUP-0001 ALP-EPC-20UMB-IC-LOP-0001 ALP-EPC-20UMB-IC-LOP-0002
ER-12.02 | Automation level | 148 | ALP-EPC-00000-IC-DBR-0001 ALP-EPC-00000-IC-LST-0002 ALP-EPC-00ACA-IC-LOG-0001 ALP-EPC-00BLA-IC-LOG-0001 ALP-EPC-00BMA-IC-LOG-0001 ALP-EPC-00BRA-IC-LOG-0001 ALP-EPC-00BTA-IC-LOG-0001 ALP-EPC-00CJA-IC-LOG-0001 ALP-EPC-00CKA-IC-LOG-0001 ALP-EPC-00CQA-IC-LOG-0001 ALP-EPC-00CYA-IC-LOG-0001 ALP-EPC-00EGA-IC-CNR-0001 ALP-EPC-00EGA-IC-HMI-0001 ALP-EPC-00EGA-IC-LOG-0001 ALP-EPC-00EGB-IC-CNR-0001 ALP-EPC-00EGB-IC-HMI-0001 ALP-EPC-00EGB-IC-LOG-0001 ALP-EPC-00EGC-IC-CNR-0001 ALP-EPC-00EGC-IC-HMI-0001 ALP-EPC-00EGC-IC-LOG-0001 ALP-EPC-00EKA-IC-CNR-0001 ALP-EPC-00EKA-IC-HMI-0001 ALP-EPC-00EKA-IC-LOG-0001 ALP-EPC-00EKC-IC-CNR-0001 ALP-EPC-00EKC-IC-HMI-0001 ALP-EPC-00EKC-IC-LOG-0001 ALP-EPC-00GBA-IC-CNR-0001 ALP-EPC-00GBA-IC-HMI-0001 ALP-EPC-00GCA-IC-CNR-0001 ALP-EPC-00GCA-IC-HMI-0001 ALP-EPC-00GHA-IC-CNR-0001 ALP-EPC-00GHA-IC-HMI-0001 ALP-EPC-00GHA-IC-LOG-0001 ALP-EPC-00GKA-IC-CNR-0001 ALP-EPC-00GKA-IC-HMI-0001 ALP-EPC-00GKA-IC-LOG-0001 ALP-EPC-00GMA-IC-CNR-0001 ALP-EPC-00GMA-IC-HMI-0001 ALP-EPC-00GMA-IC-LOG-0001 ALP-EPC-00GNA-IC-CNR-0001 ALP-EPC-00GNA-IC-HMI-0001 ALP-EPC-00GUA-IC-CNR-0001 ALP-EPC-00GUA-IC-HMI-0001 ALP-EPC-00LBG-IC-CNR-0001 ALP-EPC-00LBG-IC-HMI-0001 ALP-EPC-00LBG-IC-LOG-0001 ALP-EPC-00LDA-IC-CNR-0001 ALP-EPC-00LDA-IC-HMI-0001 ALP-EPC-00PAA-IC-CNR-0001 ALP-EPC-00PAA-IC-HMI-0001 ALP-EPC-00PAA-IC-LOG-0001 ALP-EPC-00PAB-IC-CNR-0001 ALP-EPC-00PAB-IC-HMI-0001 ALP-EPC-00PAB-IC-LOG-0001 ALP-EPC-00PAC-IC-CNR-0001 ALP-EPC-00PAC-IC-HMI-0001 ALP-EPC-00PAC-IC-LOG-0001 ALP-EPC-00PAH-IC-CNR-0001 ALP-EPC-00PAH-IC-HMI-0001 ALP-EPC-00PAH-IC-LOG-0001 ALP-EPC-00PBA-IC-CNR-0001 ALP-EPC-00PBA-IC-HMI-0001 ALP-EPC-00PGA-IC-CNR-0001 ALP-EPC-00PGA-IC-HMI-0001 ALP-EPC-00PGA-IC-LOG-0001 ALP-EPC-00QCA-IC-CNR-0001 ALP-EPC-00QCA-IC-HMI-0001 ALP-EPC-00QCA-IC-LOG-0001 ALP-EPC-00QEA-IC-CNR-0001 ALP-EPC-00QEA-IC-HMI-0001 ALP-EPC-00QHA-IC-CNR-0001 ALP-EPC-00QHA-IC-HMI-0001 ALP-EPC-00QJA-IC-CNR-0001 ALP-EPC-00QJA-IC-HMI-0001 ALP-EPC-00QJA-IC-LOG-0001 ALP-EPC-00QJB-IC-CNR-0001 ALP-EPC-00QJB-IC-HMI-0001 ALP-EPC-00QJB-IC-LOG-0001 ALP-EPC-00QUA-IC-CNR-0001 ALP-EPC-00QUA-IC-HMI-0001 ALP-EPC-00QUA-IC-LOG-0001 ALP-EPC-00SAA-IC-CNR-0001 ALP-EPC-00SAA-IC-HMI-0001 ALP-EPC-00SAA-IC-LOG-0001 ALP-EPC-00SAA-IC-LOG-0002 ALP-EPC-00SGA-IC-CNR-0001 ALP-EPC-00SGA-IC-HMI-0001 ALP-EPC-00SGA-IC-LOG-0001 ALP-EPC-00SGC-IC-CNR-0001 ALP-EPC-00SGC-IC-HMI-0001 ALP-EPC-00SGC-IC-LOG-0001 ALP-EPC-00SGY-IC-LOG-0001 ALP-EPC-00SMA-IC-LOG-0001 ALP-EPC-00XJA-IC-LOG-0001 ALP-EPC-10BBT-IC-LOG-0001 ALP-EPC-10HAN-IC-CNR-0001 ALP-EPC-10HAN-IC-HMI-0001 ALP-EPC-10HAN-IC-LOG-0001 ALP-EPC-10HNE-IC-LOG-0001 ALP-EPC-10HSB-IC-CNR-0001 ALP-EPC-10HSB-IC-HMI-0001 ALP-EPC-10HSB-IC-LOG-0001 ALP-EPC-10LAB-IC-CNR-0001 ALP-EPC-10LAB-IC-HMI-0001 ALP-EPC-10LAB-IC-LOG-0001 ALP-EPC-10LAC-IC-CNR-0001 ALP-EPC-10LAC-IC-HMI-0001 ALP-EPC-10LAC-IC-LOG-0001 ALP-EPC-10LAE-IC-CNR-0001 ALP-EPC-10LAE-IC-HMI-0001 ALP-EPC-10LAE-IC-LOG-0001 ALP-EPC-10LAF-IC-CNR-0001 ALP-EPC-10LAF-IC-HMI-0001 ALP-EPC-10LAF-IC-LOG-0001 ALP-EPC-10LBA-IC-CNR-0001 ALP-EPC-10LBA-IC-HMI-0001 ALP-EPC-10LBA-IC-LOG-0001 ALP-EPC-10LBB-IC-CNR-0001 ALP-EPC-10LBB-IC-HMI-0001 ALP-EPC-10LBB-IC-LOG-0001 ALP-EPC-10LBC-IC-CNR-0001 ALP-EPC-10LBC-IC-HMI-0001 ALP-EPC-10LBC-IC-LOG-0001 ALP-EPC-10LBD-IC-CNR-0001 ALP-EPC-10LBD-IC-HMI-0001 ALP-EPC-10LBD-IC-LOG-0001 ALP-EPC-20BBT-IC-LOG-0001 ALP-EPC-20LCA-IC-CNR-0001 ALP-EPC-20LCA-IC-HMI-0001 ALP-EPC-20LCA-IC-LOG-0001 ALP-EPC-20LCB-IC-CNR-0001 ALP-EPC-20LCB-IC-HMI-0001 ALP-EPC-20LCB-IC-LOG-0001 ALP-EPC-20MAN-IC-CNR-0001 ALP-EPC-20MAN-IC-HMI-0001 ALP-EPC-20MAN-IC-LOG-0001 ALP-I08-00CJG-IC-LOG-0001 ALP-IEC-10MBY-IC-LOG-0001 ALP-IEC-10MBY-IC-LOG-0002 ALP-IEC-10MBY-IC-LOG-0003 ALP-IEC-10MBY-IC-LOG-0004 ALP-IEC-10MBY-IC-LOG-0005 ALP-IEC-10MBY-IC-LOG-0006 ALP-M05-00PBA-IC-LOG-0001 ALP-M08-00QEA-IC-LOG-0001 ALP-M09-00QHA-IC-LOG-0001 ALP-M12-00GBA-IC-LOG-0001 ALP-M14-00GNA-IC-LOG-0001
ER-12.03 | Safety instrumented systems | 30 | ALP-EPC-00000-HS-HAZ-0007 ALP-EPC-00000-IC-LST-0003 ALP-EPC-00000-IC-SPC-0006 ALP-EPC-00EGA-IC-CEM-0001 ALP-EPC-00EGB-IC-CEM-0001 ALP-EPC-00EGC-IC-CEM-0001 ALP-EPC-00EKA-IC-CEM-0001 ALP-EPC-00EKC-IC-CEM-0001 ALP-EPC-00LBG-IC-CEM-0001 ALP-EPC-00QCA-IC-CEM-0001 ALP-EPC-00QEA-IC-CEM-0001 ALP-EPC-00QHA-IC-CEM-0001 ALP-EPC-00QJA-IC-CEM-0001 ALP-EPC-00QJB-IC-CEM-0001 ALP-EPC-00QUA-IC-CEM-0001 ALP-EPC-00SGA-IC-CEM-0001 ALP-EPC-00SGC-IC-CEM-0001 ALP-EPC-10HAN-IC-CEM-0001 ALP-EPC-10HSB-IC-CEM-0001 ALP-EPC-10LAB-IC-CEM-0001 ALP-EPC-10LAC-IC-CEM-0001 ALP-EPC-10LAE-IC-CEM-0001 ALP-EPC-10LAF-IC-CEM-0001 ALP-EPC-10LBA-IC-CEM-0001 ALP-EPC-10LBB-IC-CEM-0001 ALP-EPC-10LBC-IC-CEM-0001 ALP-EPC-10LBD-IC-CEM-0001 ALP-EPC-20LCA-IC-CEM-0001 ALP-EPC-20LCB-IC-CEM-0001 ALP-EPC-20MAN-IC-CEM-0001
ER-12.04 | CEMS | 2 | ALP-EPC-00CQA-IC-SPC-0001 ALP-EPC-00CQA-IC-TRP-0001
ER-12.05 | Historian and performance monitoring | 1 | ALP-EPC-00CKA-IC-BLK-0001
ER-12.06 | Operator training simulator | 1 | ALP-EPC-00CKA-IC-BLK-0001
ER-12.07 | Cybersecurity | 3 | ALP-EPC-00000-IC-RPT-0002 ALP-EPC-00000-IC-TRP-0001 ALP-EPC-00000-IC-TST-0002
ER-12.08 | Time synchronisation | 1 | ALP-EPC-00CJA-IC-BLK-0001
ER-13.01 | Foundations | 62 | ALP-EPC-00000-CV-CAL-0001 ALP-EPC-00000-CV-DBR-0001 ALP-EPC-00000-CV-TRP-0001 ALP-EPC-00000-CV-TST-0001 ALP-EPC-00UAC-CV-CAL-0001 ALP-EPC-00UAC-CV-EFD-0001 ALP-EPC-00UAC-CV-FND-0001 ALP-EPC-00UBA-CV-CAL-0001 ALP-EPC-00UBA-CV-EFD-0001 ALP-EPC-00UBA-CV-FND-0001 ALP-EPC-00UBF-CV-CAL-0001 ALP-EPC-00UBF-CV-EFD-0001 ALP-EPC-00UBF-CV-FND-0001 ALP-EPC-00UBF-CV-FND-0002 ALP-EPC-00UCA-CV-CAL-0001 ALP-EPC-00UCA-CV-FND-0001 ALP-EPC-00UEG-CV-CAL-0001 ALP-EPC-00UEG-CV-EFD-0001 ALP-EPC-00UEG-CV-FND-0001 ALP-EPC-00UEK-CV-CAL-0001 ALP-EPC-00UEK-CV-EFD-0001 ALP-EPC-00UEK-CV-FND-0001 ALP-EPC-00UGA-CV-CAL-0001 ALP-EPC-00UGA-CV-EFD-0001 ALP-EPC-00UGA-CV-FND-0001 ALP-EPC-00UPA-CV-CAL-0001 ALP-EPC-00UPC-CV-CAL-0001 ALP-EPC-00UPC-CV-EFD-0001 ALP-EPC-00UPC-CV-FND-0001 ALP-EPC-00UPC-CV-FND-0002 ALP-EPC-00UQA-CV-CAL-0001 ALP-EPC-00UQA-CV-EFD-0001 ALP-EPC-00UQA-CV-FND-0001 ALP-EPC-00USA-CV-CAL-0001 ALP-EPC-00USA-CV-FND-0001 ALP-EPC-00UYA-CV-CAL-0001 ALP-EPC-00UYA-CV-FND-0001 ALP-EPC-00UZA-CV-CAL-0001 ALP-EPC-00UZB-CV-CAL-0001 ALP-EPC-00UZC-CV-CAL-0001 ALP-EPC-00UZD-CV-CAL-0001 ALP-EPC-00UZD-CV-FND-0001 ALP-EPC-00UZE-CV-CAL-0001 ALP-EPC-00UZF-CV-CAL-0001 ALP-EPC-00UZF-CV-FND-0001 ALP-EPC-00UZF-CV-FND-0002 ALP-EPC-10UHA-CV-CAL-0001 ALP-EPC-10UHA-CV-EFD-0001 ALP-EPC-10UHA-CV-FND-0001 ALP-EPC-10UHA-CV-FND-0002 ALP-EPC-10UHN-CV-CAL-0001 ALP-EPC-10UHN-CV-EFD-0001 ALP-EPC-10UHN-CV-FND-0001 ALP-EPC-10UHN-CV-FND-0002 ALP-EPC-10UMA-CV-CAL-0001 ALP-EPC-10UMA-CV-EFD-0001 ALP-EPC-10UMA-CV-FND-0001 ALP-EPC-10UMA-CV-FND-0002 ALP-EPC-20UMB-CV-CAL-0001 ALP-EPC-20UMB-CV-EFD-0001 ALP-EPC-20UMB-CV-FND-0001 ALP-EPC-20UMB-CV-FND-0002
ER-13.02 | Buildings | 18 | ALP-EPC-00000-CV-DBR-0001 ALP-EPC-00UAC-CV-ARC-0001 ALP-EPC-00UAC-SS-STL-0001 ALP-EPC-00UBA-CV-ARC-0001 ALP-EPC-00UBA-SS-STL-0001 ALP-EPC-00UCA-CV-ARC-0001 ALP-EPC-00UCA-SS-STL-0001 ALP-EPC-00UEK-CV-ARC-0001 ALP-EPC-00UGA-CV-ARC-0001 ALP-EPC-00UGA-SS-STL-0001 ALP-EPC-00UPC-CV-ARC-0001 ALP-EPC-00UQA-CV-ARC-0001 ALP-EPC-00USA-CV-ARC-0001 ALP-EPC-00USA-SS-STL-0001 ALP-EPC-00UYA-CV-ARC-0001 ALP-EPC-00UYA-SS-STL-0001 ALP-EPC-10UMA-CV-ARC-0001 ALP-EPC-20UMB-CV-ARC-0001
ER-13.03 | Structural steel | 74 | ALP-EPC-00000-SS-SPC-0001 ALP-EPC-00EGA-PI-SUP-0001 ALP-EPC-00EGB-PI-SUP-0001 ALP-EPC-00EGC-PI-SUP-0001 ALP-EPC-00EKA-PI-SUP-0001 ALP-EPC-00EKC-PI-SUP-0001 ALP-EPC-00GBA-PI-SUP-0001 ALP-EPC-00GCA-PI-SUP-0001 ALP-EPC-00GHA-PI-SUP-0001 ALP-EPC-00GKA-PI-SUP-0001 ALP-EPC-00GMA-PI-SUP-0001 ALP-EPC-00GNA-PI-SUP-0001 ALP-EPC-00GUA-PI-SUP-0001 ALP-EPC-00LBG-PI-SUP-0001 ALP-EPC-00LDA-PI-SUP-0001 ALP-EPC-00PAA-PI-SUP-0001 ALP-EPC-00PAB-PI-SUP-0001 ALP-EPC-00PAC-PI-SUP-0001 ALP-EPC-00PAH-PI-SUP-0001 ALP-EPC-00PBA-PI-SUP-0001 ALP-EPC-00PGA-PI-SUP-0001 ALP-EPC-00QCA-PI-SUP-0001 ALP-EPC-00QEA-PI-SUP-0001 ALP-EPC-00QHA-PI-SUP-0001 ALP-EPC-00QJA-PI-SUP-0001 ALP-EPC-00QJB-PI-SUP-0001 ALP-EPC-00QUA-PI-SUP-0001 ALP-EPC-00SAA-PI-SUP-0001 ALP-EPC-00SGA-PI-SUP-0001 ALP-EPC-00SGC-PI-SUP-0001 ALP-EPC-00UAC-SS-STL-0002 ALP-EPC-00UBA-SS-STL-0002 ALP-EPC-00UBF-SS-STL-0001 ALP-EPC-00UCA-SS-STL-0002 ALP-EPC-00UEG-SS-STL-0001 ALP-EPC-00UEK-SS-STL-0001 ALP-EPC-00UGA-SS-STL-0002 ALP-EPC-00UPC-SS-STL-0001 ALP-EPC-00UQA-SS-STL-0001 ALP-EPC-00USA-SS-STL-0002 ALP-EPC-00UYA-SS-STL-0002 ALP-EPC-00UZD-SS-STL-0001 ALP-EPC-00UZF-SS-STL-0001 ALP-EPC-10HAN-PI-SUP-0001 ALP-EPC-10HSB-PI-SUP-0001 ALP-EPC-10LAB-PI-SUP-0001 ALP-EPC-10LAC-PI-SUP-0001 ALP-EPC-10LAE-PI-SUP-0001 ALP-EPC-10LAF-PI-SUP-0001 ALP-EPC-10LBA-PI-SUP-0001 ALP-EPC-10LBB-PI-SUP-0001 ALP-EPC-10LBC-PI-SUP-0001 ALP-EPC-10LBD-PI-SUP-0001 ALP-EPC-10UMA-SS-STL-0001 ALP-EPC-20LCA-PI-SUP-0001 ALP-EPC-20LCB-PI-SUP-0001 ALP-EPC-20MAN-PI-SUP-0001 ALP-EPC-20UMB-SS-STL-0001 ALP-S01-00UAC-SS-STL-0001 ALP-S01-00UBA-SS-STL-0001 ALP-S01-00UBF-SS-STL-0001 ALP-S01-00UCA-SS-STL-0001 ALP-S01-00UEG-SS-STL-0001 ALP-S01-00UEK-SS-STL-0001 ALP-S01-00UGA-SS-STL-0001 ALP-S01-00UPC-SS-STL-0001 ALP-S01-00UQA-SS-STL-0001 ALP-S01-00USA-SS-STL-0001 ALP-S01-00UYA-SS-STL-0001 ALP-S01-00UZD-SS-STL-0001 ALP-S01-00UZD-SS-STL-0002 ALP-S01-00UZF-SS-STL-0001 ALP-S01-10UMA-SS-STL-0001 ALP-S01-20UMB-SS-STL-0001
ER-13.04 | Concrete | 21 | ALP-EPC-00000-CV-SPC-0001 ALP-EPC-00UAC-CV-RBR-0001 ALP-EPC-00UBA-CV-RBR-0001 ALP-EPC-00UBF-CV-RBR-0001 ALP-EPC-00UCA-CV-RBR-0001 ALP-EPC-00UEG-CV-RBR-0001 ALP-EPC-00UEK-CV-RBR-0001 ALP-EPC-00UGA-CV-RBR-0001 ALP-EPC-00UPA-CV-RBR-0001 ALP-EPC-00UPC-CV-RBR-0001 ALP-EPC-00UQA-CV-RBR-0001 ALP-EPC-00USA-CV-RBR-0001 ALP-EPC-00UYA-CV-RBR-0001 ALP-EPC-00UZC-CV-RBR-0001 ALP-EPC-00UZD-CV-RBR-0001 ALP-EPC-00UZE-CV-RBR-0001 ALP-EPC-00UZF-CV-RBR-0001 ALP-EPC-10UHA-CV-RBR-0001 ALP-EPC-10UHN-CV-RBR-0001 ALP-EPC-10UMA-CV-RBR-0001 ALP-EPC-20UMB-CV-RBR-0001
ER-13.05 | Roads and drainage | 9 | ALP-EPC-00GKA-PI-PPL-0001 ALP-EPC-00GMA-PI-PPL-0001 ALP-EPC-00PAB-PI-PPL-0001 ALP-EPC-00SGA-PI-PPL-0001 ALP-EPC-00UPA-CV-CVL-0001 ALP-EPC-00UZA-CV-CVL-0002 ALP-EPC-00UZB-CV-CVL-0001 ALP-EPC-00UZC-CV-CVL-0001 ALP-EPC-00UZE-CV-CVL-0001
ER-13.06 | Marine works | 1 | ALP-EPC-00UPA-CV-CVL-0001
ER-14.01 | EIA compliance | 4 | ALP-EPC-00000-HS-PLN-0003 ALP-EPC-00000-HS-PLN-0004 ALP-EPC-00000-HS-RPT-0001 ALP-EPC-00000-PR-LST-0003
ER-14.02 | Air emissions | 2 | ALP-EPC-00000-HS-STU-0002 ALP-EPC-00CQA-IC-SPC-0001
ER-14.03 | Near-field noise | 2 | ALP-EPC-00000-HS-DBR-0001 ALP-EPC-00000-HS-STU-0001
ER-14.04 | Environmental noise | 1 | ALP-EPC-00000-HS-STU-0001
ER-14.05 | Occupational health and safety | 65 | ALP-C01-00000-GE-MOS-0001 ALP-C01-00000-GE-MOS-0002 ALP-C01-00000-GE-MOS-0003 ALP-C01-00000-GE-MOS-0004 ALP-C01-00000-GE-MOS-0005 ALP-C01-00000-GE-MOS-0006 ALP-C02-00000-GE-MOS-0001 ALP-C02-00000-GE-MOS-0002 ALP-C02-00000-GE-MOS-0003 ALP-C02-00000-GE-MOS-0004 ALP-C02-00000-GE-MOS-0005 ALP-C02-00000-GE-MOS-0006 ALP-C03-00UPA-GE-MOS-0001 ALP-C03-00UPA-GE-MOS-0002 ALP-C03-00UPA-GE-MOS-0003 ALP-C03-00UPA-GE-MOS-0004 ALP-C03-00UPA-GE-MOS-0005 ALP-C03-00UPA-GE-MOS-0006 ALP-E12-00000-GE-MOS-0001 ALP-E12-00000-GE-MOS-0002 ALP-E12-00000-GE-MOS-0003 ALP-E12-00000-GE-MOS-0004 ALP-E12-00000-GE-MOS-0005 ALP-E12-00000-GE-MOS-0006 ALP-EPC-00000-HS-DBR-0001 ALP-EPC-00000-HS-PLN-0001 ALP-EPC-00000-HS-PLN-0002 ALP-EPC-00000-HS-PLN-0005 ALP-EPC-00000-HS-RPT-0006 ALP-M17-00EGB-GE-MOS-0001 ALP-M17-00EGB-GE-MOS-0002 ALP-M17-00EGB-GE-MOS-0003 ALP-M17-00EGB-GE-MOS-0004 ALP-M17-00EGB-GE-MOS-0005 ALP-M17-00EGB-GE-MOS-0006 ALP-M22-00000-GE-MOS-0001 ALP-M22-00000-GE-MOS-0002 ALP-M22-00000-GE-MOS-0003 ALP-M22-00000-GE-MOS-0004 ALP-M22-00000-GE-MOS-0005 ALP-M22-00000-GE-MOS-0006 ALP-M23-00000-GE-MOS-0001 ALP-M23-00000-GE-MOS-0002 ALP-M23-00000-GE-MOS-0003 ALP-M23-00000-GE-MOS-0004 ALP-M23-00000-GE-MOS-0005 ALP-M23-00000-GE-MOS-0006 ALP-M24-00UZF-GE-MOS-0001 ALP-M24-00UZF-GE-MOS-0002 ALP-M24-00UZF-GE-MOS-0003 ALP-M24-00UZF-GE-MOS-0004 ALP-M24-00UZF-GE-MOS-0005 ALP-M24-00UZF-GE-MOS-0006 ALP-S01-00000-GE-MOS-0001 ALP-S01-00000-GE-MOS-0002 ALP-S01-00000-GE-MOS-0003 ALP-S01-00000-GE-MOS-0004 ALP-S01-00000-GE-MOS-0005 ALP-S01-00000-GE-MOS-0006 ALP-S02-10HNE-GE-MOS-0001 ALP-S02-10HNE-GE-MOS-0002 ALP-S02-10HNE-GE-MOS-0003 ALP-S02-10HNE-GE-MOS-0004 ALP-S02-10HNE-GE-MOS-0005 ALP-S02-10HNE-GE-MOS-0006
ER-14.06 | Hazardous areas | 3 | ALP-EPC-00000-EL-LST-0004 ALP-EPC-00000-HS-HAZ-0008 ALP-EPC-00000-HS-RPT-0005
ER-14.07 | Process safety studies | 5 | ALP-EPC-00000-HS-DBR-0001 ALP-EPC-00000-HS-HAZ-0002 ALP-EPC-00000-HS-HAZ-0010 ALP-EPC-00000-HS-RPT-0004 ALP-EPC-00000-PR-RPT-0003
ER-14.08 | Carbon capture readiness | 1 | ALP-EPC-00000-PR-STU-0004
ER-15.01 | Quality management | 2 | ALP-EPC-00000-GE-PLN-0003 ALP-EPC-00000-GE-PLN-0005
ER-15.02 | Inspection and test plans | 225 | ALP-C01-00000-GE-ITP-0001 ALP-C02-00000-GE-ITP-0001 ALP-C03-00UPA-GE-ITP-0001 ALP-E12-00000-GE-ITP-0001 ALP-EPC-00000-CV-MRQ-0001 ALP-EPC-00000-CV-MRQ-0002 ALP-EPC-00000-CV-MRQ-0003 ALP-EPC-00000-CV-SPC-0003 ALP-EPC-00000-CV-SPC-0004 ALP-EPC-00000-CV-SPC-0005 ALP-EPC-00000-EL-MRQ-0001 ALP-EPC-00000-EL-MRQ-0002 ALP-EPC-00000-EL-SPC-0004 ALP-EPC-00000-EL-SPC-0005 ALP-EPC-00000-GE-ITP-0001 ALP-EPC-00000-GE-MRQ-0001 ALP-EPC-00000-GE-MRQ-0002 ALP-EPC-00000-GE-MRQ-0003 ALP-EPC-00000-GE-MRQ-0004 ALP-EPC-00000-GE-MRQ-0005 ALP-EPC-00000-GE-MRQ-0006 ALP-EPC-00000-GE-MRQ-0007 ALP-EPC-00000-GE-MRQ-0008 ALP-EPC-00000-GE-RPT-0001 ALP-EPC-00000-GE-RPT-0002 ALP-EPC-00000-GE-RPT-0003 ALP-EPC-00000-GE-RPT-0004 ALP-EPC-00000-GE-RPT-0005 ALP-EPC-00000-GE-RPT-0006 ALP-EPC-00000-GE-RPT-0007 ALP-EPC-00000-GE-RPT-0008 ALP-EPC-00000-GE-RPT-0009 ALP-EPC-00000-GE-RPT-0010 ALP-EPC-00000-GE-RPT-0011 ALP-EPC-00000-GE-RPT-0012 ALP-EPC-00000-GE-RPT-0013 ALP-EPC-00000-GE-RPT-0014 ALP-EPC-00000-GE-RPT-0015 ALP-EPC-00000-GE-RPT-0016 ALP-EPC-00000-GE-SPC-0001 ALP-EPC-00000-GE-SPC-0002 ALP-EPC-00000-GE-SPC-0003 ALP-EPC-00000-GE-SPC-0004 ALP-EPC-00000-GE-SPC-0005 ALP-EPC-00000-GE-SPC-0006 ALP-EPC-00000-GE-SPC-0007 ALP-EPC-00000-GE-SPC-0008 ALP-EPC-00000-IC-MRQ-0001 ALP-EPC-00000-IC-MRQ-0002 ALP-EPC-00000-IC-SPC-0003 ALP-EPC-00000-IC-SPC-0004 ALP-EPC-00000-PI-MRQ-0001 ALP-EPC-00000-PI-MRQ-0002 ALP-EPC-00000-PI-MRQ-0003 ALP-EPC-00000-PI-MRQ-0004 ALP-EPC-00000-PI-SPC-0004 ALP-EPC-00000-PI-SPC-0005 ALP-EPC-00000-PI-SPC-0006 ALP-EPC-00000-PI-SPC-0007 ALP-EPC-00000-SS-MRQ-0001 ALP-EPC-00000-SS-SPC-0002 ALP-EPC-00ACA-EL-ITP-0001 ALP-EPC-00ACA-EL-MRQ-0001 ALP-EPC-00ACA-EL-SPC-0001 ALP-EPC-00ACA-GE-RPT-0001 ALP-EPC-00BBA-EL-ITP-0001 ALP-EPC-00BBA-EL-MRQ-0001 ALP-EPC-00BBA-EL-SPC-0001 ALP-EPC-00BBA-GE-RPT-0001 ALP-EPC-00BFA-EL-ITP-0001 ALP-EPC-00BFA-EL-MRQ-0001 ALP-EPC-00BFA-EL-SPC-0001 ALP-EPC-00BFA-GE-RPT-0001 ALP-EPC-00BFT-EL-ITP-0001 ALP-EPC-00BFT-EL-MRQ-0001 ALP-EPC-00BFT-EL-SPC-0001 ALP-EPC-00BFT-GE-RPT-0001 ALP-EPC-00BLA-GE-RPT-0001 ALP-EPC-00BRA-EL-ITP-0001 ALP-EPC-00BRA-EL-MRQ-0001 ALP-EPC-00BRA-EL-SPC-0001 ALP-EPC-00BRA-GE-RPT-0001 ALP-EPC-00BXA-GE-ITP-0001 ALP-EPC-00BXA-GE-MRQ-0001 ALP-EPC-00BXA-GE-RPT-0001 ALP-EPC-00BXA-GE-SPC-0001 ALP-EPC-00CJA-GE-RPT-0001 ALP-EPC-00CJA-IC-ITP-0001 ALP-EPC-00CJA-IC-MRQ-0001 ALP-EPC-00CJA-IC-SPC-0001 ALP-EPC-00CJG-GE-ITP-0001 ALP-EPC-00CJG-GE-MRQ-0001 ALP-EPC-00CJG-GE-RPT-0001 ALP-EPC-00CJG-GE-SPC-0001 ALP-EPC-00CKA-GE-ITP-0001 ALP-EPC-00CKA-GE-MRQ-0001 ALP-EPC-00CKA-GE-RPT-0001 ALP-EPC-00CKA-GE-SPC-0001 ALP-EPC-00CQA-GE-RPT-0001 ALP-EPC-00CQA-IC-ITP-0001 ALP-EPC-00CQA-IC-MRQ-0001 ALP-EPC-00CQA-IC-SPC-0001 ALP-EPC-00CYA-GE-ITP-0001 ALP-EPC-00CYA-GE-MRQ-0001 ALP-EPC-00CYA-GE-RPT-0001 ALP-EPC-00CYA-GE-SPC-0001 ALP-EPC-00EGA-GE-RPT-0001 ALP-EPC-00EGA-ME-ITP-0001 ALP-EPC-00EGA-ME-MRQ-0001 ALP-EPC-00EGA-ME-SPC-0001 ALP-EPC-00EGB-GE-RPT-0001 ALP-EPC-00EGB-ME-MRQ-0001 ALP-EPC-00EGB-ME-SPC-0001 ALP-EPC-00EKA-GE-RPT-0001 ALP-EPC-00EKA-ME-ITP-0001 ALP-EPC-00EKA-ME-MRQ-0001 ALP-EPC-00EKA-ME-SPC-0001 ALP-EPC-00GBA-GE-RPT-0001 ALP-EPC-00GHA-GE-RPT-0001 ALP-EPC-00GHA-ME-ITP-0001 ALP-EPC-00GHA-ME-MRQ-0001 ALP-EPC-00GHA-ME-SPC-0001 ALP-EPC-00GNA-GE-RPT-0001 ALP-EPC-00GNA-ME-ITP-0001 ALP-EPC-00GNA-ME-MRQ-0001 ALP-EPC-00GNA-ME-SPC-0001 ALP-EPC-00LDA-ME-ITP-0001 ALP-EPC-00LDA-ME-MRQ-0001 ALP-EPC-00LDA-ME-SPC-0001 ALP-EPC-00PAA-GE-RPT-0001 ALP-EPC-00PAA-ME-ITP-0001 ALP-EPC-00PAA-ME-MRQ-0001 ALP-EPC-00PAA-ME-SPC-0001 ALP-EPC-00PAB-GE-RPT-0001 ALP-EPC-00PAC-GE-RPT-0001 ALP-EPC-00PAC-ME-ITP-0001 ALP-EPC-00PAC-ME-MRQ-0001 ALP-EPC-00PAC-ME-SPC-0001 ALP-EPC-00PAH-GE-RPT-0001 ALP-EPC-00PAH-ME-ITP-0001 ALP-EPC-00PAH-ME-MRQ-0001 ALP-EPC-00PAH-ME-SPC-0001 ALP-EPC-00PBA-GE-RPT-0001 ALP-EPC-00PBA-ME-ITP-0001 ALP-EPC-00PBA-ME-MRQ-0001 ALP-EPC-00PBA-ME-SPC-0001 ALP-EPC-00PGA-GE-RPT-0001 ALP-EPC-00PGA-ME-ITP-0001 ALP-EPC-00PGA-ME-MRQ-0001 ALP-EPC-00PGA-ME-SPC-0001 ALP-EPC-00QCA-GE-RPT-0001 ALP-EPC-00QCA-ME-ITP-0001 ALP-EPC-00QCA-ME-MRQ-0001 ALP-EPC-00QCA-ME-SPC-0001 ALP-EPC-00QEA-GE-RPT-0001 ALP-EPC-00QEA-ME-ITP-0001 ALP-EPC-00QEA-ME-MRQ-0001 ALP-EPC-00QEA-ME-SPC-0001 ALP-EPC-00QHA-GE-RPT-0001 ALP-EPC-00QHA-ME-ITP-0001 ALP-EPC-00QHA-ME-MRQ-0001 ALP-EPC-00QHA-ME-SPC-0001 ALP-EPC-00QJA-GE-RPT-0001 ALP-EPC-00QJA-ME-ITP-0001 ALP-EPC-00QJA-ME-MRQ-0001 ALP-EPC-00QJA-ME-SPC-0001 ALP-EPC-00QUA-GE-RPT-0001 ALP-EPC-00QUA-IC-ITP-0001 ALP-EPC-00QUA-IC-MRQ-0001 ALP-EPC-00QUA-IC-SPC-0001 ALP-EPC-00SAA-GE-RPT-0001 ALP-EPC-00SAA-HV-ITP-0001 ALP-EPC-00SAA-HV-MRQ-0001 ALP-EPC-00SAA-HV-SPC-0001 ALP-EPC-00SGA-GE-RPT-0001 ALP-EPC-00SGA-ME-ITP-0001 ALP-EPC-00SGA-ME-MRQ-0001 ALP-EPC-00SGA-ME-SPC-0001 ALP-EPC-00SGY-GE-ITP-0001 ALP-EPC-00SGY-GE-MRQ-0001 ALP-EPC-00SGY-GE-RPT-0001 ALP-EPC-00SGY-GE-SPC-0001 ALP-EPC-00SMA-GE-RPT-0001 ALP-EPC-00SMA-ME-ITP-0001 ALP-EPC-00SMA-ME-MRQ-0001 ALP-EPC-00SMA-ME-SPC-0001 ALP-EPC-00UPA-GE-RPT-0001 ALP-EPC-00UZF-GE-MRQ-0001 ALP-EPC-00UZF-GE-RPT-0001 ALP-EPC-00UZF-GE-SPC-0001 ALP-EPC-00XJA-EL-ITP-0001 ALP-EPC-00XJA-EL-MRQ-0001 ALP-EPC-00XJA-EL-SPC-0001 ALP-EPC-00XJA-GE-RPT-0001 ALP-EPC-10BBT-EL-ITP-0001 ALP-EPC-10BBT-EL-MRQ-0001 ALP-EPC-10BBT-EL-SPC-0001 ALP-EPC-10BBT-GE-RPT-0001 ALP-EPC-10HAN-GE-RPT-0001 ALP-EPC-10HAN-ME-ITP-0001 ALP-EPC-10HAN-ME-MRQ-0001 ALP-EPC-10HAN-ME-SPC-0001 ALP-EPC-10HNE-GE-RPT-0001 ALP-EPC-10HNE-SS-MRQ-0001 ALP-EPC-10HNE-SS-SPC-0001 ALP-EPC-10HSB-GE-RPT-0001 ALP-EPC-10HSB-ME-ITP-0001 ALP-EPC-10HSB-ME-MRQ-0001 ALP-EPC-10HSB-ME-SPC-0001 ALP-EPC-10LAC-GE-RPT-0001 ALP-EPC-10LAC-ME-ITP-0001 ALP-EPC-10LAC-ME-MRQ-0001 ALP-EPC-10LAC-ME-SPC-0001 ALP-EPC-10LBA-GE-RPT-0001 ALP-EPC-20LCB-GE-RPT-0001 ALP-EPC-20LCB-ME-ITP-0001 ALP-EPC-20LCB-ME-MRQ-0001 ALP-EPC-20LCB-ME-SPC-0001 ALP-IEC-10MBA-ME-ITP-0001 ALP-M17-00EGB-GE-ITP-0001 ALP-M22-00000-GE-ITP-0001 ALP-M23-00000-GE-ITP-0001 ALP-M24-00UZF-GE-ITP-0001 ALP-S01-00000-GE-ITP-0001 ALP-S02-10HNE-GE-ITP-0001
ER-15.03 | Factory acceptance tests | 87 | ALP-E01-00ACA-ME-TRP-0001 ALP-E01-00ACA-ME-TST-0001 ALP-E02-10BBT-ME-TRP-0001 ALP-E02-10BBT-ME-TST-0001 ALP-E03-00BBA-ME-TRP-0001 ALP-E03-00BBA-ME-TST-0001 ALP-E04-00BFT-ME-TRP-0001 ALP-E04-00BFT-ME-TST-0001 ALP-E05-00BFA-ME-TRP-0001 ALP-E05-00BFA-ME-TST-0001 ALP-E06-00XJA-ME-TRP-0001 ALP-E06-00XJA-ME-TST-0001 ALP-E07-00BRA-ME-TRP-0001 ALP-E07-00BRA-ME-TST-0001 ALP-E10-00BXA-ME-TRP-0001 ALP-E10-00BXA-ME-TST-0001 ALP-E11-00000-ME-TRP-0001 ALP-E11-00000-ME-TST-0001 ALP-EPC-00000-GE-PLN-0003 ALP-H01-00SAA-ME-TRP-0001 ALP-H01-00SAA-ME-TST-0001 ALP-I01-00CJA-ME-TRP-0001 ALP-I01-00CJA-ME-TST-0001 ALP-I02-00CQA-ME-TRP-0001 ALP-I02-00CQA-ME-TST-0001 ALP-I03-00QUA-ME-TRP-0001 ALP-I03-00QUA-ME-TST-0001 ALP-I06-00SGY-ME-TRP-0001 ALP-I06-00SGY-ME-TST-0001 ALP-I07-00CYA-ME-TRP-0001 ALP-I07-00CYA-ME-TST-0001 ALP-I08-00CJG-ME-TRP-0001 ALP-I08-00CJG-ME-TST-0001 ALP-I09-00CKA-ME-TRP-0001 ALP-I09-00CKA-ME-TST-0001 ALP-IEC-10BAT-ME-TRP-0001 ALP-IEC-10BAT-ME-TST-0001 ALP-IEC-10HAA-ME-TRP-0001 ALP-IEC-10HAA-ME-TST-0001 ALP-IEC-10MBA-ME-TRP-0001 ALP-IEC-10MBA-ME-TST-0001 ALP-IEC-10MBY-ME-TRP-0001 ALP-IEC-10MBY-ME-TST-0001 ALP-IEC-10MKA-ME-TRP-0001 ALP-IEC-10MKA-ME-TST-0001 ALP-IEC-20MAA-ME-TRP-0001 ALP-IEC-20MAA-ME-TST-0001 ALP-M01-10LAC-ME-TRP-0001 ALP-M01-10LAC-ME-TST-0001 ALP-M02-20LCB-ME-TRP-0001 ALP-M02-20LCB-ME-TST-0001 ALP-M03-00PAC-ME-TRP-0001 ALP-M03-00PAC-ME-TST-0001 ALP-M04-00PAA-ME-TRP-0001 ALP-M04-00PAA-ME-TST-0001 ALP-M05-00PBA-ME-TRP-0001 ALP-M05-00PBA-ME-TST-0001 ALP-M06-00PAH-ME-TRP-0001 ALP-M06-00PAH-ME-TST-0001 ALP-M07-00PGA-ME-TRP-0001 ALP-M07-00PGA-ME-TST-0001 ALP-M08-00QEA-ME-TRP-0001 ALP-M08-00QEA-ME-TST-0001 ALP-M09-00QHA-ME-TRP-0001 ALP-M09-00QHA-ME-TST-0001 ALP-M10-00QJA-ME-TRP-0001 ALP-M10-00QJA-ME-TST-0001 ALP-M11-00QCA-ME-TRP-0001 ALP-M11-00QCA-ME-TST-0001 ALP-M12-00GBA-ME-TRP-0001 ALP-M12-00GBA-ME-TST-0001 ALP-M13-00GHA-ME-TRP-0001 ALP-M13-00GHA-ME-TST-0001 ALP-M14-00GNA-ME-TRP-0001 ALP-M14-00GNA-ME-TST-0001 ALP-M15-00EKA-ME-TRP-0001 ALP-M15-00EKA-ME-TST-0001 ALP-M16-00EGA-ME-TRP-0001 ALP-M16-00EGA-ME-TST-0001 ALP-M18-10HSB-ME-TRP-0001 ALP-M18-10HSB-ME-TST-0001 ALP-M19-10HAN-ME-TRP-0001 ALP-M19-10HAN-ME-TST-0001 ALP-M20-00SGA-ME-TRP-0001 ALP-M20-00SGA-ME-TST-0001 ALP-M21-00SMA-ME-TRP-0001 ALP-M21-00SMA-ME-TST-0001
ER-15.04 | Material traceability | 80 | ALP-E01-00ACA-ME-MDB-0001 ALP-E02-10BBT-ME-MDB-0001 ALP-E03-00BBA-ME-MDB-0001 ALP-E04-00BFT-ME-MDB-0001 ALP-E05-00BFA-ME-MDB-0001 ALP-E06-00XJA-ME-MDB-0001 ALP-E07-00BRA-ME-MDB-0001 ALP-E08-00000-ME-MDB-0001 ALP-E09-00BLA-ME-MDB-0001 ALP-E10-00BXA-ME-MDB-0001 ALP-E11-00000-ME-MDB-0001 ALP-EPC-00000-PI-SPC-0003 ALP-EPC-00EGA-PR-DSH-0001 ALP-EPC-00EGB-PR-DSH-0001 ALP-EPC-00EGC-PR-DSH-0001 ALP-EPC-00EKA-PR-DSH-0001 ALP-EPC-00EKC-PR-DSH-0001 ALP-EPC-00GBA-PR-DSH-0001 ALP-EPC-00GCA-PR-DSH-0001 ALP-EPC-00GHA-PR-DSH-0001 ALP-EPC-00LBG-PR-DSH-0001 ALP-EPC-00LDA-PR-DSH-0001 ALP-EPC-00PGA-PR-DSH-0001 ALP-EPC-00QCA-PR-DSH-0001 ALP-EPC-00QEA-PR-DSH-0001 ALP-EPC-00QHA-PR-DSH-0001 ALP-EPC-00QJA-PR-DSH-0001 ALP-EPC-00QJB-PR-DSH-0001 ALP-EPC-00SAA-PR-DSH-0001 ALP-EPC-00SGA-PR-DSH-0001 ALP-EPC-10HAN-PR-DSH-0001 ALP-EPC-10HSB-PR-DSH-0001 ALP-EPC-10LAB-PR-DSH-0001 ALP-EPC-10LAC-PR-DSH-0001 ALP-EPC-20LCA-PR-DSH-0001 ALP-EPC-20MAN-PR-DSH-0001 ALP-H01-00SAA-ME-MDB-0001 ALP-I01-00CJA-ME-MDB-0001 ALP-I02-00CQA-ME-MDB-0001 ALP-I03-00QUA-ME-MDB-0001 ALP-I04-00000-ME-MDB-0001 ALP-I05-00000-ME-MDB-0001 ALP-I06-00SGY-ME-MDB-0001 ALP-I07-00CYA-ME-MDB-0001 ALP-I08-00CJG-ME-MDB-0001 ALP-I09-00CKA-ME-MDB-0001 ALP-I10-00000-ME-MDB-0001 ALP-IEC-10BAT-ME-MDB-0001 ALP-IEC-10HAA-ME-MDB-0001 ALP-IEC-10MBA-ME-MDB-0001 ALP-IEC-10MBY-ME-MDB-0001 ALP-IEC-10MKA-ME-MDB-0001 ALP-IEC-20MAA-ME-MDB-0001 ALP-M01-10LAC-ME-MDB-0001 ALP-M02-20LCB-ME-MDB-0001 ALP-M03-00PAC-ME-MDB-0001 ALP-M04-00PAA-ME-MDB-0001 ALP-M05-00PBA-ME-MDB-0001 ALP-M06-00PAH-ME-MDB-0001 ALP-M07-00PGA-ME-MDB-0001 ALP-M08-00QEA-ME-MDB-0001 ALP-M09-00QHA-ME-MDB-0001 ALP-M10-00QJA-ME-MDB-0001 ALP-M11-00QCA-ME-MDB-0001 ALP-M12-00GBA-ME-MDB-0001 ALP-M13-00GHA-ME-MDB-0001 ALP-M14-00GNA-ME-MDB-0001 ALP-M15-00EKA-ME-MDB-0001 ALP-M16-00EGA-ME-MDB-0001 ALP-M18-10HSB-ME-MDB-0001 ALP-M19-10HAN-ME-MDB-0001 ALP-M20-00SGA-ME-MDB-0001 ALP-M21-00SMA-ME-MDB-0001 ALP-P01-00000-ME-MDB-0001 ALP-P02-10LBA-ME-MDB-0001 ALP-P03-00000-ME-MDB-0001 ALP-P04-00PAB-ME-MDB-0001 ALP-P05-00000-ME-MDB-0001 ALP-P06-00000-ME-MDB-0001 ALP-P07-00000-ME-MDB-0001
ER-15.05 | Welding | 1 | ALP-EPC-00000-PI-SPC-0003
ER-16.01 | Commissioning plan | 162 | ALP-EPC-00000-CM-PLN-0001 ALP-EPC-00000-CM-PRC-0002 ALP-EPC-00ACA-CM-CMP-0001 ALP-EPC-00ACA-CM-MDB-0001 ALP-EPC-00BBA-CM-CMP-0001 ALP-EPC-00BBA-CM-MDB-0001 ALP-EPC-00BFA-CM-CMP-0001 ALP-EPC-00BFA-CM-MDB-0001 ALP-EPC-00BFT-CM-CMP-0001 ALP-EPC-00BFT-CM-MDB-0001 ALP-EPC-00BLA-CM-CMP-0001 ALP-EPC-00BLA-CM-MDB-0001 ALP-EPC-00BMA-CM-CMP-0001 ALP-EPC-00BMA-CM-MDB-0001 ALP-EPC-00BRA-CM-CMP-0001 ALP-EPC-00BRA-CM-MDB-0001 ALP-EPC-00BTA-CM-CMP-0001 ALP-EPC-00BTA-CM-MDB-0001 ALP-EPC-00BXA-CM-CMP-0001 ALP-EPC-00BXA-CM-MDB-0001 ALP-EPC-00CJA-CM-CMP-0001 ALP-EPC-00CJA-CM-MDB-0001 ALP-EPC-00CJG-CM-CMP-0001 ALP-EPC-00CJG-CM-MDB-0001 ALP-EPC-00CKA-CM-CMP-0001 ALP-EPC-00CKA-CM-MDB-0001 ALP-EPC-00CQA-CM-CMP-0001 ALP-EPC-00CQA-CM-MDB-0001 ALP-EPC-00CYA-CM-CMP-0001 ALP-EPC-00CYA-CM-MDB-0001 ALP-EPC-00EGA-CM-CMP-0001 ALP-EPC-00EGA-CM-MDB-0001 ALP-EPC-00EGB-CM-CMP-0001 ALP-EPC-00EGB-CM-MDB-0001 ALP-EPC-00EGC-CM-CMP-0001 ALP-EPC-00EGC-CM-MDB-0001 ALP-EPC-00EKA-CM-CMP-0001 ALP-EPC-00EKA-CM-MDB-0001 ALP-EPC-00EKC-CM-CMP-0001 ALP-EPC-00EKC-CM-MDB-0001 ALP-EPC-00GBA-CM-CMP-0001 ALP-EPC-00GBA-CM-MDB-0001 ALP-EPC-00GCA-CM-CMP-0001 ALP-EPC-00GCA-CM-MDB-0001 ALP-EPC-00GHA-CM-CMP-0001 ALP-EPC-00GHA-CM-MDB-0001 ALP-EPC-00GKA-CM-CMP-0001 ALP-EPC-00GKA-CM-MDB-0001 ALP-EPC-00GMA-CM-CMP-0001 ALP-EPC-00GMA-CM-MDB-0001 ALP-EPC-00GNA-CM-CMP-0001 ALP-EPC-00GNA-CM-MDB-0001 ALP-EPC-00GQA-CM-MDB-0001 ALP-EPC-00GUA-CM-CMP-0001 ALP-EPC-00GUA-CM-MDB-0001 ALP-EPC-00LBG-CM-CMP-0001 ALP-EPC-00LBG-CM-MDB-0001 ALP-EPC-00LDA-CM-CMP-0001 ALP-EPC-00LDA-CM-MDB-0001 ALP-EPC-00PAA-CM-CMP-0001 ALP-EPC-00PAA-CM-MDB-0001 ALP-EPC-00PAB-CM-CMP-0001 ALP-EPC-00PAB-CM-MDB-0001 ALP-EPC-00PAC-CM-CMP-0001 ALP-EPC-00PAC-CM-MDB-0001 ALP-EPC-00PAH-CM-CMP-0001 ALP-EPC-00PAH-CM-MDB-0001 ALP-EPC-00PBA-CM-CMP-0001 ALP-EPC-00PBA-CM-MDB-0001 ALP-EPC-00PGA-CM-CMP-0001 ALP-EPC-00PGA-CM-MDB-0001 ALP-EPC-00QCA-CM-CMP-0001 ALP-EPC-00QCA-CM-MDB-0001 ALP-EPC-00QEA-CM-CMP-0001 ALP-EPC-00QEA-CM-MDB-0001 ALP-EPC-00QHA-CM-CMP-0001 ALP-EPC-00QHA-CM-MDB-0001 ALP-EPC-00QJA-CM-CMP-0001 ALP-EPC-00QJA-CM-MDB-0001 ALP-EPC-00QJB-CM-CMP-0001 ALP-EPC-00QJB-CM-MDB-0001 ALP-EPC-00QUA-CM-CMP-0001 ALP-EPC-00QUA-CM-MDB-0001 ALP-EPC-00SAA-CM-CMP-0001 ALP-EPC-00SAA-CM-MDB-0001 ALP-EPC-00SGA-CM-CMP-0001 ALP-EPC-00SGA-CM-MDB-0001 ALP-EPC-00SGC-CM-CMP-0001 ALP-EPC-00SGC-CM-MDB-0001 ALP-EPC-00SGY-CM-CMP-0001 ALP-EPC-00SGY-CM-MDB-0001 ALP-EPC-00SMA-CM-CMP-0001 ALP-EPC-00SMA-CM-MDB-0001 ALP-EPC-00XJA-CM-CMP-0001 ALP-EPC-00XJA-CM-MDB-0001 ALP-EPC-10BAA-CM-MDB-0001 ALP-EPC-10BAC-CM-MDB-0001 ALP-EPC-10BAT-CM-MDB-0001 ALP-EPC-10BBT-CM-CMP-0001 ALP-EPC-10BBT-CM-MDB-0001 ALP-EPC-10HAA-CM-MDB-0001 ALP-EPC-10HAN-CM-CMP-0001 ALP-EPC-10HAN-CM-MDB-0001 ALP-EPC-10HNA-CM-MDB-0001 ALP-EPC-10HNE-CM-CMP-0001 ALP-EPC-10HNE-CM-MDB-0001 ALP-EPC-10HSA-CM-MDB-0001 ALP-EPC-10HSB-CM-CMP-0001 ALP-EPC-10HSB-CM-MDB-0001 ALP-EPC-10LAB-CM-CMP-0001 ALP-EPC-10LAB-CM-MDB-0001 ALP-EPC-10LAC-CM-CMP-0001 ALP-EPC-10LAC-CM-MDB-0001 ALP-EPC-10LAE-CM-CMP-0001 ALP-EPC-10LAE-CM-MDB-0001 ALP-EPC-10LAF-CM-CMP-0001 ALP-EPC-10LAF-CM-MDB-0001 ALP-EPC-10LBA-CM-CMP-0001 ALP-EPC-10LBA-CM-MDB-0001 ALP-EPC-10LBB-CM-CMP-0001 ALP-EPC-10LBB-CM-MDB-0001 ALP-EPC-10LBC-CM-CMP-0001 ALP-EPC-10LBC-CM-MDB-0001 ALP-EPC-10LBD-CM-CMP-0001 ALP-EPC-10LBD-CM-MDB-0001 ALP-EPC-10MBA-CM-MDB-0001 ALP-EPC-10MBL-CM-MDB-0001 ALP-EPC-10MBN-CM-MDB-0001 ALP-EPC-10MBP-CM-MDB-0001 ALP-EPC-10MBU-CM-MDB-0001 ALP-EPC-10MBV-CM-MDB-0001 ALP-EPC-10MBY-CM-MDB-0001 ALP-EPC-10MKA-CM-MDB-0001 ALP-EPC-10MKC-CM-MDB-0001 ALP-EPC-10MKG-CM-MDB-0001 ALP-EPC-20BAA-CM-MDB-0001 ALP-EPC-20BAC-CM-MDB-0001 ALP-EPC-20BAT-CM-MDB-0001 ALP-EPC-20BBT-CM-CMP-0001 ALP-EPC-20BBT-CM-MDB-0001 ALP-EPC-20LCA-CM-CMP-0001 ALP-EPC-20LCA-CM-MDB-0001 ALP-EPC-20LCB-CM-CMP-0001 ALP-EPC-20LCB-CM-MDB-0001 ALP-EPC-20MAA-CM-MDB-0001 ALP-EPC-20MAB-CM-MDB-0001 ALP-EPC-20MAG-CM-MDB-0001 ALP-EPC-20MAJ-CM-MDB-0001 ALP-EPC-20MAN-CM-CMP-0001 ALP-EPC-20MAN-CM-MDB-0001 ALP-EPC-20MAV-CM-MDB-0001 ALP-EPC-20MAW-CM-MDB-0001 ALP-EPC-20MAX-CM-MDB-0001 ALP-EPC-20MAY-CM-MDB-0001 ALP-EPC-20MKA-CM-MDB-0001 ALP-EPC-20MKC-CM-MDB-0001 ALP-IEC-10BAT-CM-CMP-0001 ALP-IEC-10HAA-CM-CMP-0001 ALP-IEC-10MBA-CM-CMP-0001 ALP-IEC-10MBY-CM-CMP-0001 ALP-IEC-10MKA-CM-CMP-0001 ALP-IEC-20MAA-CM-CMP-0001
ER-16.02 | Steam blowing and chemical cleaning | 2 | ALP-EPC-00000-CM-CMP-0001 ALP-EPC-00000-CM-TRP-0001
ER-16.03 | Grid Code compliance tests | 2 | ALP-EPC-00000-CM-CMP-0003 ALP-EPC-00000-CM-TRP-0003
ER-16.04 | Performance test | 2 | ALP-EPC-00000-CM-CMP-0002 ALP-EPC-00000-CM-TRP-0002
ER-16.05 | Emission and noise tests | 2 | ALP-EPC-00000-CM-CMP-0006 ALP-EPC-00000-CM-TRP-0006
ER-16.06 | Operational demonstration | 2 | ALP-EPC-00000-CM-CMP-0004 ALP-EPC-00000-CM-TRP-0004
ER-16.07 | Reliability run | 2 | ALP-EPC-00000-CM-CMP-0004 ALP-EPC-00000-CM-TRP-0004
ER-16.08 | Tests on LDO | 2 | ALP-EPC-00000-CM-CMP-0005 ALP-EPC-00000-CM-TRP-0005
ER-17.01 | Document management | 1 | ALP-EPC-00000-GE-PRC-0002
ER-17.02 | Schedule and reporting | 1 | ALP-EPC-00000-PC-SCH-0001
ER-17.03 | As-built documentation | 3 | ALP-EPC-00000-GE-LST-0005 ALP-EPC-00000-GE-PRC-0003 ALP-EPC-00000-PI-M3D-0004
ER-17.04 | O&M manuals | 103 | ALP-E01-00ACA-ME-OMM-0001 ALP-E02-10BBT-ME-OMM-0001 ALP-E03-00BBA-ME-OMM-0001 ALP-E04-00BFT-ME-OMM-0001 ALP-E05-00BFA-ME-OMM-0001 ALP-E06-00XJA-ME-OMM-0001 ALP-E07-00BRA-ME-OMM-0001 ALP-E10-00BXA-ME-OMM-0001 ALP-E11-00000-ME-OMM-0001 ALP-EPC-00000-CM-OMM-0001 ALP-EPC-00ACA-CM-OMM-0001 ALP-EPC-00BBA-CM-OMM-0001 ALP-EPC-00BFA-CM-OMM-0001 ALP-EPC-00BFT-CM-OMM-0001 ALP-EPC-00BLA-CM-OMM-0001 ALP-EPC-00BMA-CM-OMM-0001 ALP-EPC-00BRA-CM-OMM-0001 ALP-EPC-00BTA-CM-OMM-0001 ALP-EPC-00CJA-CM-OMM-0001 ALP-EPC-00CJG-CM-OMM-0001 ALP-EPC-00CKA-CM-OMM-0001 ALP-EPC-00CQA-CM-OMM-0001 ALP-EPC-00CYA-CM-OMM-0001 ALP-EPC-00EGA-CM-OMM-0001 ALP-EPC-00EGB-CM-OMM-0001 ALP-EPC-00EGC-CM-OMM-0001 ALP-EPC-00EKA-CM-OMM-0001 ALP-EPC-00EKC-CM-OMM-0001 ALP-EPC-00GBA-CM-OMM-0001 ALP-EPC-00GCA-CM-OMM-0001 ALP-EPC-00GHA-CM-OMM-0001 ALP-EPC-00GKA-CM-OMM-0001 ALP-EPC-00GMA-CM-OMM-0001 ALP-EPC-00GNA-CM-OMM-0001 ALP-EPC-00GUA-CM-OMM-0001 ALP-EPC-00LBG-CM-OMM-0001 ALP-EPC-00LDA-CM-OMM-0001 ALP-EPC-00PAA-CM-OMM-0001 ALP-EPC-00PAB-CM-OMM-0001 ALP-EPC-00PAC-CM-OMM-0001 ALP-EPC-00PAH-CM-OMM-0001 ALP-EPC-00PBA-CM-OMM-0001 ALP-EPC-00PGA-CM-OMM-0001 ALP-EPC-00QCA-CM-OMM-0001 ALP-EPC-00QEA-CM-OMM-0001 ALP-EPC-00QHA-CM-OMM-0001 ALP-EPC-00QJA-CM-OMM-0001 ALP-EPC-00QJB-CM-OMM-0001 ALP-EPC-00QUA-CM-OMM-0001 ALP-EPC-00SAA-CM-OMM-0001 ALP-EPC-00SGA-CM-OMM-0001 ALP-EPC-00SGC-CM-OMM-0001 ALP-EPC-00SGY-CM-OMM-0001 ALP-EPC-00XJA-CM-OMM-0001 ALP-EPC-10BBT-CM-OMM-0001 ALP-EPC-10HAN-CM-OMM-0001 ALP-EPC-10HSB-CM-OMM-0001 ALP-EPC-10LAB-CM-OMM-0001 ALP-EPC-10LAC-CM-OMM-0001 ALP-EPC-10LAE-CM-OMM-0001 ALP-EPC-10LAF-CM-OMM-0001 ALP-EPC-10LBA-CM-OMM-0001 ALP-EPC-10LBB-CM-OMM-0001 ALP-EPC-10LBC-CM-OMM-0001 ALP-EPC-10LBD-CM-OMM-0001 ALP-EPC-20BBT-CM-OMM-0001 ALP-EPC-20LCA-CM-OMM-0001 ALP-EPC-20LCB-CM-OMM-0001 ALP-EPC-20MAN-CM-OMM-0001 ALP-H01-00SAA-ME-OMM-0001 ALP-I01-00CJA-ME-OMM-0001 ALP-I02-00CQA-ME-OMM-0001 ALP-I03-00QUA-ME-OMM-0001 ALP-I06-00SGY-ME-OMM-0001 ALP-I07-00CYA-ME-OMM-0001 ALP-I08-00CJG-ME-OMM-0001 ALP-I09-00CKA-ME-OMM-0001 ALP-IEC-10BAT-ME-OMM-0001 ALP-IEC-10HAA-ME-OMM-0001 ALP-IEC-10MBA-ME-OMM-0001 ALP-IEC-10MBY-ME-OMM-0001 ALP-IEC-10MKA-ME-OMM-0001 ALP-IEC-20MAA-ME-OMM-0001 ALP-M01-10LAC-ME-OMM-0001 ALP-M02-20LCB-ME-OMM-0001 ALP-M03-00PAC-ME-OMM-0001 ALP-M04-00PAA-ME-OMM-0001 ALP-M05-00PBA-ME-OMM-0001 ALP-M06-00PAH-ME-OMM-0001 ALP-M07-00PGA-ME-OMM-0001 ALP-M08-00QEA-ME-OMM-0001 ALP-M09-00QHA-ME-OMM-0001 ALP-M10-00QJA-ME-OMM-0001 ALP-M11-00QCA-ME-OMM-0001 ALP-M12-00GBA-ME-OMM-0001 ALP-M13-00GHA-ME-OMM-0001 ALP-M14-00GNA-ME-OMM-0001 ALP-M15-00EKA-ME-OMM-0001 ALP-M16-00EGA-ME-OMM-0001 ALP-M18-10HSB-ME-OMM-0001 ALP-M19-10HAN-ME-OMM-0001 ALP-M20-00SGA-ME-OMM-0001 ALP-M21-00SMA-ME-OMM-0001
ER-17.05 | Training | 2 | ALP-EPC-00000-CM-OMM-0002 ALP-EPC-00000-CM-PLN-0002
ER-17.06 | Spare parts | 45 | ALP-E01-00ACA-ME-LST-0001 ALP-E02-10BBT-ME-LST-0001 ALP-E03-00BBA-ME-LST-0001 ALP-E04-00BFT-ME-LST-0001 ALP-E05-00BFA-ME-LST-0001 ALP-E06-00XJA-ME-LST-0001 ALP-E07-00BRA-ME-LST-0001 ALP-E10-00BXA-ME-LST-0001 ALP-E11-00000-ME-LST-0001 ALP-EPC-00000-CM-LST-0002 ALP-EPC-00000-CM-LST-0004 ALP-H01-00SAA-ME-LST-0001 ALP-I01-00CJA-ME-LST-0001 ALP-I02-00CQA-ME-LST-0001 ALP-I03-00QUA-ME-LST-0001 ALP-I06-00SGY-ME-LST-0001 ALP-I07-00CYA-ME-LST-0001 ALP-I08-00CJG-ME-LST-0001 ALP-I09-00CKA-ME-LST-0001 ALP-IEC-10BAT-ME-LST-0001 ALP-IEC-10HAA-ME-LST-0001 ALP-IEC-10MBA-ME-LST-0001 ALP-IEC-10MBY-ME-LST-0001 ALP-IEC-10MKA-ME-LST-0001 ALP-IEC-20MAA-ME-LST-0001 ALP-M01-10LAC-ME-LST-0001 ALP-M02-20LCB-ME-LST-0001 ALP-M03-00PAC-ME-LST-0001 ALP-M04-00PAA-ME-LST-0001 ALP-M05-00PBA-ME-LST-0001 ALP-M06-00PAH-ME-LST-0001 ALP-M07-00PGA-ME-LST-0001 ALP-M08-00QEA-ME-LST-0001 ALP-M09-00QHA-ME-LST-0001 ALP-M10-00QJA-ME-LST-0001 ALP-M11-00QCA-ME-LST-0001 ALP-M12-00GBA-ME-LST-0001 ALP-M13-00GHA-ME-LST-0001 ALP-M14-00GNA-ME-LST-0001 ALP-M15-00EKA-ME-LST-0001 ALP-M16-00EGA-ME-LST-0001 ALP-M18-10HSB-ME-LST-0001 ALP-M19-10HAN-ME-LST-0001 ALP-M20-00SGA-ME-LST-0001 ALP-M21-00SMA-ME-LST-0001
ER-17.07 | Long-term service | 1 | ALP-IEC-10MBA-ME-RPT-0001
ER-18.01 | Terminal points | 1 | ALP-EPC-00000-GE-LST-0003
ER-18.02 | Grid connection interface | 1 | ALP-EPC-00000-EL-STU-0006
ER-18.03 | Gas network interface | 1 | ALP-EPC-00EKA-ME-SPC-0001
ER-18.04 | Owner's engineering database | 1 | ALP-EPC-00000-GE-PRC-0003
ER-18.05 | Tie-in register | 1 | ALP-EPC-00000-GE-LST-0003

## Coverage scope
Alpilla 600 MW Combined Cycle Power Plant - Coverage: scope items (Owner contract SC-, consortium split DR-)
engine engineering_plan v1.6.0 ¦ generated 2026-09-29T03:49:44Z by EPCE ¦ data 73eaa92ce7c1ff26 ¦ dates computed from the workflow network and the CPM (working days)
Item | Area | Scope | Design | Docs | Documents
DR-001 | Gas turbine and fuel | Gas turbine package incl. enclosure, lube oil, hydraulic and fuel skids | IEC | 2 | ALP-IEC-10MBA-ME-DSH-0001 ALP-IEC-10MBA-PR-PID-0001
DR-002 | Gas turbine and fuel | GT inlet air filter house, anti-icing, silencer, inlet duct | IEC | 1 | ALP-IEC-10MBA-PR-PID-0001
DR-003 | Gas turbine and fuel | GT exhaust diffuser and expansion joint to HRSG | IEC | 3 | ALP-IEC-10HAA-PR-PID-0001 ALP-IEC-10MBA-ME-GAD-0001 ALP-IEC-10MBA-PR-PID-0001
DR-004 | Gas turbine and fuel | Performance fuel gas heater and GT gas skid (from IF-01) | IEC | 1 | ALP-IEC-10MBA-PR-PID-0001
DR-005 | Gas turbine and fuel | Gas receiving and metering station, start-up gas heating, final filtration 3 um | IEPC | 2 | ALP-EPC-00EKA-PR-PID-0001 ALP-EPC-00EKA-PR-SDS-0001
DR-006 | Gas turbine and fuel | Liquid fuel skid, water injection skid, purge and recirculation (from IF-02/03) | IEC | 1 | ALP-IEC-10MBA-PR-PID-0001
DR-007 | Gas turbine and fuel | LDO unloading, storage, forwarding and treatment | IEPC | 4 | ALP-EPC-00EGA-PR-PID-0001 ALP-EPC-00EGB-PR-PID-0001 ALP-EPC-00EGC-PR-PID-0001 ALP-EPC-00EGC-PR-SDS-0001
DR-008 | Gas turbine and fuel | Compressor washing skid | IEC | 1 | ALP-IEC-10MBA-PR-PID-0001
DR-009 | Gas turbine and fuel | GT enclosure fire suppression (CO2) and gas detection | IEC | 3 | ALP-EPC-00SGC-PR-PID-0001 ALP-IEC-10MBA-ME-DSH-0001 ALP-IEC-10MBA-PR-PID-0001
DR-010 | HRSG | HRSG pressure parts, casing, drums, platforms, CPH recirculation pumps | IEC | 2 | ALP-IEC-10HAA-ME-DSH-0001 ALP-IEC-10HAA-PR-PID-0001
DR-011 | HRSG | SCR catalyst, ammonia injection grid and skid, CO catalyst | IEC | 1 | ALP-IEC-10HAA-PR-PID-0001
DR-012 | HRSG | Aqueous ammonia unloading, storage and forwarding | IEPC | 2 | ALP-EPC-10HSB-PR-PID-0001 ALP-EPC-10HSB-PR-SDS-0001
DR-013 | HRSG | HRSG blowdown tanks, drain tanks, atmospheric flash tanks | IEPC | 2 | ALP-EPC-10HAN-PR-PID-0001 ALP-EPC-10HAN-PR-SDS-0001
DR-014 | HRSG | Chemical dosing and steam/water sampling (SWAS) | IEPC | 4 | ALP-EPC-00QCA-PR-PID-0001 ALP-EPC-00QCA-PR-SDS-0001 ALP-EPC-00QUA-PR-PID-0001 ALP-EPC-00QUA-PR-SDS-0001
DR-015 | HRSG | Stack incl. silencer, CEMS, aviation lighting | IEPC | 2 | ALP-EPC-00CQA-IC-BLK-0001 ALP-EPC-10HNE-SS-SPC-0001
DR-016 | Steam turbine and steam piping | Steam turbine with valves, lube/EHC oil, gland steam system, turning gear | IEC | 2 | ALP-IEC-20MAA-ME-DSH-0001 ALP-IEC-20MAA-PR-PID-0001
DR-017 | Steam turbine and steam piping | HP / IP / LP bypass valves with desuperheaters | IEC | 2 | ALP-EPC-20MAN-PR-PID-0001 ALP-IEC-20MAA-PR-PID-0001
DR-018 | Steam turbine and steam piping | HP, cold reheat, hot reheat and LP steam piping HRSG - ST incl. supports | IEPC | 8 | ALP-EPC-10LBA-PR-PID-0001 ALP-EPC-10LBA-PR-SDS-0001 ALP-EPC-10LBB-PR-PID-0001 ALP-EPC-10LBB-PR-SDS-0001 ALP-EPC-10LBC-PR-PID-0001 ALP-EPC-10LBC-PR-SDS-0001 ALP-EPC-10LBD-PR-PID-0001 ALP-EPC-10LBD-PR-SDS-0001
DR-019 | Steam turbine and steam piping | Bypass piping and spray water piping | IEPC | 6 | ALP-EPC-10LAE-PR-PID-0001 ALP-EPC-10LAE-PR-SDS-0001 ALP-EPC-10LAF-PR-PID-0001 ALP-EPC-10LAF-PR-SDS-0001 ALP-EPC-20MAN-PR-PID-0001 ALP-EPC-20MAN-PR-SDS-0001
DR-020 | Steam turbine and steam piping | ST drains, drain collection and flash tank | IEPC | 2 | ALP-EPC-20MAN-PR-SDS-0001 ALP-IEC-20MAA-PR-PID-0001
DR-021 | Condenser and cycle | Condenser incl. dump devices, hotwell, vacuum pumps | IEC | 2 | ALP-IEC-20MAA-PR-PID-0001 ALP-IEC-20MAG-ME-DSH-0001
DR-022 | Condenser and cycle | Tube cleaning ball system and debris filters | IEPC | 2 | ALP-EPC-00PAH-PR-PID-0001 ALP-EPC-00PAH-PR-SDS-0001
DR-023 | Condenser and cycle | Circulating water system, intake, pumps, outfall, electro-chlorination | IEPC | 6 | ALP-EPC-00PAA-PR-PID-0001 ALP-EPC-00PAB-PR-PID-0001 ALP-EPC-00PAC-PR-PID-0001 ALP-EPC-00PAC-PR-SDS-0001 ALP-EPC-00PBA-PR-PID-0001 ALP-EPC-00UPA-CV-CVL-0001
DR-024 | Condenser and cycle | Condensate pumps, boiler feed pumps, condensate polishing | IEPC | 6 | ALP-EPC-00LDA-PR-PID-0001 ALP-EPC-00LDA-PR-SDS-0001 ALP-EPC-10LAC-PR-PID-0001 ALP-EPC-10LAC-PR-SDS-0001 ALP-EPC-20LCB-PR-PID-0001 ALP-EPC-20LCB-PR-SDS-0001
DR-025 | Condenser and cycle | Closed cooling water system | IEPC | 2 | ALP-EPC-00PGA-PR-PID-0001 ALP-EPC-00PGA-PR-SDS-0001
DR-026 | Electrical | GT and ST generators incl. excitation, neutral earthing | IEC | 2 | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-PR-PID-0001
DR-027 | Electrical | Generator circuit breakers, isolated phase busducts | IEC | 2 | ALP-IEC-10BAA-EL-SLD-0001 ALP-IEC-10MKA-PR-PID-0001
DR-028 | Electrical | GT and ST generator step-up transformers | IEC | 2 | ALP-IEC-10BAT-EL-DSH-0001 ALP-IEC-10BAT-EL-GAD-0001
DR-029 | Electrical | SFC and isolation transformer | IEC | 2 | ALP-IEC-10BAA-EL-SLD-0001 ALP-IEC-10MKA-PR-PID-0001
DR-030 | Electrical | Generator and GSU protection panels | IEC | 2 | ALP-IEC-10BAA-EL-SLD-0001 ALP-IEC-10MKA-PR-PID-0001
DR-031 | Electrical | H2 and CO2 bottle racks and supply piping | IEPC | 2 | ALP-EPC-00QJB-PR-PID-0001 ALP-EPC-00QJB-PR-SDS-0001
DR-032 | Electrical | Unit auxiliary transformers, MV/LV switchgear, UPS/DC, cabling | IEPC | 5 | ALP-E02-10BBT-ME-GAD-0001 ALP-E07-00BRA-ME-GAD-0001 ALP-EPC-00BBA-EL-SLD-0001 ALP-EPC-00BFA-EL-SLD-0001 ALP-EPC-00BRA-EL-SLD-0001
DR-033 | Electrical | 380 kV connection GSU - GIS, GIS switchyard | IEPC | 1 | ALP-EPC-00ACA-EL-SLD-0001
DR-034 | I&C | Turbine control system (TCS) for GT, ST, generators, HRSG protection (SIS) | IEC | 2 | ALP-IEC-10MBY-IC-BLK-0001 ALP-IEC-10MBY-ME-GAD-0001
DR-035 | I&C | Plant DCS incl. HRSG and BOP control, operator stations | IEPC | 1 | ALP-EPC-00CJA-IC-BLK-0001
DR-036 | I&C | CEMS | IEPC | 1 | ALP-EPC-00CQA-IC-BLK-0001
DR-037 | I&C | Vibration and performance monitoring, remote diagnostics | IEC | 2 | ALP-EPC-00CKA-IC-BLK-0001 ALP-IEC-10MBY-IC-BLK-0001
DR-038 | Civil | Foundations of IEC equipment (GT, generators, ST, HRSG, condenser, GSUs) | IEPC | 3 | ALP-EPC-10UHA-CV-FND-0001 ALP-EPC-10UMA-CV-FND-0002 ALP-EPC-20UMB-CV-FND-0002
DR-039 | Civil | Turbine hall(s), cranes, HRSG access structures beyond IEC platforms | IEPC | 4 | ALP-EPC-10UMA-CV-FND-0002 ALP-EPC-10UMA-SS-STL-0001 ALP-EPC-20UMB-CV-FND-0002 ALP-M21-00SMA-ME-GAD-0001
DR-040 | Transport, tests, training | Transport of IEC equipment to site (incl. heavy transport, barge, SPMT) |  | 2 | ALP-EPC-00000-ME-LST-0001 ALP-EPC-00000-ME-STU-0001
DR-041 | Transport, tests, training | Performance test | IEPC | 1 | ALP-EPC-00000-CM-CMP-0002
DR-042 | Transport, tests, training | Training of Owner staff on IEC equipment | IEC | 3 | ALP-EPC-00000-CM-OMM-0002 ALP-EPC-00000-CM-PLN-0002 ALP-IEC-10MBA-ME-OMM-0001
SC-001 | Site | Land, access rights and site handover (levelled to +15.0 m) | OWNER | 0
SC-002 | Site | Environmental Impact Assessment (EIA) positive decision | OWNER | 0
SC-003 | Site | Construction, operating and building permits (Contractor supplies all design inputs) | IEPC | 1 | ALP-EPC-00000-GE-LST-0002
SC-004 | Site | Geotechnical and topographic surveys (baseline supplied by Owner, confirmatory by Contractor) | IEPC | 2 | ALP-EPC-00000-CV-RPT-0001 ALP-EPC-00000-CV-RPT-0003
SC-005 | Site | Site preparation, fencing, roads, drainage, temporary facilities | IEPC | 4 | ALP-EPC-00UZA-CV-CVL-0001 ALP-EPC-00UZA-CV-CVL-0002 ALP-EPC-00UZB-CV-CVL-0001 ALP-EPC-00UZC-CV-CVL-0001
SC-006 | Power island | Gas turbine package incl. auxiliaries, enclosure, inlet air filtration, exhaust diffuser | IEC | 2 | ALP-IEC-10MBA-ME-DSH-0001 ALP-IEC-10MBA-PR-PID-0001
SC-007 | Power island | GT generator incl. excitation, protection, cooling | IEC | 2 | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-PR-PID-0001
SC-008 | Power island | Steam turbine (HP/IP/LP, reheat) incl. lube/control oil, gland steam, turning gear | IEC | 2 | ALP-IEC-20MAA-ME-DSH-0001 ALP-IEC-20MAA-PR-PID-0001
SC-009 | Power island | ST generator incl. excitation, protection | IEC | 2 | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-PR-PID-0001
SC-010 | Power island | HRSG triple-pressure reheat, horizontal, natural circulation, with SCR and CO catalyst | IEC | 2 | ALP-IEC-10HAA-ME-DSH-0001 ALP-IEC-10HAA-PR-PID-0001
SC-011 | Power island | Stack 65 m with CEMS platform and silencer | IEPC | 1 | ALP-EPC-10HNE-SS-SPC-0001
SC-012 | Power island | Water-cooled condenser (seawater), vacuum system | IEC | 2 | ALP-IEC-20MAA-PR-PID-0001 ALP-IEC-20MAG-ME-DSH-0001
SC-013 | Power island | Power island control system (TCS) by IEC, integrated with the plant DCS: native graphics and alarms on the DCS operator stations, one KKS tag database, common time synchronisation, separate IEC 62443 zone (IF-40) | IEC | 2 | ALP-IEC-10MBY-IC-BLK-0001 ALP-IEC-10MBY-ME-GAD-0001
SC-014 | Power island | GSU transformers (GT and ST), isolated phase busducts, generator circuit breakers | IEC | 4 | ALP-IEC-10BAA-EL-SLD-0001 ALP-IEC-10BAT-EL-DSH-0001 ALP-IEC-10BAT-EL-GAD-0001 ALP-IEC-10MKA-PR-PID-0001
SC-015 | Balance of plant | Condensate and boiler feed water systems (pumps 2x100 %) | IEPC | 6 | ALP-EPC-10LAB-PR-PID-0001 ALP-EPC-10LAC-PR-PID-0001 ALP-EPC-10LAC-PR-SDS-0001 ALP-EPC-20LCA-PR-PID-0001 ALP-EPC-20LCB-PR-PID-0001 ALP-EPC-20LCB-PR-SDS-0001
SC-016 | Balance of plant | Seawater intake, screens, CW pumps (2x50 %), outfall and diffuser | IEPC | 5 | ALP-EPC-00PAA-PR-PID-0001 ALP-EPC-00PAA-PR-SDS-0001 ALP-EPC-00PAC-PR-PID-0001 ALP-EPC-00PAC-PR-SDS-0001 ALP-EPC-00UPA-CV-CVL-0001
SC-017 | Balance of plant | Electro-chlorination for biofouling control | IEPC | 2 | ALP-EPC-00PBA-PR-PID-0001 ALP-EPC-00PBA-PR-SDS-0001
SC-018 | Balance of plant | Seawater reverse osmosis and demineralisation plant | IEPC | 4 | ALP-EPC-00GBA-PR-PID-0001 ALP-EPC-00GBA-PR-SDS-0001 ALP-EPC-00GCA-PR-PID-0001 ALP-EPC-00GCA-PR-SDS-0001
SC-019 | Balance of plant | Condensate polishing plant | IEPC | 2 | ALP-EPC-00LDA-PR-PID-0001 ALP-EPC-00LDA-PR-SDS-0001
SC-020 | Balance of plant | Waste water treatment and effluent monitoring | IEPC | 2 | ALP-EPC-00GNA-PR-PID-0001 ALP-EPC-00GNA-PR-SDS-0001
SC-021 | Balance of plant | Closed cooling water system with plate heat exchangers | IEPC | 2 | ALP-EPC-00PGA-PR-PID-0001 ALP-EPC-00PGA-PR-SDS-0001
SC-022 | Balance of plant | Compressed air (service and instrument) 2x100 % | IEPC | 2 | ALP-EPC-00QEA-PR-PID-0001 ALP-EPC-00QEA-PR-SDS-0001
SC-023 | Balance of plant | Auxiliary boiler (gas-fired) for start-up steam | IEPC | 2 | ALP-EPC-00QHA-PR-PID-0001 ALP-EPC-00QHA-PR-SDS-0001
SC-024 | Balance of plant | Fire detection and protection per NFPA 850 | IEPC | 5 | ALP-EPC-00000-HS-HAZ-0009 ALP-EPC-00SGA-PR-PID-0001 ALP-EPC-00SGA-PR-SDS-0001 ALP-EPC-00SGC-PR-PID-0001 ALP-EPC-00SGY-IC-BLK-0001
SC-025 | Balance of plant | HVAC for all buildings and electrical rooms | IEPC | 2 | ALP-EPC-00SAA-HV-PID-0001 ALP-EPC-00SAA-HV-SDS-0001
SC-026 | Balance of plant | Cranes and hoists (turbine hall EOT crane) | IEPC | 2 | ALP-EPC-00SMA-ME-SPC-0001 ALP-M21-00SMA-ME-GAD-0001
SC-027 | Fuel gas | Gas pipeline from national transmission system to plant boundary | OWNER | 0
SC-028 | Fuel gas | Gas receiving and metering station (fiscal metering, filtration, heating, pressure control) | IEPC | 2 | ALP-EPC-00EKA-PR-PID-0001 ALP-EPC-00EKA-PR-SDS-0001
SC-029 | Fuel gas | Performance gas heater and GT fuel skid | IEC | 1 | ALP-IEC-10MBA-PR-PID-0001
SC-030 | Electrical | 380 kV GIS switchyard (double busbar) within plant boundary | IEPC | 1 | ALP-EPC-00ACA-EL-SLD-0001
SC-031 | Electrical | 380 kV transmission connection line and remote substation works | OWNER | 0
SC-032 | Electrical | Unit auxiliary transformers, MV switchgear 10.5 kV, LV 0.4 kV distribution | IEPC | 3 | ALP-E02-10BBT-ME-GAD-0001 ALP-EPC-00BBA-EL-SLD-0001 ALP-EPC-00BFA-EL-SLD-0001
SC-033 | Electrical | Emergency diesel generator and UPS / DC systems | IEPC | 4 | ALP-E06-00XJA-ME-GAD-0001 ALP-E07-00BRA-ME-GAD-0001 ALP-EPC-00BMA-EL-SLD-0001 ALP-EPC-00BRA-EL-SLD-0001
SC-034 | Electrical | Earthing, lightning protection, cabling, cable trays | IEPC | 3 | ALP-EPC-00000-EL-SPC-0001 ALP-EPC-00000-EL-STU-0003 ALP-EPC-00BXA-GE-SPC-0001
SC-035 | Electrical | Revenue metering and TSO SCADA/telecom interface | IEPC | 3 | ALP-EPC-00000-EL-SPC-0003 ALP-EPC-00ACA-EL-SLD-0001 ALP-EPC-00CYA-IC-BLK-0001
SC-036 | I&C | Plant DCS, historian, operator training simulator | IEPC | 2 | ALP-EPC-00CJA-IC-BLK-0001 ALP-EPC-00CKA-IC-BLK-0001
SC-037 | I&C | Safety instrumented systems (burner management, HRSG protection) per IEC 61511 | IEC | 3 | ALP-EPC-00000-HS-HAZ-0007 ALP-EPC-00CJG-IC-BLK-0001 ALP-IEC-10MBY-IC-BLK-0001
SC-038 | I&C | Continuous emission monitoring system (CEMS) | IEPC | 1 | ALP-EPC-00CQA-IC-BLK-0001
SC-039 | I&C | Plant security, CCTV, access control, cybersecurity (IEC 62443) | IEPC | 2 | ALP-EPC-00000-IC-RPT-0002 ALP-EPC-00CYA-IC-BLK-0001
SC-040 | Civil | Piling, foundations, structures, turbine hall, HRSG structure | IEPC | 5 | ALP-EPC-00000-CV-DBR-0001 ALP-EPC-10UHA-CV-FND-0001 ALP-EPC-10UHN-CV-FND-0001 ALP-EPC-10UMA-CV-FND-0002 ALP-EPC-20UMB-CV-FND-0002
SC-041 | Civil | Buildings: control, administration, workshop/warehouse, water treatment, gatehouse | IEPC | 5 | ALP-EPC-00UCA-CV-ARC-0001 ALP-EPC-00UCA-CV-FND-0001 ALP-EPC-00UGA-CV-FND-0001 ALP-EPC-00USA-CV-FND-0001 ALP-EPC-00UYA-CV-FND-0001
SC-042 | Civil | Marine works for intake and outfall (dredging, pipes, heads) | IEPC | 1 | ALP-EPC-00UPA-CV-CVL-0001
SC-043 | Utilities | Potable water connection at site boundary (no sewer available) | OWNER | 0
SC-044 | Utilities | Telecommunication connection (fibre) to site boundary | OWNER | 0
SC-045 | Utilities | Construction power and water | IEPC | 1 | ALP-EPC-00UZA-CV-CVL-0001
SC-046 | Commissioning | Consumables until Taking-Over (except natural gas) | IEPC | 1 | ALP-EPC-00000-CM-PLN-0001
SC-047 | Commissioning | Natural gas for commissioning and tests | OWNER | 0
SC-048 | Commissioning | Grid access for back-feed and test energy; purchase of test energy | OWNER | 0
SC-049 | Commissioning | Operation and maintenance staff for training and commissioning participation | OWNER | 0
SC-050 | Spares | Commissioning spares and special tools | IEPC | 1 | ALP-EPC-00000-CM-LST-0002
SC-051 | Spares | Two-year operating spares (priced list, Owner option) | IEPC | 2 | ALP-EPC-00000-CM-LST-0002 ALP-EPC-00000-CM-LST-0004
SC-052 | Fuel oil | LDO truck unloading station (4 bays), storage tanks 2 x 50 %, bund, foam system | IEPC | 4 | ALP-EPC-00EGA-PR-PID-0001 ALP-EPC-00EGA-PR-SDS-0001 ALP-EPC-00EGB-PR-PID-0001 ALP-EPC-00EGB-PR-SDS-0001
SC-053 | Fuel oil | LDO forwarding pumps, filters, metering, fuel treatment (2 x 100 % centrifugal separators) | IEPC | 2 | ALP-EPC-00EGC-PR-PID-0001 ALP-EPC-00EGC-PR-SDS-0001
SC-054 | Power island | Dual-fuel GT combustion system, liquid fuel skid, water injection skid, purge system | IEC | 1 | ALP-IEC-10MBA-PR-PID-0001
SC-055 | Commissioning | LDO first fill of the storage tanks | OWNER | 0
SC-056 | Commissioning | LDO for tests beyond the first fill |  | 1 | ALP-EPC-00000-CM-CMP-0005
SC-057 | Balance of plant | Packaged sanitary wastewater treatment plant (biological + UV), discharge via outfall | IEPC | 2 | ALP-EPC-00GUA-PR-PID-0001 ALP-EPC-00GUA-PR-SDS-0001

## Plant assets
Alpilla 600 MW Combined Cycle Power Plant - Plant assets: KKS tag, datasheet, PWP, CWP, CWA
engine engineering_plan v1.6.0 ¦ generated 2026-09-29T03:49:44Z by EPCE ¦ data 73eaa92ce7c1ff26 ¦ dates computed from the workflow network and the CPM (working days)
Tag | Description | System | Supply | Datasheet | MR | CWP | CWA
00ACA10 | 380 kV GIS, double busbar, 6 bays | 00ACA | IEPC | ALP-E01-00ACA-IC-DSH-0001 ALP-E01-00ACA-ME-DSH-0001 ALP-EPC-00ACA-EL-DSH-0001 | MR-EL-001 | CWP-04-EL-01 | CWA-04
00BBA10 | MV switchgear 10.5 kV, section A | 00BBA | IEPC | ALP-E03-00BBA-ME-DSH-0001 ALP-EPC-00BBA-EL-DSH-0001 | MR-EL-003 | CWP-03-EL-01 | CWA-03
00BBA20 | MV switchgear 10.5 kV, section B | 00BBA | IEPC | ALP-E03-00BBA-ME-DSH-0001 ALP-EPC-00BBA-EL-DSH-0001 | MR-EL-003 | CWP-03-EL-01 | CWA-03
00BFA10 | LV main switchboard 0.42 kV - GT and HRSG, A | 00BFA | IEPC | ALP-E05-00BFA-ME-DSH-0001 ALP-EPC-00BFA-EL-DSH-0001 | MR-EL-005 | CWP-03-EL-01 | CWA-03
00BFA11 | LV main switchboard 0.42 kV - ST and cooling, A | 00BFA | IEPC | ALP-E05-00BFA-ME-DSH-0001 ALP-EPC-00BFA-EL-DSH-0001 | MR-EL-005 | CWP-03-EL-01 | CWA-03
00BFA12 | LV main switchboard 0.42 kV - BOP, fuel and buildings, A | 00BFA | IEPC | ALP-E05-00BFA-ME-DSH-0001 ALP-EPC-00BFA-EL-DSH-0001 | MR-EL-005 | CWP-03-EL-01 | CWA-03
00BFA20 | LV main switchboard 0.42 kV - GT and HRSG, B | 00BFA | IEPC | ALP-E05-00BFA-ME-DSH-0001 ALP-EPC-00BFA-EL-DSH-0001 | MR-EL-005 | CWP-03-EL-01 | CWA-03
00BFA21 | LV main switchboard 0.42 kV - ST and cooling, B | 00BFA | IEPC | ALP-E05-00BFA-ME-DSH-0001 ALP-EPC-00BFA-EL-DSH-0001 | MR-EL-005 | CWP-03-EL-01 | CWA-03
00BFA22 | LV main switchboard 0.42 kV - BOP, fuel and buildings, B | 00BFA | IEPC | ALP-E05-00BFA-ME-DSH-0001 ALP-EPC-00BFA-EL-DSH-0001 | MR-EL-005 | CWP-03-EL-01 | CWA-03
00BFA30 | LV MCC - power block | 00BFA | IEPC | ALP-E05-00BFA-ME-DSH-0001 ALP-EPC-00BFA-EL-DSH-0001 | MR-EL-005 | CWP-03-EL-01 | CWA-03
00BFA40 | LV MCC - CW pump house | 00BFA | IEPC | ALP-E05-00BFA-ME-DSH-0001 ALP-EPC-00BFA-EL-DSH-0001 | MR-EL-005 | CWP-03-EL-01 | CWA-03
00BFA50 | LV MCC - water treatment | 00BFA | IEPC | ALP-E05-00BFA-ME-DSH-0001 ALP-EPC-00BFA-EL-DSH-0001 | MR-EL-005 | CWP-03-EL-01 | CWA-03
00BFA60 | LV MCC - BOP utilities | 00BFA | IEPC | ALP-E05-00BFA-ME-DSH-0001 ALP-EPC-00BFA-EL-DSH-0001 | MR-EL-005 | CWP-03-EL-01 | CWA-03
00BFA70 | LV MCC - fuel gas and LDO | 00BFA | IEPC | ALP-E05-00BFA-ME-DSH-0001 ALP-EPC-00BFA-EL-DSH-0001 | MR-EL-005 | CWP-03-EL-01 | CWA-03
00BFA80 | LV MCC - buildings and HVAC | 00BFA | IEPC | ALP-E05-00BFA-ME-DSH-0001 ALP-EPC-00BFA-EL-DSH-0001 | MR-EL-005 | CWP-03-EL-01 | CWA-03
00BFT10 | LV transformer 10.5/0.42 kV 3.15 MVA - GT and HRSG, A | 00BFT | IEPC | ALP-E04-00BFT-ME-DSH-0001 ALP-EPC-00BFT-EL-DSH-0001 | MR-EL-004 | CWP-03-EL-01 | CWA-03
00BFT20 | LV transformer 10.5/0.42 kV 3.15 MVA - GT and HRSG, B | 00BFT | IEPC | ALP-E04-00BFT-ME-DSH-0001 ALP-EPC-00BFT-EL-DSH-0001 | MR-EL-004 | CWP-03-EL-01 | CWA-03
00BFT30 | LV transformer 10.5/0.42 kV 3.15 MVA - BOP, fuel and buildings, A | 00BFT | IEPC | ALP-E04-00BFT-ME-DSH-0001 ALP-EPC-00BFT-EL-DSH-0001 | MR-EL-004 | CWP-03-EL-01 | CWA-03
00BFT40 | LV transformer 10.5/0.42 kV 3.15 MVA - BOP, fuel and buildings, B | 00BFT | IEPC | ALP-E04-00BFT-ME-DSH-0001 ALP-EPC-00BFT-EL-DSH-0001 | MR-EL-004 | CWP-03-EL-01 | CWA-03
00BFT50 | LV transformer 10.5/0.42 kV 1.0 MVA - CW intake, A | 00BFT | IEPC | ALP-E04-00BFT-ME-DSH-0001 ALP-EPC-00BFT-EL-DSH-0001 | MR-EL-004 | CWP-03-EL-01 | CWA-03
00BFT60 | LV transformer 10.5/0.42 kV 1.0 MVA - CW intake, B | 00BFT | IEPC | ALP-E04-00BFT-ME-DSH-0001 ALP-EPC-00BFT-EL-DSH-0001 | MR-EL-004 | CWP-03-EL-01 | CWA-03
00BFT70 | LV transformer 10.5/0.42 kV 1.6 MVA - ST and cooling, A | 00BFT | IEPC | ALP-E04-00BFT-ME-DSH-0001 ALP-EPC-00BFT-EL-DSH-0001 | MR-EL-004 | CWP-03-EL-01 | CWA-03
00BFT80 | LV transformer 10.5/0.42 kV 1.6 MVA - ST and cooling, B | 00BFT | IEPC | ALP-E04-00BFT-ME-DSH-0001 ALP-EPC-00BFT-EL-DSH-0001 | MR-EL-004 | CWP-03-EL-01 | CWA-03
00BMA10 | Emergency LV switchboard | 00BMA | IEPC | ALP-E05-00BFA-ME-DSH-0001 ALP-EPC-00BMA-EL-DSH-0001 | MR-EL-005 | CWP-03-EL-01 | CWA-03
00BMA20 | Emergency MCC - power block | 00BMA | IEPC | ALP-E05-00BFA-ME-DSH-0001 ALP-EPC-00BMA-EL-DSH-0001 | MR-EL-005 | CWP-03-EL-01 | CWA-03
00BRA10 | UPS 230 V AC (2 x 100 %) | 00BRA | IEPC | ALP-E07-00BRA-ME-DSH-0001 ALP-EPC-00BRA-EL-DSH-0001 | MR-EL-007 | CWP-03-EL-01 | CWA-03
00BRA20 | DC 220 V distribution board | 00BRA | IEPC | ALP-E05-00BFA-ME-DSH-0001 ALP-EPC-00BRA-EL-DSH-0002 | MR-EL-005 | CWP-03-EL-01 | CWA-03
00BTA10 | Battery and charger 220 V DC (2 x 100 %) | 00BTA | IEPC | ALP-E07-00BRA-ME-DSH-0001 ALP-EPC-00BTA-EL-DSH-0001 | MR-EL-007 | CWP-03-EL-01 | CWA-03
00CJA10 | Plant DCS (controllers, networks, operator stations) | 00CJA | IEPC | ALP-EPC-00CJA-IC-DSH-0001 ALP-I01-00CJA-ME-DSH-0001 | MR-IC-001 | CWP-11-IC-01 | CWA-11
00CJA20 | DCS remote I/O cabinets - power block | 00CJA | IEPC | ALP-EPC-00CJA-IC-DSH-0001 ALP-I01-00CJA-ME-DSH-0001 | MR-IC-001 | CWP-11-IC-01 | CWA-11
00CJA30 | DCS remote I/O cabinets - CW pump house | 00CJA | IEPC | ALP-EPC-00CJA-IC-DSH-0001 ALP-I01-00CJA-ME-DSH-0001 | MR-IC-001 | CWP-11-IC-01 | CWA-11
00CJA40 | DCS remote I/O cabinets - water treatment | 00CJA | IEPC | ALP-EPC-00CJA-IC-DSH-0001 ALP-I01-00CJA-ME-DSH-0001 | MR-IC-001 | CWP-11-IC-01 | CWA-11
00CJA50 | DCS remote I/O cabinets - BOP utilities | 00CJA | IEPC | ALP-EPC-00CJA-IC-DSH-0001 ALP-I01-00CJA-ME-DSH-0001 | MR-IC-001 | CWP-11-IC-01 | CWA-11
00CJA60 | DCS remote I/O cabinets - fuel gas and LDO | 00CJA | IEPC | ALP-EPC-00CJA-IC-DSH-0001 ALP-I01-00CJA-ME-DSH-0001 | MR-IC-001 | CWP-11-IC-01 | CWA-11
00CJG10 | BOP safety instrumented system (logic solver and cabinets) | 00CJG | IEPC | ALP-EPC-00CJG-IC-DSH-0001 ALP-I08-00CJG-ME-DSH-0001 | MR-IC-008 | CWP-11-IC-01 | CWA-11
00CKA10 | Historian, performance monitoring and operator training simulator | 00CKA | IEPC | ALP-EPC-00CKA-IC-DSH-0001 ALP-I09-00CKA-ME-DSH-0001 | MR-IC-009 | CWP-11-IC-01 | CWA-11
00CQA10 | Continuous emission monitoring system | 00CQA | IEPC | ALP-EPC-00CQA-IC-DSH-0001 ALP-I02-00CQA-IC-DSH-0001 ALP-I02-00CQA-ME-DSH-0001 | MR-IC-002 | CWP-01-IC-01 | CWA-01
00CYA10 | Telecom, CCTV, access control and security system | 00CYA | IEPC | ALP-EPC-00CYA-IC-DSH-0001 ALP-I07-00CYA-ME-DSH-0001 | MR-IC-007 | CWP-11-IC-01 | CWA-11
00EGA10 | LDO unloading station (4 bays) | 00EGA | IEPC | ALP-EPC-00EGA-ME-DSH-0001 ALP-M16-00EGA-IC-DSH-0001 ALP-M16-00EGA-ME-DSH-0001 | MR-ME-016 | CWP-10-ME-01 | CWA-10
00EGA10AP001 | LDO unloading pump A | 00EGA | IEPC | ALP-EPC-00EGA-ME-DSH-0003 ALP-M16-00EGA-IC-DSH-0001 ALP-M16-00EGA-ME-DSH-0001 | MR-ME-016 | CWP-10-ME-01 | CWA-10
00EGA10AP002 | LDO unloading pump B | 00EGA | IEPC | ALP-EPC-00EGA-ME-DSH-0003 ALP-M16-00EGA-IC-DSH-0001 ALP-M16-00EGA-ME-DSH-0001 | MR-ME-016 | CWP-10-ME-01 | CWA-10
00EGA10AP003 | LDO unloading pump C | 00EGA | IEPC | ALP-EPC-00EGA-ME-DSH-0003 ALP-M16-00EGA-IC-DSH-0001 ALP-M16-00EGA-ME-DSH-0001 | MR-ME-016 | CWP-10-ME-01 | CWA-10
00EGA10AP004 | LDO unloading pump D | 00EGA | IEPC | ALP-EPC-00EGA-ME-DSH-0003 ALP-M16-00EGA-IC-DSH-0001 ALP-M16-00EGA-ME-DSH-0001 | MR-ME-016 | CWP-10-ME-01 | CWA-10
00EGA10AT001 | LDO unloading basket filter A | 00EGA | IEPC | ALP-EPC-00EGA-ME-DSH-0002 ALP-M16-00EGA-IC-DSH-0001 ALP-M16-00EGA-ME-DSH-0001 | MR-ME-016 | CWP-10-ME-01 | CWA-10
00EGA10AT002 | LDO unloading basket filter B | 00EGA | IEPC | ALP-EPC-00EGA-ME-DSH-0002 ALP-M16-00EGA-IC-DSH-0001 ALP-M16-00EGA-ME-DSH-0001 | MR-ME-016 | CWP-10-ME-01 | CWA-10
00EGA10BB001 | LDO unloading slop tank | 00EGA | IEPC | ALP-EPC-00EGA-ME-DSH-0004 ALP-M16-00EGA-IC-DSH-0001 ALP-M16-00EGA-ME-DSH-0001 | MR-ME-016 | CWP-10-ME-01 | CWA-10
00EGB10BB001 | LDO storage tank A 3,800 m3 | 00EGB | IEPC | ALP-EPC-00EGB-ME-DSH-0001 | MR-ME-017 | CWP-10-ME-01 | CWA-10
00EGB10BB002 | LDO storage tank B 3,800 m3 | 00EGB | IEPC | ALP-EPC-00EGB-ME-DSH-0001 | MR-ME-017 | CWP-10-ME-01 | CWA-10
00EGB10BB003 | LDO tank farm recovery sump | 00EGB | IEPC | ALP-EPC-00EGB-ME-DSH-0001 | MR-ME-017 | CWP-10-ME-01 | CWA-10
00EGC10 | LDO forwarding and treatment skid | 00EGC | IEPC | ALP-EPC-00EGC-ME-DSH-0001 ALP-M16-00EGA-IC-DSH-0001 ALP-M16-00EGA-ME-DSH-0001 | MR-ME-016 | CWP-10-ME-01 | CWA-10
00EGC10AP001 | LDO forwarding pump A (3 x 50 %) | 00EGC | IEPC | ALP-EPC-00EGC-ME-DSH-0003 ALP-M16-00EGA-IC-DSH-0001 ALP-M16-00EGA-ME-DSH-0001 | MR-ME-016 | CWP-10-ME-01 | CWA-10
00EGC10AP002 | LDO forwarding pump B (3 x 50 %) | 00EGC | IEPC | ALP-EPC-00EGC-ME-DSH-0003 ALP-M16-00EGA-IC-DSH-0001 ALP-M16-00EGA-ME-DSH-0001 | MR-ME-016 | CWP-10-ME-01 | CWA-10
00EGC10AP003 | LDO forwarding pump C (3 x 50 %) | 00EGC | IEPC | ALP-EPC-00EGC-ME-DSH-0003 ALP-M16-00EGA-IC-DSH-0001 ALP-M16-00EGA-ME-DSH-0001 | MR-ME-016 | CWP-10-ME-01 | CWA-10
00EGC10AT001 | LDO duplex filter A | 00EGC | IEPC | ALP-EPC-00EGC-ME-DSH-0002 ALP-M16-00EGA-IC-DSH-0001 ALP-M16-00EGA-ME-DSH-0001 | MR-ME-016 | CWP-10-ME-01 | CWA-10
00EGC10AT002 | LDO duplex filter B | 00EGC | IEPC | ALP-EPC-00EGC-ME-DSH-0002 ALP-M16-00EGA-IC-DSH-0001 ALP-M16-00EGA-ME-DSH-0001 | MR-ME-016 | CWP-10-ME-01 | CWA-10
00EGC10AT003 | LDO treatment centrifuge | 00EGC | IEPC | ALP-EPC-00EGC-ME-DSH-0002 ALP-M16-00EGA-IC-DSH-0001 ALP-M16-00EGA-ME-DSH-0001 | MR-ME-016 | CWP-10-ME-01 | CWA-10
00EKA10 | Gas receiving, filtration and fiscal metering station | 00EKA | IEPC | ALP-EPC-00EKA-ME-DSH-0001 ALP-M15-00EKA-IC-DSH-0001 ALP-M15-00EKA-ME-DSH-0001 | MR-ME-015 | CWP-09-ME-01 | CWA-09
00EKA10AC001 | Gas preheater A (indirect water-bath, gas-fired) | 00EKA | IEPC | ALP-EPC-00EKA-ME-DSH-0003 ALP-M15-00EKA-IC-DSH-0001 ALP-M15-00EKA-ME-DSH-0001 | MR-ME-015 | CWP-09-ME-01 | CWA-09
00EKA10AC002 | Gas preheater B (indirect water-bath, gas-fired) | 00EKA | IEPC | ALP-EPC-00EKA-ME-DSH-0003 ALP-M15-00EKA-IC-DSH-0001 ALP-M15-00EKA-ME-DSH-0001 | MR-ME-015 | CWP-09-ME-01 | CWA-09
00EKA10AT001 | Gas filter separator A | 00EKA | IEPC | ALP-EPC-00EKA-ME-DSH-0002 ALP-M15-00EKA-IC-DSH-0001 ALP-M15-00EKA-ME-DSH-0001 | MR-ME-015 | CWP-09-ME-01 | CWA-09
00EKA10AT002 | Gas filter separator B | 00EKA | IEPC | ALP-EPC-00EKA-ME-DSH-0002 ALP-M15-00EKA-IC-DSH-0001 ALP-M15-00EKA-ME-DSH-0001 | MR-ME-015 | CWP-09-ME-01 | CWA-09
00EKA10BB001 | Gas station condensate drain vessel | 00EKA | IEPC | ALP-EPC-00EKA-ME-DSH-0004 ALP-M15-00EKA-IC-DSH-0001 ALP-M15-00EKA-ME-DSH-0001 | MR-ME-015 | CWP-09-ME-01 | CWA-09
00GBA10 | Seawater reverse osmosis package (2 x 100 %) | 00GBA | IEPC | ALP-EPC-00GBA-ME-DSH-0001 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GBA10AP001 | SWRO feed pump A | 00GBA | IEPC | ALP-EPC-00GBA-ME-DSH-0003 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GBA10AP002 | SWRO feed pump B | 00GBA | IEPC | ALP-EPC-00GBA-ME-DSH-0003 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GBA10AP003 | SWRO high-pressure pump A | 00GBA | IEPC | ALP-EPC-00GBA-ME-DSH-0003 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GBA10AP004 | SWRO high-pressure pump B | 00GBA | IEPC | ALP-EPC-00GBA-ME-DSH-0003 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GBA10AP005 | SWRO energy recovery device and booster pump A | 00GBA | IEPC | ALP-EPC-00GBA-ME-DSH-0003 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GBA10AP006 | SWRO energy recovery device and booster pump B | 00GBA | IEPC | ALP-EPC-00GBA-ME-DSH-0003 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GBA10AT001 | SWRO multimedia filter A | 00GBA | IEPC | ALP-EPC-00GBA-ME-DSH-0002 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GBA10AT002 | SWRO multimedia filter B | 00GBA | IEPC | ALP-EPC-00GBA-ME-DSH-0002 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GBA10AT003 | SWRO multimedia filter C | 00GBA | IEPC | ALP-EPC-00GBA-ME-DSH-0002 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GBA10AT004 | SWRO cartridge filter A | 00GBA | IEPC | ALP-EPC-00GBA-ME-DSH-0002 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GBA10AT005 | SWRO cartridge filter B | 00GBA | IEPC | ALP-EPC-00GBA-ME-DSH-0002 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GBA10BB001 | SWRO permeate tank | 00GBA | IEPC | ALP-EPC-00GBA-ME-DSH-0004 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GCA10 | Demineralisation package (EDI / mixed bed) | 00GCA | IEPC | ALP-EPC-00GCA-ME-DSH-0001 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GCA10AP001 | EDI feed pump A | 00GCA | IEPC | ALP-EPC-00GCA-ME-DSH-0003 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GCA10AP002 | EDI feed pump B | 00GCA | IEPC | ALP-EPC-00GCA-ME-DSH-0003 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GCA10AT001 | EDI stack A | 00GCA | IEPC | ALP-EPC-00GCA-ME-DSH-0002 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GCA10AT002 | EDI stack B | 00GCA | IEPC | ALP-EPC-00GCA-ME-DSH-0002 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GCA10AT003 | Mixed bed polisher A | 00GCA | IEPC | ALP-EPC-00GCA-ME-DSH-0002 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GCA10AT004 | Mixed bed polisher B | 00GCA | IEPC | ALP-EPC-00GCA-ME-DSH-0002 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00GHA10AP001 | Demin water forwarding pump A | 00GHA | IEPC | ALP-EPC-00GHA-ME-DSH-0002 ALP-M13-00GHA-IC-DSH-0001 ALP-M13-00GHA-ME-DSH-0001 | MR-ME-013 | CWP-07-ME-01 | CWA-07
00GHA10AP002 | Demin water forwarding pump B | 00GHA | IEPC | ALP-EPC-00GHA-ME-DSH-0002 ALP-M13-00GHA-IC-DSH-0001 ALP-M13-00GHA-ME-DSH-0001 | MR-ME-013 | CWP-07-ME-01 | CWA-07
00GHA10BB001 | Demineralised water tank A | 00GHA | IEPC | ALP-EPC-00GHA-ME-DSH-0001 ALP-M13-00GHA-IC-DSH-0001 ALP-M13-00GHA-ME-DSH-0001 | MR-ME-013 | CWP-07-ME-01 | CWA-07
00GHA10BB002 | Demineralised water tank B | 00GHA | IEPC | ALP-EPC-00GHA-ME-DSH-0001 ALP-M13-00GHA-IC-DSH-0001 ALP-M13-00GHA-ME-DSH-0001 | MR-ME-013 | CWP-07-ME-01 | CWA-07
00GKA10AP001 | Potable water pump A | 00GKA | IEPC | ALP-EPC-00GKA-ME-DSH-0003 ALP-M13-00GHA-IC-DSH-0001 ALP-M13-00GHA-ME-DSH-0001 | MR-ME-013 | CWP-12-EL-01 | CWA-12
00GKA10AP002 | Potable water pump B | 00GKA | IEPC | ALP-EPC-00GKA-ME-DSH-0003 ALP-M13-00GHA-IC-DSH-0001 ALP-M13-00GHA-ME-DSH-0001 | MR-ME-013 | CWP-12-EL-01 | CWA-12
00GKA10AP003 | Potable water hypochlorite dosing pump | 00GKA | IEPC | ALP-EPC-00GKA-ME-DSH-0003 ALP-M13-00GHA-IC-DSH-0001 ALP-M13-00GHA-ME-DSH-0001 | MR-ME-013 | CWP-12-EL-01 | CWA-12
00GKA10AT001 | Potable water UV disinfection | 00GKA | IEPC | ALP-EPC-00GKA-ME-DSH-0002 ALP-M13-00GHA-IC-DSH-0001 ALP-M13-00GHA-ME-DSH-0001 | MR-ME-013 | CWP-12-EL-01 | CWA-12
00GKA10AT002 | Potable water remineralisation filter (calcite) | 00GKA | IEPC | ALP-EPC-00GKA-ME-DSH-0002 ALP-M13-00GHA-IC-DSH-0001 ALP-M13-00GHA-ME-DSH-0001 | MR-ME-013 | CWP-12-EL-01 | CWA-12
00GKA10BB001 | Potable water tank | 00GKA | IEPC | ALP-EPC-00GKA-ME-DSH-0001 ALP-M13-00GHA-IC-DSH-0001 ALP-M13-00GHA-ME-DSH-0001 | MR-ME-013 | CWP-07-ME-01 | CWA-07
00GMA10AP001 | Process drain sump pump - power block A | 00GMA | IEPC | ALP-EPC-00GMA-ME-DSH-0005 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-12-EL-01 | CWA-12
00GMA10AP002 | Process drain sump pump - power block B | 00GMA | IEPC | ALP-EPC-00GMA-ME-DSH-0005 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-12-EL-01 | CWA-12
00GMA10AP003 | Oily water sump pump - transformer area | 00GMA | IEPC | ALP-EPC-00GMA-ME-DSH-0005 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-12-EL-01 | CWA-12
00GMA10AP004 | Oily water sump pump - LDO area | 00GMA | IEPC | ALP-EPC-00GMA-ME-DSH-0005 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-12-EL-01 | CWA-12
00GMA10AP005 | Chemical drain sump pump - water treatment | 00GMA | IEPC | ALP-EPC-00GMA-ME-DSH-0005 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-12-EL-01 | CWA-12
00GMA10AP006 | Drain sump pump - CW pump house | 00GMA | IEPC | ALP-EPC-00GMA-ME-DSH-0005 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-12-EL-01 | CWA-12
00GMA10AT001 | Oil separator (API / coalescing) | 00GMA | IEPC | ALP-EPC-00GMA-ME-DSH-0004 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-12-EL-01 | CWA-12
00GMA10BB001 | Neutralisation pit | 00GMA | IEPC | ALP-EPC-00GMA-ME-DSH-0006 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-12-EL-01 | CWA-12
00GNA10 | Waste water treatment package | 00GNA | IEPC | ALP-EPC-00GNA-ME-DSH-0001 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-07-ME-01 | CWA-07
00GNA10AP001 | Waste water transfer pump A | 00GNA | IEPC | ALP-EPC-00GNA-ME-DSH-0002 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-07-ME-01 | CWA-07
00GNA10AP002 | Waste water transfer pump B | 00GNA | IEPC | ALP-EPC-00GNA-ME-DSH-0002 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-07-ME-01 | CWA-07
00GNA10AP003 | Treated effluent pump A | 00GNA | IEPC | ALP-EPC-00GNA-ME-DSH-0002 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-07-ME-01 | CWA-07
00GNA10AP004 | Treated effluent pump B | 00GNA | IEPC | ALP-EPC-00GNA-ME-DSH-0002 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-07-ME-01 | CWA-07
00GNA10AP005 | Neutralisation acid dosing pump | 00GNA | IEPC | ALP-EPC-00GNA-ME-DSH-0002 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-07-ME-01 | CWA-07
00GNA10AP006 | Neutralisation caustic dosing pump | 00GNA | IEPC | ALP-EPC-00GNA-ME-DSH-0002 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-07-ME-01 | CWA-07
00GNA10BB001 | Equalisation tank | 00GNA | IEPC | ALP-EPC-00GNA-ME-DSH-0003 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-07-ME-01 | CWA-07
00GNA10BB002 | Neutralisation tank | 00GNA | IEPC | ALP-EPC-00GNA-ME-DSH-0003 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-07-ME-01 | CWA-07
00GNA10BB003 | Sulphuric acid tank (neutralisation) | 00GNA | IEPC | ALP-EPC-00GNA-ME-DSH-0003 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-07-ME-01 | CWA-07
00GNA10BB004 | Caustic tank (neutralisation) | 00GNA | IEPC | ALP-EPC-00GNA-ME-DSH-0003 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-07-ME-01 | CWA-07
00GUA10 | Sanitary treatment package | 00GUA | IEPC | ALP-EPC-00GUA-ME-DSH-0001 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-07-ME-01 | CWA-07
00GUA10AP001 | Sanitary lift pump A | 00GUA | IEPC | ALP-EPC-00GUA-ME-DSH-0002 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-07-ME-01 | CWA-07
00GUA10AP002 | Sanitary lift pump B | 00GUA | IEPC | ALP-EPC-00GUA-ME-DSH-0002 ALP-M14-00GNA-IC-DSH-0001 ALP-M14-00GNA-ME-DSH-0001 | MR-ME-014 | CWP-07-ME-01 | CWA-07
00LDA10 | Condensate polishing plant | 00LDA | IEPC | ALP-EPC-00LDA-ME-DSH-0001 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00LDA10AT001 | Condensate polisher vessel A | 00LDA | IEPC | ALP-EPC-00LDA-ME-DSH-0002 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00LDA10AT002 | Condensate polisher vessel B | 00LDA | IEPC | ALP-EPC-00LDA-ME-DSH-0002 ALP-M12-00GBA-IC-DSH-0001 ALP-M12-00GBA-ME-DSH-0001 | MR-ME-012 | CWP-07-ME-01 | CWA-07
00PAA10AA001 | Intake stop log / sluice gate A (motorised) | 00PAA | IEPC | ALP-EPC-00PAA-ME-DSH-0003 ALP-M04-00PAA-IC-DSH-0001 ALP-M04-00PAA-ME-DSH-0001 | MR-ME-004 | CWP-05-ME-01 | CWA-05
00PAA10AA002 | Intake stop log / sluice gate B (motorised) | 00PAA | IEPC | ALP-EPC-00PAA-ME-DSH-0003 ALP-M04-00PAA-IC-DSH-0001 ALP-M04-00PAA-ME-DSH-0001 | MR-ME-004 | CWP-05-ME-01 | CWA-05
00PAA10AP001 | Screen wash pump A | 00PAA | IEPC | ALP-EPC-00PAA-ME-DSH-0002 ALP-M04-00PAA-IC-DSH-0001 ALP-M04-00PAA-ME-DSH-0001 | MR-ME-004 | CWP-05-ME-01 | CWA-05
00PAA10AP002 | Screen wash pump B | 00PAA | IEPC | ALP-EPC-00PAA-ME-DSH-0002 ALP-M04-00PAA-IC-DSH-0001 ALP-M04-00PAA-ME-DSH-0001 | MR-ME-004 | CWP-05-ME-01 | CWA-05
00PAA10AT001 | Travelling band screen A | 00PAA | IEPC | ALP-EPC-00PAA-ME-DSH-0001 ALP-M04-00PAA-IC-DSH-0001 ALP-M04-00PAA-ME-DSH-0001 | MR-ME-004 | CWP-05-ME-01 | CWA-05
00PAA10AT002 | Travelling band screen B | 00PAA | IEPC | ALP-EPC-00PAA-ME-DSH-0001 ALP-M04-00PAA-IC-DSH-0001 ALP-M04-00PAA-ME-DSH-0001 | MR-ME-004 | CWP-05-ME-01 | CWA-05
00PAA10AT003 | Trash rake A | 00PAA | IEPC | ALP-EPC-00PAA-ME-DSH-0001 ALP-M04-00PAA-IC-DSH-0001 ALP-M04-00PAA-ME-DSH-0001 | MR-ME-004 | CWP-05-ME-01 | CWA-05
00PAA10AT004 | Trash rake B | 00PAA | IEPC | ALP-EPC-00PAA-ME-DSH-0001 ALP-M04-00PAA-IC-DSH-0001 ALP-M04-00PAA-ME-DSH-0001 | MR-ME-004 | CWP-05-ME-01 | CWA-05
00PAB10AA001 | CW pump discharge butterfly valve A DN2800 (motorised) | 00PAB | IEPC | ALP-EPC-00PAB-ME-DSH-0001 ALP-P04-00PAB-ME-DSH-0001 | MR-PI-004 | CWP-05-ME-01 | CWA-05
00PAB10AA002 | CW pump discharge butterfly valve B DN2800 (motorised) | 00PAB | IEPC | ALP-EPC-00PAB-ME-DSH-0001 ALP-P04-00PAB-ME-DSH-0001 | MR-PI-004 | CWP-05-ME-01 | CWA-05
00PAC10AP001 | CW pump A (2 x 50 %, vertical) | 00PAC | IEPC | ALP-EPC-00PAC-ME-DSH-0001 ALP-M03-00PAC-IC-DSH-0001 ALP-M03-00PAC-ME-DSH-0001 | MR-ME-003 | CWP-05-ME-01 | CWA-05
00PAC10AP002 | CW pump B (2 x 50 %, vertical) | 00PAC | IEPC | ALP-EPC-00PAC-ME-DSH-0001 ALP-M03-00PAC-IC-DSH-0001 ALP-M03-00PAC-ME-DSH-0001 | MR-ME-003 | CWP-05-ME-01 | CWA-05
00PAH10 | Condenser tube cleaning system (balls, strainers) | 00PAH | IEPC | ALP-EPC-00PAH-ME-DSH-0001 ALP-M06-00PAH-IC-DSH-0001 ALP-M06-00PAH-ME-DSH-0001 | MR-ME-006 | CWP-02-ME-01 | CWA-02
00PAH10AP001 | Ball recirculation pump A | 00PAH | IEPC | ALP-EPC-00PAH-ME-DSH-0003 ALP-M06-00PAH-IC-DSH-0001 ALP-M06-00PAH-ME-DSH-0001 | MR-ME-006 | CWP-02-ME-01 | CWA-02
00PAH10AP002 | Ball recirculation pump B | 00PAH | IEPC | ALP-EPC-00PAH-ME-DSH-0003 ALP-M06-00PAH-IC-DSH-0001 ALP-M06-00PAH-ME-DSH-0001 | MR-ME-006 | CWP-02-ME-01 | CWA-02
00PAH10AT001 | Debris filter A | 00PAH | IEPC | ALP-EPC-00PAH-ME-DSH-0002 ALP-M06-00PAH-IC-DSH-0001 ALP-M06-00PAH-ME-DSH-0001 | MR-ME-006 | CWP-02-ME-01 | CWA-02
00PAH10AT002 | Debris filter B | 00PAH | IEPC | ALP-EPC-00PAH-ME-DSH-0002 ALP-M06-00PAH-IC-DSH-0001 ALP-M06-00PAH-ME-DSH-0001 | MR-ME-006 | CWP-02-ME-01 | CWA-02
00PBA10 | Electro-chlorination package | 00PBA | IEPC | ALP-EPC-00PBA-ME-DSH-0001 ALP-M05-00PBA-IC-DSH-0001 ALP-M05-00PBA-ME-DSH-0001 | MR-ME-005 | CWP-05-ME-01 | CWA-05
00PBA10AN001 | Hydrogen dilution fan A | 00PBA | IEPC | ALP-EPC-00PBA-ME-DSH-0002 ALP-M05-00PBA-IC-DSH-0001 ALP-M05-00PBA-ME-DSH-0001 | MR-ME-005 | CWP-05-ME-01 | CWA-05
00PBA10AN002 | Hydrogen dilution fan B | 00PBA | IEPC | ALP-EPC-00PBA-ME-DSH-0002 ALP-M05-00PBA-IC-DSH-0001 ALP-M05-00PBA-ME-DSH-0001 | MR-ME-005 | CWP-05-ME-01 | CWA-05
00PBA10AP001 | Chlorination seawater booster pump A | 00PBA | IEPC | ALP-EPC-00PBA-ME-DSH-0004 ALP-M05-00PBA-IC-DSH-0001 ALP-M05-00PBA-ME-DSH-0001 | MR-ME-005 | CWP-05-ME-01 | CWA-05
00PBA10AP002 | Chlorination seawater booster pump B | 00PBA | IEPC | ALP-EPC-00PBA-ME-DSH-0004 ALP-M05-00PBA-IC-DSH-0001 ALP-M05-00PBA-ME-DSH-0001 | MR-ME-005 | CWP-05-ME-01 | CWA-05
00PBA10AP003 | Hypochlorite dosing pump A | 00PBA | IEPC | ALP-EPC-00PBA-ME-DSH-0004 ALP-M05-00PBA-IC-DSH-0001 ALP-M05-00PBA-ME-DSH-0001 | MR-ME-005 | CWP-05-ME-01 | CWA-05
00PBA10AP004 | Hypochlorite dosing pump B | 00PBA | IEPC | ALP-EPC-00PBA-ME-DSH-0004 ALP-M05-00PBA-IC-DSH-0001 ALP-M05-00PBA-ME-DSH-0001 | MR-ME-005 | CWP-05-ME-01 | CWA-05
00PBA10AT001 | Electrolyser cell stack A | 00PBA | IEPC | ALP-EPC-00PBA-ME-DSH-0003 ALP-M05-00PBA-IC-DSH-0001 ALP-M05-00PBA-ME-DSH-0001 | MR-ME-005 | CWP-05-ME-01 | CWA-05
00PBA10AT002 | Electrolyser cell stack B | 00PBA | IEPC | ALP-EPC-00PBA-ME-DSH-0003 ALP-M05-00PBA-IC-DSH-0001 ALP-M05-00PBA-ME-DSH-0001 | MR-ME-005 | CWP-05-ME-01 | CWA-05
00PBA10BB001 | Hypochlorite storage tank A | 00PBA | IEPC | ALP-EPC-00PBA-ME-DSH-0005 ALP-M05-00PBA-IC-DSH-0001 ALP-M05-00PBA-ME-DSH-0001 | MR-ME-005 | CWP-05-ME-01 | CWA-05
00PBA10BB002 | Hypochlorite storage tank B | 00PBA | IEPC | ALP-EPC-00PBA-ME-DSH-0005 ALP-M05-00PBA-IC-DSH-0001 ALP-M05-00PBA-ME-DSH-0001 | MR-ME-005 | CWP-05-ME-01 | CWA-05
00PGA10AC001 | CCW plate heat exchanger A (2 x 100 %) | 00PGA | IEPC | ALP-EPC-00PGA-ME-DSH-0001 ALP-M07-00PGA-IC-DSH-0001 ALP-M07-00PGA-ME-DSH-0001 | MR-ME-007 | CWP-08-ME-01 | CWA-08
00PGA10AC002 | CCW plate heat exchanger B (2 x 100 %) | 00PGA | IEPC | ALP-EPC-00PGA-ME-DSH-0001 ALP-M07-00PGA-IC-DSH-0001 ALP-M07-00PGA-ME-DSH-0001 | MR-ME-007 | CWP-08-ME-01 | CWA-08
00PGA10AP001 | CCW pump A (2 x 100 %) | 00PGA | IEPC | ALP-EPC-00PGA-ME-DSH-0002 ALP-M07-00PGA-IC-DSH-0001 ALP-M07-00PGA-ME-DSH-0001 | MR-ME-007 | CWP-08-ME-01 | CWA-08
00PGA10AP002 | CCW pump B (2 x 100 %) | 00PGA | IEPC | ALP-EPC-00PGA-ME-DSH-0002 ALP-M07-00PGA-IC-DSH-0001 ALP-M07-00PGA-ME-DSH-0001 | MR-ME-007 | CWP-08-ME-01 | CWA-08
00PGA10AT001 | CCW side-stream filter | 00PGA | IEPC | ALP-EPC-00PGA-ME-DSH-0004 ALP-M07-00PGA-IC-DSH-0001 ALP-M07-00PGA-ME-DSH-0001 | MR-ME-007 | CWP-08-ME-01 | CWA-08
00PGA10BB001 | CCW expansion tank | 00PGA | IEPC | ALP-EPC-00PGA-ME-DSH-0003 ALP-M07-00PGA-IC-DSH-0001 ALP-M07-00PGA-ME-DSH-0001 | MR-ME-007 | CWP-08-ME-01 | CWA-08
00PGA10BB002 | CCW chemical pot feeder | 00PGA | IEPC | ALP-EPC-00PGA-ME-DSH-0003 ALP-M07-00PGA-IC-DSH-0001 ALP-M07-00PGA-ME-DSH-0001 | MR-ME-007 | CWP-08-ME-01 | CWA-08
00QCA10 | Chemical dosing skid (ammonia, phosphate / caustic trim, lay-up dosing) | 00QCA | IEPC | ALP-EPC-00QCA-ME-DSH-0001 ALP-M11-00QCA-IC-DSH-0001 ALP-M11-00QCA-ME-DSH-0001 | MR-ME-011 | CWP-08-ME-01 | CWA-08
00QCA10AP001 | Ammonia dosing pump A | 00QCA | IEPC | ALP-EPC-00QCA-ME-DSH-0002 ALP-M11-00QCA-IC-DSH-0001 ALP-M11-00QCA-ME-DSH-0001 | MR-ME-011 | CWP-08-ME-01 | CWA-08
00QCA10AP002 | Ammonia dosing pump B | 00QCA | IEPC | ALP-EPC-00QCA-ME-DSH-0002 ALP-M11-00QCA-IC-DSH-0001 ALP-M11-00QCA-ME-DSH-0001 | MR-ME-011 | CWP-08-ME-01 | CWA-08
00QCA10AP003 | Oxygen scavenger dosing pump A | 00QCA | IEPC | ALP-EPC-00QCA-ME-DSH-0002 ALP-M11-00QCA-IC-DSH-0001 ALP-M11-00QCA-ME-DSH-0001 | MR-ME-011 | CWP-08-ME-01 | CWA-08
00QCA10AP004 | Oxygen scavenger dosing pump B | 00QCA | IEPC | ALP-EPC-00QCA-ME-DSH-0002 ALP-M11-00QCA-IC-DSH-0001 ALP-M11-00QCA-ME-DSH-0001 | MR-ME-011 | CWP-08-ME-01 | CWA-08
00QCA10AP005 | Phosphate / caustic dosing pump A | 00QCA | IEPC | ALP-EPC-00QCA-ME-DSH-0002 ALP-M11-00QCA-IC-DSH-0001 ALP-M11-00QCA-ME-DSH-0001 | MR-ME-011 | CWP-08-ME-01 | CWA-08
00QCA10AP006 | Phosphate / caustic dosing pump B | 00QCA | IEPC | ALP-EPC-00QCA-ME-DSH-0002 ALP-M11-00QCA-IC-DSH-0001 ALP-M11-00QCA-ME-DSH-0001 | MR-ME-011 | CWP-08-ME-01 | CWA-08
00QCA10BB001 | Ammonia solution tank | 00QCA | IEPC | ALP-EPC-00QCA-ME-DSH-0003 ALP-M11-00QCA-IC-DSH-0001 ALP-M11-00QCA-ME-DSH-0001 | MR-ME-011 | CWP-08-ME-01 | CWA-08
00QCA10BB002 | Oxygen scavenger tank | 00QCA | IEPC | ALP-EPC-00QCA-ME-DSH-0003 ALP-M11-00QCA-IC-DSH-0001 ALP-M11-00QCA-ME-DSH-0001 | MR-ME-011 | CWP-08-ME-01 | CWA-08
00QCA10BB003 | Caustic solution tank | 00QCA | IEPC | ALP-EPC-00QCA-ME-DSH-0003 ALP-M11-00QCA-IC-DSH-0001 ALP-M11-00QCA-ME-DSH-0001 | MR-ME-011 | CWP-08-ME-01 | CWA-08
00QEA10AN001 | Air compressor A (2 x 100 %) | 00QEA | IEPC | ALP-EPC-00QEA-ME-DSH-0001 ALP-M08-00QEA-IC-DSH-0001 ALP-M08-00QEA-ME-DSH-0001 | MR-ME-008 | CWP-08-ME-01 | CWA-08
00QEA10AN002 | Air compressor B (2 x 100 %) | 00QEA | IEPC | ALP-EPC-00QEA-ME-DSH-0001 ALP-M08-00QEA-IC-DSH-0001 ALP-M08-00QEA-ME-DSH-0001 | MR-ME-008 | CWP-08-ME-01 | CWA-08
00QEA10AN003 | Service air compressor | 00QEA | IEPC | ALP-EPC-00QEA-ME-DSH-0001 ALP-M08-00QEA-IC-DSH-0001 ALP-M08-00QEA-ME-DSH-0001 | MR-ME-008 | CWP-08-ME-01 | CWA-08
00QEA10AT001 | Instrument air dryer A | 00QEA | IEPC | ALP-EPC-00QEA-ME-DSH-0002 ALP-M08-00QEA-IC-DSH-0001 ALP-M08-00QEA-ME-DSH-0001 | MR-ME-008 | CWP-08-ME-01 | CWA-08
00QEA10AT002 | Instrument air dryer B | 00QEA | IEPC | ALP-EPC-00QEA-ME-DSH-0002 ALP-M08-00QEA-IC-DSH-0001 ALP-M08-00QEA-ME-DSH-0001 | MR-ME-008 | CWP-08-ME-01 | CWA-08
00QEA10AT003 | Instrument air after-filters | 00QEA | IEPC | ALP-EPC-00QEA-ME-DSH-0002 ALP-M08-00QEA-IC-DSH-0001 ALP-M08-00QEA-ME-DSH-0001 | MR-ME-008 | CWP-08-ME-01 | CWA-08
00QEA10BB001 | Instrument air receiver | 00QEA | IEPC | ALP-EPC-00QEA-ME-DSH-0003 ALP-M08-00QEA-IC-DSH-0001 ALP-M08-00QEA-ME-DSH-0001 | MR-ME-008 | CWP-08-ME-01 | CWA-08
00QEA10BB002 | Service air receiver | 00QEA | IEPC | ALP-EPC-00QEA-ME-DSH-0003 ALP-M08-00QEA-IC-DSH-0001 ALP-M08-00QEA-ME-DSH-0001 | MR-ME-008 | CWP-08-ME-01 | CWA-08
00QHA10 | Auxiliary boiler 12 t/h, gas-fired | 00QHA | IEPC | ALP-EPC-00QHA-ME-DSH-0001 ALP-M09-00QHA-IC-DSH-0001 ALP-M09-00QHA-ME-DSH-0001 | MR-ME-009 | CWP-08-ME-01 | CWA-08
00QHA10AN001 | Auxiliary boiler combustion air fan | 00QHA | IEPC | ALP-EPC-00QHA-ME-DSH-0002 ALP-M09-00QHA-IC-DSH-0001 ALP-M09-00QHA-ME-DSH-0001 | MR-ME-009 | CWP-08-ME-01 | CWA-08
00QHA10AP001 | Auxiliary boiler feed pump A | 00QHA | IEPC | ALP-EPC-00QHA-ME-DSH-0003 ALP-M09-00QHA-IC-DSH-0001 ALP-M09-00QHA-ME-DSH-0001 | MR-ME-009 | CWP-08-ME-01 | CWA-08
00QHA10AP002 | Auxiliary boiler feed pump B | 00QHA | IEPC | ALP-EPC-00QHA-ME-DSH-0003 ALP-M09-00QHA-IC-DSH-0001 ALP-M09-00QHA-ME-DSH-0001 | MR-ME-009 | CWP-08-ME-01 | CWA-08
00QHA10BB001 | Auxiliary boiler feed water tank / deaerator | 00QHA | IEPC | ALP-EPC-00QHA-ME-DSH-0004 ALP-M09-00QHA-IC-DSH-0001 ALP-M09-00QHA-ME-DSH-0001 | MR-ME-009 | CWP-08-ME-01 | CWA-08
00QHA10BB002 | Auxiliary boiler blowdown vessel | 00QHA | IEPC | ALP-EPC-00QHA-ME-DSH-0004 ALP-M09-00QHA-IC-DSH-0001 ALP-M09-00QHA-ME-DSH-0001 | MR-ME-009 | CWP-08-ME-01 | CWA-08
00QJA10 | Nitrogen supply package (bottle racks / generator) | 00QJA | IEPC | ALP-EPC-00QJA-ME-DSH-0001 ALP-M10-00QJA-IC-DSH-0001 ALP-M10-00QJA-ME-DSH-0001 | MR-ME-010 | CWP-08-ME-01 | CWA-08
00QJA10BB001 | Nitrogen buffer vessel | 00QJA | IEPC | ALP-EPC-00QJA-ME-DSH-0002 ALP-M10-00QJA-IC-DSH-0001 ALP-M10-00QJA-ME-DSH-0001 | MR-ME-010 | CWP-08-ME-01 | CWA-08
00QJB10 | Hydrogen and CO2 bottle racks | 00QJB | IEPC | ALP-EPC-00QJB-ME-DSH-0001 ALP-M10-00QJA-IC-DSH-0001 ALP-M10-00QJA-ME-DSH-0001 | MR-ME-010 | CWP-01-ME-01 | CWA-01
00QUA10 | Steam/water analysis system (SWAS) | 00QUA | IEPC | ALP-EPC-00QUA-ME-DSH-0001 ALP-I03-00QUA-IC-DSH-0001 ALP-I03-00QUA-ME-DSH-0001 | MR-IC-003 | CWP-01-ME-01 | CWA-01
00QUA10AC001 | Sample cooler rack | 00QUA | IEPC | ALP-EPC-00QUA-ME-DSH-0002 ALP-I03-00QUA-IC-DSH-0001 ALP-I03-00QUA-ME-DSH-0001 | MR-IC-003 | CWP-01-ME-01 | CWA-01
00SAA10 | HVAC plant (chillers, AHUs, pressurisation) | 00SAA | IEPC | ALP-EPC-00SAA-HV-DSH-0001 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA10AN001 | Chiller A | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0001 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA10AN002 | Chiller B | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0001 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA10AN003 | Chiller C | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0001 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA10AP001 | Chilled water pump A | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0003 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA10AP002 | Chilled water pump B | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0003 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA11AN001 | AHU - control room | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA11AN002 | AHU - electronic rooms | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA11AN003 | AHU - electrical building MV rooms | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA11AN004 | AHU - electrical building LV rooms | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA11AN005 | AHU - GIS building | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA11AN006 | AHU - administration building | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA11AN007 | AHU - workshop | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA11AN008 | Pressurisation unit - control building | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA12AN001 | GT hall roof ventilator A | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA12AN002 | GT hall roof ventilator B | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA12AN003 | GT hall roof ventilator C | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA12AN004 | GT hall roof ventilator D | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA13AN001 | ST hall roof ventilator A | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA13AN002 | ST hall roof ventilator B | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA13AN003 | ST hall roof ventilator C | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA13AN004 | ST hall roof ventilator D | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA14AN001 | Battery room exhaust fan A | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SAA14AN002 | Battery room exhaust fan B | 00SAA | IEPC | ALP-EPC-00SAA-ME-DSH-0002 ALP-H01-00SAA-IC-DSH-0001 ALP-H01-00SAA-ME-DSH-0001 | MR-HV-001 | CWP-03-HV-01 | CWA-03
00SGA10AP001 | Electric fire pump | 00SGA | IEPC | ALP-EPC-00SGA-ME-DSH-0001 ALP-M20-00SGA-IC-DSH-0001 ALP-M20-00SGA-ME-DSH-0001 | MR-ME-020 | CWP-08-ME-01 | CWA-08
00SGA10AP002 | Diesel fire pump | 00SGA | IEPC | ALP-EPC-00SGA-ME-DSH-0001 ALP-M20-00SGA-IC-DSH-0001 ALP-M20-00SGA-ME-DSH-0001 | MR-ME-020 | CWP-08-ME-01 | CWA-08
00SGA10AP003 | Jockey pump | 00SGA | IEPC | ALP-EPC-00SGA-ME-DSH-0001 ALP-M20-00SGA-IC-DSH-0001 ALP-M20-00SGA-ME-DSH-0001 | MR-ME-020 | CWP-08-ME-01 | CWA-08
00SGA10BB001 | Fire water tank A | 00SGA | IEPC | ALP-EPC-00SGA-ME-DSH-0002 ALP-M13-00GHA-IC-DSH-0001 ALP-M13-00GHA-ME-DSH-0001 | MR-ME-017 | CWP-08-ME-01 | CWA-08
00SGA10BB002 | Fire water tank B | 00SGA | IEPC | ALP-EPC-00SGA-ME-DSH-0002 ALP-M20-00SGA-IC-DSH-0001 ALP-M20-00SGA-ME-DSH-0001 | MR-ME-017 | CWP-08-ME-01 | CWA-08
00SGC10AA001 | Deluge valve set - GSU transformer GT | 00SGC | IEPC | ALP-EPC-00SGC-ME-DSH-0002 ALP-M20-00SGA-IC-DSH-0001 ALP-M20-00SGA-ME-DSH-0001 | MR-ME-020 | CWP-08-ME-01 | CWA-08
00SGC10AA002 | Deluge valve set - GSU transformer ST | 00SGC | IEPC | ALP-EPC-00SGC-ME-DSH-0002 ALP-M20-00SGA-IC-DSH-0001 ALP-M20-00SGA-ME-DSH-0001 | MR-ME-020 | CWP-08-ME-01 | CWA-08
00SGC10AA003 | Deluge valve set - unit auxiliary transformers | 00SGC | IEPC | ALP-EPC-00SGC-ME-DSH-0002 ALP-M20-00SGA-IC-DSH-0001 ALP-M20-00SGA-ME-DSH-0001 | MR-ME-020 | CWP-08-ME-01 | CWA-08
00SGC10AA004 | Deluge valve set - GT lube oil module | 00SGC | IEPC | ALP-EPC-00SGC-ME-DSH-0002 ALP-M20-00SGA-IC-DSH-0001 ALP-M20-00SGA-ME-DSH-0001 | MR-ME-020 | CWP-08-ME-01 | CWA-08
00SGC10AA005 | Deluge valve set - ST lube oil module | 00SGC | IEPC | ALP-EPC-00SGC-ME-DSH-0002 ALP-M20-00SGA-IC-DSH-0001 ALP-M20-00SGA-ME-DSH-0001 | MR-ME-020 | CWP-08-ME-01 | CWA-08
00SGC10AA006 | Deluge valve set - LDO tank A | 00SGC | IEPC | ALP-EPC-00SGC-ME-DSH-0002 ALP-M20-00SGA-IC-DSH-0001 ALP-M20-00SGA-ME-DSH-0001 | MR-ME-020 | CWP-08-ME-01 | CWA-08
00SGC10AA007 | Deluge valve set - LDO tank B | 00SGC | IEPC | ALP-EPC-00SGC-ME-DSH-0002 ALP-M20-00SGA-IC-DSH-0001 ALP-M20-00SGA-ME-DSH-0001 | MR-ME-020 | CWP-08-ME-01 | CWA-08
00SGC10AA008 | Deluge valve set - LDO forwarding | 00SGC | IEPC | ALP-EPC-00SGC-ME-DSH-0002 ALP-M20-00SGA-IC-DSH-0001 ALP-M20-00SGA-ME-DSH-0001 | MR-ME-020 | CWP-08-ME-01 | CWA-08
00SGC10AA009 | Deluge valve set - cable spreading room | 00SGC | IEPC | ALP-EPC-00SGC-ME-DSH-0002 ALP-M20-00SGA-IC-DSH-0001 ALP-M20-00SGA-ME-DSH-0001 | MR-ME-020 | CWP-08-ME-01 | CWA-08
00SGC10AA010 | Foam proportioner - LDO unloading | 00SGC | IEPC | ALP-EPC-00SGC-ME-DSH-0002 ALP-M20-00SGA-IC-DSH-0001 ALP-M20-00SGA-ME-DSH-0001 | MR-ME-020 | CWP-08-ME-01 | CWA-08
00SGC10BB001 | Foam concentrate tank | 00SGC | IEPC | ALP-EPC-00SGC-ME-DSH-0001 ALP-M20-00SGA-IC-DSH-0001 ALP-M20-00SGA-ME-DSH-0001 | MR-ME-020 | CWP-08-ME-01 | CWA-08
00SGY10 | Fire alarm control panel and detection network | 00SGY | IEPC | ALP-EPC-00SGY-IC-DSH-0001 ALP-I06-00SGY-ME-DSH-0001 | MR-IC-006 | CWP-11-IC-01 | CWA-11
00SMA10 | GT hall EOT crane 120/20 t | 00SMA | IEPC | ALP-EPC-00SMA-ME-DSH-0001 ALP-M21-00SMA-ME-DSH-0001 | MR-ME-021 | CWP-01-SS-01 | CWA-01
00SMA20 | ST hall EOT crane 100 t | 00SMA | IEPC | ALP-EPC-00SMA-ME-DSH-0001 ALP-M21-00SMA-ME-DSH-0001 | MR-ME-021 | CWP-02-SS-01 | CWA-02
00SMA30 | CW pump house overhead crane 25 t | 00SMA | IEPC | ALP-EPC-00SMA-ME-DSH-0001 ALP-M21-00SMA-ME-DSH-0001 | MR-ME-021 | CWP-01-ME-01 | CWA-01
00SMA40 | Workshop overhead crane 10 t | 00SMA | IEPC | ALP-EPC-00SMA-ME-DSH-0001 ALP-M21-00SMA-ME-DSH-0001 | MR-ME-021 | CWP-01-ME-01 | CWA-01
00SMA50 | BFP maintenance hoist 16 t | 00SMA | IEPC | ALP-EPC-00SMA-ME-DSH-0001 ALP-M21-00SMA-ME-DSH-0001 | MR-ME-021 | CWP-01-ME-01 | CWA-01
00SMA60 | Water treatment building hoist 5 t | 00SMA | IEPC | ALP-EPC-00SMA-ME-DSH-0001 ALP-M21-00SMA-ME-DSH-0001 | MR-ME-021 | CWP-01-ME-01 | CWA-01
00XJA10 | Emergency diesel generator 1,250 kVA | 00XJA | IEPC | ALP-E06-00XJA-IC-DSH-0001 ALP-E06-00XJA-ME-DSH-0001 ALP-EPC-00XJA-EL-DSH-0001 | MR-EL-006 | CWP-03-EL-01 | CWA-03
00XJA10BB001 | Emergency diesel generator day tank | 00XJA | IEPC | ALP-E06-00XJA-IC-DSH-0001 ALP-E06-00XJA-ME-DSH-0001 ALP-EPC-00XJA-ME-DSH-0001 | MR-EL-006 | CWP-03-HV-01 | CWA-03
10BAA10 | GT isolated phase busduct | 10BAA | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-01-EL-01 | CWA-01
10BAC10 | GT generator circuit breaker | 10BAC | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-01-EL-01 | CWA-01
10BAT10 | GT step-up transformer 560 MVA 400/21 kV | 10BAT | IEC | ALP-IEC-10BAT-EL-DSH-0001 ALP-IEC-10BAT-IC-DSH-0001 | MR-EL-102 | CWP-01-EL-01 | CWA-01
10BBT10 | GT unit auxiliary transformer 21/10.5 kV 31.5 MVA | 10BBT | IEPC | ALP-E02-10BBT-IC-DSH-0001 ALP-E02-10BBT-ME-DSH-0001 ALP-EPC-10BBT-EL-DSH-0001 | MR-EL-002 | CWP-01-EL-01 | CWA-01
10HAA10 | Heat recovery steam generator, 3-pressure reheat | 10HAA | IEC | ALP-IEC-10HAA-IC-DSH-0001 ALP-IEC-10HAA-IC-DSH-0002 ALP-IEC-10HAA-ME-DSH-0001 | MR-ME-102 | CWP-01-ME-01 | CWA-01
10HAA10AP001 | HRSG condensate preheater recirculation pump A | 10HAA | IEC | ALP-IEC-10HAA-IC-DSH-0001 ALP-IEC-10HAA-IC-DSH-0002 ALP-IEC-10HAA-ME-DSH-0001 | MR-ME-102 | CWP-01-ME-01 | CWA-01
10HAA10AP002 | HRSG condensate preheater recirculation pump B | 10HAA | IEC | ALP-IEC-10HAA-IC-DSH-0001 ALP-IEC-10HAA-IC-DSH-0002 ALP-IEC-10HAA-ME-DSH-0001 | MR-ME-102 | CWP-01-ME-01 | CWA-01
10HAN10AP001 | HRSG drain pump A | 10HAN | IEPC | ALP-EPC-10HAN-ME-DSH-0002 ALP-M19-10HAN-IC-DSH-0001 ALP-M19-10HAN-ME-DSH-0001 | MR-ME-019 | CWP-01-ME-01 | CWA-01
10HAN10AP002 | HRSG drain pump B | 10HAN | IEPC | ALP-EPC-10HAN-ME-DSH-0002 ALP-M19-10HAN-IC-DSH-0001 ALP-M19-10HAN-ME-DSH-0001 | MR-ME-019 | CWP-01-ME-01 | CWA-01
10HAN10BB001 | HRSG blowdown tank | 10HAN | IEPC | ALP-EPC-10HAN-ME-DSH-0001 ALP-M19-10HAN-IC-DSH-0001 ALP-M19-10HAN-ME-DSH-0001 | MR-ME-019 | CWP-01-ME-01 | CWA-01
10HAN10BB002 | Atmospheric drain tank | 10HAN | IEPC | ALP-EPC-10HAN-ME-DSH-0001 ALP-M19-10HAN-IC-DSH-0001 ALP-M19-10HAN-ME-DSH-0001 | MR-ME-019 | CWP-01-ME-01 | CWA-01
10HNA10 | HRSG inlet duct and flue gas ducting | 10HNA | IEC | ALP-IEC-10HAA-IC-DSH-0001 ALP-IEC-10HAA-IC-DSH-0002 ALP-IEC-10HAA-ME-DSH-0001 | MR-ME-102 | CWP-01-ME-01 | CWA-01
10HNE10 | Stack 65 m, D 9.2 m, with silencer and CEMS platform | 10HNE | IEPC | ALP-EPC-10HNE-ME-DSH-0001 | MR-SS-002 | CWP-01-ME-01 | CWA-01
10HSA10 | SCR catalyst and ammonia injection grid | 10HSA | IEC | ALP-IEC-10HAA-IC-DSH-0001 ALP-IEC-10HAA-IC-DSH-0002 ALP-IEC-10HAA-ME-DSH-0001 | MR-ME-102 | CWP-01-ME-01 | CWA-01
10HSB10AP001 | Ammonia forwarding pump A | 10HSB | IEPC | ALP-EPC-10HSB-ME-DSH-0002 ALP-M18-10HSB-IC-DSH-0001 ALP-M18-10HSB-ME-DSH-0001 | MR-ME-018 | CWP-08-ME-01 | CWA-08
10HSB10AP002 | Ammonia forwarding pump B | 10HSB | IEPC | ALP-EPC-10HSB-ME-DSH-0002 ALP-M18-10HSB-IC-DSH-0001 ALP-M18-10HSB-ME-DSH-0001 | MR-ME-018 | CWP-08-ME-01 | CWA-08
10HSB10BB001 | Aqueous ammonia tank A 30 m3 | 10HSB | IEPC | ALP-EPC-10HSB-ME-DSH-0001 ALP-M18-10HSB-IC-DSH-0001 ALP-M18-10HSB-ME-DSH-0001 | MR-ME-018 | CWP-08-ME-01 | CWA-08
10HSB10BB002 | Aqueous ammonia tank B 30 m3 | 10HSB | IEPC | ALP-EPC-10HSB-ME-DSH-0001 ALP-M18-10HSB-IC-DSH-0001 ALP-M18-10HSB-ME-DSH-0001 | MR-ME-018 | CWP-08-ME-01 | CWA-08
10LAC10AP001 | Boiler feed pump A (2 x 100 %, VFD) | 10LAC | IEPC | ALP-EPC-10LAC-ME-DSH-0001 ALP-M01-10LAC-IC-DSH-0001 ALP-M01-10LAC-ME-DSH-0001 | MR-ME-001 | CWP-08-ME-01 | CWA-08
10LAC10AP002 | Boiler feed pump B (2 x 100 %, VFD) | 10LAC | IEPC | ALP-EPC-10LAC-ME-DSH-0001 ALP-M01-10LAC-IC-DSH-0001 ALP-M01-10LAC-ME-DSH-0001 | MR-ME-001 | CWP-08-ME-01 | CWA-08
10LBA10AA501 | HP bypass valve (to cold reheat) | 10LBA | IEC | ALP-IEC-20MAA-IC-DSH-0001 ALP-IEC-20MAA-IC-DSH-0002 ALP-IEC-20MAA-IC-DSH-0003 ALP-IEC-20MAA-ME-DSH-0001 | MR-ME-103 | CWP-02-ME-01 | CWA-02
10LBB10AA501 | IP bypass valve (to condenser) | 10LBB | IEC | ALP-IEC-20MAA-IC-DSH-0001 ALP-IEC-20MAA-IC-DSH-0002 ALP-IEC-20MAA-IC-DSH-0003 ALP-IEC-20MAA-ME-DSH-0001 | MR-ME-103 | CWP-02-ME-01 | CWA-02
10LBD10AA501 | LP bypass valve (to condenser) | 10LBD | IEC | ALP-IEC-20MAA-IC-DSH-0001 ALP-IEC-20MAA-IC-DSH-0002 ALP-IEC-20MAA-IC-DSH-0003 ALP-IEC-20MAA-ME-DSH-0001 | MR-ME-103 | CWP-02-ME-01 | CWA-02
10MBA10 | Gas turbine | 10MBA | IEC | ALP-IEC-10MBA-IC-DSH-0001 ALP-IEC-10MBA-IC-DSH-0002 ALP-IEC-10MBA-IC-DSH-0003 ALP-IEC-10MBA-ME-DSH-0001 | MR-ME-101 | CWP-01-ME-01 | CWA-01
10MBL10 | GT inlet air filter house | 10MBL | IEC | ALP-IEC-10MBA-IC-DSH-0001 ALP-IEC-10MBA-IC-DSH-0002 ALP-IEC-10MBA-IC-DSH-0003 ALP-IEC-10MBA-ME-DSH-0001 | MR-ME-101 | CWP-01-ME-01 | CWA-01
10MBN10 | GT liquid fuel and water injection module | 10MBN | IEC | ALP-IEC-10MBA-IC-DSH-0001 ALP-IEC-10MBA-IC-DSH-0002 ALP-IEC-10MBA-IC-DSH-0003 ALP-IEC-10MBA-ME-DSH-0001 | MR-ME-101 | CWP-01-ME-01 | CWA-01
10MBP10 | GT fuel gas module incl. performance heater | 10MBP | IEC | ALP-IEC-10MBA-IC-DSH-0001 ALP-IEC-10MBA-IC-DSH-0002 ALP-IEC-10MBA-IC-DSH-0003 ALP-IEC-10MBA-ME-DSH-0001 | MR-ME-101 | CWP-01-ME-01 | CWA-01
10MBU10 | GT compressor wash skid | 10MBU | IEC | ALP-IEC-10MBA-IC-DSH-0001 ALP-IEC-10MBA-IC-DSH-0002 ALP-IEC-10MBA-IC-DSH-0003 ALP-IEC-10MBA-ME-DSH-0001 | MR-ME-101 | CWP-01-ME-01 | CWA-01
10MBV10 | GT lube oil module | 10MBV | IEC | ALP-IEC-10MBA-IC-DSH-0001 ALP-IEC-10MBA-IC-DSH-0002 ALP-IEC-10MBA-IC-DSH-0003 ALP-IEC-10MBA-ME-DSH-0001 | MR-ME-101 | CWP-01-ME-01 | CWA-01
10MBY10 | GT control and protection cabinets (TCS) | 10MBY | IEC | ALP-IEC-10MBY-ME-DSH-0001 | MR-IC-101 | CWP-01-IC-01 | CWA-01
10MKA10 | GT generator 560 MVA, H2-cooled | 10MKA | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-01-ME-01 | CWA-01
10MKA20 | GT generator neutral earthing transformer | 10MKA | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-01-ME-01 | CWA-01
10MKA30 | GT generator protection panels (main 1 / main 2) | 10MKA | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-01-ME-01 | CWA-01
10MKC10 | GT static excitation | 10MKC | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-01-EL-01 | CWA-01
10MKC20 | GT static frequency converter | 10MKC | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-01-EL-01 | CWA-01
10MKC30 | GT excitation transformer | 10MKC | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-01-EL-01 | CWA-01
10MKG10 | GT generator gas unit (H2/CO2) | 10MKG | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-01-ME-01 | CWA-01
20BAA10 | ST isolated phase busduct | 20BAA | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-02-EL-01 | CWA-02
20BAC10 | ST generator circuit breaker | 20BAC | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-02-EL-01 | CWA-02
20BAT10 | ST step-up transformer 270 MVA 400/15.75 kV | 20BAT | IEC | ALP-IEC-10BAT-EL-DSH-0001 ALP-IEC-10BAT-IC-DSH-0001 | MR-EL-102 | CWP-02-EL-01 | CWA-02
20BBT10 | ST unit auxiliary transformer 15.75/10.5 kV 16 MVA | 20BBT | IEPC | ALP-E02-10BBT-IC-DSH-0001 ALP-E02-10BBT-ME-DSH-0001 ALP-EPC-20BBT-EL-DSH-0001 | MR-EL-002 | CWP-02-EL-01 | CWA-02
20LCB10AP001 | Condensate extraction pump A (2 x 100 %) | 20LCB | IEPC | ALP-EPC-20LCB-ME-DSH-0001 ALP-M02-20LCB-IC-DSH-0001 ALP-M02-20LCB-ME-DSH-0001 | MR-ME-002 | CWP-02-ME-01 | CWA-02
20LCB10AP002 | Condensate extraction pump B (2 x 100 %) | 20LCB | IEPC | ALP-EPC-20LCB-ME-DSH-0001 ALP-M02-20LCB-IC-DSH-0001 ALP-M02-20LCB-ME-DSH-0001 | MR-ME-002 | CWP-02-ME-01 | CWA-02
20MAA10 | Steam turbine, reheat condensing, 2 casings | 20MAA | IEC | ALP-IEC-20MAA-IC-DSH-0001 ALP-IEC-20MAA-IC-DSH-0002 ALP-IEC-20MAA-IC-DSH-0003 ALP-IEC-20MAA-ME-DSH-0001 | MR-ME-103 | CWP-02-ME-01 | CWA-02
20MAB10 | IP/LP steam turbine | 20MAB | IEC | ALP-IEC-20MAA-IC-DSH-0001 ALP-IEC-20MAA-IC-DSH-0002 ALP-IEC-20MAA-IC-DSH-0003 ALP-IEC-20MAA-ME-DSH-0001 | MR-ME-103 | CWP-02-ME-01 | CWA-02
20MAG10 | Surface condenser, titanium tubes, 15,200 m2 | 20MAG | IEC | ALP-IEC-20MAA-IC-DSH-0001 ALP-IEC-20MAA-IC-DSH-0002 ALP-IEC-20MAA-IC-DSH-0003 ALP-IEC-20MAA-ME-DSH-0001 ALP-IEC-20MAG-ME-DSH-0001 | MR-ME-103 | CWP-02-ME-01 | CWA-02
20MAJ10AP001 | Condenser vacuum pump A | 20MAJ | IEC | ALP-IEC-20MAA-IC-DSH-0001 ALP-IEC-20MAA-IC-DSH-0002 ALP-IEC-20MAA-IC-DSH-0003 ALP-IEC-20MAA-ME-DSH-0001 | MR-ME-103 | CWP-02-ME-01 | CWA-02
20MAJ10AP002 | Condenser vacuum pump B | 20MAJ | IEC | ALP-IEC-20MAA-IC-DSH-0001 ALP-IEC-20MAA-IC-DSH-0002 ALP-IEC-20MAA-IC-DSH-0003 ALP-IEC-20MAA-ME-DSH-0001 | MR-ME-103 | CWP-02-ME-01 | CWA-02
20MAV10 | ST lube oil module | 20MAV | IEC | ALP-IEC-20MAA-IC-DSH-0001 ALP-IEC-20MAA-IC-DSH-0002 ALP-IEC-20MAA-IC-DSH-0003 ALP-IEC-20MAA-ME-DSH-0001 | MR-ME-103 | CWP-02-ME-01 | CWA-02
20MAW10 | Gland steam condenser and exhausters | 20MAW | IEC | ALP-IEC-20MAA-IC-DSH-0001 ALP-IEC-20MAA-IC-DSH-0002 ALP-IEC-20MAA-IC-DSH-0003 ALP-IEC-20MAA-ME-DSH-0001 | MR-ME-103 | CWP-02-ME-01 | CWA-02
20MAX10 | ST control fluid unit | 20MAX | IEC | ALP-IEC-20MAA-IC-DSH-0001 ALP-IEC-20MAA-IC-DSH-0002 ALP-IEC-20MAA-IC-DSH-0003 ALP-IEC-20MAA-ME-DSH-0001 | MR-ME-103 | CWP-02-ME-01 | CWA-02
20MAY10 | ST control and protection cabinets | 20MAY | IEC | ALP-IEC-10MBY-ME-DSH-0001 | MR-IC-101 | CWP-02-IC-01 | CWA-02
20MKA10 | ST generator 270 MVA, TEWAC | 20MKA | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-02-ME-01 | CWA-02
20MKA20 | ST generator neutral earthing transformer | 20MKA | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-02-ME-01 | CWA-02
20MKA30 | ST generator protection panels (main 1 / main 2) | 20MKA | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-02-ME-01 | CWA-02
20MKC10 | ST static excitation | 20MKC | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-02-EL-01 | CWA-02
20MKC20 | ST excitation transformer | 20MKC | IEC | ALP-IEC-10MKA-EL-DSH-0001 ALP-IEC-10MKA-IC-DSH-0001 | MR-EL-101 | CWP-02-EL-01 | CWA-02

## Checks
Alpilla 600 MW Combined Cycle Power Plant - Checks
engine engineering_plan v1.6.0 ¦ generated 2026-09-29T03:49:44Z by EPCE ¦ data 73eaa92ce7c1ff26 ¦ dates computed from the workflow network and the CPM (working days)
Item | Check | Result | Detail
- | numbering | OK | 2238 document numbers checked, 0 finding(s)
- | KKS key list | INFO | 128 key titles not yet verified against the licensed VGB key list
- | AVEVA class | OK | 287 of 287 equipment records classified
- | AVEVA class | OK | 119 of 119 system records classified
- | AVEVA class | OK | 2238 of 2238 document records classified
- | agreement | OK | kks_key: 128 of 128 agreed
- | agreement | OK | cwa: 12 of 12 agreed
- | agreement | OK | cwp: 59 of 59 agreed
- | agreement | OK | ewp: 59 of 59 agreed
- | agreement | OK | mr: 65 of 65 agreed
- | MDL rules | OK | 80 rules: 0 required document(s) missing, 0 to update, 0 orphan(s)
BM-ALL-EPC | benchmark | OK | all EPC sheets 13,430 vs indicative 8,000 - 20,000
BM-ALL-EPC | benchmark | OK | all EPC hours 201,984 vs indicative 150,000 - 320,000
BM-ALL-SUP | benchmark | OK | all SUPPLIER sheets 7,979 vs indicative 3,000 - 10,000
BM-CM | benchmark | OK | commissioning EPC docs 236 vs indicative 150 - 400
BM-CV | benchmark | OK | civil EPC sheets 704 vs indicative 500 - 1,500
BM-EL | benchmark | OK | electrical EPC sheets 1,884 vs indicative 1,200 - 3,000
BM-GE | benchmark | OK | general EPC docs 108 vs indicative 50 - 200
BM-HS | benchmark | OK | hse EPC docs 37 vs indicative 30 - 120
BM-HV | benchmark | OK | hvac EPC sheets 156 vs indicative 100 - 400
BM-IC | benchmark | OK | i_and_c EPC sheets 5,259 vs indicative 4,000 - 9,000
BM-ME | benchmark | OK | mechanical EPC sheets 478 vs indicative 250 - 800
BM-PI | benchmark | OK | piping EPC sheets 4,074 vs indicative 3,500 - 7,000
BM-PR | benchmark | OK | process EPC sheets 248 vs indicative 200 - 500
BM-SS | benchmark | OK | structural EPC sheets 223 vs indicative 150 - 600
process | design criteria | OK | ALP-EPC-00000-PR-DBR-0001
mechanical | design criteria | OK | ALP-EPC-00000-ME-DBR-0001
piping | design criteria | OK | ALP-EPC-00000-PI-RPT-0001, ALP-EPC-00000-PI-SPC-0002
electrical | design criteria | OK | ALP-EPC-00000-EL-DBR-0001
i_and_c | design criteria | OK | ALP-EPC-00000-IC-DBR-0001
civil | design criteria | OK | ALP-EPC-00000-CV-DBR-0001
hvac | design criteria | OK | ALP-EPC-00000-HV-DBR-0001
hse | design criteria | OK | ALP-EPC-00000-HS-DBR-0001
ALP-EPC-00000-CM-OMM-0002 | inputs | INFO | none of the typical inputs ['CMP', 'PID'] of a OMM
ALP-EPC-00000-PI-M3D-0004 | inputs | INFO | none of the typical inputs ['ISO', 'LAY', 'PLT', 'PPL'] of a M3D
ALP-EPC-00GQA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-00UPA-CV-RBR-0001 | inputs | INFO | none of the typical inputs ['FND'] of a RBR
ALP-EPC-00UZC-CV-RBR-0001 | inputs | INFO | none of the typical inputs ['FND'] of a RBR
ALP-EPC-00UZE-CV-RBR-0001 | inputs | INFO | none of the typical inputs ['FND'] of a RBR
ALP-EPC-10BAA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-10BAC-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-10BAT-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-10HAA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-10HNA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-10HSA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-10MBA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-10MBL-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-10MBN-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-10MBP-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-10MBU-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-10MBV-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-10MBY-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-10MKA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-10MKC-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-10MKG-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-20BAA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-20BAC-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-20BAT-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-20MAA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-20MAB-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-20MAG-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-20MAJ-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-20MAV-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-20MAW-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-20MAX-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-20MAY-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-20MKA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
ALP-EPC-20MKC-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB
- | coverage requirement | OK | 150 of 150 requirements answered
- | coverage scope | OK | 88 of 88 EPC/IEC scope items covered
EWP-01-CV-01 | EWP float | WARN | IFC 2027-04-12 (ALP-EPC-10UMA-CV-FND-0001), needed 2027-03-22 for CWP-01-CV-01 start 2027-04-19: float -3 wd
EWP-01-CV-02 | EWP float | WARN | IFC 2027-06-22 (ALP-EPC-10UMA-CV-RBR-0001), needed 2027-04-19 for CWP-01-CV-02 start 2027-05-17: float -7 wd
EWP-01-EL-01 | EWP float | OK | IFC 2027-10-28 (ALP-EPC-00UBF-EL-ELY-0001), needed 2028-01-10 for CWP-01-EL-01 start 2028-02-07: float 81 wd
EWP-01-HV-01 | EWP float | OK | IFC 2027-06-11 (ALP-EPC-10UMA-HV-GAD-0001), needed 2027-11-01 for CWP-01-HV-01 start 2027-11-29: float 125 wd
EWP-01-IC-01 | EWP float | OK | IFC 2027-10-05 (ALP-EPC-10UMA-IC-ELY-0001), needed 2028-02-07 for CWP-01-IC-01 start 2028-03-06: float 128 wd
EWP-01-ME-01 | EWP float | OK | IFC 2027-09-06 (ALP-IEC-10MBA-ME-PRC-0001), needed 2027-10-18 for CWP-01-ME-01 start 2027-11-15: float 30 wd
EWP-01-PI-01 | EWP float | OK | IFC 2028-02-29 (ALP-EPC-10LAE-PI-SUP-0001), needed 2027-12-13 for CWP-01-PI-01 start 2028-01-10: float 19 wd
EWP-01-SS-01 | EWP float | OK | IFC 2027-07-07 (ALP-EPC-10UMA-SS-STL-0001), needed 2027-07-12 for CWP-01-SS-01 start 2027-08-09: float 36 wd
EWP-02-CV-01 | EWP float | WARN | IFC 2027-04-12 (ALP-EPC-20UMB-CV-FND-0001), needed 2027-03-22 for CWP-02-CV-01 start 2027-04-19: float -5 wd
EWP-02-CV-02 | EWP float | WARN | IFC 2027-06-25 (ALP-EPC-20UMB-CV-RBR-0001), needed 2027-04-19 for CWP-02-CV-02 start 2027-05-17: float -4 wd
EWP-02-EL-01 | EWP float | OK | IFC 2027-11-24 (ALP-EPC-20UMB-EL-ELY-0002), needed 2028-02-28 for CWP-02-EL-01 start 2028-03-27: float 90 wd
EWP-02-IC-01 | EWP float | OK | IFC 2027-10-01 (ALP-EPC-20UMB-IC-ELY-0001), needed 2028-03-27 for CWP-02-IC-01 start 2028-04-24: float 168 wd
EWP-02-ME-01 | EWP float | OK | IFC 2027-06-11 (ALP-M02-20LCB-ME-GAD-0001), needed 2027-12-20 for CWP-02-ME-01 start 2028-01-17: float 208 wd
EWP-02-PI-01 | EWP float | OK | IFC 2028-04-26 (ALP-EPC-20LCA-PI-SUP-0001), needed 2028-01-31 for CWP-02-PI-01 start 2028-02-28: float 13 wd
EWP-02-SS-01 | EWP float | OK | IFC 2027-07-08 (ALP-EPC-20UMB-SS-STL-0001), needed 2027-07-12 for CWP-02-SS-01 start 2027-08-09: float 35 wd
EWP-03-CV-01 | EWP float | WARN | IFC 2027-05-11 (ALP-EPC-00UBA-HV-GAD-0002), needed 2027-03-29 for CWP-03-CV-01 start 2027-04-26: float -10 wd
EWP-03-EL-01 | EWP float | OK | IFC 2027-09-21 (ALP-EPC-00UBA-IC-ELY-0002), needed 2027-10-25 for CWP-03-EL-01 start 2027-11-22: float 53 wd
EWP-03-HV-01 | EWP float | OK | IFC 2027-10-20 (ALP-EPC-00SAA-PI-SUP-0001), needed 2027-10-11 for CWP-03-HV-01 start 2027-11-08: float 28 wd
EWP-03-SS-01 | EWP float | OK | IFC 2027-05-07 (ALP-EPC-00UBA-SS-STL-0002), needed 2027-05-24 for CWP-03-SS-01 start 2027-06-21: float 56 wd
EWP-04-CV-01 | EWP float | WARN | IFC 2027-05-04 (ALP-EPC-00UAC-HV-GAD-0001), needed 2027-04-05 for CWP-04-CV-01 start 2027-05-03: float -3 wd
EWP-04-EL-01 | EWP float | OK | IFC 2027-10-07 (ALP-EPC-00UAC-EL-CBL-0001), needed 2028-01-04 for CWP-04-EL-01 start 2028-02-01: float 93 wd
EWP-04-SS-01 | EWP float | OK | IFC 2027-04-23 (ALP-EPC-00UAC-SS-STL-0002), needed 2027-05-31 for CWP-04-SS-01 start 2027-06-28: float 56 wd
EWP-05-CV-01 | EWP float | WARN | IFC 2027-06-10 (ALP-EPC-00UPC-CV-RBR-0001), needed 2027-03-25 for CWP-05-CV-01 start 2027-04-22: float -10 wd
EWP-05-EL-01 | EWP float | OK | IFC 2027-11-03 (ALP-EPC-00UPC-EL-ELY-0003), needed 2028-01-31 for CWP-05-EL-01 start 2028-02-28: float 77 wd
EWP-05-IC-01 | EWP float | OK | IFC 2027-09-14 (ALP-EPC-00UPC-IC-ELY-0001), needed 2028-02-28 for CWP-05-IC-01 start 2028-03-27: float 138 wd
EWP-05-ME-01 | EWP float | OK | IFC 2027-05-27 (ALP-M05-00PBA-EL-WIR-0001), needed 2027-12-20 for CWP-05-ME-01 start 2028-01-17: float 187 wd
EWP-05-PI-01 | EWP float | OK | IFC 2027-10-05 (ALP-EPC-00PBA-PI-SUP-0001), needed 2027-09-20 for CWP-05-PI-01 start 2027-10-18: float 49 wd
EWP-06-CV-01 | EWP float | WARN | IFC 2027-10-20 (ALP-EPC-00UPA-EL-ELY-0001), needed 2027-09-03 for CWP-06-CV-01 start 2027-10-01: float -7 wd
EWP-07-CV-01 | EWP float | WARN | IFC 2027-06-07 (ALP-EPC-00UGA-HV-GAD-0001), needed 2027-04-05 for CWP-07-CV-01 start 2027-05-03: float -12 wd
EWP-07-EL-01 | EWP float | OK | IFC 2027-11-08 (ALP-EPC-00UGA-EL-ELY-0002), needed 2028-02-21 for CWP-07-EL-01 start 2028-03-20: float 91 wd
EWP-07-IC-01 | EWP float | OK | IFC 2027-09-24 (ALP-EPC-00UGA-IC-ELY-0001), needed 2028-03-20 for CWP-07-IC-01 start 2028-04-17: float 153 wd
EWP-07-ME-01 | EWP float | OK | IFC 2027-06-03 (ALP-M12-00GBA-EL-WIR-0001), needed 2027-12-27 for CWP-07-ME-01 start 2028-01-24: float 197 wd
EWP-07-PI-01 | EWP float | OK | IFC 2028-03-09 (ALP-EPC-00GHA-PI-SUP-0001), needed 2028-01-24 for CWP-07-PI-01 start 2028-02-21: float 17 wd
EWP-07-SS-01 | EWP float | OK | IFC 2027-05-05 (ALP-EPC-00UGA-SS-STL-0002), needed 2027-06-14 for CWP-07-SS-01 start 2027-07-12: float 58 wd
EWP-08-CV-01 | EWP float | INFO | IFC 2027-06-10 (ALP-EPC-00UQA-HV-GAD-0001), needed 2027-05-04 for CWP-08-CV-01 start 2027-06-01: float 3 wd
EWP-08-EL-01 | EWP float | OK | IFC 2027-10-25 (ALP-EPC-00UQA-EL-CBL-0001), needed 2028-01-10 for CWP-08-EL-01 start 2028-02-07: float 85 wd
EWP-08-IC-01 | EWP float | OK | IFC 2027-10-08 (ALP-EPC-00UQA-IC-ELY-0001), needed 2028-02-21 for CWP-08-IC-01 start 2028-03-20: float 129 wd
EWP-08-ME-01 | EWP float | OK | IFC 2027-08-19 (ALP-M11-00QCA-ME-GAD-0001), needed 2027-11-01 for CWP-08-ME-01 start 2027-11-29: float 108 wd
EWP-08-PI-01 | EWP float | OK | IFC 2028-01-26 (ALP-EPC-10LAB-PI-SUP-0001), needed 2027-12-13 for CWP-08-PI-01 start 2028-01-10: float 28 wd
EWP-08-SS-01 | EWP float | OK | IFC 2027-06-16 (ALP-EPC-00UQA-SS-STL-0001), needed 2027-06-29 for CWP-08-SS-01 start 2027-07-27: float 39 wd
EWP-09-CV-01 | EWP float | OK | IFC 2027-08-13 (ALP-EPC-00UEK-CV-RBR-0001), needed 2027-08-04 for CWP-09-CV-01 start 2027-09-01: float 18 wd
EWP-09-EL-01 | EWP float | OK | IFC 2027-09-08 (ALP-EPC-00UEK-EL-ELY-0003), needed 2027-12-27 for CWP-09-EL-01 start 2028-01-24: float 89 wd
EWP-09-IC-01 | EWP float | OK | IFC 2027-09-15 (ALP-EPC-00UEK-IC-ELY-0001), needed 2028-01-24 for CWP-09-IC-01 start 2028-02-21: float 111 wd
EWP-09-ME-01 | EWP float | OK | IFC 2027-05-20 (ALP-M15-00EKA-EL-WIR-0001), needed 2027-11-01 for CWP-09-ME-01 start 2027-11-29: float 147 wd
EWP-09-PI-01 | EWP float | OK | IFC 2027-12-08 (ALP-EPC-00EKC-PI-SUP-0001), needed 2027-11-29 for CWP-09-PI-01 start 2027-12-27: float 33 wd
EWP-10-CV-01 | EWP float | OK | IFC 2027-07-08 (ALP-EPC-00UEG-CV-EFD-0001), needed 2027-06-03 for CWP-10-CV-01 start 2027-07-01: float 20 wd
EWP-10-EL-01 | EWP float | OK | IFC 2027-10-12 (ALP-EPC-00UEG-EL-CBL-0001), needed 2028-01-24 for CWP-10-EL-01 start 2028-02-21: float 92 wd
EWP-10-IC-01 | EWP float | OK | IFC 2027-09-14 (ALP-EPC-00UEG-IC-ELY-0001), needed 2028-02-21 for CWP-10-IC-01 start 2028-03-20: float 133 wd
EWP-10-ME-01 | EWP float | OK | IFC 2027-05-07 (ALP-M16-00EGA-ME-GAD-0001), needed 2027-10-04 for CWP-10-ME-01 start 2027-11-01: float 175 wd
EWP-10-PI-01 | EWP float | OK | IFC 2028-01-24 (ALP-EPC-00EGC-PI-SUP-0001), needed 2027-12-27 for CWP-10-PI-01 start 2028-01-24: float 30 wd
EWP-11-CV-01 | EWP float | WARN | IFC 2027-05-03 (ALP-EPC-00USA-HV-GAD-0001), needed 2027-03-29 for CWP-11-CV-01 start 2027-04-26: float -1 wd
EWP-11-EL-01 | EWP float | OK | IFC 2027-09-03 (ALP-EPC-00UCA-EL-ELY-0002), needed 2027-11-08 for CWP-11-EL-01 start 2027-12-06: float 62 wd
EWP-11-HV-01 | EWP float | OK | IFC 2027-08-04 (ALP-EPC-00UCA-PI-PPL-0001), needed 2027-11-08 for CWP-11-HV-01 start 2027-12-06: float 82 wd
EWP-11-IC-01 | EWP float | OK | IFC 2027-10-07 (ALP-EPC-00UCA-IC-ELY-0001), needed 2027-11-22 for CWP-11-IC-01 start 2027-12-20: float 76 wd
EWP-11-SS-01 | EWP float | OK | IFC 2027-06-18 (ALP-EPC-00USA-SS-STL-0002), needed 2027-05-24 for CWP-11-SS-01 start 2027-06-21: float 35 wd
EWP-12-CV-01 | EWP float | WARN | IFC 2027-02-22 (ALP-EPC-00UZB-CV-CVL-0001), needed 2027-01-18 for CWP-12-CV-01 start 2027-01-25: float -13 wd
EWP-12-CV-02 | EWP float | OK | IFC 2027-06-21 (ALP-EPC-00UZD-CV-FND-0001), needed 2027-03-22 for CWP-12-CV-02 start 2027-04-19: float 16 wd
EWP-12-EL-01 | EWP float | OK | IFC 2027-06-17 (ALP-EPC-00UZD-EL-ELY-0001), needed 2027-05-17 for CWP-12-EL-01 start 2027-06-14: float 27 wd
EWP-12-PI-01 | EWP float | INFO | IFC 2027-10-18 (ALP-EPC-00UZA-IC-ELY-0001), needed 2027-07-12 for CWP-12-PI-01 start 2027-08-09: float 4 wd
MR-CV-001 | PWP float | OK | PO 2027-01-14, on site 2027-02-11, needed 2027-04-19 (CWP-01-CV-01): float 47 wd
MR-CV-002 | PWP float | OK | PO 2026-12-24, on site 2027-01-07, needed 2027-01-25 (CWP-12-CV-01): float 12 wd
MR-CV-003 | PWP float | OK | PO 2027-03-02, on site 2027-07-20, needed 2027-10-01 (CWP-06-CV-01): float 53 wd
MR-EL-001 | PWP float | INFO | PO 2026-12-15, on site 2028-01-25, needed 2028-02-01 (CWP-04-EL-01): float 5 wd
MR-EL-002 | PWP float | OK | PO 2027-02-09, on site 2027-12-14, needed 2028-02-07 (CWP-01-EL-01): float 39 wd
MR-EL-003 | PWP float | OK | PO 2027-01-14, on site 2027-10-21, needed 2027-11-22 (CWP-03-EL-01): float 22 wd
MR-EL-004 | PWP float | OK | PO 2027-02-19, on site 2027-09-03, needed 2027-11-22 (CWP-03-EL-01): float 56 wd
MR-EL-005 | PWP float | OK | PO 2027-01-28, on site 2027-09-23, needed 2027-11-22 (CWP-03-EL-01): float 42 wd
MR-EL-006 | PWP float | OK | PO 2027-01-14, on site 2027-10-21, needed 2027-11-22 (CWP-03-EL-01): float 22 wd
MR-EL-007 | PWP float | OK | PO 2027-03-02, on site 2027-09-14, needed 2027-11-22 (CWP-03-EL-01): float 49 wd
MR-EL-008 | PWP float | OK | PO 2027-04-08, on site 2027-09-09, needed 2027-11-22 (CWP-03-EL-01): float 52 wd
MR-EL-009 | PWP float | WARN | PO 2027-03-11, on site 2027-07-15, needed 2027-06-14 (CWP-12-EL-01): float -23 wd
MR-EL-010 | PWP float | OK | PO 2027-04-27, on site 2027-09-07, needed 2027-11-01 (CWP-12-PI-01): float 39 wd
MR-EL-011 | PWP float | INFO | PO 2026-11-16, on site 2027-01-18, needed 2027-01-25 (CWP-12-CV-01): float 5 wd
MR-EL-012 | PWP float | OK | PO 2027-07-05, on site 2027-07-05, needed 2027-11-22 (CWP-03-EL-01): float 100 wd
MR-EL-101 | PWP float | INFO | PO 2026-11-02, on site 2027-11-08, needed 2027-11-15 (CWP-01-ME-01): float 5 wd
MR-EL-102 | PWP float | OK | PO 2026-11-02, on site 2027-11-29, needed 2028-02-07 (CWP-01-EL-01): float 50 wd
MR-HV-001 | PWP float | OK | PO 2027-01-28, on site 2027-09-23, needed 2027-11-08 (CWP-03-HV-01): float 32 wd
MR-IC-001 | PWP float | OK | PO 2027-01-21, on site 2027-11-25, needed 2027-12-20 (CWP-11-IC-01): float 17 wd
MR-IC-002 | PWP float | OK | PO 2027-03-15, on site 2027-11-08, needed 2028-03-06 (CWP-01-IC-01): float 85 wd
MR-IC-003 | PWP float | OK | PO 2027-03-15, on site 2027-11-08, needed 2028-03-06 (CWP-01-IC-01): float 85 wd
MR-IC-004 | PWP float | OK | PO 2027-03-25, on site 2027-10-21, needed 2028-02-21 (CWP-09-IC-01): float 87 wd
MR-IC-005 | PWP float | OK | PO 2027-03-25, on site 2027-11-18, needed 2028-01-10 (CWP-01-PI-01): float 37 wd
MR-IC-006 | PWP float | OK | PO 2027-05-28, on site 2027-10-29, needed 2027-12-20 (CWP-11-IC-01): float 36 wd
MR-IC-007 | PWP float | OK | PO 2027-05-25, on site 2027-10-26, needed 2027-12-20 (CWP-11-IC-01): float 39 wd
MR-IC-008 | PWP float | OK | PO 2027-05-20, on site 2027-12-02, needed 2027-12-20 (CWP-11-IC-01): float 12 wd
MR-IC-009 | PWP float | OK | PO 2027-06-03, on site 2028-03-23, needed 2028-04-10 (CWP-11-IC-01): float 12 wd
MR-IC-010 | PWP float | OK | PO 2027-06-14, on site 2027-09-20, needed 2028-03-06 (CWP-01-IC-01): float 120 wd
MR-IC-101 | PWP float | OK | PO 2026-11-02, on site 2027-08-23, needed 2028-03-06 (CWP-01-IC-01): float 140 wd
MR-ME-001 | PWP float | INFO | PO 2027-01-14, on site 2027-11-18, needed 2027-11-29 (CWP-08-ME-01): float 7 wd
MR-ME-002 | PWP float | OK | PO 2027-02-18, on site 2027-11-25, needed 2028-01-17 (CWP-02-ME-01): float 37 wd
MR-ME-003 | PWP float | OK | PO 2027-01-14, on site 2027-12-30, needed 2028-01-17 (CWP-05-ME-01): float 12 wd
MR-ME-004 | PWP float | OK | PO 2027-02-02, on site 2027-11-09, needed 2028-01-17 (CWP-05-ME-01): float 49 wd
MR-ME-005 | PWP float | OK | PO 2027-02-03, on site 2027-11-10, needed 2028-01-17 (CWP-05-ME-01): float 48 wd
MR-ME-006 | PWP float | OK | PO 2027-03-12, on site 2027-11-05, needed 2028-02-28 (CWP-02-PI-01): float 81 wd
MR-ME-007 | PWP float | OK | PO 2027-02-09, on site 2027-10-05, needed 2027-11-29 (CWP-08-ME-01): float 39 wd
MR-ME-008 | PWP float | OK | PO 2027-02-15, on site 2027-10-11, needed 2027-11-29 (CWP-08-ME-01): float 35 wd
MR-ME-009 | PWP float | INFO | PO 2027-01-14, on site 2027-11-18, needed 2027-11-29 (CWP-08-ME-01): float 7 wd
MR-ME-010 | PWP float | OK | PO 2027-06-03, on site 2027-11-04, needed 2027-11-29 (CWP-08-ME-01): float 17 wd
MR-ME-011 | PWP float | WARN | PO 2027-05-28, on site 2027-12-10, needed 2027-11-29 (CWP-08-ME-01): float -9 wd
MR-ME-012 | PWP float | INFO | PO 2027-01-28, on site 2028-01-13, needed 2028-01-24 (CWP-07-ME-01): float 7 wd
MR-ME-013 | PWP float | OK | PO 2027-01-14, on site 2027-07-29, needed 2027-11-29 (CWP-08-ME-01): float 87 wd
MR-ME-014 | PWP float | OK | PO 2027-01-28, on site 2027-09-23, needed 2028-01-24 (CWP-07-ME-01): float 87 wd
MR-ME-015 | PWP float | INFO | PO 2027-01-14, on site 2027-11-18, needed 2027-11-29 (CWP-09-ME-01): float 7 wd
MR-ME-016 | PWP float | INFO | PO 2027-01-14, on site 2027-10-21, needed 2027-11-01 (CWP-10-ME-01): float 7 wd
MR-ME-017 | PWP float | OK | PO 2027-03-24, on site 2027-06-30, needed 2027-11-01 (CWP-10-ME-01): float 88 wd
MR-ME-018 | PWP float | OK | PO 2027-02-18, on site 2027-10-14, needed 2027-11-29 (CWP-08-ME-01): float 32 wd
MR-ME-019 | PWP float | OK | PO 2027-02-05, on site 2027-08-20, needed 2027-11-15 (CWP-01-ME-01): float 61 wd
MR-ME-020 | PWP float | OK | PO 2027-01-28, on site 2027-10-07, needed 2027-11-29 (CWP-01-HV-01): float 37 wd
MR-ME-021 | PWP float | OK | PO 2027-01-14, on site 2027-10-21, needed 2027-11-15 (CWP-01-ME-01): float 17 wd
MR-ME-022 | PWP float | OK | PO 2027-06-29, on site 2027-06-29, needed 2028-01-10 (CWP-01-PI-01): float 139 wd
MR-ME-023 | PWP float | OK | PO 2027-09-15, on site 2027-09-15, needed 2027-11-15 (CWP-01-ME-01): float 43 wd
MR-ME-024 | PWP float | OK | PO 2027-09-17, on site 2027-09-17, needed 2027-11-15 (CWP-01-ME-01): float 41 wd
MR-ME-101 | PWP float | INFO | PO 2026-11-02, on site 2027-11-15, needed 2027-11-15 (CWP-01-ME-01): float 0 wd
MR-ME-102 | PWP float | INFO | PO 2026-11-02, on site 2027-11-15, needed 2027-11-15 (CWP-01-ME-01): float 0 wd
MR-ME-103 | PWP float | INFO | PO 2026-11-02, on site 2028-01-10, needed 2028-01-17 (CWP-02-ME-01): float 5 wd
MR-PI-001 | PWP float | OK | PO 2027-01-28, on site 2027-07-15, needed 2027-08-09 (CWP-12-PI-01): float 17 wd
MR-PI-002 | PWP float | WARN | PO 2027-03-25, on site 2028-02-10, needed 2028-01-10 (CWP-01-PI-01): float -23 wd
MR-PI-003 | PWP float | OK | PO 2027-03-08, on site 2027-10-04, needed 2028-01-10 (CWP-01-PI-01): float 70 wd
MR-PI-004 | PWP float | OK | PO 2027-01-13, on site 2027-09-08, needed 2027-10-18 (CWP-05-PI-01): float 28 wd
MR-PI-005 | PWP float | OK | PO 2027-05-25, on site 2027-10-05, needed 2028-01-10 (CWP-01-PI-01): float 69 wd
MR-PI-006 | PWP float | OK | PO 2027-04-05, on site 2027-08-16, needed 2028-01-10 (CWP-01-PI-01): float 105 wd
MR-PI-007 | PWP float | OK | PO 2027-04-01, on site 2027-09-09, needed 2028-01-10 (CWP-01-PI-01): float 87 wd
MR-SS-001 | PWP float | OK | PO 2027-01-28, on site 2027-06-03, needed 2027-07-27 (CWP-08-SS-01): float 38 wd
MR-SS-002 | PWP float | OK | PO 2027-01-28, on site 2027-09-23, needed 2027-11-15 (CWP-01-ME-01): float 37 wd
KD-010 | key date | OK | Back-feed energisation (key date): forecast 2028-07-04, float 21 wd
KD-020 | key date | OK | GT first fire (key date): forecast 2028-09-18, float 10 wd
KD-030 | key date | OK | First synchronisation in combined cycle (key date): forecast 2028-11-20, float 31 wd
KD-040 | key date | OK | Taking-Over of the Works (Time for Completion, 975 days): forecast 2029-04-18, float 55 wd
10BAA10 | equipment data | INFO | switchgear: missing capacity (supplier data per VDRL)
10MKC10 | equipment data | INFO | switchgear: missing capacity, voltage (supplier data per VDRL)
20BAA10 | equipment data | INFO | switchgear: missing capacity (supplier data per VDRL)
20MAJ10AP001 | equipment data | INFO | pump: missing capacity, head, design_pressure, design_temperature (supplier data per VDRL)
20MAJ10AP002 | equipment data | INFO | pump: missing capacity, head, design_pressure, design_temperature (supplier data per VDRL)
20MKC10 | equipment data | INFO | switchgear: missing capacity, voltage (supplier data per VDRL)
- | equipment data | OK | 287 items: 281 complete, 0 EPC items incomplete, 6 supplier items awaiting supplier data
- | document inputs | OK | 1487 EPC documents, 0 without inputs outside the first-start types
- | production coverage | INFO | 18 of 1487 EPC documents have a producing engine; types covered: DBR 6/8, HMB 1/1, PLN 2/14, PRC 3/6, RPT 3/80, SPC 3/75; types without engine: ARC 11, BLK 8, CAL 74, CBL 11, CEM 27, CMP 68, CNR 43, CVL 6, DSH 198, EFD 12, ELY 67, FND 24, GAD 25, HAZ 10, HMI 42, HUP 11, IOL 1, ISO 42, ITP 37, LAY 12, LOG 50, LOP 24, LST 21, M3D 4, MDB 92, MDL 1, MOS 1, MRQ 59, OMM 61, PFD 2, PID 42, PLT 1, PPL 16, RBR 20, SCH 1, SDS 42, SLD 8, STL 21, STR 20, STU 18, SUP 42, TRP 11, TST 3, WIR 14

## Summary
Alpilla 600 MW Combined Cycle Power Plant - Summary by originator and discipline
engine engineering_plan v1.6.0 ¦ generated 2026-09-29T03:49:44Z by EPCE ¦ data 73eaa92ce7c1ff26 ¦ dates computed from the workflow network and the CPM (working days)
Originator | Discipline | Documents | Sheets | Hours | BDP | In EWP | In MR | Last IFC
C01 | general | 7 | 7 | 56 | 0 | 0 | 7 | 2027-02-11
C02 | general | 7 | 7 | 56 | 0 | 0 | 7 | 2027-01-21
C03 | general | 7 | 7 | 56 | 0 | 0 | 7 | 2027-03-30
E01 | civil | 1 | 3 | 7 | 0 | 0 | 1 | 2027-02-23
E01 | electrical | 1 | 12 | 10 | 0 | 1 | 1 | 2027-04-20
E01 | i_and_c | 2 | 21 | 13 | 0 | 0 | 2 | 2027-04-20
E01 | mechanical | 10 | 35 | 94 | 0 | 1 | 10 | 2028-03-07
E02 | civil | 1 | 1 | 5 | 0 | 0 | 1 | 2027-04-20
E02 | electrical | 1 | 16 | 12 | 0 | 1 | 1 | 2027-06-15
E02 | i_and_c | 2 | 11 | 11 | 0 | 0 | 2 | 2027-06-15
E02 | mechanical | 10 | 12 | 66 | 0 | 1 | 10 | 2028-02-08
E03 | i_and_c | 1 | 1 | 5 | 0 | 0 | 1 | 2027-04-13
E03 | mechanical | 10 | 12 | 66 | 0 | 1 | 10 | 2027-12-16
E04 | i_and_c | 1 | 1 | 5 | 0 | 0 | 1 | 2027-04-26
E04 | mechanical | 10 | 26 | 83 | 0 | 1 | 10 | 2027-11-12
E05 | electrical | 1 | 60 | 34 | 0 | 1 | 1 | 2027-05-04
E05 | i_and_c | 1 | 1 | 5 | 0 | 0 | 1 | 2027-04-12
E05 | mechanical | 10 | 52 | 114 | 0 | 1 | 10 | 2027-11-18
E06 | civil | 1 | 1 | 5 | 0 | 0 | 1 | 2027-03-18
E06 | electrical | 1 | 8 | 8 | 0 | 1 | 1 | 2027-05-07
E06 | i_and_c | 2 | 11 | 11 | 0 | 0 | 2 | 2027-05-07
E06 | mechanical | 10 | 14 | 68 | 0 | 1 | 10 | 2027-12-16
E07 | electrical | 1 | 60 | 34 | 0 | 1 | 1 | 2027-05-24
E07 | i_and_c | 1 | 1 | 5 | 0 | 0 | 1 | 2027-05-05
E07 | mechanical | 10 | 26 | 83 | 0 | 1 | 10 | 2027-11-23
E08 | mechanical | 3 | 3 | 18 | 0 | 0 | 3 | 2027-10-07
E09 | mechanical | 3 | 3 | 18 | 0 | 0 | 3 | 2027-08-12
E10 | i_and_c | 1 | 1 | 5 | 0 | 0 | 1 | 2027-06-15
E10 | mechanical | 7 | 7 | 48 | 0 | 0 | 7 | 2027-11-09
E11 | i_and_c | 1 | 1 | 5 | 0 | 0 | 1 | 2027-01-04
E11 | mechanical | 7 | 7 | 48 | 0 | 0 | 7 | 2027-04-05
E12 | general | 7 | 7 | 56 | 0 | 0 | 7 | 2027-08-02
EPC | civil | 115 | 704 | 29692 | 1 | 73 | 6 | 2027-10-07
EPC | commissioning | 236 | 236 | 7804 | 0 | 0 | 0 | 2029-04-25
EPC | electrical | 137 | 1884 | 15566 | 2 | 70 | 39 | 2028-08-01
EPC | general | 108 | 108 | 5332 | 2 | 0 | 93 | 2027-09-24
EPC | hse | 37 | 58 | 3864 | 1 | 11 | 0 | 2027-11-12
EPC | hvac | 22 | 156 | 4850 | 0 | 14 | 4 | 2027-06-28
EPC | i_and_c | 333 | 5259 | 26466 | 2 | 57 | 115 | 2029-03-12
EPC | mechanical | 195 | 478 | 8830 | 1 | 0 | 144 | 2027-05-04
EPC | piping | 150 | 4074 | 74668 | 3 | 112 | 50 | 2028-07-05
EPC | process | 126 | 248 | 16835 | 13 | 0 | 24 | 2027-08-13
EPC | project_control | 2 | 2 | 160 | 0 | 0 | 0 | 2027-07-12
EPC | structural | 26 | 223 | 7918 | 0 | 21 | 4 | 2027-08-16
H01 | electrical | 2 | 120 | 68 | 0 | 2 | 2 | 2027-05-04
H01 | i_and_c | 2 | 79 | 27 | 0 | 0 | 2 | 2027-05-04
H01 | mechanical | 10 | 147 | 230 | 0 | 1 | 10 | 2027-11-18
H01 | process | 1 | 10 | 34 | 0 | 0 | 1 | 2027-04-12
I01 | electrical | 1 | 40 | 24 | 0 | 1 | 1 | 2027-05-27
I01 | i_and_c | 1 | 1 | 5 | 0 | 0 | 1 | 2027-04-29
I01 | mechanical | 10 | 54 | 117 | 0 | 1 | 10 | 2028-01-20
I02 | electrical | 1 | 8 | 8 | 0 | 1 | 1 | 2027-06-17
I02 | i_and_c | 2 | 16 | 12 | 0 | 0 | 2 | 2027-06-17
I02 | mechanical | 10 | 17 | 72 | 0 | 1 | 10 | 2028-01-03
I03 | electrical | 1 | 8 | 8 | 0 | 1 | 1 | 2027-06-17
I03 | i_and_c | 2 | 32 | 16 | 0 | 0 | 2 | 2027-06-17
I03 | mechanical | 10 | 14 | 68 | 0 | 1 | 10 | 2028-01-03
I03 | process | 1 | 2 | 10 | 0 | 0 | 1 | 2027-05-26
I04 | mechanical | 3 | 3 | 18 | 0 | 0 | 3 | 2027-11-04
I05 | mechanical | 3 | 3 | 18 | 0 | 0 | 3 | 2027-12-02
I06 | electrical | 1 | 8 | 8 | 0 | 1 | 1 | 2027-07-30
I06 | i_and_c | 1 | 1 | 5 | 0 | 0 | 1 | 2027-07-16
I06 | mechanical | 10 | 77 | 145 | 0 | 1 | 10 | 2028-01-07
I07 | electrical | 1 | 12 | 10 | 0 | 1 | 1 | 2027-07-27
I07 | i_and_c | 1 | 1 | 5 | 0 | 0 | 1 | 2027-07-13
I07 | mechanical | 10 | 54 | 117 | 0 | 1 | 10 | 2028-01-04
I08 | electrical | 1 | 4 | 6 | 0 | 1 | 1 | 2027-08-11
I08 | i_and_c | 2 | 151 | 88 | 0 | 0 | 2 | 2027-10-13
I08 | mechanical | 10 | 17 | 72 | 0 | 1 | 10 | 2028-02-10
I09 | electrical | 1 | 4 | 6 | 0 | 1 | 1 | 2027-10-07
I09 | i_and_c | 1 | 1 | 5 | 0 | 0 | 1 | 2027-09-09
I09 | mechanical | 10 | 21 | 77 | 0 | 1 | 10 | 2028-06-01
I10 | mechanical | 3 | 3 | 18 | 0 | 0 | 3 | 2027-10-18
IEC | civil | 5 | 38 | 58 | 0 | 0 | 5 | 2027-01-25
IEC | commissioning | 6 | 31 | 110 | 0 | 0 | 6 | 2027-10-04
IEC | electrical | 13 | 379 | 458 | 0 | 8 | 10 | 2027-03-22
IEC | general | 3 | 3 | 220 | 0 | 0 | 0 | 2026-11-02
IEC | hse | 1 | 1 | 60 | 0 | 0 | 0 | 2027-02-22
IEC | i_and_c | 25 | 2649 | 1298 | 0 | 1 | 22 | 2027-07-26
IEC | mechanical | 60 | 492 | 1052 | 0 | 7 | 57 | 2028-07-24
IEC | piping | 2 | 2 | 160 | 0 | 0 | 0 | 2027-04-19
IEC | process | 6 | 65 | 821 | 0 | 0 | 4 | 2027-03-22
M01 | civil | 1 | 1 | 5 | 0 | 0 | 1 | 2027-03-25
M01 | electrical | 1 | 16 | 12 | 0 | 1 | 1 | 2027-05-20
M01 | i_and_c | 2 | 37 | 17 | 0 | 0 | 2 | 2027-05-20
M01 | mechanical | 10 | 17 | 72 | 0 | 1 | 10 | 2028-01-13
M01 | process | 1 | 2 | 10 | 0 | 0 | 1 | 2027-04-22
M02 | civil | 1 | 1 | 5 | 0 | 0 | 1 | 2027-04-22
M02 | electrical | 1 | 8 | 8 | 0 | 1 | 1 | 2027-06-11
M02 | i_and_c | 2 | 21 | 13 | 0 | 0 | 2 | 2027-06-11
M02 | mechanical | 10 | 14 | 68 | 0 | 1 | 10 | 2028-01-20
M02 | process | 1 | 1 | 7 | 0 | 0 | 1 | 2027-05-18
M03 | civil | 1 | 1 | 5 | 0 | 0 | 1 | 2027-03-25
M03 | electrical | 1 | 12 | 10 | 0 | 1 | 1 | 2027-05-20
M03 | i_and_c | 2 | 16 | 12 | 0 | 0 | 2 | 2027-05-20
M03 | mechanical | 10 | 14 | 68 | 0 | 1 | 10 | 2028-02-10
M03 | process | 1 | 2 | 10 | 0 | 0 | 1 | 2027-04-22
M04 | civil | 1 | 2 | 6 | 0 | 0 | 1 | 2027-04-06
M04 | electrical | 1 | 40 | 24 | 0 | 1 | 1 | 2027-05-26
M04 | i_and_c | 2 | 21 | 13 | 0 | 0 | 2 | 2027-05-26
M04 | mechanical | 10 | 31 | 89 | 0 | 1 | 10 | 2028-01-04
M04 | process | 1 | 3 | 13 | 0 | 0 | 1 | 2027-04-30
M05 | civil | 1 | 3 | 7 | 0 | 0 | 1 | 2027-04-07
M05 | electrical | 1 | 20 | 14 | 0 | 1 | 1 | 2027-05-27
M05 | i_and_c | 3 | 52 | 36 | 0 | 0 | 3 | 2027-08-24
M05 | mechanical | 10 | 33 | 92 | 0 | 1 | 10 | 2028-01-05
M05 | process | 1 | 3 | 13 | 0 | 0 | 1 | 2027-05-03
M06 | electrical | 1 | 12 | 10 | 0 | 1 | 1 | 2027-06-16
M06 | i_and_c | 2 | 11 | 11 | 0 | 0 | 2 | 2027-06-16
M06 | mechanical | 10 | 21 | 77 | 0 | 1 | 10 | 2027-12-31
M06 | process | 1 | 2 | 10 | 0 | 0 | 1 | 2027-05-25
M07 | civil | 1 | 2 | 6 | 0 | 0 | 1 | 2027-04-02
M07 | electrical | 1 | 16 | 12 | 0 | 1 | 1 | 2027-05-14
M07 | i_and_c | 2 | 37 | 17 | 0 | 0 | 2 | 2027-05-14
M07 | mechanical | 10 | 26 | 83 | 0 | 1 | 10 | 2027-11-30
M07 | process | 1 | 4 | 16 | 0 | 0 | 1 | 2027-04-22
M08 | civil | 1 | 2 | 6 | 0 | 0 | 1 | 2027-04-08
M08 | electrical | 1 | 16 | 12 | 0 | 1 | 1 | 2027-05-20
M08 | i_and_c | 3 | 54 | 37 | 0 | 0 | 3 | 2027-08-02
M08 | mechanical | 10 | 31 | 89 | 0 | 1 | 10 | 2027-12-06
M08 | process | 1 | 3 | 13 | 0 | 0 | 1 | 2027-04-28
M09 | civil | 1 | 2 | 6 | 0 | 0 | 1 | 2027-03-25
M09 | electrical | 1 | 20 | 14 | 0 | 1 | 1 | 2027-05-20
M09 | i_and_c | 3 | 68 | 42 | 0 | 0 | 3 | 2027-08-26
M09 | mechanical | 10 | 26 | 83 | 0 | 1 | 10 | 2028-01-13
M09 | process | 1 | 3 | 13 | 0 | 0 | 1 | 2027-04-22
M10 | electrical | 1 | 4 | 6 | 0 | 1 | 1 | 2027-08-05
M10 | i_and_c | 2 | 21 | 13 | 0 | 0 | 2 | 2027-08-05
M10 | mechanical | 10 | 26 | 83 | 0 | 1 | 10 | 2028-01-13
M10 | process | 1 | 4 | 16 | 0 | 0 | 1 | 2027-07-22
M11 | electrical | 1 | 28 | 18 | 0 | 1 | 1 | 2027-08-19
M11 | i_and_c | 2 | 21 | 13 | 0 | 0 | 2 | 2027-08-19
M11 | mechanical | 10 | 35 | 94 | 0 | 1 | 10 | 2028-02-18
M11 | process | 1 | 3 | 13 | 0 | 0 | 1 | 2027-08-02
M12 | civil | 1 | 6 | 10 | 0 | 0 | 1 | 2027-04-08
M12 | electrical | 1 | 72 | 40 | 0 | 1 | 1 | 2027-06-03
M12 | i_and_c | 3 | 177 | 86 | 0 | 0 | 3 | 2027-09-09
M12 | mechanical | 10 | 70 | 136 | 0 | 1 | 10 | 2028-02-24
M12 | process | 1 | 7 | 25 | 0 | 0 | 1 | 2027-05-06
M13 | civil | 1 | 3 | 7 | 0 | 0 | 1 | 2027-03-01
M13 | electrical | 1 | 20 | 14 | 0 | 1 | 1 | 2027-04-07
M13 | i_and_c | 2 | 19 | 13 | 0 | 0 | 2 | 2027-04-07
M13 | mechanical | 10 | 35 | 94 | 0 | 1 | 10 | 2027-10-07
M13 | process | 1 | 3 | 13 | 0 | 0 | 1 | 2027-03-19
M14 | civil | 1 | 6 | 10 | 0 | 0 | 1 | 2027-03-23
M14 | electrical | 1 | 76 | 42 | 0 | 1 | 1 | 2027-05-04
M14 | i_and_c | 3 | 133 | 72 | 0 | 0 | 3 | 2027-07-15
M14 | mechanical | 10 | 68 | 134 | 0 | 1 | 10 | 2027-11-18
M14 | process | 1 | 7 | 25 | 0 | 0 | 1 | 2027-04-12
M15 | civil | 1 | 3 | 7 | 0 | 0 | 1 | 2027-03-25
M15 | electrical | 1 | 20 | 14 | 0 | 1 | 1 | 2027-05-20
M15 | i_and_c | 2 | 58 | 22 | 0 | 0 | 2 | 2027-05-20
M15 | mechanical | 10 | 40 | 100 | 0 | 1 | 10 | 2028-01-13
M15 | process | 1 | 5 | 19 | 0 | 0 | 1 | 2027-04-22
M16 | civil | 1 | 4 | 8 | 0 | 0 | 1 | 2027-03-18
M16 | electrical | 1 | 40 | 24 | 0 | 1 | 1 | 2027-05-07
M16 | i_and_c | 2 | 53 | 21 | 0 | 0 | 2 | 2027-05-07
M16 | mechanical | 10 | 49 | 111 | 0 | 1 | 10 | 2027-12-16
M16 | process | 1 | 6 | 22 | 0 | 0 | 1 | 2027-04-13
M17 | general | 7 | 7 | 56 | 0 | 0 | 7 | 2027-04-21
M18 | civil | 1 | 2 | 6 | 0 | 0 | 1 | 2027-04-13
M18 | electrical | 1 | 12 | 10 | 0 | 1 | 1 | 2027-05-25
M18 | i_and_c | 2 | 21 | 13 | 0 | 0 | 2 | 2027-05-25
M18 | mechanical | 10 | 26 | 83 | 0 | 1 | 10 | 2027-12-09
M18 | process | 1 | 2 | 10 | 0 | 0 | 1 | 2027-05-03
M19 | civil | 1 | 1 | 5 | 0 | 0 | 1 | 2027-03-23
M19 | electrical | 1 | 4 | 6 | 0 | 1 | 1 | 2027-04-29
M19 | i_and_c | 2 | 14 | 12 | 0 | 0 | 2 | 2027-04-29
M19 | mechanical | 10 | 17 | 72 | 0 | 1 | 10 | 2027-10-29
M19 | process | 1 | 2 | 10 | 0 | 0 | 1 | 2027-04-12
M20 | civil | 1 | 6 | 10 | 0 | 0 | 1 | 2027-03-25
M20 | electrical | 1 | 24 | 16 | 0 | 1 | 1 | 2027-05-10
M20 | i_and_c | 2 | 74 | 26 | 0 | 0 | 2 | 2027-05-10
M20 | mechanical | 10 | 73 | 140 | 0 | 1 | 10 | 2027-12-02
M20 | process | 1 | 12 | 40 | 0 | 0 | 1 | 2027-04-16
M21 | civil | 1 | 2 | 6 | 0 | 0 | 1 | 2027-03-18
M21 | electrical | 1 | 16 | 12 | 0 | 1 | 1 | 2027-05-07
M21 | i_and_c | 1 | 1 | 5 | 0 | 0 | 1 | 2027-04-13
M21 | mechanical | 10 | 26 | 83 | 0 | 1 | 10 | 2027-12-16
M22 | general | 7 | 7 | 56 | 0 | 0 | 7 | 2027-07-27
M23 | general | 7 | 7 | 56 | 0 | 0 | 7 | 2027-10-13
M24 | general | 7 | 7 | 56 | 0 | 0 | 7 | 2027-10-15
P01 | mechanical | 3 | 3 | 18 | 0 | 0 | 3 | 2027-07-29
P02 | mechanical | 3 | 3 | 18 | 0 | 0 | 3 | 2028-02-10
P03 | mechanical | 3 | 3 | 18 | 0 | 0 | 3 | 2027-10-18
P04 | mechanical | 3 | 3 | 18 | 0 | 0 | 3 | 2027-09-22
P05 | mechanical | 3 | 3 | 18 | 0 | 0 | 3 | 2027-10-26
P06 | mechanical | 3 | 3 | 18 | 0 | 0 | 3 | 2027-09-06
P07 | mechanical | 3 | 3 | 18 | 0 | 0 | 3 | 2027-09-30
S01 | general | 7 | 7 | 56 | 0 | 0 | 7 | 2027-02-25
S01 | structural | 16 | 728 | 364 | 0 | 16 | 16 | 2027-03-25
S02 | civil | 1 | 1 | 5 | 0 | 0 | 1 | 2027-03-23
S02 | general | 7 | 7 | 56 | 0 | 0 | 7 | 2027-03-11
Total |  | 2238 | 21409 | 212536 | 25 | 459 | 1213 | 2029-04-25

## Void numbers
Alpilla 600 MW Combined Cycle Power Plant - Cancelled document numbers (kept, never reused)
engine engineering_plan v1.6.0 ¦ generated 2026-09-29T03:49:44Z by EPCE ¦ data 73eaa92ce7c1ff26 ¦ dates computed from the workflow network and the CPM (working days)
Document number | Title | Rule | Remarks
ALP-E03-00BBA-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - MV switchgear 10.5 kV | DL-V-FDL¦MR-EL-003¦1
ALP-E04-00BFT-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - LV transformers | DL-V-FDL¦MR-EL-004¦1
ALP-E05-00BFA-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - LV switchboards and MCCs | DL-V-FDL¦MR-EL-005¦1
ALP-E07-00BRA-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - UPS, batteries and DC systems | DL-V-FDL¦MR-EL-007¦1
ALP-EPC-00000-IC-SPC-0007 | Operator training simulator specification |  | Duplicate of the OTS package specification ALP-EPC-00CKA-GE-SPC-0001 (MR-IC-009)
ALP-EPC-00CJG-IC-LOG-0001 | Logic diagrams - Safety instrumented systems (BOP) - part 1 of 2 | DL-IC-LOG¦00CJG¦1
ALP-EPC-00CJG-IC-LOG-0002 | Logic diagrams - Safety instrumented systems (BOP) - part 2 of 2 | DL-IC-LOG¦00CJG¦2
ALP-EPC-00GBA-IC-LOG-0001 | Logic diagrams - Seawater reverse osmosis | DL-IC-LOG¦00GBA¦1
ALP-EPC-00GCA-IC-LOG-0001 | Logic diagrams - Demineralisation | DL-IC-LOG¦00GCA¦1
ALP-EPC-00GMA-ME-DSH-0001 | Datasheet - Process drains and waste water collection: filter | DL-ME-DSH¦00GMA:-:filter¦1
ALP-EPC-00GMA-ME-DSH-0002 | Datasheet - Process drains and waste water collection: pump (6 items) | DL-ME-DSH¦00GMA:-:pump¦1
ALP-EPC-00GMA-ME-DSH-0003 | Datasheet - Process drains and waste water collection: tank | DL-ME-DSH¦00GMA:-:tank¦1
ALP-EPC-00GNA-IC-LOG-0001 | Logic diagrams - Waste water treatment | DL-IC-LOG¦00GNA¦1
ALP-EPC-00GUA-IC-LOG-0001 | Logic diagrams - Sanitary waste water treatment | DL-IC-LOG¦00GUA¦1
ALP-EPC-00LDA-IC-LOG-0001 | Logic diagrams - Condensate polishing | DL-IC-LOG¦00LDA¦1
ALP-EPC-00PBA-IC-LOG-0001 | Logic diagrams - Electro-chlorination | DL-IC-LOG¦00PBA¦1
ALP-EPC-00QEA-IC-LOG-0001 | Logic diagrams - Compressed air | DL-IC-LOG¦00QEA¦1
ALP-EPC-00QHA-IC-LOG-0001 | Logic diagrams - Auxiliary boiler | DL-IC-LOG¦00QHA¦1
ALP-EPC-00SGA-ME-DSH-0003 | Fire Water System: Tank - Datasheet | DL-ME-DSH¦00SGA:MR-ME-020:tank¦1
ALP-EPC-00UAC-HS-LAY-0001 | Fire fighting, escape route and safety signage layouts - GIS building | DL-HS-ESC¦00UAC¦1
ALP-EPC-00UBA-HS-LAY-0001 | Fire fighting, escape route and safety signage layouts - Electrical building | DL-HS-ESC¦00UBA¦1
ALP-EPC-00UCA-HS-LAY-0001 | Fire fighting, escape route and safety signage layouts - Control building | DL-HS-ESC¦00UCA¦1
ALP-EPC-00UEK-HS-LAY-0001 | Fire fighting, escape route and safety signage layouts - Gas station structures | DL-HS-ESC¦00UEK¦1
ALP-EPC-00UGA-HS-LAY-0001 | Fire fighting, escape route and safety signage layouts - Water treatment building and basins | DL-HS-ESC¦00UGA¦1
ALP-EPC-00UPC-HS-LAY-0001 | Fire fighting, escape route and safety signage layouts - CW pump house | DL-HS-ESC¦00UPC¦1
ALP-EPC-00UQA-HS-LAY-0001 | Fire fighting, escape route and safety signage layouts - Utility building | DL-HS-ESC¦00UQA¦1
ALP-EPC-00USA-HS-LAY-0001 | Fire fighting, escape route and safety signage layouts - Workshop and warehouse | DL-HS-ESC¦00USA¦1
ALP-EPC-00UYA-HS-LAY-0001 | Fire fighting, escape route and safety signage layouts - Administration building | DL-HS-ESC¦00UYA¦1
ALP-EPC-00UZD-CV-FND-0002 | Piling layout and pile schedule - Pipe racks and pipe sleepers | DL-CV-PIL¦00UZD¦1
ALP-EPC-10UMA-HS-LAY-0001 | Fire fighting, escape route and safety signage layouts - Gas turbine hall | DL-HS-ESC¦10UMA¦1
ALP-EPC-20UMB-HS-LAY-0001 | Fire fighting, escape route and safety signage layouts - Steam turbine hall | DL-HS-ESC¦20UMB¦1
ALP-H01-00SAA-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - HVAC plant and equipment | DL-V-FDL¦MR-HV-001¦1
ALP-I01-00CJA-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - Plant DCS | DL-V-FDL¦MR-IC-001¦1
ALP-I02-00CQA-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - Continuous emission monitoring system | DL-V-FDL¦MR-IC-002¦1
ALP-I03-00QUA-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - Steam/water analysis system | DL-V-FDL¦MR-IC-003¦1
ALP-I06-00SGY-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - Fire detection and alarm system | DL-V-FDL¦MR-IC-006¦1
ALP-I07-00CYA-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - Telecom, CCTV, access control and perimeter security | DL-V-FDL¦MR-IC-007¦1
ALP-I08-00CJG-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - BOP safety instrumented system (IEC 61511) | DL-V-FDL¦MR-IC-008¦1
ALP-I09-00CKA-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - Operator training simulator, historian and performance monitoring | DL-V-FDL¦MR-IC-009¦1
ALP-IEC-10MBY-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - Turbine control system (IEC) | DL-V-FDL¦MR-IC-101¦1
ALP-M06-00PAH-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - Condenser tube cleaning system | DL-V-FDL¦MR-ME-006¦1
ALP-M10-00QJA-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - Nitrogen, hydrogen and CO2 supply | DL-V-FDL¦MR-ME-010¦1
ALP-M11-00QCA-CV-CAL-0001 | Supplier foundation loads and anchor bolt drawings - Chemical dosing skid | DL-V-FDL¦MR-ME-011¦1