# Alpilla 600 MW Combined Cycle Power Plant
Advanced Work Packaging Execution Plan

| Document number | ALP-EPC-00000-GE-PLN-0002 |
| --- | --- |
| Description | CWA, CWP, EWP, PWP, IWP |
| Revision / status | Rev A - IFR, draft (not issued) |
| Originator | Istanbul EPC Mühendislik ve Taahhüt A.Ş. |
| Discipline / type | general / PLN Plan (execution, quality, HSE, commissioning, training) |
| Review class | approval |

Planned issues (workflow timeline): IFR 2027-05-31, IFA 2027-06-28, IFC 2027-07-05

# 1. Purpose and definitions

Advanced Work Packaging (AWP) aligns engineering and procurement with the construction sequence: construction is planned by area and package first (path of construction), and engineering and procurement deliver what each package needs, when it needs it.

| Package | Definition on this project | Record |
| --- | --- | --- |
| CWA | Construction work area: geographic area of the plot, ordered in the path of construction | cwa |
| CWP | Construction work package: one per CWA and discipline, a level-3 CPM activity with the same id; scope, quantities and contractor | cwp / activity |
| EWP | Engineering work package: the IFC documents one CWP needs (one EWP per CWP); documents link to it | ewp |
| PWP | Procurement work package: a material requisition (MR) with its PO, vendor data, manufacture and delivery; linked to the CWPs that install its materials | mr |
| IWP | Installation work package: 1-2 weeks of work for one crew, prepared by the construction contractor from the CWP and released only when constraint-free | (construction) |

Decision: As DEC-EPCE-0006 with the release rule amended per TQ-037: a CWP is released when the documents of its first IWPs are IFC and their materials are on site or confirmed; progressive documents (document types with a progressive share) are released per IWP, needed at CWP start - lead + share x CWP duration; no IWP is issued unless all its documents are IFC and its constraints removed; EWP completeness for the next 8 weeks of IWPs is reported monthly per CWP. (DEC-EPCE-0012, agreed, OWNER / IEPC)

TQ-035 (closed, answered 2026-09-28 by Owner): (1) Accepted: the consortium numbering is the project numbering under ER-17.01; the Owner's EDMS will use it unchanged. (2) The KKS key list is approved for engineering. The Owner's Engineer verifies each key title against the VGB-S-811 key catalogue with the KKS manual review; until then keys stay flagged 'not verified'. (3) MDL accepted as baseline for the Basic Design Package. Review classes accepted with one change: logic diagrams (LOG) incl. cause and effect are safety relevant and are for approval. The MDL is updated monthly with the progress report. (4) AWP definitions accepted. The Owner requires every CWP to be released for construction only when its EWP is complete (all IFC) and its PWP materials are on site or have a confirmed delivery before the planned installation.

TQ-037 (closed, answered 2026-09-28 by Owner): Accepted as proposed, with the condition that the monthly report shows per CWP the IFC status of the documents needed for the next 8 weeks of IWPs, and that a CWP whose first-IWP documents are not IFC is not started. TQ-035 item (4) is amended accordingly.

# 2. Path of construction (CWAs)

| Seq | CWA | Title | Area (E / N, m) | Structures | Assets | Status | Description |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | CWA-12 | Site-wide infrastructure | E 0 to 400 / N 0 to 300 | 00UZA, 00UZB, 00UZC | 13 | agreed | Mobilisation, temporary facilities, roads, drainage, fencing, underground services, earthing grid, site lighting |
| 2 | CWA-01 | Power block - GT and HRSG | E 85 to 245 / N 125 to 215 | 10UMA, 10UHA, 10UHN, 00UBF | 37 | agreed | GT hall, GT, generator, filter house, HRSG, stack, GT GSU bay, ammonia injection |
| 2 | CWA-05 | CW pump house and onshore CW | E 120 to 180 / N 0 to 55 | 00UPC | 23 | agreed | CW pump house, screens, electro-chlorination, onshore CW culverts and GRP pipes |
| 3 | CWA-02 | Power block - ST and condenser | E 80 to 175 / N 55 to 125 | 20UMB, 00UBF | 29 | agreed | ST hall, ST, generator, condenser, CEPs, ST GSU bay |
| 3 | CWA-06 | Marine works (offshore) | E 100 to 300 / N -720 to 0 | 00UPA | 0 | agreed | Intake head, intake and outfall pipelines, outfall diffuser; works window 1 October - 30 April |
| 4 | CWA-03 | Electrical building and emergency power | E 20 to 75 / N 100 to 240 | 00UBA | 53 | agreed | MV/LV switchgear, UPS/DC, emergency diesel, HVAC plant rooms |
| 4 | CWA-07 | Water treatment and effluents | E 290 to 395 / N 12 to 110 | 00UGA | 42 | agreed | Demolition of the old foundations, SWRO, demineralisation, condensate polishing, tanks, WWT, sanitary |
| 4 | CWA-08 | BOP utilities | E 180 to 290 / N 55 to 125 | 00UQA | 55 | agreed | BFPs, CCW, compressed air, auxiliary boiler, N2, chemical dosing, ammonia storage, fire pumps |
| 4 | CWA-11 | Control, administration and workshop buildings | E 80 to 210 / N 215 to 295 | 00UCA, 00UYA, 00USA | 10 | agreed | Control building with CCR and DCS rooms, administration, workshop and warehouse |
| 5 | CWA-04 | 380 kV GIS switchyard | E 20 to 80 / N 240 to 295 | 00UAC | 1 | agreed | GIS building, line gantry (TP-E1) |
| 5 | CWA-09 | Fuel gas station | E 300 to 395 / N 220 to 295 | 00UEK | 6 | agreed | Gas receiving, filtration, fiscal metering (TP-G1) |
| 5 | CWA-10 | LDO tank farm and unloading | E 215 to 300 / N 220 to 295 | 00UEG | 18 | agreed | 4 unloading bays, 2 x 3,500 m3 tanks in bund, forwarding and treatment |

# 3. Construction work packages (CWPs)

| CWP | Title | Contractor | Start | Finish | EWP ready | EWP float | Last ROS | PWPs (MR) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CWP-01-CV-01 | Piling - power block GT/HRSG | Piling contractor | 2027-04-19 | 2027-07-09 | 2027-04-12 | -3 | 2027-02-11 | MR-CV-001 |
| CWP-01-CV-02 | Foundations - power block GT/HRSG | Civil contractor | 2027-05-17 | 2027-11-12 | 2027-06-22 | -7 | 2027-01-07 | MR-CV-002 |
| CWP-01-EL-01 | Electrical - power block GT/HRSG | Electrical contractor | 2028-02-07 | 2028-08-04 | 2027-10-28 | 81 | 2027-12-14 | MR-EL-002, MR-EL-008, MR-EL-009, MR-EL-012, MR-EL-102 |
| CWP-01-HV-01 | HVAC and fire protection - GT hall | HVAC contractor | 2027-11-29 | 2028-03-17 | 2027-06-11 | 125 | 2027-10-07 | MR-HV-001, MR-ME-020 |
| CWP-01-IC-01 | I&C - power block GT/HRSG | I&C contractor | 2028-03-06 | 2028-08-18 | 2027-10-05 | 128 | 2027-11-08 | MR-EL-012, MR-IC-002, MR-IC-003, MR-IC-004, MR-IC-010, MR-IC-101 |
| CWP-01-ME-01 | GT, generator and HRSG erection | Mechanical contractor | 2027-11-15 | 2028-07-07 | 2027-09-06 | 30 | 2027-11-15 | MR-EL-101, MR-ME-019, MR-ME-021, MR-ME-023, MR-ME-024, MR-ME-101, MR-ME-102, MR-SS-002 |
| CWP-01-PI-01 | Piping - power block GT/HRSG | Mechanical contractor | 2028-01-10 | 2028-08-04 | 2028-02-29 | 19 | 2028-02-10 | MR-IC-005, MR-ME-022, MR-ME-023, MR-PI-001, MR-PI-002, MR-PI-003, MR-PI-005, MR-PI-006, MR-PI-007 |
| CWP-01-SS-01 | GT hall steel, cladding, crane, pipe racks | Steel contractor | 2027-08-09 | 2028-01-07 | 2027-07-07 | 36 | 2027-06-03 | MR-SS-001 |
| CWP-02-CV-01 | Piling - ST hall and condenser | Piling contractor | 2027-04-19 | 2027-06-25 | 2027-04-12 | -5 | 2027-02-11 | MR-CV-001 |
| CWP-02-CV-02 | Foundations - ST hall and condenser | Civil contractor | 2027-05-17 | 2027-11-26 | 2027-06-25 | -4 | 2027-01-07 | MR-CV-002 |
| CWP-02-EL-01 | Electrical - ST island | Electrical contractor | 2028-03-27 | 2028-08-25 | 2027-11-24 | 90 | 2027-12-14 | MR-EL-002, MR-EL-008, MR-EL-009, MR-EL-102 |
| CWP-02-IC-01 | I&C - ST island | I&C contractor | 2028-04-24 | 2028-09-22 | 2027-10-01 | 168 | 2027-10-21 | MR-IC-004, MR-IC-010, MR-IC-101 |
| CWP-02-ME-01 | Condenser, ST and generator erection | Mechanical contractor | 2028-01-17 | 2028-08-11 | 2027-06-11 | 208 | 2028-01-10 | MR-EL-101, MR-ME-002, MR-ME-021, MR-ME-023, MR-ME-024, MR-ME-103 |
| CWP-02-PI-01 | Piping - ST island | Mechanical contractor | 2028-02-28 | 2028-09-22 | 2028-04-26 | 13 | 2028-02-10 | MR-IC-005, MR-ME-006, MR-ME-022, MR-PI-001, MR-PI-002, MR-PI-003, MR-PI-005, MR-PI-006, MR-PI-007 |
| CWP-02-SS-01 | ST hall steel, cladding, crane | Steel contractor | 2027-08-09 | 2028-01-07 | 2027-07-08 | 35 | 2027-06-03 | MR-SS-001 |
| CWP-03-CV-01 | Foundations - electrical building | Civil contractor | 2027-04-26 | 2027-07-30 | 2027-05-11 | -10 | 2027-01-07 | MR-CV-002 |
| CWP-03-EL-01 | MV/LV switchgear, UPS, DC, emergency diesel | Electrical contractor | 2027-11-22 | 2028-03-24 | 2027-09-21 | 53 | 2027-10-21 | MR-EL-003, MR-EL-004, MR-EL-005, MR-EL-006, MR-EL-007, MR-EL-008, MR-EL-012 |
| CWP-03-HV-01 | HVAC plant and electrical building HVAC | HVAC contractor | 2027-11-08 | 2028-02-11 | 2027-10-20 | 28 | 2027-09-23 | MR-HV-001 |
| CWP-03-SS-01 | Electrical building | Building contractor | 2027-06-21 | 2028-01-14 | 2027-05-07 | 56 | - | - |
| CWP-04-CV-01 | Foundations - GIS building and gantry | Civil contractor | 2027-05-03 | 2027-07-23 | 2027-05-04 | -3 | - | - |
| CWP-04-EL-01 | GIS erection, HV connections, testing | GIS supplier / electrical contractor | 2028-02-01 | 2028-06-19 | 2027-10-07 | 93 | 2028-01-25 | MR-EL-001, MR-EL-008 |
| CWP-04-SS-01 | GIS building | Building contractor | 2027-06-28 | 2027-11-12 | 2027-04-23 | 56 | - | - |
| CWP-05-CV-01 | CW pump house and onshore culverts | Civil contractor | 2027-04-22 | 2027-11-17 | 2027-06-10 | -10 | 2027-01-07 | MR-CV-002 |
| CWP-05-EL-01 | Electrical - CW pump house | Electrical contractor | 2028-02-28 | 2028-06-02 | 2027-11-03 | 77 | 2027-09-09 | MR-EL-008 |
| CWP-05-IC-01 | I&C - CW pump house | I&C contractor | 2028-03-27 | 2028-06-16 | 2027-09-14 | 138 | 2027-10-21 | MR-IC-004, MR-IC-010 |
| CWP-05-ME-01 | CW pumps, screens, electro-chlorination | Mechanical contractor | 2028-01-17 | 2028-05-05 | 2027-05-27 | 187 | 2027-12-30 | MR-ME-003, MR-ME-004, MR-ME-005 |
| CWP-05-PI-01 | CW GRP piping onshore | Mechanical contractor | 2027-10-18 | 2028-03-31 | 2027-10-05 | 49 | 2027-09-08 | MR-PI-004 |
| CWP-06-CV-01 | Marine works | Marine contractor | 2027-10-01 | 2028-03-30 | 2027-10-20 | -7 | 2027-09-07 | MR-CV-003, MR-EL-010 |
| CWP-07-CV-01 | Demolition and foundations - water treatment | Civil contractor | 2027-05-03 | 2027-10-01 | 2027-06-07 | -12 | - | - |
| CWP-07-EL-01 | Electrical - water treatment | Electrical contractor | 2028-03-20 | 2028-07-07 | 2027-11-08 | 91 | 2027-09-09 | MR-EL-008 |
| CWP-07-IC-01 | I&C - water treatment | I&C contractor | 2028-04-17 | 2028-07-21 | 2027-09-24 | 153 | 2027-10-21 | MR-IC-004 |
| CWP-07-ME-01 | Water treatment packages and tanks | Mechanical contractor | 2028-01-24 | 2028-06-09 | 2027-06-03 | 197 | 2028-01-13 | MR-ME-012, MR-ME-013, MR-ME-014 |
| CWP-07-PI-01 | Piping - water treatment | Mechanical contractor | 2028-02-21 | 2028-07-07 | 2028-03-09 | 17 | 2027-07-15 | MR-PI-001 |
| CWP-07-SS-01 | Water treatment building | Building contractor | 2027-07-12 | 2027-11-26 | 2027-05-05 | 58 | - | - |
| CWP-08-CV-01 | Foundations - BOP utilities | Civil contractor | 2027-06-01 | 2027-10-18 | 2027-06-10 | 3 | - | - |
| CWP-08-EL-01 | Electrical - BOP utilities | Electrical contractor | 2028-02-07 | 2028-06-23 | 2027-10-25 | 85 | 2027-09-09 | MR-EL-008 |
| CWP-08-IC-01 | I&C - BOP utilities | I&C contractor | 2028-03-20 | 2028-07-21 | 2027-10-08 | 129 | 2027-10-21 | MR-IC-004 |
| CWP-08-ME-01 | BOP utilities equipment | Mechanical contractor | 2027-11-29 | 2028-05-12 | 2027-08-19 | 108 | 2027-12-10 | MR-ME-001, MR-ME-007, MR-ME-008, MR-ME-009, MR-ME-010, MR-ME-011, MR-ME-013, MR-ME-017, MR-ME-018, MR-ME-020, MR-ME-023 |
| CWP-08-PI-01 | Piping - BOP utilities | Mechanical contractor | 2028-01-10 | 2028-06-23 | 2028-01-26 | 28 | 2027-11-18 | MR-IC-005, MR-ME-022, MR-PI-001, MR-PI-003, MR-PI-005, MR-PI-006, MR-PI-007 |
| CWP-08-SS-01 | Utility building and pipe racks | Steel contractor | 2027-07-27 | 2027-12-13 | 2027-06-16 | 39 | 2027-06-03 | MR-SS-001 |
| CWP-09-CV-01 | Foundations - gas station | Civil contractor | 2027-09-01 | 2027-11-23 | 2027-08-13 | 18 | - | - |
| CWP-09-EL-01 | Electrical - gas station | Electrical contractor | 2028-01-24 | 2028-03-31 | 2027-09-08 | 89 | 2027-09-09 | MR-EL-008 |
| CWP-09-IC-01 | I&C - gas station | I&C contractor | 2028-02-21 | 2028-04-28 | 2027-09-15 | 111 | 2027-10-21 | MR-IC-004 |
| CWP-09-ME-01 | Gas station equipment | Mechanical contractor | 2027-11-29 | 2028-02-18 | 2027-05-20 | 147 | 2027-11-18 | MR-ME-015 |
| CWP-09-PI-01 | Piping - gas station and gas line to the GT | Mechanical contractor | 2027-12-27 | 2028-04-14 | 2027-12-08 | 33 | 2027-07-15 | MR-PI-001 |
| CWP-10-CV-01 | Bund and tank foundations - LDO | Civil contractor | 2027-07-01 | 2027-11-03 | 2027-07-08 | 20 | - | - |
| CWP-10-EL-01 | Electrical - LDO | Electrical contractor | 2028-02-21 | 2028-05-12 | 2027-10-12 | 92 | 2027-09-09 | MR-EL-008 |
| CWP-10-IC-01 | I&C - LDO | I&C contractor | 2028-03-20 | 2028-06-09 | 2027-09-14 | 133 | 2027-10-21 | MR-IC-004 |
| CWP-10-ME-01 | LDO tanks and skids | Tank contractor | 2027-11-01 | 2028-05-12 | 2027-05-07 | 175 | 2027-10-21 | MR-ME-016, MR-ME-017 |
| CWP-10-PI-01 | Piping - LDO | Mechanical contractor | 2028-01-24 | 2028-06-09 | 2028-01-24 | 30 | 2027-07-15 | MR-PI-001 |
| CWP-11-CV-01 | Foundations - control, administration, workshop | Civil contractor | 2027-04-26 | 2027-08-13 | 2027-05-03 | -1 | - | - |
| CWP-11-EL-01 | Electrical - buildings | Electrical contractor | 2027-12-06 | 2028-03-24 | 2027-09-03 | 62 | 2027-09-09 | MR-EL-008 |
| CWP-11-HV-01 | HVAC - buildings | HVAC contractor | 2027-12-06 | 2028-03-10 | 2027-08-04 | 82 | 2027-09-23 | MR-HV-001 |
| CWP-11-IC-01 | DCS, CCR, telecom, CCTV | DCS supplier / I&C contractor | 2027-12-20 | 2028-05-05 | 2027-10-07 | 76 | 2028-03-23 | MR-IC-001, MR-IC-006, MR-IC-007, MR-IC-008, MR-IC-009 |
| CWP-11-SS-01 | Control, administration and workshop buildings | Building contractor | 2027-06-21 | 2028-02-25 | 2027-06-18 | 35 | - | - |
| CWP-12-CV-01 | Mobilisation, temporary facilities, site preparation | Civil contractor | 2027-01-25 | 2027-04-16 | 2027-02-22 | -13 | 2027-01-18 | MR-CV-002, MR-EL-011 |
| CWP-12-CV-02 | Roads, drainage and underground services | Civil contractor | 2027-04-19 | 2028-06-09 | 2027-06-21 | 16 | - | - |
| CWP-12-EL-01 | Earthing grid and site lighting | Electrical contractor | 2027-06-14 | 2028-05-26 | 2027-06-17 | 27 | 2027-07-15 | MR-EL-009 |
| CWP-12-PI-01 | Underground piping | Mechanical contractor | 2027-08-09 | 2028-05-12 | 2027-10-18 | 4 | 2027-09-07 | MR-EL-010, MR-PI-001 |

# 4. Engineering work packages (EWPs)

| EWP | CWP | Docs | Driving document | Complete (IFC) | First need | Float | Vendor data of | Vendor data | Float |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EWP-01-CV-01 | CWP-01-CV-01 | 4 | ALP-EPC-10UMA-CV-FND-0001 | 2027-04-12 | 2027-03-22 | -3 | MR-CV-001 | 2027-01-28 | 37 |
| EWP-01-CV-02 | CWP-01-CV-02 | 14 | ALP-EPC-10UMA-CV-RBR-0001 | 2027-06-22 | 2027-04-19 | -7 | MR-CV-002 | 2027-01-07 | 72 |
| EWP-01-EL-01 | CWP-01-EL-01 | 11 | ALP-EPC-00UBF-EL-ELY-0001 | 2027-10-28 | 2028-01-10 | 81 | MR-EL-012 | 2027-08-02 | 115 |
| EWP-01-HV-01 | CWP-01-HV-01 | 1 | ALP-EPC-10UMA-HV-GAD-0001 | 2027-06-11 | 2027-11-01 | 125 | MR-ME-020 | 2027-03-25 | 157 |
| EWP-01-IC-01 | CWP-01-IC-01 | 13 | ALP-EPC-10UMA-IC-ELY-0001 | 2027-10-05 | 2028-02-07 | 128 | MR-EL-012 | 2027-08-02 | 135 |
| EWP-01-ME-01 | CWP-01-ME-01 | 14 | ALP-IEC-10MBA-ME-PRC-0001 | 2027-09-06 | 2027-10-18 | 30 | MR-ME-024 | 2027-10-15 | 1 |
| EWP-01-PI-01 | CWP-01-PI-01 | 19 | ALP-EPC-10LAE-PI-SUP-0001 | 2028-02-29 | 2027-12-13 | 19 | MR-ME-023 | 2027-10-13 | 43 |
| EWP-01-SS-01 | CWP-01-SS-01 | 5 | ALP-EPC-10UMA-SS-STL-0001 | 2027-07-07 | 2027-07-12 | 36 | MR-SS-001 | 2027-02-25 | 97 |
| EWP-02-CV-01 | CWP-02-CV-01 | 1 | ALP-EPC-20UMB-CV-FND-0001 | 2027-04-12 | 2027-03-22 | -5 | MR-CV-001 | 2027-01-28 | 37 |
| EWP-02-CV-02 | CWP-02-CV-02 | 5 | ALP-EPC-20UMB-CV-RBR-0001 | 2027-06-25 | 2027-04-19 | -4 | MR-CV-002 | 2027-01-07 | 72 |
| EWP-02-EL-01 | CWP-02-EL-01 | 4 | ALP-EPC-20UMB-EL-ELY-0002 | 2027-11-24 | 2028-02-28 | 90 | MR-EL-008 | 2027-05-06 | 212 |
| EWP-02-IC-01 | CWP-02-IC-01 | 5 | ALP-EPC-20UMB-IC-ELY-0001 | 2027-10-01 | 2028-03-27 | 168 | MR-IC-010 | 2027-07-12 | 185 |
| EWP-02-ME-01 | CWP-02-ME-01 | 5 | ALP-M02-20LCB-ME-GAD-0001 | 2027-06-11 | 2027-12-20 | 208 | MR-ME-024 | 2027-10-15 | 46 |
| EWP-02-PI-01 | CWP-02-PI-01 | 11 | ALP-EPC-20LCA-PI-SUP-0001 | 2028-04-26 | 2028-01-31 | 13 | MR-ME-022 | 2027-07-27 | 134 |
| EWP-02-SS-01 | CWP-02-SS-01 | 3 | ALP-EPC-20UMB-SS-STL-0001 | 2027-07-08 | 2027-07-12 | 35 | MR-SS-001 | 2027-02-25 | 97 |
| EWP-03-CV-01 | CWP-03-CV-01 | 6 | ALP-EPC-00UBA-HV-GAD-0002 | 2027-05-11 | 2027-03-29 | -10 | MR-CV-002 | 2027-01-07 | 57 |
| EWP-03-EL-01 | CWP-03-EL-01 | 31 | ALP-EPC-00UBA-IC-ELY-0002 | 2027-09-21 | 2027-10-25 | 53 | MR-EL-012 | 2027-08-02 | 60 |
| EWP-03-HV-01 | CWP-03-HV-01 | 7 | ALP-EPC-00SAA-PI-SUP-0001 | 2027-10-20 | 2027-10-11 | 28 | MR-HV-001 | 2027-03-25 | 142 |
| EWP-03-SS-01 | CWP-03-SS-01 | 4 | ALP-EPC-00UBA-SS-STL-0002 | 2027-05-07 | 2027-05-24 | 56 | - |  |  |
| EWP-04-CV-01 | CWP-04-CV-01 | 6 | ALP-EPC-00UAC-HV-GAD-0001 | 2027-05-04 | 2027-04-05 | -3 | - |  |  |
| EWP-04-EL-01 | CWP-04-EL-01 | 11 | ALP-EPC-00UAC-EL-CBL-0001 | 2027-10-07 | 2028-01-04 | 93 | MR-EL-008 | 2027-05-06 | 173 |
| EWP-04-SS-01 | CWP-04-SS-01 | 4 | ALP-EPC-00UAC-SS-STL-0002 | 2027-04-23 | 2027-05-31 | 56 | - |  |  |
| EWP-05-CV-01 | CWP-05-CV-01 | 9 | ALP-EPC-00UPC-CV-RBR-0001 | 2027-06-10 | 2027-03-25 | -10 | MR-CV-002 | 2027-01-07 | 55 |
| EWP-05-EL-01 | CWP-05-EL-01 | 4 | ALP-EPC-00UPC-EL-ELY-0003 | 2027-11-03 | 2028-01-31 | 77 | MR-EL-008 | 2027-05-06 | 192 |
| EWP-05-IC-01 | CWP-05-IC-01 | 5 | ALP-EPC-00UPC-IC-ELY-0001 | 2027-09-14 | 2028-02-28 | 138 | MR-IC-010 | 2027-07-12 | 165 |
| EWP-05-ME-01 | CWP-05-ME-01 | 7 | ALP-M05-00PBA-EL-WIR-0001 | 2027-05-27 | 2027-12-20 | 187 | MR-ME-005 | 2027-03-31 | 188 |
| EWP-05-PI-01 | CWP-05-PI-01 | 10 | ALP-EPC-00PBA-PI-SUP-0001 | 2027-10-05 | 2027-09-20 | 49 | MR-PI-004 | 2027-02-24 | 148 |
| EWP-06-CV-01 | CWP-06-CV-01 | 11 | ALP-EPC-00UPA-EL-ELY-0001 | 2027-10-20 | 2027-09-03 | -7 | MR-CV-003 | 2027-04-13 | 103 |
| EWP-07-CV-01 | CWP-07-CV-01 | 5 | ALP-EPC-00UGA-HV-GAD-0001 | 2027-06-07 | 2027-04-05 | -12 | - |  |  |
| EWP-07-EL-01 | CWP-07-EL-01 | 4 | ALP-EPC-00UGA-EL-ELY-0002 | 2027-11-08 | 2028-02-21 | 91 | MR-EL-008 | 2027-05-06 | 207 |
| EWP-07-IC-01 | CWP-07-IC-01 | 5 | ALP-EPC-00UGA-IC-ELY-0001 | 2027-09-24 | 2028-03-20 | 153 | MR-IC-004 | 2027-05-06 | 227 |
| EWP-07-ME-01 | CWP-07-ME-01 | 7 | ALP-M12-00GBA-EL-WIR-0001 | 2027-06-03 | 2027-12-27 | 197 | MR-ME-012 | 2027-04-08 | 187 |
| EWP-07-PI-01 | CWP-07-PI-01 | 13 | ALP-EPC-00GHA-PI-SUP-0001 | 2028-03-09 | 2028-01-24 | 17 | MR-PI-001 | 2027-02-25 | 237 |
| EWP-07-SS-01 | CWP-07-SS-01 | 4 | ALP-EPC-00UGA-SS-STL-0002 | 2027-05-05 | 2027-06-14 | 58 | - |  |  |
| EWP-08-CV-01 | CWP-08-CV-01 | 5 | ALP-EPC-00UQA-HV-GAD-0001 | 2027-06-10 | 2027-05-04 | 3 | - |  |  |
| EWP-08-EL-01 | CWP-08-EL-01 | 4 | ALP-EPC-00UQA-EL-CBL-0001 | 2027-10-25 | 2028-01-10 | 85 | MR-EL-008 | 2027-05-06 | 177 |
| EWP-08-IC-01 | CWP-08-IC-01 | 6 | ALP-EPC-00UQA-IC-ELY-0001 | 2027-10-08 | 2028-02-21 | 129 | MR-IC-004 | 2027-05-06 | 207 |
| EWP-08-ME-01 | CWP-08-ME-01 | 17 | ALP-M11-00QCA-ME-GAD-0001 | 2027-08-19 | 2027-11-01 | 108 | MR-ME-023 | 2027-10-13 | 13 |
| EWP-08-PI-01 | CWP-08-PI-01 | 25 | ALP-EPC-10LAB-PI-SUP-0001 | 2028-01-26 | 2027-12-13 | 28 | MR-ME-022 | 2027-07-27 | 99 |
| EWP-08-SS-01 | CWP-08-SS-01 | 3 | ALP-EPC-00UQA-SS-STL-0001 | 2027-06-16 | 2027-06-29 | 39 | MR-SS-001 | 2027-02-25 | 88 |
| EWP-09-CV-01 | CWP-09-CV-01 | 8 | ALP-EPC-00UEK-CV-RBR-0001 | 2027-08-13 | 2027-08-04 | 18 | - |  |  |
| EWP-09-EL-01 | CWP-09-EL-01 | 4 | ALP-EPC-00UEK-EL-ELY-0003 | 2027-09-08 | 2027-12-27 | 89 | MR-EL-008 | 2027-05-06 | 167 |
| EWP-09-IC-01 | CWP-09-IC-01 | 5 | ALP-EPC-00UEK-IC-ELY-0001 | 2027-09-15 | 2028-01-24 | 111 | MR-IC-004 | 2027-05-06 | 187 |
| EWP-09-ME-01 | CWP-09-ME-01 | 3 | ALP-M15-00EKA-EL-WIR-0001 | 2027-05-20 | 2027-11-01 | 147 | MR-ME-015 | 2027-03-25 | 157 |
| EWP-09-PI-01 | CWP-09-PI-01 | 5 | ALP-EPC-00EKC-PI-SUP-0001 | 2027-12-08 | 2027-11-29 | 33 | MR-PI-001 | 2027-02-25 | 197 |
| EWP-10-CV-01 | CWP-10-CV-01 | 5 | ALP-EPC-00UEG-CV-EFD-0001 | 2027-07-08 | 2027-06-03 | 20 | - |  |  |
| EWP-10-EL-01 | CWP-10-EL-01 | 4 | ALP-EPC-00UEG-EL-CBL-0001 | 2027-10-12 | 2028-01-24 | 92 | MR-EL-008 | 2027-05-06 | 187 |
| EWP-10-IC-01 | CWP-10-IC-01 | 4 | ALP-EPC-00UEG-IC-ELY-0001 | 2027-09-14 | 2028-02-21 | 133 | MR-IC-004 | 2027-05-06 | 207 |
| EWP-10-ME-01 | CWP-10-ME-01 | 3 | ALP-M16-00EGA-ME-GAD-0001 | 2027-05-07 | 2027-10-04 | 175 | MR-ME-017 | 2027-05-05 | 108 |
| EWP-10-PI-01 | CWP-10-PI-01 | 7 | ALP-EPC-00EGC-PI-SUP-0001 | 2028-01-24 | 2027-12-27 | 30 | MR-PI-001 | 2027-02-25 | 217 |
| EWP-11-CV-01 | CWP-11-CV-01 | 13 | ALP-EPC-00USA-HV-GAD-0001 | 2027-05-03 | 2027-03-29 | -1 | - |  |  |
| EWP-11-EL-01 | CWP-11-EL-01 | 6 | ALP-EPC-00UCA-EL-ELY-0002 | 2027-09-03 | 2027-11-08 | 62 | MR-EL-008 | 2027-05-06 | 132 |
| EWP-11-HV-01 | CWP-11-HV-01 | 2 | ALP-EPC-00UCA-PI-PPL-0001 | 2027-08-04 | 2027-11-08 | 82 | MR-HV-001 | 2027-03-25 | 162 |
| EWP-11-IC-01 | CWP-11-IC-01 | 17 | ALP-EPC-00UCA-IC-ELY-0001 | 2027-10-07 | 2027-11-22 | 76 | MR-IC-008 | 2027-07-29 | 82 |
| EWP-11-SS-01 | CWP-11-SS-01 | 12 | ALP-EPC-00USA-SS-STL-0002 | 2027-06-18 | 2027-05-24 | 35 | - |  |  |
| EWP-12-CV-01 | CWP-12-CV-01 | 3 | ALP-EPC-00UZB-CV-CVL-0001 | 2027-02-22 | 2027-01-18 | -13 | MR-CV-002 | 2027-01-07 | 7 |
| EWP-12-CV-02 | CWP-12-CV-02 | 10 | ALP-EPC-00UZD-CV-FND-0001 | 2027-06-21 | 2027-03-22 | 16 | - |  |  |
| EWP-12-EL-01 | CWP-12-EL-01 | 8 | ALP-EPC-00UZD-EL-ELY-0001 | 2027-06-17 | 2027-05-17 | 27 | MR-EL-009 | 2027-04-08 | 27 |
| EWP-12-PI-01 | CWP-12-PI-01 | 12 | ALP-EPC-00UZA-IC-ELY-0001 | 2027-10-18 | 2027-07-12 | 4 | MR-EL-010 | 2027-06-22 | 74 |

# 5. Procurement work packages (PWPs / MRs)

| MR | Title | Type | Supplier | MRQ IFC | PO | Vendor data | On site | Needed | First CWP | Float |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MR-CV-001 | Piling works | subcontract | - | 2026-11-05 | 2027-01-14 | 2027-01-28 | 2027-02-11 | 2027-04-19 | CWP-01-CV-01 | 47 |
| MR-CV-002 | Civil and building works | subcontract | - | 2026-11-05 | 2026-12-24 | 2027-01-07 | 2027-01-07 | 2027-01-25 | CWP-12-CV-01 | 12 |
| MR-CV-003 | Marine works | subcontract | - | 2026-11-05 | 2027-03-02 | 2027-04-13 | 2027-07-20 | 2027-10-01 | CWP-06-CV-01 | 53 |
| MR-EL-001 | 380 kV GIS | equipment | - | fixed | 2026-12-15 | 2027-03-09 | 2028-01-25 | 2028-02-01 | CWP-04-EL-01 | 5 |
| MR-EL-002 | Unit auxiliary transformers | equipment | - | 2026-11-05 | 2027-02-09 | 2027-04-20 | 2027-12-14 | 2028-02-07 | CWP-01-EL-01 | 39 |
| MR-EL-003 | MV switchgear 10.5 kV | equipment | - | 2026-11-05 | 2027-01-14 | 2027-03-11 | 2027-10-21 | 2027-11-22 | CWP-03-EL-01 | 22 |
| MR-EL-004 | LV transformers | equipment | - | 2026-11-12 | 2027-02-19 | 2027-04-02 | 2027-09-03 | 2027-11-22 | CWP-03-EL-01 | 56 |
| MR-EL-005 | LV switchboards and MCCs | equipment | - | 2026-11-05 | 2027-01-28 | 2027-03-25 | 2027-09-23 | 2027-11-22 | CWP-03-EL-01 | 42 |
| MR-EL-006 | Emergency diesel generator | equipment | - | 2026-11-05 | 2027-01-14 | 2027-03-11 | 2027-10-21 | 2027-11-22 | CWP-03-EL-01 | 22 |
| MR-EL-007 | UPS, batteries and DC systems | equipment | - | 2026-11-26 | 2027-03-02 | 2027-04-13 | 2027-09-14 | 2027-11-22 | CWP-03-EL-01 | 49 |
| MR-EL-008 | Power and control cables | bulk | - | 2027-02-18 | 2027-04-08 | 2027-05-06 | 2027-09-09 | 2027-11-22 | CWP-03-EL-01 | 52 |
| MR-EL-009 | Cable trays, earthing and lighting materials | bulk | - | 2027-01-21 | 2027-03-11 | 2027-04-08 | 2027-07-15 | 2027-06-14 | CWP-12-EL-01 | -23 |
| MR-EL-010 | Cathodic protection (marine structures, buried piping and tanks) | equipment | - | 2027-02-23 | 2027-04-27 | 2027-06-22 | 2027-09-07 | 2027-11-01 | CWP-12-PI-01 | 39 |
| MR-EL-011 | Construction power supply (RMU, temporary distribution) | equipment | - | fixed | 2026-11-16 | 2026-12-07 | 2027-01-18 | 2027-01-25 | CWP-12-CV-01 | 5 |
| MR-EL-012 | Electrical and I&C installation (subcontract) | subcontract | - | 2027-04-19 | 2027-07-05 | 2027-08-02 | 2027-07-05 | 2027-11-22 | CWP-03-EL-01 | 100 |
| MR-EL-101 | Generators, excitation, GCB and busducts (IEC) | iec supply | IEC | fixed | 2026-11-02 | 2027-01-25 | 2027-11-08 | 2027-11-15 | CWP-01-ME-01 | 5 |
| MR-EL-102 | Generator step-up transformers (IEC) | iec supply | IEC | fixed | 2026-11-02 | 2027-01-11 | 2027-11-29 | 2028-02-07 | CWP-01-EL-01 | 50 |
| MR-HV-001 | HVAC plant and equipment | equipment | - | 2026-11-05 | 2027-01-28 | 2027-03-25 | 2027-09-23 | 2027-11-08 | CWP-03-HV-01 | 32 |
| MR-IC-001 | Plant DCS | equipment | - | 2026-11-05 | 2027-01-21 | 2027-04-01 | 2027-11-25 | 2027-12-20 | CWP-11-IC-01 | 17 |
| MR-IC-002 | Continuous emission monitoring system | equipment | - | 2026-11-05 | 2027-03-15 | 2027-05-10 | 2027-11-08 | 2028-03-06 | CWP-01-IC-01 | 85 |
| MR-IC-003 | Steam/water analysis system | equipment | - | 2026-11-05 | 2027-03-15 | 2027-05-10 | 2027-11-08 | 2028-03-06 | CWP-01-IC-01 | 85 |
| MR-IC-004 | Field instruments | bulk | - | 2027-01-21 | 2027-03-25 | 2027-05-06 | 2027-10-21 | 2028-02-21 | CWP-09-IC-01 | 87 |
| MR-IC-005 | Control valves | bulk | - | 2027-01-21 | 2027-03-25 | 2027-05-06 | 2027-11-18 | 2028-01-10 | CWP-01-PI-01 | 37 |
| MR-IC-006 | Fire detection and alarm system | equipment | - | 2027-03-26 | 2027-05-28 | 2027-07-23 | 2027-10-29 | 2027-12-20 | CWP-11-IC-01 | 36 |
| MR-IC-007 | Telecom, CCTV, access control and perimeter security | equipment | - | 2027-03-23 | 2027-05-25 | 2027-07-20 | 2027-10-26 | 2027-12-20 | CWP-11-IC-01 | 39 |
| MR-IC-008 | BOP safety instrumented system (IEC 61511) | equipment | - | 2027-03-18 | 2027-05-20 | 2027-07-29 | 2027-12-02 | 2027-12-20 | CWP-11-IC-01 | 12 |
| MR-IC-009 | Operator training simulator, historian and performance monitoring | equipment | - | 2027-03-18 | 2027-06-03 | 2027-08-26 | 2028-03-23 | 2028-04-10 | CWP-11-IC-01 | 12 |
| MR-IC-010 | Instrument installation materials (tubing, fittings, junction boxes, supports) | bulk | - | 2027-04-26 | 2027-06-14 | 2027-07-12 | 2027-09-20 | 2028-03-06 | CWP-01-IC-01 | 120 |
| MR-IC-101 | Turbine control system (IEC) | iec supply | IEC | fixed | 2026-11-02 | 2027-01-25 | 2027-08-23 | 2028-03-06 | CWP-01-IC-01 | 140 |
| MR-ME-001 | Boiler feed pumps | equipment | - | 2026-11-05 | 2027-01-14 | 2027-03-11 | 2027-11-18 | 2027-11-29 | CWP-08-ME-01 | 7 |
| MR-ME-002 | Condensate extraction pumps | equipment | - | 2026-11-05 | 2027-02-18 | 2027-04-15 | 2027-11-25 | 2028-01-17 | CWP-02-ME-01 | 37 |
| MR-ME-003 | CW pumps | equipment | - | 2026-11-05 | 2027-01-14 | 2027-03-25 | 2027-12-30 | 2028-01-17 | CWP-05-ME-01 | 12 |
| MR-ME-004 | Travelling band screens and trash rakes | equipment | - | 2026-11-05 | 2027-02-02 | 2027-03-30 | 2027-11-09 | 2028-01-17 | CWP-05-ME-01 | 49 |
| MR-ME-005 | Electro-chlorination package | equipment | - | 2026-11-05 | 2027-02-03 | 2027-03-31 | 2027-11-10 | 2028-01-17 | CWP-05-ME-01 | 48 |
| MR-ME-006 | Condenser tube cleaning system | equipment | - | 2026-11-05 | 2027-03-12 | 2027-05-07 | 2027-11-05 | 2028-02-28 | CWP-02-PI-01 | 81 |
| MR-ME-007 | Closed cooling water heat exchangers, pumps, tank | equipment | - | 2026-11-05 | 2027-02-09 | 2027-04-06 | 2027-10-05 | 2027-11-29 | CWP-08-ME-01 | 39 |
| MR-ME-008 | Air compressors and dryers | equipment | - | 2026-11-05 | 2027-02-15 | 2027-04-12 | 2027-10-11 | 2027-11-29 | CWP-08-ME-01 | 35 |
| MR-ME-009 | Auxiliary boiler | equipment | - | 2026-11-05 | 2027-01-14 | 2027-03-25 | 2027-11-18 | 2027-11-29 | CWP-08-ME-01 | 7 |
| MR-ME-010 | Nitrogen, hydrogen and CO2 supply | equipment | - | 2027-04-15 | 2027-06-03 | 2027-07-15 | 2027-11-04 | 2027-11-29 | CWP-08-ME-01 | 17 |
| MR-ME-011 | Chemical dosing skid | equipment | - | 2027-04-16 | 2027-05-28 | 2027-07-09 | 2027-12-10 | 2027-11-29 | CWP-08-ME-01 | -9 |
| MR-ME-012 | Water treatment package (SWRO, demin, condensate polishing) | equipment | - | 2026-11-05 | 2027-01-28 | 2027-04-08 | 2028-01-13 | 2028-01-24 | CWP-07-ME-01 | 7 |
| MR-ME-013 | Shop-built tanks and demin forwarding pumps | equipment | - | 2026-11-05 | 2027-01-14 | 2027-02-25 | 2027-07-29 | 2027-11-29 | CWP-08-ME-01 | 87 |
| MR-ME-014 | Waste water and sanitary treatment packages | equipment | - | 2026-11-05 | 2027-01-28 | 2027-03-25 | 2027-09-23 | 2028-01-24 | CWP-07-ME-01 | 87 |
| MR-ME-015 | Gas receiving and metering station | equipment | - | 2026-11-05 | 2027-01-14 | 2027-03-25 | 2027-11-18 | 2027-11-29 | CWP-09-ME-01 | 7 |
| MR-ME-016 | LDO unloading and forwarding / treatment skids | equipment | - | 2026-11-05 | 2027-01-14 | 2027-03-11 | 2027-10-21 | 2027-11-01 | CWP-10-ME-01 | 7 |
| MR-ME-017 | Field-erected storage tanks (API 650): LDO storage and fire water | subcontract | - | 2026-11-26 | 2027-03-24 | 2027-05-05 | 2027-06-30 | 2027-11-01 | CWP-10-ME-01 | 88 |
| MR-ME-018 | Aqueous ammonia storage and forwarding | equipment | - | 2026-11-05 | 2027-02-18 | 2027-04-15 | 2027-10-14 | 2027-11-29 | CWP-08-ME-01 | 32 |
| MR-ME-019 | HRSG blowdown and drain tanks | equipment | - | 2026-11-05 | 2027-02-05 | 2027-03-19 | 2027-08-20 | 2027-11-15 | CWP-01-ME-01 | 61 |
| MR-ME-020 | Fire pumps and fire protection systems | equipment | - | 2026-11-05 | 2027-01-28 | 2027-03-25 | 2027-10-07 | 2027-11-29 | CWP-01-HV-01 | 37 |
| MR-ME-021 | EOT cranes | equipment | - | 2026-11-05 | 2027-01-14 | 2027-03-11 | 2027-10-21 | 2027-11-15 | CWP-01-ME-01 | 17 |
| MR-ME-022 | Painting and insulation (subcontract) | subcontract | - | 2027-04-27 | 2027-06-29 | 2027-07-27 | 2027-06-29 | 2028-01-10 | CWP-01-PI-01 | 139 |
| MR-ME-023 | Mechanical and piping erection (subcontract) | subcontract | - | 2027-06-30 | 2027-09-15 | 2027-10-13 | 2027-09-15 | 2027-11-15 | CWP-01-ME-01 | 43 |
| MR-ME-024 | Heavy transport, barge landing and marine logistics (subcontract) | subcontract | - | 2027-07-16 | 2027-09-17 | 2027-10-15 | 2027-09-17 | 2027-11-15 | CWP-01-ME-01 | 41 |
| MR-ME-101 | Gas turbine package incl. auxiliaries (IEC) | iec supply | IEC | fixed | 2026-11-02 | 2027-01-25 | 2027-11-15 | 2027-11-15 | CWP-01-ME-01 | 0 |
| MR-ME-102 | HRSG incl. SCR (IEC) | iec supply | IEC | fixed | 2026-11-02 | 2027-01-25 | 2027-11-15 | 2027-11-15 | CWP-01-ME-01 | 0 |
| MR-ME-103 | Steam turbine and condenser (IEC) | iec supply | IEC | fixed | 2026-11-02 | 2027-02-08 | 2028-01-10 | 2028-01-17 | CWP-02-ME-01 | 5 |
| MR-PI-001 | Piping bulk materials (carbon steel, stainless) | bulk | - | 2026-12-10 | 2027-01-28 | 2027-02-25 | 2027-07-15 | 2027-08-09 | CWP-12-PI-01 | 17 |
| MR-PI-002 | Alloy piping P91 / P22 (main steam, reheat) | bulk | - | 2027-01-21 | 2027-03-25 | 2027-05-06 | 2028-02-10 | 2028-01-10 | CWP-01-PI-01 | -23 |
| MR-PI-003 | Valves (manual and check) | bulk | - | 2026-12-25 | 2027-03-08 | 2027-04-19 | 2027-10-04 | 2028-01-10 | CWP-01-PI-01 | 70 |
| MR-PI-004 | GRP CW pipes and fittings | bulk | - | 2026-11-05 | 2027-01-13 | 2027-02-24 | 2027-09-08 | 2027-10-18 | CWP-05-PI-01 | 28 |
| MR-PI-005 | Pipe supports, spring hangers and snubbers | bulk | - | 2027-03-30 | 2027-05-25 | 2027-07-06 | 2027-10-05 | 2028-01-10 | CWP-01-PI-01 | 69 |
| MR-PI-006 | Piping specialty items (strainers, steam traps, expansion joints, sight glasses) | bulk | - | 2026-12-10 | 2027-04-05 | 2027-05-17 | 2027-08-16 | 2028-01-10 | CWP-01-PI-01 | 105 |
| MR-PI-007 | Safety and relief valves | bulk | - | 2026-12-10 | 2027-04-01 | 2027-05-27 | 2027-09-09 | 2028-01-10 | CWP-01-PI-01 | 87 |
| MR-SS-001 | Structural steel supply and fabrication | subcontract | - | 2026-11-12 | 2027-01-28 | 2027-02-25 | 2027-06-03 | 2027-07-27 | CWP-08-SS-01 | 38 |
| MR-SS-002 | Stack 65 m with silencer | subcontract | - | 2026-11-12 | 2027-01-28 | 2027-03-25 | 2027-09-23 | 2027-11-15 | CWP-01-ME-01 | 37 |

# 6. Release rules and IWPs

A CWP is released when the documents of its first IWPs are IFC and their materials are on site or have a confirmed delivery; no IWP is issued to the field unless all its documents are IFC and its constraints are removed; the EWP completeness for the next 8 weeks of IWPs is reported monthly per CWP (TQ-037, amending TQ-035).

Documents of progressive types (isometrics, supports, schematics, loop diagrams, reinforcement, equipment foundations ...) are released to the later IWPs of the CWP: needed at CWP start - lead + share x CWP duration.

The engineering_plan engine reports EWP float (smallest float of its documents), vendor data float and PWP float (on site before the first CWP start) at every run; negative float is a warning to be resolved by re-sequencing, expediting or a TQ before the plan is re-issued.

IWPs are prepared by the construction contractors from the released CWP: scope of 1-2 weeks for one crew, with the IFC documents, material pick list (from the PWPs), permits, scaffolding and equipment; an IWP is issued to the field only when all its constraints are removed.

Plant assets carry cwa / cwp / mr; documents carry ewp / mr; construction progress is reported per CWP (activity percent complete) and rolls up to the level-3 schedule.

# Check results (engine)

102 OK, 13 INFO, 14 WARN (checks: AWP, EWP float, EWP vendor data, PWP float, agreement, coverage CWP, coverage EWP). WARN must be resolved before the next issue; INFO is noted.

| Item | Check | Result | Detail |
| --- | --- | --- | --- |
| - | agreement | OK | kks_key: 128 of 128 agreed |
| - | agreement | OK | cwa: 12 of 12 agreed |
| - | agreement | OK | cwp: 59 of 59 agreed |
| - | agreement | OK | ewp: 59 of 59 agreed |
| - | agreement | OK | mr: 65 of 65 agreed |
| EWP-01-CV-01 | EWP float | WARN | IFC 2027-04-12 (ALP-EPC-10UMA-CV-FND-0001), needed 2027-03-22 for CWP-01-CV-01 start 2027-04-19: float -3 wd |
| EWP-01-CV-02 | EWP float | WARN | IFC 2027-06-22 (ALP-EPC-10UMA-CV-RBR-0001), needed 2027-04-19 for CWP-01-CV-02 start 2027-05-17: float -7 wd |
| EWP-02-CV-01 | EWP float | WARN | IFC 2027-04-12 (ALP-EPC-20UMB-CV-FND-0001), needed 2027-03-22 for CWP-02-CV-01 start 2027-04-19: float -5 wd |
| EWP-02-CV-02 | EWP float | WARN | IFC 2027-06-25 (ALP-EPC-20UMB-CV-RBR-0001), needed 2027-04-19 for CWP-02-CV-02 start 2027-05-17: float -4 wd |
| EWP-03-CV-01 | EWP float | WARN | IFC 2027-05-11 (ALP-EPC-00UBA-HV-GAD-0002), needed 2027-03-29 for CWP-03-CV-01 start 2027-04-26: float -10 wd |
| EWP-04-CV-01 | EWP float | WARN | IFC 2027-05-04 (ALP-EPC-00UAC-HV-GAD-0001), needed 2027-04-05 for CWP-04-CV-01 start 2027-05-03: float -3 wd |
| EWP-05-CV-01 | EWP float | WARN | IFC 2027-06-10 (ALP-EPC-00UPC-CV-RBR-0001), needed 2027-03-25 for CWP-05-CV-01 start 2027-04-22: float -10 wd |
| EWP-06-CV-01 | EWP float | WARN | IFC 2027-10-20 (ALP-EPC-00UPA-EL-ELY-0001), needed 2027-09-03 for CWP-06-CV-01 start 2027-10-01: float -7 wd |
| EWP-07-CV-01 | EWP float | WARN | IFC 2027-06-07 (ALP-EPC-00UGA-HV-GAD-0001), needed 2027-04-05 for CWP-07-CV-01 start 2027-05-03: float -12 wd |
| EWP-08-CV-01 | EWP float | INFO | IFC 2027-06-10 (ALP-EPC-00UQA-HV-GAD-0001), needed 2027-05-04 for CWP-08-CV-01 start 2027-06-01: float 3 wd |
| EWP-11-CV-01 | EWP float | WARN | IFC 2027-05-03 (ALP-EPC-00USA-HV-GAD-0001), needed 2027-03-29 for CWP-11-CV-01 start 2027-04-26: float -1 wd |
| EWP-12-CV-01 | EWP float | WARN | IFC 2027-02-22 (ALP-EPC-00UZB-CV-CVL-0001), needed 2027-01-18 for CWP-12-CV-01 start 2027-01-25: float -13 wd |
| EWP-12-PI-01 | EWP float | INFO | IFC 2027-10-18 (ALP-EPC-00UZA-IC-ELY-0001), needed 2027-07-12 for CWP-12-PI-01 start 2027-08-09: float 4 wd |
| MR-EL-001 | PWP float | INFO | PO 2026-12-15, on site 2028-01-25, needed 2028-02-01 (CWP-04-EL-01): float 5 wd |
| MR-EL-009 | PWP float | WARN | PO 2027-03-11, on site 2027-07-15, needed 2027-06-14 (CWP-12-EL-01): float -23 wd |
| MR-EL-011 | PWP float | INFO | PO 2026-11-16, on site 2027-01-18, needed 2027-01-25 (CWP-12-CV-01): float 5 wd |
| MR-EL-101 | PWP float | INFO | PO 2026-11-02, on site 2027-11-08, needed 2027-11-15 (CWP-01-ME-01): float 5 wd |
| MR-ME-001 | PWP float | INFO | PO 2027-01-14, on site 2027-11-18, needed 2027-11-29 (CWP-08-ME-01): float 7 wd |
| MR-ME-009 | PWP float | INFO | PO 2027-01-14, on site 2027-11-18, needed 2027-11-29 (CWP-08-ME-01): float 7 wd |
| MR-ME-011 | PWP float | WARN | PO 2027-05-28, on site 2027-12-10, needed 2027-11-29 (CWP-08-ME-01): float -9 wd |
| MR-ME-012 | PWP float | INFO | PO 2027-01-28, on site 2028-01-13, needed 2028-01-24 (CWP-07-ME-01): float 7 wd |
| MR-ME-015 | PWP float | INFO | PO 2027-01-14, on site 2027-11-18, needed 2027-11-29 (CWP-09-ME-01): float 7 wd |
| MR-ME-016 | PWP float | INFO | PO 2027-01-14, on site 2027-10-21, needed 2027-11-01 (CWP-10-ME-01): float 7 wd |
| MR-ME-101 | PWP float | INFO | PO 2026-11-02, on site 2027-11-15, needed 2027-11-15 (CWP-01-ME-01): float 0 wd |
| MR-ME-102 | PWP float | INFO | PO 2026-11-02, on site 2027-11-15, needed 2027-11-15 (CWP-01-ME-01): float 0 wd |
| MR-ME-103 | PWP float | INFO | PO 2026-11-02, on site 2028-01-10, needed 2028-01-17 (CWP-02-ME-01): float 5 wd |
| MR-PI-002 | PWP float | WARN | PO 2027-03-25, on site 2028-02-10, needed 2028-01-10 (CWP-01-PI-01): float -23 wd |