# Alpilla 600 MW Combined Cycle Power Plant
Document numbering and document control procedure

| Document number | ALP-EPC-00000-GE-PRC-0002 |
| --- | --- |
| Revision | draft - not yet issued (next issue: IFR rev A) |
| Originator | Istanbul EPC |
| Review class | approval |
| Planned issue (workflow timeline) | IFR 2027-02-03, IFA 2027-03-03, IFC 2027-03-10 |
| Basis | requirement:ER-17.01 |

# 1. Purpose, scope and basis

This procedure sets the numbering of all project documents (consortium, Imaginary Electric, subsuppliers), the document types and their review class, revisions and purposes, the review cycle with the Owner and the maintenance of the master document list (MDL).

ER-17.01: Documents submitted electronically with the project numbering (consortium proposal adopted by the Owner in TQ-035: ALP-<ORG>-<KKS>-<DISC>-<TYPE>-<NNNN>) and a master document register; review period 14 days (21 days for the Basic Design Package).

TQ-035 (closed, answered 2026-09-28 by Owner): (1) Accepted: the consortium numbering is the project numbering under ER-17.01; the Owner's EDMS will use it unchanged. (2) The KKS key list is approved for engineering. The Owner's Engineer verifies each key title against the VGB-S-811 key catalogue with the KKS manual review; until then keys stay flagged 'not verified'. (3) MDL accepted as baseline for the Basic Design Package. Review classes accepted with one change: logic diagrams (LOG) incl. cause and effect are safety relevant and are for approval. The MDL is updated monthly with the progress report. (4) AWP definitions accepted. The Owner requires every CWP to be released for construction only when its EWP is complete (all IFC) and its PWP materials are on site or have a confirmed delivery before the planned installation.

TQ-IEC-023 (closed, answered 2026-09-28 by Imaginary Electric): (1) Confirmed. IEC tags the power island with the project KKS to component level (B), systems and equipment units per the project key list; IEC part numbers are kept as vendor attributes below component level. IEC checks the key titles of its main groups against its VGB-S-811 licence copy and reports deviations with the KKS manual review (IFR). (2) Confirmed: project number primary, IEC number as vendor reference on the title block. (3) Confirmed: the VDRL dates in the MDL are the IEC commitment. (4) Confirmed with an improvement: generator shop tests are brought forward; the GT generators leave the works in week 49 together with the GT (sea transport 4 weeks), on site 2027-11-08. The ST generator follows the ST train (no change).

# 2. Document number

Format: ALP-<ORG>-<KKS>-<DISC>-<TYPE>-<NNNN>

| Field | Format | Meaning |
| --- | --- | --- |
| ALP | fixed | Project code |
| ORG | 3 characters | Originator (section 3) |
| KKS | NNAAA / 00000 | KKS system G F0 F1F2F3 of the main system the document belongs to (ALP-EPC-00000-GE-PRC-0001); 00000 for plant-general documents |
| DISC | 2 letters | Discipline (section 3) |
| TYPE | 3 characters | Document type (section 4); defines the IEC 61355 class and the workflow rules |
| NNNN | 4 digits | Running number per ORG-KKS-DISC-TYPE, from 0001; never reused |

Example ALP-C03-00UPA-GE-ITP-0001: originator C03 (subsupplier); KKS 00UPA (CW intake and outfall structures (marine)); discipline GE (general); type ITP; number 0001

Sheets of a multi-sheet drawing share the number (sheet count in the MDL); a supplier's own number is recorded as vendor reference and shown as a secondary number in the title block (TQ-IEC-023).

# 3. Originator and discipline codes

| ORG | Originator |
| --- | --- |
| EPC | Istanbul EPC (consortium leader) |
| IEC | Imaginary Electric (consortium member) |
| OWN | Owner |
| xxx | Subsupplier: 3-character code allocated by Istanbul EPC with the purchase order |

| DISC | Discipline |
| --- | --- |
| GE | general |
| PR | process |
| ME | mechanical |
| PI | piping |
| EL | electrical |
| IC | instrumentation and control |
| CV | civil |
| SS | structural |
| HV | hvac |
| HS | hse |
| CM | commissioning |
| PC | project control |

# 4. Document types and workflow rules

Prep = working days from inputs ready to first issue (longer for multi-sheet documents, at most double); Update = working days to incorporate comments; Inputs at = maturity the inputs must have reached (IFR or IFC); C = construction document (belongs to an EWP), P = procurement document (belongs to an MR).

Share = AWP progressive release: a construction document of this type is needed at CWP start - lead + share x CWP duration (0 = at the CWP start).

| Type | Title | IEC 61355 | Review class | Prep | Upd. | Inputs at | Typical inputs | C/P | Share |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ARC | Architectural drawing | L | approval | 20 | 10 | IFR | LAY | C | 0.3 |
| BLK | Block / architecture diagram | F | approval | 15 | 10 | IFR | DBR, IOL, SLD |  |  |
| CAL | Calculation | E | review | 15 | 5 | IFR | CAL, DBR, HMB, LST, PID, RPT, SDS, SLD, STU |  |  |
| CBL | Cable schedule and routing | M | information | 15 | 5 | IFR | SLD, LAY | C | 0.3 |
| CEM | Cause and effect matrix | F | approval | 15 | 10 | IFR | PID, CNR, HAZ |  |  |
| CMP | Commissioning procedure | B | approval | 20 | 10 | IFR | CAL, CNR, PID, PLN, SPC, STU |  |  |
| CNR | Control narrative / functional description | F | review | 15 | 10 | IFR | PID, CNR |  |  |
| CVL | Civil drawing (grading, roads, drainage, marine) | L | approval | 20 | 10 | IFR | PLT, STU, SDS | C | 0.2 |
| DBR | Design basis report | D | approval | 20 | 10 | IFR | - |  |  |
| DSH | Datasheet | E | approval | 10 | 5 | IFR | PID, SPC | P |  |
| EFD | Equipment foundation drawings (vendor-certified loads) | L | approval | 15 | 10 | IFR | CAL, FND | C | 0.5 |
| ELY | Electrical layout (earthing, lighting, trays, equipment) | L | review | 20 | 10 | IFR | ARC, CVL, ELY, FND, LAY, PPL, SLD, STU | C | 0.2 |
| FND | Foundation / underground drawing | L | approval | 20 | 10 | IFR | LAY, CAL | C | 0.2 |
| GAD | General arrangement drawing | L | review | 20 | 10 | IFR | ARC, DBR, LAY | C | 0.3 |
| HAZ | Safety study (HAZID, HAZOP, SIL, hazardous areas, fire, QRA) | S | approval | 20 | 10 | IFR | PID, PLT, HAZ |  |  |
| HMB | Heat and mass balance | F | approval | 15 | 10 | IFR | DBR |  |  |
| HMI | Operator display (HMI graphics) drawings | F | review | 15 | 5 | IFR | PID, CNR |  |  |
| HUP | Instrument hook-up drawings | M | information | 10 | 5 | IFR | PID, SPC | C | 0.5 |
| IOL | I/O list | P | review | 15 | 10 | IFR | PID, CNR, LST, IOL |  |  |
| ISO | Isometric drawing package | L | information | 20 | 5 | IFR | PPL | C | 0.4 |
| ITP | Inspection and test plan | Q | approval | 10 | 5 | IFR | SPC |  |  |
| LAY | Equipment layout / arrangement | L | approval | 20 | 10 | IFR | ARC, HAZ, PLT | C |  |
| LOG | Logic diagram | F | approval | 20 | 10 | IFR | CNR, IOL, RPT |  |  |
| LOP | Loop / connection diagram | M | information | 15 | 5 | IFR | IOL | C | 0.5 |
| LST | List / index (equipment, lines, valves, instruments, loads, tie-ins) | P | review | 15 | 10 | IFR | DBR, HAZ, LST, PFD, PID, PRC, RPT, SLD, STU |  |  |
| M3D | 3D model review report (30 / 60 / 90 %) | L | review | 15 | 5 | IFR | PLT, LAY, PPL, ISO |  |  |
| MDB | Manufacturing record book / conformity certificates / turnover dossier | Q | information | 10 | 5 | IFR | CMP, ITP |  |  |
| MDL | Master document list | A | information | 10 | 5 | IFR | - |  |  |
| MOS | Method statement / construction execution plan | B | review | 10 | 5 | IFR | CVL, PLN |  |  |
| MRQ | Material requisition | C | information | 5 | 3 | IFR | SPC | P |  |
| OMM | Operation and maintenance manual | D | review | 30 | 10 | IFR | CMP, PID |  |  |
| PFD | Process flow diagram | F | approval | 15 | 10 | IFR | HMB |  |  |
| PID | Piping and instrumentation diagram | F | approval | 25 | 15 | IFR | SDS |  |  |
| PLN | Plan (execution, quality, HSE, commissioning, training) | B | approval | 20 | 10 | IFR | DBR, HAZ, LST, PFD, PLN, PRC, RPT, SPC, STU |  |  |
| PLT | Plot plan | L | approval | 20 | 10 | IFR | DBR |  |  |
| PPL | Piping general arrangement / plans | L | review | 25 | 10 | IFR | PID, LAY | C | 0.2 |
| PRC | Procedure / project standard | B | approval | 15 | 10 | IFR | - |  |  |
| RBR | Reinforcement drawings | L | review | 15 | 5 | IFR | FND | C | 0.3 |
| RPT | Technical report | D | review | 15 | 5 | IFR | - |  |  |
| SCH | Schedule | B | review | 15 | 5 | IFR | MDL |  |  |
| SDS | System design description | D | review | 15 | 10 | IFR | DBR |  |  |
| SLD | Single line diagram | F | approval | 15 | 10 | IFR | DBR, LST |  |  |
| SPC | Technical specification | E | approval | 20 | 10 | IFR | - | P |  |
| STL | Steel structure drawing | L | approval | 20 | 10 | IFR | GAD, CAL | C | 0.3 |
| STR | Pipe stress analysis report | E | review | 20 | 5 | IFR | PPL |  |  |
| STU | Engineering study | D | review | 25 | 10 | IFR | - |  |  |
| SUP | Pipe support drawings | L | information | 15 | 5 | IFC | ISO, STR | C | 0.5 |
| TRP | Test report / test record / certificate | Q | review | 5 | 5 | IFR | CMP, SPC, TST |  |  |
| TST | Test procedure (FAT, SAT, site and performance tests) | Q | approval | 15 | 10 | IFR | DBR, ITP, RPT, SPC |  |  |
| WIR | Schematic and wiring diagrams | F | information | 15 | 5 | IFC | SLD, LST | C | 0.5 |

# 5. Number allocation

Numbers are allocated only in the database: python -m engine kks --next <ORG> <KKS> <DISC> <TYPE> gives the next free number; the document is registered with python -m engine db add document ... --reason.

Every document record carries type_code, discipline, originator and system consistent with its number; the engineering_plan engine checks all numbers at every run.

A cancelled document keeps its number (status cancelled, purpose VOID); numbers are never reused.

# 6. Revisions and issue purposes

| Purpose | Meaning | Revision |
| --- | --- | --- |
| IFR | Issued for review / first issue | A, B, C ... |
| IFA | Issued for approval (approval class, after the Owner's comments are incorporated) | A, B, C ... |
| IFD | Issued for design (released internally for dependent design, e.g. vendor data frozen) | A, B, C ... |
| IFP | Issued for purchase (requisitions, specifications, datasheets) | A, B, C ... |
| IFC | Issued for construction / final | 0, 1, 2 ... |
| IFI | Issued for information (information class, supplier documents received) | A, B, C ... or supplier rev. |
| AB | As built | next number |
| VOID | Cancelled; the number is never reused | - |

Each issue is a document_revision record (revision, purpose, date, prepared / checked / approved by, file); packages are transmitted with python -m engine deliver (frozen copy and transmittal).

# 7. Review and approval

| Class | Cycle |
| --- | --- |
| approval | Owner approval: IFR -> Owner review -> update -> IFA -> approval code 1 -> IFC |
| review | Owner review: IFR -> Owner review -> update -> IFC |
| information | sent to the Owner for information: IFR -> update -> IFC (no review period) |
| internal | consortium internal, not transmitted for review |

Owner review period: 10 working days (14 calendar days, ER-17.01), 15 working days (21 calendar days) for Basic Design Package documents; after approval code 1 the IFC follows within 5 working days. Review codes:

| Code | Meaning |
| --- | --- |
| 1 | No comments - proceed (approval: approved) |
| 2 | Proceed with the comments incorporated; re-issue |
| 3 | Do not proceed; revise and re-submit |
| 4 | For information / reference only; no review |

Comments are recorded as review_comment records against the revision (comment -> response -> closed in the revision that incorporates it). The review class of a document type may be overridden per document (review field of the MDL line).

# 8. Supplier documents

Imaginary Electric and subsuppliers submit per their VDRL, which is part of the MDL (originator IEC / subsupplier code) with committed first-issue and final dates.

Supplier documents are numbered by Istanbul EPC before the purchase order, carry the project number as the primary number and are reviewed by Istanbul EPC before transmittal to the Owner where the class requires it.

Received files are registered as source records (sources/) and linked to the MDL line (source field) with an IFR / IFI revision.

# 9. Master document list

The MDL is generated by the engineering_plan engine from the document records (2208 documents: C01 7, C02 7, C03 7, E01 14, E02 14, E03 11, E04 11, E05 12, E06 14, E07 12, E08 3, E09 3, E10 8, E11 8, E12 7, EPC 1458, H01 15, I01 12, I02 13, I03 14, I04 3, I05 3, I06 12, I07 12, I08 13, I09 12, I10 3, IEC 120, M01 15, M02 15, M03 15, M04 15, M05 16, M06 14, M07 15, M08 16, M09 16, M10 14, M11 14, M12 16, M13 15, M14 16, M15 15, M16 15, M17 7, M18 15, M19 15, M20 15, M21 13, M22 7, M23 7, M24 7, P01 3, P02 3, P03 3, P04 3, P05 3, P06 3, P07 3, S01 23, S02 8; 25 in the Basic Design Package). It is updated with every change of the records and issued monthly with the progress report (TQ-035).

| Discipline | Documents | Hours | Sheets |
| --- | --- | --- | --- |
| civil | 141 | 29,888 | 796 |
| commissioning | 212 | 7,430 | 235 |
| electrical | 184 | 16,506 | 3107 |
| general | 181 | 6,112 | 181 |
| hse | 38 | 3,924 | 59 |
| hvac | 22 | 4,850 | 156 |
| i and c | 425 | 28,480 | 9148 |
| mechanical | 656 | 13,418 | 2253 |
| piping | 152 | 74,788 | 4075 |
| process | 153 | 18,007 | 402 |
| project control | 2 | 160 | 2 |
| structural | 42 | 8,282 | 951 |

# Check results (engine)

1 OK, 0 INFO, 0 WARN (checks: numbering). WARN must be resolved before the next issue; INFO is noted.

| Item | Check | Result | Detail |
| --- | --- | --- | --- |
| - | numbering | OK | 2208 document numbers checked, 0 finding(s) |