# Alpilla 600 MW Combined Cycle Power Plant
Engineering Execution Plan

| Document number | ALP-EPC-00000-GE-PLN-0001 |
| --- | --- |
| Description | workflow, interfaces, timeline |
| Revision / status | Rev A - IFR, draft (not issued) |
| Originator | Istanbul EPC Mühendislik ve Taahhüt A.Ş. |
| Discipline / type | general / PLN Plan (execution, quality, HSE, commissioning, training) |
| Review class | approval |
| Basis | requirement:ER-01.09 |

Planned issues (workflow timeline): IFR 2027-05-03, IFA 2027-05-31, IFC 2027-06-07

# 1. Purpose and scope

This plan sets how the engineering of the project is executed: scope (the MDL), organisation, the workflow between documents and disciplines, the review cycle and the timeline against the construction need dates (Advanced Work Packaging, ALP-EPC-00000-GE-PLN-0002). All figures are taken from the MDL and the workflow timeline computed from it; they change when the records change.

# 2. Organisation and responsibilities

| Party | Responsibility |
| --- | --- |
| Istanbul EPC | Consortium leader: plant design and balance of plant engineering, integration of the power island, MDL and document control, procurement of BOP packages, construction and commissioning management |
| Imaginary Electric | Power island design and supply (GT, HRSG, ST, generators, GSUs, TCS); VDRL documents per the MDL dates (TQ-IEC-023); interface data (IF- points) |
| Owner | Review and approval per the review class (14 / 21 days); approval of the KKS key list, numbering and AWP (TQ-035) |
| Engineer | Owner's Engineer: technical review on behalf of the Owner, KKS key verification |

# 3. Engineering scope (MDL)

| Discipline | Docs | EPC | Supplier | BDP | In EWP | Hours | First IFR | Last IFC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| civil | 141 | 115 | 26 | 1 | 73 | 29,887 | 2026-11-02 | 2027-08-24 |
| commissioning | 242 | 236 | 6 | 0 | 0 | 7,910 | 2026-11-25 | 2029-04-25 |
| electrical | 184 | 137 | 47 | 2 | 112 | 16,518 | 2026-09-28 | 2028-08-01 |
| general | 181 | 108 | 73 | 2 | 0 | 6,112 | 2026-09-28 | 2027-10-13 |
| hse | 38 | 37 | 1 | 1 | 11 | 3,924 | 2026-12-07 | 2027-10-19 |
| hvac | 22 | 22 | 0 | 0 | 14 | 4,850 | 2026-11-02 | 2027-07-20 |
| i and c | 425 | 333 | 92 | 2 | 58 | 28,472 | 2026-11-02 | 2029-03-12 |
| mechanical | 655 | 195 | 460 | 1 | 42 | 13,492 | 2026-09-28 | 2028-07-24 |
| piping | 152 | 150 | 2 | 3 | 112 | 74,828 | 2026-11-02 | 2028-07-06 |
| process | 153 | 126 | 27 | 13 | 0 | 17,989 | 2026-09-28 | 2027-07-28 |
| project control | 2 | 2 | 0 | 0 | 0 | 160 | 2026-12-22 | 2027-07-12 |
| structural | 42 | 26 | 16 | 0 | 37 | 8,282 | 2026-11-02 | 2027-07-28 |

Total 2237 documents, 212,424 hours: EPC document preparation incl. checking and the plant 3D model; for supplier documents the EPC review. Site support, expediting and management are budgeted separately.

## 3.1 How the MDL is derived

80 MDL rules (records mdl_rule) define the documents per plant, system, structure, construction area, procurement package and equipment group: type, quantity basis (sheets per P&ID sheet, instrument, loop, line, isometric, consumer, structure ...), hours, inputs, EWP / MR links and, for supplier documents, the timing after the purchase order. Quantities are system estimates (basis DEC-EPCE-0008) until the equipment, instrument and line registers are larger; python -m engine mdl sync keeps the documents in line with the rules and registers. Single deliverables (studies, plans, permit dossiers, test reports) are individual records citing their requirement, permit or clause.

| Rule scope | Rules |
| --- | --- |
| cwa | 10 |
| eqgroup | 3 |
| mr | 24 |
| plant | 11 |
| structure | 14 |
| system | 18 |

## 3.2 Completeness against indicative benchmarks

Indicative ranges for a comparable 1x1 H-class CCGT (engineering judgement, not contractual): below the minimum = scope probably missing (WARN), above the maximum = review for duplication (INFO).

| Benchmark | Scope | Measure | MDL | Indicative range |
| --- | --- | --- | --- | --- |
| BM-ALL-EPC | all / EPC | sheets | 13,424 | 8,000 - 20,000 |
| BM-ALL-EPC | all / EPC | hours | 201,924 | 150,000 - 320,000 |
| BM-ALL-SUP | all / SUPPLIER | sheets | 7,920 | 3,000 - 10,000 |
| BM-CM | commissioning / EPC | docs | 236 | 150 - 400 |
| BM-CV | civil / EPC | sheets | 704 | 500 - 1,500 |
| BM-EL | electrical / EPC | sheets | 1,878 | 1,200 - 3,000 |
| BM-GE | general / EPC | docs | 108 | 50 - 200 |
| BM-HS | hse / EPC | docs | 37 | 30 - 120 |
| BM-HV | hvac / EPC | sheets | 156 | 100 - 400 |
| BM-IC | i_and_c / EPC | sheets | 5,259 | 4,000 - 9,000 |
| BM-ME | mechanical / EPC | sheets | 478 | 250 - 800 |
| BM-PI | piping / EPC | sheets | 4,074 | 3,500 - 7,000 |
| BM-PR | process / EPC | sheets | 248 | 200 - 500 |
| BM-SS | structural / EPC | sheets | 223 | 150 - 600 |

Coverage is checked at every engine run: every design discipline has its design criteria, every KKS system has the document types its category requires, every Employer's Requirement and every EPC / IEC scope item is answered by at least one document, every equipment item has a datasheet, an MR and a CWP, every MR a specification and a requisition, every CWP an EWP.

# 4. Workflow rules

Documents form a network through their inputs (MDL column Inputs). A document starts when all its inputs have reached the maturity its type requires (IFR or IFC, section 4 of ALP-EPC-00000-GE-PRC-0002), not before NTP.

First issue (IFR) = start + preparation time of the type (+5 % per extra sheet, at most double).

Owner review 10 wd (15 wd for the Basic Design Package); approval class: IFA = IFR + review + update, IFC = IFA + 5 wd; review class: IFC = IFR + review + update; information / internal: IFC = IFR + update.

Tender-stage documents (bid design, and the requisitions of long-lead packages per the procurement decision) are issued at NTP. Supplier documents with committed dates keep them (IEC, TQ-IEC-023); the others are timed from their MR: weeks after the PO for design data, weeks before delivery for FAT, erection and O&M documents. Issued revisions replace the planned dates.

Construction documents belong to the EWP of their CWP. An EWP is needed ewp_lead_days before its CWP starts for the first IWPs; documents of progressive types (isometrics, supports, schematics, loop diagrams, reinforcement, equipment foundations ...) are released to later IWPs at CWP start - lead + share x CWP duration (share per document type, section 4 of ALP-EPC-00000-GE-PRC-0002). EPC documents that need certified vendor data (e.g. equipment foundations) take the supplier documents as inputs.

Requisitions start the PWP (MR) cycle: PO = MRQ IFC + bid + award; delivery on site = PO + manufacture + transport; needed at the first CWP start (+ need lag for materials installed late in the CWP).

Engineering capacity per discipline (eng_resource) with a mobilisation ramp from 30 % at NTP; documents are scheduled in need-date priority within the capacity (levelled timeline).

# 5. Interdisciplinary inputs (who feeds whom)

Number of input links from the supplying discipline (row) to the receiving discipline (column).

| from \ to | CV | CM | EL | GE | HS | HV | IC | ME | PI | PR | PC | SS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CV | 215 |  | 24 | 25 | 12 | 11 | 11 |  | 4 |  |  | 37 |
| CM |  | 198 |  |  |  |  |  |  |  |  |  |  |
| EL | 4 | 12 | 257 | 15 |  |  | 10 | 77 |  |  |  |  |
| GE | 1 |  | 5 | 76 | 3 | 2 | 12 | 71 | 3 | 43 | 3 |  |
| HS |  | 1 | 1 | 1 | 45 |  | 41 |  |  |  |  | 1 |
| HV | 11 | 4 | 2 | 1 |  | 23 | 9 | 16 | 2 | 3 |  |  |
| IC |  | 47 | 5 | 20 |  |  | 412 | 38 |  | 1 |  |  |
| ME | 19 | 36 | 22 | 36 | 1 | 4 | 46 | 596 | 5 | 22 |  | 1 |
| PI | 41 |  | 26 | 9 | 8 | 4 | 11 | 15 | 357 | 41 |  | 15 |
| PR | 11 | 144 | 1 |  | 40 | 3 | 249 | 112 | 95 | 229 |  |  |
| PC |  |  |  |  |  |  |  |  |  |  |  |  |
| SS | 1 |  |  | 16 |  |  |  | 1 |  |  |  | 35 |

Typical inputs per document type (checked at every run; a document without any of them is reported):

| Type | Title | Inputs at | Typical inputs |
| --- | --- | --- | --- |
| ARC | Architectural drawing | IFR | LAY |
| BLK | Block / architecture diagram | IFR | DBR, IOL, SLD |
| CAL | Calculation | IFR | CAL, DBR, HMB, LST, PID, RPT, SDS, SLD, STU |
| CBL | Cable schedule and routing | IFR | SLD, LAY |
| CEM | Cause and effect matrix | IFR | PID, CNR, HAZ |
| CMP | Commissioning procedure | IFR | CAL, CNR, PID, PLN, SPC, STU |
| CNR | Control narrative / functional description | IFR | PID, CNR |
| CVL | Civil drawing (grading, roads, drainage, marine) | IFR | PLT, STU, SDS |
| DSH | Datasheet | IFR | PID, SPC |
| EFD | Equipment foundation drawings (vendor-certified loads) | IFR | CAL, FND |
| ELY | Electrical layout (earthing, lighting, trays, equipment) | IFR | ARC, CVL, ELY, FND, LAY, PPL, SLD, STU |
| FND | Foundation / underground drawing | IFR | LAY, CAL |
| GAD | General arrangement drawing | IFR | ARC, DBR, LAY |
| HAZ | Safety study (HAZID, HAZOP, SIL, hazardous areas, fire, QRA) | IFR | PID, PLT, HAZ |
| HMB | Heat and mass balance | IFR | DBR |
| HMI | Operator display (HMI graphics) drawings | IFR | PID, CNR |
| HUP | Instrument hook-up drawings | IFR | PID, SPC |
| IOL | I/O list | IFR | PID, CNR, LST, IOL |
| ISO | Isometric drawing package | IFR | PPL |
| ITP | Inspection and test plan | IFR | SPC |
| LAY | Equipment layout / arrangement | IFR | ARC, HAZ, PLT |
| LOG | Logic diagram | IFR | CNR, IOL, RPT |
| LOP | Loop / connection diagram | IFR | IOL |
| LST | List / index (equipment, lines, valves, instruments, loads, tie-ins) | IFR | DBR, HAZ, LST, PFD, PID, PRC, RPT, SLD, STU |
| M3D | 3D model review report (30 / 60 / 90 %) | IFR | PLT, LAY, PPL, ISO |
| MDB | Manufacturing record book / conformity certificates / turnover dossier | IFR | CMP, ITP |
| MOS | Method statement / construction execution plan | IFR | CVL, PLN |
| MRQ | Material requisition | IFR | SPC |
| OMM | Operation and maintenance manual | IFR | CMP, PID |
| PFD | Process flow diagram | IFR | HMB |
| PID | Piping and instrumentation diagram | IFR | SDS |
| PLN | Plan (execution, quality, HSE, commissioning, training) | IFR | DBR, HAZ, LST, PFD, PLN, PRC, RPT, SPC, STU |
| PLT | Plot plan | IFR | DBR |
| PPL | Piping general arrangement / plans | IFR | PID, LAY |
| RBR | Reinforcement drawings | IFR | FND |
| SCH | Schedule | IFR | MDL |
| SDS | System design description | IFR | DBR |
| SLD | Single line diagram | IFR | DBR, LST |
| STL | Steel structure drawing | IFR | GAD, CAL |
| STR | Pipe stress analysis report | IFR | PPL |
| SUP | Pipe support drawings | IFC | ISO, STR |
| TRP | Test report / test record / certificate | IFR | CMP, SPC, TST |
| TST | Test procedure (FAT, SAT, site and performance tests) | IFR | DBR, ITP, RPT, SPC |
| WIR | Schematic and wiring diagrams | IFC | SLD, LST |

# 6. Timeline

IFC / final issues per quarter and discipline (the monthly curve and the AWP bars are in ALP_engineering_timeline.pdf of the engineering_plan engine):

| Quarter | CV | CM | EL | GE | HS | HV | IC | ME | PI | PR | PC | SS | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2026 Q4 | 11 | 1 | 38 | 13 |  | 6 | 16 | 111 | 6 | 50 |  | 5 | 257 |
| 2027 Q1 | 51 | 26 | 35 | 82 | 13 | 3 | 74 | 157 | 23 | 15 | 1 | 16 | 496 |
| 2027 Q2 | 70 | 31 | 51 | 51 | 12 | 12 | 137 | 152 | 8 | 63 |  | 16 | 603 |
| 2027 Q3 | 9 | 50 | 32 | 28 | 11 | 1 | 108 | 119 | 36 | 25 | 1 | 5 | 425 |
| 2027 Q4 |  | 35 | 27 | 7 | 2 |  | 85 | 86 | 26 |  |  |  | 268 |
| 2028 Q1 |  | 19 |  |  |  |  | 3 | 28 | 48 |  |  |  | 98 |
| 2028 Q2 |  | 73 |  |  |  |  |  | 1 | 4 |  |  |  | 78 |
| 2028 Q3 |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  | 4 |
| 2028 Q4 |  | 1 |  |  |  |  | 1 |  |  |  |  |  | 2 |
| 2029 Q1 |  | 2 |  |  |  |  | 1 |  |  |  |  |  | 3 |
| 2029 Q2 |  | 3 |  |  |  |  |  |  |  |  |  |  | 3 |

Document preparation capacity at full mobilisation (eng_resource, levelled timeline): CV 30 FTE, CM 3 FTE, EL 8 FTE, GE 5 FTE, HS 3 FTE, HV 7 FTE, IC 14 FTE, ME 12 FTE, PI 32 FTE, PR 13 FTE, PC 1 FTE, SS 18 FTE - total 146 FTE. Documents are scheduled in the order of their latest start (backwards from the EWP and PWP need dates) within these capacities.

Engineering load per month: hours of each EPC document as booked by the levelled timeline (spread over its preparation when not levelled); 180 tender-stage documents (10,697 h) were prepared in the bid and are excluded; FTE at 150 h / month.

| Month | CV | CM | EL | GE | HS | HV | IC | ME | PI | PR | PC | SS | Hours | FTE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2026-11 | 613 | 175 | 511 | 292 | 172 | 16 | 869 | 676 | 2,070 | 821 | 12 | 48 | 6,275 | 42 |
| 2026-12 | 3,366 | 328 | 899 | 550 | 325 | 462 | 1,603 | 1,123 | 2,990 | 1,382 | 68 |  | 13,097 | 87 |
| 2027-01 | 4,366 | 417 | 1,165 | 701 | 409 | 969 | 1,698 | 1,735 | 4,658 | 1,885 |  |  | 18,004 | 120 |
| 2027-02 | 4,497 | 435 | 1,182 | 725 | 419 | 1,048 | 2,079 | 1,702 | 4,800 | 1,947 |  | 857 | 19,691 | 131 |
| 2027-03 | 5,170 | 496 | 1,376 | 838 | 488 | 1,194 | 2,391 | 536 | 5,520 | 2,223 |  | 2,107 | 22,339 | 149 |
| 2027-04 | 4,945 | 475 | 1,319 | 712 | 295 | 735 | 2,291 |  | 5,280 | 2,142 |  | 2,821 | 21,015 | 140 |
| 2027-05 | 4,102 | 467 | 1,260 | 691 | 360 | 29 | 2,193 |  | 5,031 | 2,026 | 5 | 1,747 | 17,909 | 119 |
| 2027-06 | 1,344 | 480 | 1,317 | 262 | 473 | 36 | 2,304 |  | 5,251 | 464 | 75 | 97 | 12,103 | 81 |
| 2027-07 | 659 | 479 | 1,315 |  | 494 |  | 2,299 |  | 5,280 |  |  |  | 10,527 | 70 |
| 2027-08 | 16 | 478 | 1,302 | 53 | 350 |  | 2,298 |  | 5,262 |  |  |  | 9,759 | 65 |
| 2027-09 |  | 475 | 1,298 | 27 | 80 |  | 2,305 |  | 5,275 |  |  |  | 9,459 | 63 |
| 2027-10 |  | 463 | 1,064 |  |  |  | 2,191 |  | 5,022 |  |  |  | 8,741 | 58 |
| 2027-11 |  | 391 | 96 |  |  |  | 1,186 |  | 5,273 |  |  |  | 6,945 | 46 |
| 2027-12 |  | 309 |  |  |  |  | 126 |  | 5,382 |  |  |  | 5,818 | 39 |
| 2028-01 |  | 328 |  |  |  |  |  |  | 3,578 |  |  |  | 3,906 | 26 |
| 2028-02 |  |  |  |  |  |  |  |  | 1,692 |  |  |  | 1,692 | 11 |
| 2028-03 |  | 224 |  |  |  |  |  |  | 549 |  |  |  | 773 | 5 |
| 2028-04 |  | 448 |  |  |  |  |  |  | 625 |  |  |  | 1,073 | 7 |
| 2028-05 |  | 355 |  |  |  |  |  |  | 575 |  |  |  | 930 | 6 |
| 2028-06 |  | 141 |  |  |  |  |  |  | 250 |  |  |  | 391 | 3 |
| 2028-07 |  | 40 | 40 |  |  |  |  |  |  |  |  |  | 80 | 1 |
| 2028-09 |  | 40 |  |  |  |  | 40 |  |  |  |  |  | 80 | 1 |
| 2029-01 |  | 48 |  |  |  |  |  |  |  |  |  |  | 48 | 0 |
| 2029-02 |  | 56 |  |  |  |  | 40 |  |  |  |  |  | 96 | 1 |
| 2029-03 |  | 228 |  |  |  |  |  |  |  |  |  |  | 228 | 2 |
| 2029-04 |  | 28 |  |  |  |  |  |  |  |  |  |  | 28 | 0 |

Peak 2027-03: 22,339 h (about 149 FTE).

Key dates (CPM, driven by mechanical completion of the CWPs):

| Key date | Title | Forecast | Float (wd) |
| --- | --- | --- | --- |
| KD-000 | Notice to Proceed | 2026-11-02 | 457 |
| KD-010 | Back-feed energisation (key date) | 2028-07-04 | 21 |
| KD-020 | GT first fire (key date) | 2028-09-18 | 10 |
| KD-030 | First synchronisation in combined cycle (key date) | 2028-11-20 | 31 |
| KD-040 | Taking-Over of the Works (Time for Completion, 975 days) | 2029-04-18 | 55 |

# 7. Supplier documents (VDRL)

750 supplier documents in 66 packages. Per package:

| MR | Originator | Docs | Sheets | First IFR | Last final |
| --- | --- | --- | --- | --- | --- |
| - | IEC | 17 | 26 | 2026-09-28 | 2027-10-04 |
| MR-CV-001 | C01 | 7 | 7 | 2027-01-28 | 2027-02-11 |
| MR-CV-002 | C02 | 7 | 7 | 2027-01-07 | 2027-01-21 |
| MR-CV-003 | C03 | 7 | 7 | 2027-03-25 | 2027-04-08 |
| MR-EL-001 | E01 | 14 | 71 | 2027-01-12 | 2028-03-07 |
| MR-EL-002 | E02 | 14 | 40 | 2027-03-18 | 2028-02-17 |
| MR-EL-003 | E03 | 11 | 13 | 2027-02-09 | 2027-12-16 |
| MR-EL-004 | E04 | 11 | 22 | 2027-03-19 | 2027-11-23 |
| MR-EL-005 | E05 | 12 | 103 | 2027-02-25 | 2027-11-25 |
| MR-EL-006 | E06 | 14 | 34 | 2027-02-09 | 2027-12-16 |
| MR-EL-007 | E07 | 12 | 87 | 2027-03-29 | 2027-12-01 |
| MR-EL-008 | E08 | 3 | 3 | 2027-03-29 | 2027-09-13 |
| MR-EL-009 | E09 | 3 | 3 | 2027-02-11 | 2027-07-01 |
| MR-EL-010 | E10 | 8 | 8 | 2027-05-11 | 2027-11-23 |
| MR-EL-011 | E11 | 8 | 8 | 2026-11-02 | 2027-04-05 |
| MR-EL-012 | E12 | 7 | 7 | 2027-06-23 | 2027-07-07 |
| MR-EL-101 | IEC | 16 | 274 | 2026-09-28 | 2028-01-03 |
| MR-EL-102 | IEC | 15 | 65 | 2026-09-28 | 2028-01-10 |
| MR-HV-001 | H01 | 15 | 356 | 2027-02-18 | 2027-11-18 |
| MR-IC-001 | I01 | 12 | 95 | 2027-02-18 | 2028-01-20 |
| MR-IC-002 | I02 | 13 | 41 | 2027-04-09 | 2028-01-07 |
| MR-IC-003 | I03 | 14 | 56 | 2027-04-13 | 2028-01-11 |
| MR-IC-004 | I04 | 3 | 3 | 2027-04-12 | 2027-11-03 |
| MR-IC-005 | I05 | 3 | 3 | 2027-04-05 | 2027-11-22 |
| MR-IC-006 | I06 | 12 | 86 | 2027-06-14 | 2028-01-10 |
| MR-IC-007 | I07 | 12 | 67 | 2027-06-07 | 2028-01-03 |
| MR-IC-008 | I08 | 13 | 172 | 2027-05-18 | 2028-01-20 |
| MR-IC-009 | I09 | 12 | 26 | 2027-06-10 | 2028-05-11 |
| MR-IC-010 | I10 | 3 | 3 | 2027-06-16 | 2027-10-06 |
| MR-IC-101 | IEC | 19 | 1584 | 2026-11-30 | 2027-11-01 |
| MR-ME-001 | M01 | 15 | 73 | 2027-02-11 | 2028-01-13 |
| MR-ME-002 | M02 | 15 | 45 | 2027-03-18 | 2028-01-24 |
| MR-ME-003 | M03 | 15 | 45 | 2027-02-11 | 2028-02-10 |
| MR-ME-004 | M04 | 15 | 97 | 2027-03-10 | 2028-01-14 |
| MR-ME-005 | M05 | 16 | 111 | 2027-03-11 | 2028-01-17 |
| MR-ME-006 | M06 | 14 | 46 | 2027-04-07 | 2028-01-05 |
| MR-ME-007 | M07 | 15 | 85 | 2027-03-11 | 2027-12-09 |
| MR-ME-008 | M08 | 16 | 106 | 2027-03-11 | 2027-12-09 |
| MR-ME-009 | M09 | 16 | 119 | 2027-02-11 | 2028-01-13 |
| MR-ME-010 | M10 | 14 | 55 | 2027-06-01 | 2027-12-28 |
| MR-ME-011 | M11 | 14 | 87 | 2027-05-31 | 2028-02-02 |
| MR-ME-012 | M12 | 16 | 332 | 2027-02-25 | 2028-02-24 |
| MR-ME-013 | M13 | 15 | 80 | 2027-02-10 | 2027-10-15 |
| MR-ME-014 | M14 | 16 | 290 | 2027-02-18 | 2027-11-18 |
| MR-ME-015 | M15 | 15 | 126 | 2027-02-11 | 2028-01-13 |
| MR-ME-016 | M16 | 15 | 152 | 2027-02-09 | 2027-12-16 |
| MR-ME-017 | M17 | 7 | 7 | 2027-04-08 | 2027-04-22 |
| MR-ME-018 | M18 | 15 | 63 | 2027-03-15 | 2027-12-13 |
| MR-ME-019 | M19 | 15 | 38 | 2027-03-04 | 2027-11-08 |
| MR-ME-020 | M20 | 15 | 189 | 2027-02-19 | 2027-12-02 |
| MR-ME-021 | M21 | 13 | 45 | 2027-02-09 | 2027-12-16 |
| MR-ME-022 | M22 | 7 | 7 | 2027-07-14 | 2027-07-28 |
| MR-ME-023 | M23 | 7 | 7 | 2027-09-29 | 2027-10-13 |
| MR-ME-024 | M24 | 7 | 7 | 2027-09-13 | 2027-09-27 |
| MR-ME-101 | IEC | 19 | 628 | 2026-09-28 | 2028-07-24 |
| MR-ME-102 | IEC | 17 | 526 | 2026-09-28 | 2027-12-27 |
| MR-ME-103 | IEC | 17 | 513 | 2026-09-28 | 2028-02-21 |
| MR-PI-001 | P01 | 3 | 3 | 2027-02-11 | 2027-07-29 |
| MR-PI-002 | P02 | 3 | 3 | 2027-03-11 | 2027-12-30 |
| MR-PI-003 | P03 | 3 | 3 | 2027-04-01 | 2027-10-25 |
| MR-PI-004 | P04 | 3 | 3 | 2027-02-03 | 2027-09-22 |
| MR-PI-005 | P05 | 3 | 3 | 2027-06-10 | 2027-10-28 |
| MR-PI-006 | P06 | 3 | 3 | 2027-04-19 | 2027-09-06 |
| MR-PI-007 | P07 | 3 | 3 | 2027-04-15 | 2027-09-30 |
| MR-SS-001 | S01 | 23 | 735 | 2027-02-17 | 2027-03-31 |
| MR-SS-002 | S02 | 8 | 8 | 2027-02-23 | 2027-03-26 |

Power island (IEC) documents:

| Number | IEC ref | Title | IFR | IFC | Feeds |
| --- | --- | --- | --- | --- | --- |
| ALP-IEC-00000-GE-LST-0001 | IEC-ALP-IF-001 | Power Island - Terminal Points and Interface Data | 2026-09-28 | 2026-11-02 | 1 |
| ALP-IEC-00000-GE-RPT-0001 | IEC-ALP-DOR-001 | Power Island and Balance of Plant - Division of Responsibility | 2026-09-28 | 2026-11-02 | 0 |
| ALP-IEC-00000-GE-SPC-0001 | IEC-ALP-REQ-001 | Power Island Interface Requirements to the EPC | 2026-09-28 | 2026-11-02 | 0 |
| ALP-IEC-10BAT-EL-DSH-0001 | IEC-ALP-DS-106 | Generator Step-Up Transformers - Supplier Certified Datasheets and Performance Curves | 2026-09-28 | 2026-12-28 | 0 |
| ALP-IEC-10BAT-EL-GAD-0001 | IEC-ALP-GA-104 | Generator Step-Up Transformers - Supplier GA Drawings | 2026-09-28 | 2027-01-11 | 1 |
| ALP-IEC-10HAA-ME-DSH-0001 | IEC-ALP-DS-104 | HRSG incl. SCR - Supplier Certified Datasheets and Performance Curves | 2026-09-28 | 2026-12-28 | 0 |
| ALP-IEC-10HAA-ME-GAD-0001 | IEC-ALP-GA-103 | HRSG incl. SCR - Supplier GA Drawings | 2026-09-28 | 2027-01-11 | 1 |
| ALP-IEC-10MBA-ME-DSH-0001 | IEC-ALP-DS-101 | Gas Turbine Package incl. Auxiliaries - Supplier Certified Datasheets and Performance Curves | 2026-09-28 | 2026-12-28 | 0 |
| ALP-IEC-10MBA-ME-GAD-0001 | IEC-ALP-GA-101 | Gas Turbine Package incl. Auxiliaries - Supplier GA Drawings | 2026-09-28 | 2027-01-11 | 1 |
| ALP-IEC-10MBA-ME-LAY-0001 | IEC-ALP-GA-100 | Power Island Arrangement - Installation and Maintenance Spaces | 2026-09-28 | 2027-01-11 | 1 |
| ALP-IEC-10MBA-PR-HMB-0001 | IEC-ALP-PER-001 | Power Island Thermal Performance Data | 2026-09-28 | 2026-11-02 | 1 |
| ALP-IEC-10MBA-PR-HMB-0002 | IEC-ALP-PER-003 | Power Island Off-Design Heat Balances | 2026-09-28 | 2026-11-02 | 0 |
| ALP-IEC-10MKA-EL-DSH-0001 | IEC-ALP-DS-102 | Generators, Excitation, GCB and Busducts - Supplier Certified Datasheets and Performance Curves | 2026-09-28 | 2026-12-28 | 1 |
| ALP-IEC-20MAA-ME-DSH-0001 | IEC-ALP-DS-103 | Steam Turbine and Condenser - Supplier Certified Datasheets and Performance Curves | 2026-09-28 | 2026-12-28 | 0 |
| ALP-IEC-20MAA-ME-GAD-0001 | IEC-ALP-GA-102 | Steam Turbine and Condenser - Supplier GA Drawings | 2026-09-28 | 2027-01-11 | 1 |
| ALP-IEC-20MAG-ME-DSH-0001 | IEC-ALP-DS-105 | Seawater-Cooled Surface Condenser - Datasheet | 2026-09-28 | 2026-12-28 | 0 |
| ALP-IEC-10BAT-ME-ITP-0001 | - | Generator Step-Up Transformers - Supplier Inspection and Test Plan | 2026-11-30 | 2026-12-28 | 0 |
| ALP-IEC-10HAA-ME-ITP-0001 | - | HRSG incl. SCR - Supplier Inspection and Test Plan | 2026-11-30 | 2026-12-28 | 0 |
| ALP-IEC-10MBY-ME-DSH-0001 | - | Turbine Control System - Supplier Certified Datasheets and Performance Curves | 2026-11-30 | 2027-01-11 | 0 |
| ALP-IEC-10MBY-ME-ITP-0001 | - | Turbine Control System - Supplier Inspection and Test Plan | 2026-11-30 | 2026-12-28 | 0 |
| ALP-IEC-10MKA-ME-ITP-0001 | - | Generators, Excitation, GCB and Busducts - Supplier Inspection and Test Plan | 2026-11-30 | 2026-12-28 | 0 |
| ALP-IEC-20MAA-ME-ITP-0001 | - | Steam Turbine and Condenser - Supplier Inspection and Test Plan | 2026-11-30 | 2026-12-28 | 0 |
| ALP-IEC-10BAT-CV-CAL-0001 | - | Generator Step-Up Transformers - Supplier Foundation Loads and Anchor Bolt Drawings | 2026-12-14 | 2027-01-11 | 1 |
| ALP-IEC-10HAA-CV-CAL-0001 | IEC-ALP-FL-102 | HRSG incl. SCR - Supplier Foundation Loads and Anchor Bolt Drawings | 2026-12-14 | 2027-01-11 | 13 |
| ALP-IEC-10MBA-CV-CAL-0001 | IEC-ALP-FL-101 | Gas Turbine Package incl. Auxiliaries - Supplier Foundation Loads and Anchor Bolt Drawings | 2026-12-14 | 2027-01-11 | 14 |
| ALP-IEC-10MBY-ME-GAD-0001 | - | Turbine Control System - Supplier GA Drawings | 2026-12-14 | 2027-01-25 | 0 |
| ALP-IEC-10MKA-CV-CAL-0001 | - | Generators, Excitation, GCB and Busducts - Supplier Foundation Loads and Anchor Bolt Drawings | 2026-12-14 | 2027-01-11 | 2 |
| ALP-IEC-10MKA-ME-GAD-0001 | - | Generators, Excitation, GCB and Busducts - Supplier GA Drawings | 2026-12-14 | 2027-01-25 | 0 |
| ALP-IEC-00000-PI-LST-0001 | IEC-ALP-IF-001-A | Terminal Point Nozzle Loads | 2026-12-28 | 2027-01-25 | 9 |
| ALP-IEC-10BAA-EL-SLD-0001 | IEC-ALP-SLD-101 | Power Island Single Line Diagram | 2026-12-28 | 2027-02-08 | 1 |
| ALP-IEC-10BAT-IC-IOL-0001 | - | Generator Step-Up Transformers - Supplier I/O List, Control Philosophy and Interface Signals | 2026-12-28 | 2027-02-08 | 0 |
| ALP-IEC-10BAT-ME-CAL-0001 | - | Generator Step-Up Transformers - Supplier Design Calculations | 2026-12-28 | 2027-02-08 | 0 |
| ALP-IEC-10HAA-IC-IOL-0001 | - | HRSG incl. SCR - Supplier I/O List, Control Philosophy and Interface Signals | 2026-12-28 | 2027-02-08 | 0 |
| ALP-IEC-10HAA-ME-CAL-0001 | - | HRSG incl. SCR - Supplier Design Calculations | 2026-12-28 | 2027-02-08 | 0 |
| ALP-IEC-10MBA-EL-LST-0001 | IEC-ALP-EL-101 | Power Island Electrical Load List | 2026-12-28 | 2027-02-08 | 1 |
| ALP-IEC-10MBA-IC-IOL-0001 | - | Gas Turbine Package incl. Auxiliaries - Supplier I/O List, Control Philosophy and Interface Signals | 2026-12-28 | 2027-02-08 | 0 |
| ALP-IEC-10MBA-ME-CAL-0001 | - | Gas Turbine Package incl. Auxiliaries - Supplier Design Calculations | 2026-12-28 | 2027-02-08 | 0 |
| ALP-IEC-10MBY-ME-CAL-0001 | - | Turbine Control System - Supplier Design Calculations | 2026-12-28 | 2027-02-08 | 0 |
| ALP-IEC-10MKA-IC-IOL-0001 | - | Generators, Excitation, GCB and Busducts - Supplier I/O List, Control Philosophy and Interface Signals | 2026-12-28 | 2027-02-08 | 0 |
| ALP-IEC-10MKA-ME-CAL-0001 | - | Generators, Excitation, GCB and Busducts - Supplier Design Calculations | 2026-12-28 | 2027-02-08 | 0 |
| ALP-IEC-20MAA-CV-CAL-0001 | IEC-ALP-FL-103 | Steam Turbine and Condenser - Supplier Foundation Loads and Anchor Bolt Drawings | 2026-12-28 | 2027-01-25 | 5 |
| ALP-IEC-20MAA-IC-IOL-0001 | - | Steam Turbine and Condenser - Supplier I/O List, Control Philosophy and Interface Signals | 2026-12-28 | 2027-02-08 | 0 |
| ALP-IEC-20MAA-ME-CAL-0001 | - | Steam Turbine and Condenser - Supplier Design Calculations | 2026-12-28 | 2027-02-08 | 0 |
| ALP-IEC-10BAT-EL-WIR-0001 | - | Generator Step-Up Transformers - Supplier Electrical Schematics and Wiring Diagrams | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-10BAT-IC-DSH-0001 | - | Generator Step-Up Transformers - Supplier Instrument List and Datasheets | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-10HAA-EL-WIR-0001 | - | HRSG incl. SCR - Supplier Electrical Schematics and Wiring Diagrams | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-10HAA-IC-DSH-0001 | - | HRSG incl. SCR - Supplier Instrument List and Datasheets, Part 1 of 2 | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-10HAA-IC-DSH-0002 | - | HRSG incl. SCR - Supplier Instrument List and Datasheets, Part 2 of 2 | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-10HAA-PR-PID-0001 | IEC-ALP-PID-102 | HRSG incl. SCR - Supplier P&IDs | 2027-01-11 | 2027-03-08 | 2 |
| ALP-IEC-10MBA-EL-WIR-0001 | - | Gas Turbine Package incl. Auxiliaries - Supplier Electrical Schematics and Wiring Diagrams, Part 1 of 2 | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-10MBA-EL-WIR-0002 | - | Gas Turbine Package incl. Auxiliaries - Supplier Electrical Schematics and Wiring Diagrams, Part 2 of 2 | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-10MBA-HS-RPT-0001 | IEC-ALP-HS-101 | Power Island Noise Data | 2027-01-11 | 2027-02-22 | 1 |
| ALP-IEC-10MBA-IC-DSH-0001 | - | Gas Turbine Package incl. Auxiliaries - Supplier Instrument List and Datasheets, Part 1 of 3 | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-10MBA-IC-DSH-0002 | - | Gas Turbine Package incl. Auxiliaries - Supplier Instrument List and Datasheets, Part 2 of 3 | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-10MBA-IC-DSH-0003 | - | Gas Turbine Package incl. Auxiliaries - Supplier Instrument List and Datasheets, Part 3 of 3 | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-10MBA-PR-PID-0001 | IEC-ALP-PID-101 | Gas Turbine Package incl. Auxiliaries - Supplier P&IDs | 2027-01-11 | 2027-03-08 | 2 |
| ALP-IEC-10MBY-EL-WIR-0001 | - | Turbine Control System - Supplier Electrical Schematics and Wiring Diagrams | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-10MBY-IC-BLK-0001 | IEC-ALP-IC-101 | TCS Architecture and DCS Integration | 2027-01-11 | 2027-02-22 | 1 |
| ALP-IEC-10MKA-EL-WIR-0001 | - | Generators, Excitation, GCB and Busducts - Supplier Electrical Schematics and Wiring Diagrams | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-10MKA-IC-DSH-0001 | - | Generators, Excitation, GCB and Busducts - Supplier Instrument List and Datasheets | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-20MAA-EL-WIR-0001 | - | Steam Turbine and Condenser - Supplier Electrical Schematics and Wiring Diagrams | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-20MAA-IC-DSH-0001 | - | Steam Turbine and Condenser - Supplier Instrument List and Datasheets, Part 1 of 2 | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-20MAA-IC-DSH-0002 | - | Steam Turbine and Condenser - Supplier Instrument List and Datasheets, Part 2 of 2 | 2027-01-11 | 2027-03-08 | 0 |
| ALP-IEC-10BAT-ME-LST-0001 | - | Generator Step-Up Transformers - Spare Parts and Special Tools Lists | 2027-01-25 | 2027-03-22 | 0 |
| ALP-IEC-10HAA-ME-LST-0001 | - | HRSG incl. SCR - Spare Parts and Special Tools Lists | 2027-01-25 | 2027-03-22 | 0 |
| ALP-IEC-10MBA-ME-ITP-0001 | IEC-ALP-QA-101 | Gas Turbine Package incl. Auxiliaries - Supplier Inspection and Test Plan | 2027-01-25 | 2027-02-22 | 0 |
| ALP-IEC-10MBA-ME-LST-0001 | - | Gas Turbine Package incl. Auxiliaries - Spare Parts and Special Tools Lists | 2027-01-25 | 2027-03-22 | 0 |
| ALP-IEC-10MBY-ME-LST-0001 | - | Turbine Control System - Spare Parts and Special Tools Lists | 2027-01-25 | 2027-03-22 | 0 |
| ALP-IEC-10MKA-EL-RPT-0001 | IEC-ALP-EL-102 | Generator Capability Curves and Dynamic Models | 2027-01-25 | 2027-03-22 | 1 |
| ALP-IEC-10MKA-ME-LST-0001 | - | Generators, Excitation, GCB and Busducts - Spare Parts and Special Tools Lists | 2027-01-25 | 2027-03-22 | 0 |
| ALP-IEC-10MKA-PR-PID-0001 | IEC-ALP-PID-104 | Generators, Excitation, GCB and Busducts - Supplier P&IDs | 2027-01-25 | 2027-03-22 | 0 |
| ALP-IEC-20MAA-ME-LST-0001 | - | Steam Turbine and Condenser - Spare Parts and Special Tools Lists | 2027-01-25 | 2027-03-22 | 0 |
| ALP-IEC-20MAA-PR-PID-0001 | IEC-ALP-PID-103 | Steam Turbine and Condenser - Supplier P&IDs | 2027-01-25 | 2027-03-22 | 1 |
| ALP-IEC-10MBY-IC-CNR-0001 | IEC-ALP-IC-103 | Power Island Operating and Control Description | 2027-02-08 | 2027-04-05 | 2 |
| ALP-IEC-10MBA-PI-M3D-0001 | IEC-ALP-M3D-101 | Power Island 3D Model Export | 2027-02-22 | 2027-04-19 | 0 |
| ALP-IEC-10MBY-IC-IOL-0001 | IEC-ALP-IC-102 | Turbine Control System - Supplier I/O List, Control Philosophy and Interface Signals | 2027-02-22 | 2027-04-19 | 3 |
| ALP-IEC-10MBY-CM-CMP-0001 | - | Turbine Control System - Supplier Commissioning Procedures | 2027-03-22 | 2027-06-14 | 0 |
| ALP-IEC-10MBY-IC-LOG-0001 | - | Turbine Control System - Supplier Logic Diagrams, Part 1 of 6 | 2027-03-22 | 2027-06-14 | 0 |
| ALP-IEC-10MBY-IC-LOG-0002 | - | Turbine Control System - Supplier Logic Diagrams, Part 2 of 6 | 2027-03-22 | 2027-06-14 | 0 |
| ALP-IEC-10MBY-IC-LOG-0003 | - | Turbine Control System - Supplier Logic Diagrams, Part 3 of 6 | 2027-03-22 | 2027-06-14 | 0 |
| ALP-IEC-10MBY-IC-LOG-0004 | - | Turbine Control System - Supplier Logic Diagrams, Part 4 of 6 | 2027-03-22 | 2027-06-14 | 0 |
| ALP-IEC-10MBY-IC-LOG-0005 | - | Turbine Control System - Supplier Logic Diagrams, Part 5 of 6 | 2027-03-22 | 2027-06-14 | 0 |
| ALP-IEC-10MBY-IC-LOG-0006 | - | Turbine Control System - Supplier Logic Diagrams, Part 6 of 6 | 2027-03-22 | 2027-06-14 | 0 |
| ALP-IEC-10MBY-ME-TST-0001 | - | Turbine Control System - Factory Acceptance Test Procedure | 2027-04-19 | 2027-05-31 | 0 |
| ALP-IEC-10HAA-CM-CMP-0001 | - | HRSG incl. SCR - Supplier Commissioning Procedures | 2027-05-17 | 2027-08-09 | 0 |
| ALP-IEC-10MBY-ME-PRC-0001 | - | Turbine Control System - Supplier Installation and Erection Manual | 2027-05-17 | 2027-06-28 | 0 |
| ALP-IEC-10MKA-CM-CMP-0001 | - | Generators, Excitation, GCB and Busducts - Supplier Commissioning Procedures | 2027-05-24 | 2027-08-16 | 0 |
| ALP-IEC-10BAT-CM-CMP-0001 | - | Generator Step-Up Transformers - Supplier Commissioning Procedures | 2027-05-31 | 2027-08-23 | 0 |
| ALP-IEC-10MBA-CM-CMP-0001 | - | Gas Turbine Package incl. Auxiliaries - Supplier Commissioning Procedures | 2027-05-31 | 2027-08-23 | 0 |
| ALP-IEC-10MBY-IC-CBL-0001 | IEC-ALP-IC-104 | Power Island Cable List | 2027-05-31 | 2027-07-26 | 2 |
| ALP-IEC-10HAA-ME-TST-0001 | - | HRSG incl. SCR - Factory Acceptance Test Procedure | 2027-06-14 | 2027-07-26 | 0 |
| ALP-IEC-10MBY-ME-OMM-0001 | - | Turbine Control System - Supplier Operation and Maintenance Manual | 2027-06-14 | 2027-11-01 | 0 |
| ALP-IEC-10MKA-ME-TST-0001 | - | Generators, Excitation, GCB and Busducts - Factory Acceptance Test Procedure | 2027-06-21 | 2027-08-02 | 0 |
| ALP-IEC-10BAT-ME-TST-0001 | - | Generator Step-Up Transformers - Factory Acceptance Test Procedure | 2027-06-28 | 2027-08-09 | 0 |
| ALP-IEC-10MBA-ME-TST-0001 | - | Gas Turbine Package incl. Auxiliaries - Factory Acceptance Test Procedure | 2027-06-28 | 2027-08-09 | 0 |
| ALP-IEC-10HAA-ME-PRC-0001 | - | HRSG incl. SCR - Supplier Installation and Erection Manual | 2027-07-12 | 2027-08-23 | 0 |
| ALP-IEC-10MBA-ME-PRC-0001 | IEC-ALP-ER-101 | Gas Turbine Package incl. Auxiliaries - Supplier Installation and Erection Manual | 2027-07-12 | 2027-09-06 | 0 |
| ALP-IEC-10MBY-ME-TRP-0001 | - | Turbine Control System - Factory Acceptance Test Report | 2027-07-12 | 2027-07-26 | 0 |
| ALP-IEC-20MAA-CM-CMP-0001 | - | Steam Turbine and Condenser - Supplier Commissioning Procedures | 2027-07-12 | 2027-10-04 | 0 |
| ALP-IEC-10MKA-ME-PRC-0001 | - | Generators, Excitation, GCB and Busducts - Supplier Installation and Erection Manual | 2027-07-19 | 2027-08-30 | 0 |
| ALP-IEC-10BAT-ME-PRC-0001 | - | Generator Step-Up Transformers - Supplier Installation and Erection Manual | 2027-07-26 | 2027-09-06 | 0 |
| ALP-IEC-10MBY-ME-MDB-0001 | - | Turbine Control System - Manufacturing Record Book and Conformity Certificates | 2027-07-26 | 2027-09-20 | 0 |
| ALP-IEC-10HAA-ME-OMM-0001 | - | HRSG incl. SCR - Supplier Operation and Maintenance Manual | 2027-08-09 | 2027-12-27 | 0 |
| ALP-IEC-10MBA-ME-RPT-0001 | IEC-ALP-OM-102 | Maintenance Concept and Long-Term Service Offer | 2027-08-09 | 2027-10-04 | 0 |
| ALP-IEC-20MAA-ME-TST-0001 | - | Steam Turbine and Condenser - Factory Acceptance Test Procedure | 2027-08-09 | 2027-09-20 | 0 |
| ALP-IEC-10MKA-ME-OMM-0001 | - | Generators, Excitation, GCB and Busducts - Supplier Operation and Maintenance Manual | 2027-08-16 | 2028-01-03 | 0 |
| ALP-IEC-10BAT-ME-OMM-0001 | - | Generator Step-Up Transformers - Supplier Operation and Maintenance Manual | 2027-08-23 | 2028-01-10 | 0 |
| ALP-IEC-10HAA-ME-TRP-0001 | - | HRSG incl. SCR - Factory Acceptance Test Report | 2027-09-06 | 2027-09-20 | 0 |
| ALP-IEC-20MAA-ME-PRC-0001 | - | Steam Turbine and Condenser - Supplier Installation and Erection Manual | 2027-09-06 | 2027-10-18 | 0 |
| ALP-IEC-10MKA-ME-TRP-0001 | - | Generators, Excitation, GCB and Busducts - Factory Acceptance Test Report | 2027-09-13 | 2027-09-27 | 0 |
| ALP-IEC-10BAT-ME-TRP-0001 | - | Generator Step-Up Transformers - Factory Acceptance Test Report | 2027-09-20 | 2027-10-04 | 0 |
| ALP-IEC-10HAA-ME-MDB-0001 | - | HRSG incl. SCR - Manufacturing Record Book and Conformity Certificates | 2027-09-20 | 2027-11-15 | 0 |
| ALP-IEC-10MBA-ME-TRP-0001 | - | Gas Turbine Package incl. Auxiliaries - Factory Acceptance Test Report | 2027-09-20 | 2027-10-04 | 0 |
| ALP-IEC-10MKA-ME-MDB-0001 | - | Generators, Excitation, GCB and Busducts - Manufacturing Record Book and Conformity Certificates | 2027-09-27 | 2027-11-22 | 0 |
| ALP-IEC-10BAT-ME-MDB-0001 | - | Generator Step-Up Transformers - Manufacturing Record Book and Conformity Certificates | 2027-10-04 | 2027-11-29 | 0 |
| ALP-IEC-10MBA-ME-MDB-0001 | - | Gas Turbine Package incl. Auxiliaries - Manufacturing Record Book and Conformity Certificates | 2027-10-04 | 2027-11-29 | 0 |
| ALP-IEC-20MAA-ME-OMM-0001 | - | Steam Turbine and Condenser - Supplier Operation and Maintenance Manual | 2027-10-04 | 2028-02-21 | 0 |
| ALP-IEC-20MAA-ME-TRP-0001 | - | Steam Turbine and Condenser - Factory Acceptance Test Report | 2027-11-01 | 2027-11-15 | 0 |
| ALP-IEC-20MAA-ME-MDB-0001 | - | Steam Turbine and Condenser - Manufacturing Record Book and Conformity Certificates | 2027-11-15 | 2028-01-10 | 0 |
| ALP-IEC-10MBA-ME-OMM-0001 | IEC-ALP-OM-101 | Gas Turbine Package incl. Auxiliaries - Supplier Operation and Maintenance Manual | 2028-03-06 | 2028-07-24 | 0 |

# 8. Near-critical items

EWPs with less than 20 working days float (the document with the smallest float drives the EWP):

| EWP | CWP | Driving document | Ready | Needed | Float |
| --- | --- | --- | --- | --- | --- |
| EWP-11-CV-01 | CWP-11-CV-01 | ALP-EPC-00UCA-HV-GAD-0002 | 2027-04-26 | 2027-03-29 | 4 |
| EWP-12-PI-01 | CWP-12-PI-01 | ALP-EPC-00SGA-PI-ISO-0001 | 2027-10-20 | 2027-07-12 | 8 |
| EWP-08-CV-01 | CWP-08-CV-01 | ALP-EPC-00UQA-HV-GAD-0001 | 2027-06-07 | 2027-05-04 | 9 |
| EWP-12-CV-01 | CWP-12-CV-01 | ALP-EPC-00UZA-PI-LAY-0001 | 2027-01-11 | 2027-01-18 | 9 |
| EWP-07-CV-01 | CWP-07-CV-01 | ALP-EPC-00UGA-HV-GAD-0001 | 2027-06-01 | 2027-04-05 | 10 |
| EWP-03-CV-01 | CWP-03-CV-01 | ALP-EPC-00UBA-CV-RBR-0001 | 2027-04-20 | 2027-03-29 | 11 |
| EWP-02-PI-01 | CWP-02-PI-01 | ALP-EPC-20LCA-PI-SUP-0001 | 2028-04-27 | 2028-01-31 | 12 |
| EWP-05-CV-01 | CWP-05-CV-01 | ALP-EPC-00UPC-CV-RBR-0001 | 2027-06-04 | 2027-03-25 | 13 |
| EWP-01-CV-02 | CWP-01-CV-02 | ALP-EPC-00UBF-CV-RBR-0001 | 2027-06-21 | 2027-04-19 | 15 |
| EWP-04-CV-01 | CWP-04-CV-01 | ALP-EPC-00UAC-CV-RBR-0001 | 2027-04-16 | 2027-04-05 | 15 |
| EWP-07-PI-01 | CWP-07-PI-01 | ALP-EPC-00GUA-PI-SUP-0001 | 2028-03-10 | 2028-01-24 | 16 |
| EWP-01-PI-01 | CWP-01-PI-01 | ALP-EPC-10LAE-PI-SUP-0001 | 2028-03-01 | 2027-12-13 | 18 |
| EWP-02-CV-02 | CWP-02-CV-02 | ALP-EPC-20UMB-HV-GAD-0001 | 2027-06-28 | 2027-04-19 | 19 |

PWPs (MRs) with less than 20 working days float between delivery on site and the first CWP start:

| MR | Title | PO | On site | Needed | CWP | Float |
| --- | --- | --- | --- | --- | --- | --- |
| MR-ME-101 | Gas turbine package incl. auxiliaries (IEC) | 2026-11-02 | 2027-11-15 | 2027-11-15 | CWP-01-ME-01 | 0 |
| MR-ME-102 | HRSG incl. SCR (IEC) | 2026-11-02 | 2027-11-15 | 2027-11-15 | CWP-01-ME-01 | 0 |
| MR-ME-011 | Chemical dosing skid | 2027-05-12 | 2027-11-24 | 2027-11-29 | CWP-08-ME-01 | 3 |
| MR-EL-001 | 380 kV GIS | 2026-12-15 | 2028-01-25 | 2028-02-01 | CWP-04-EL-01 | 5 |
| MR-EL-011 | Construction power supply (RMU, temporary distribution) | 2026-11-16 | 2027-01-18 | 2027-01-25 | CWP-12-CV-01 | 5 |
| MR-EL-101 | Generators, excitation, GCB and busducts (IEC) | 2026-11-02 | 2027-11-08 | 2027-11-15 | CWP-01-ME-01 | 5 |
| MR-ME-103 | Steam turbine and condenser (IEC) | 2026-11-02 | 2028-01-10 | 2028-01-17 | CWP-02-ME-01 | 5 |
| MR-EL-009 | Cable trays, earthing and lighting materials | 2027-01-28 | 2027-06-03 | 2027-06-14 | CWP-12-EL-01 | 7 |
| MR-ME-001 | Boiler feed pumps | 2027-01-14 | 2027-11-18 | 2027-11-29 | CWP-08-ME-01 | 7 |
| MR-ME-009 | Auxiliary boiler | 2027-01-14 | 2027-11-18 | 2027-11-29 | CWP-08-ME-01 | 7 |
| MR-ME-012 | Water treatment package (SWRO, demin, condensate polishing) | 2027-01-28 | 2028-01-13 | 2028-01-24 | CWP-07-ME-01 | 7 |
| MR-ME-015 | Gas receiving and metering station | 2027-01-14 | 2027-11-18 | 2027-11-29 | CWP-09-ME-01 | 7 |
| MR-ME-016 | LDO unloading and forwarding / treatment skids | 2027-01-14 | 2027-10-21 | 2027-11-01 | CWP-10-ME-01 | 7 |
| MR-PI-002 | Alloy piping P91 / P22 (main steam, reheat) | 2027-02-11 | 2027-12-30 | 2028-01-10 | CWP-01-PI-01 | 7 |
| MR-CV-002 | Civil and building works | 2026-12-24 | 2027-01-07 | 2027-01-25 | CWP-12-CV-01 | 12 |
| MR-ME-003 | CW pumps | 2027-01-14 | 2027-12-30 | 2028-01-17 | CWP-05-ME-01 | 12 |
| MR-IC-001 | Plant DCS | 2027-01-21 | 2027-11-25 | 2027-12-20 | CWP-11-IC-01 | 17 |
| MR-ME-021 | EOT cranes | 2027-01-14 | 2027-10-21 | 2027-11-15 | CWP-01-ME-01 | 17 |
| MR-PI-001 | Piping bulk materials (carbon steel, stainless) | 2027-01-28 | 2027-07-15 | 2027-08-09 | CWP-12-PI-01 | 17 |

# 9. Limitations of this revision

Dates are levelled against the document preparation capacity of section 6 (basis decision:DEC-EPCE-0010); a change of staffing changes the dates at the next run.

Document quantities are estimates per system until the P&IDs and the 3D model produce the instrument, line and valve registers; the rules then use the register counts (section 3.1).

Benchmarks are indicative ranges (engineering judgement), to be replaced by company historical data.

Supplier document quantities follow the package rules; the supplier's own VDRL replaces them after the PO.

KKS key titles are not yet verified against the licensed VGB key catalogue (Owner's Engineer, TQ-035).

# Check results (engine)

29 OK, 35 INFO, 0 WARN (checks: MDL rules, benchmark, coverage MR, coverage equipment, coverage requirement, coverage scope, coverage system, design criteria, inputs, key date). WARN must be resolved before the next issue; INFO is noted.

| Item | Check | Result | Detail |
| --- | --- | --- | --- |
| - | MDL rules | OK | 80 rules: 0 required document(s) missing, 0 to update, 0 orphan(s) |
| ALP-EPC-00000-CM-OMM-0002 | inputs | INFO | none of the typical inputs ['CMP', 'PID'] of a OMM |
| ALP-EPC-00000-PI-M3D-0004 | inputs | INFO | none of the typical inputs ['ISO', 'LAY', 'PLT', 'PPL'] of a M3D |
| ALP-EPC-00GQA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-00UPA-CV-RBR-0001 | inputs | INFO | none of the typical inputs ['FND'] of a RBR |
| ALP-EPC-00UZC-CV-RBR-0001 | inputs | INFO | none of the typical inputs ['FND'] of a RBR |
| ALP-EPC-00UZE-CV-RBR-0001 | inputs | INFO | none of the typical inputs ['FND'] of a RBR |
| ALP-EPC-10BAA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-10BAC-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-10BAT-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-10HAA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-10HNA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-10HSA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-10MBA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-10MBL-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-10MBN-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-10MBP-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-10MBU-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-10MBV-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-10MBY-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-10MKA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-10MKC-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-10MKG-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-20BAA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-20BAC-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-20BAT-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-20MAA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-20MAB-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-20MAG-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-20MAJ-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-20MAV-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-20MAW-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-20MAX-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-20MAY-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-20MKA-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| ALP-EPC-20MKC-CM-MDB-0001 | inputs | INFO | none of the typical inputs ['CMP', 'ITP'] of a MDB |
| - | coverage requirement | OK | 150 of 150 requirements answered |
| - | coverage scope | OK | 88 of 88 EPC/IEC scope items covered |